## ITP
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP003 - Asphalt Production of Surface Mixes | [5 empty] | ITP003 - Asphalt Production of Surface Mixes
section | 1 Mix Production
checkpoint | 1.01 - Asphalt production plan
label | Frequency: Not less than 48 hours prior to the commencement of a work period.
label | Acceptance Criteria:
label | • Plan demonstrates that the hot storage capacity and production capacity of the mixing plant is capable of supplying asphalt to complete the work proposed to be undertaken within that work period on time and to make the runway suitable for aircraft operation in the event of an asphalt plant breakdown.
label | Reference Documents: GHD-DD-SPC-002 5116(e) HP5116-1
label | Inspection/ Test Method: N/A
label | Record of conformity: Production plan
label | HP
label | Responsibility: Production Supervisor
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Temperature of bitumen
label | Frequency: Not less than once per work period. To be recorded at the time of taking bitumen volumetric readings.
label | Acceptance Criteria:
label | • Temperature to be within the below range for the relevant bitumen type when introduced into the mixer:
label | – Residual bitumen C320: 140-165°C
label | – Polymer modified bitumen: 160-175°C
label | – Polymer modified bitumen with warm mix additives: 140-175°C
label | Reference Documents: GHD-DD-SPC-001 5116(f)
label | Inspection/ Test Method: Asphalt plant temperature probe
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.03 - Temperature of aggregates
label | Frequency: Not less than once per work period.
label | Acceptance Criteria: Temperature to be not more than 10°C above or more than 15°C below the temperature of the bitumen.
label | Reference Documents: GHD-DD-SPC-001 5116(f)
label | Inspection/ Test Method: Asphalt plant temperature probe
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.04 - Temperature of asphalt
label | Frequency: Not less than once per work period.
label | Acceptance Criteria: Temperature to be within 10oC of the job mix temperature
label | Reference Documents: GHD-DD-SPC-001 5116(f)
label | Inspection/ Test Method: Asphalt plant temperature probe
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.05 - Daily bitumen usage
label | Frequency: Once per work period for each production run for each nominal size of asphalt mix.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-001 5131(e)
label | Inspection/ Test Method: Inspection of plant digital readouts before and after each production run
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.06 - Supplementary bitumen content determination
label | Frequency: Once per work period for each nominal size of asphalt mix.
label | Acceptance Criteria: Not less than the job bitumen content.
label | Reference Documents:
label | • GHD-DD-SPC-001 5131(e)
label | • Table 5116-7
label | Inspection/ Test Method: Calculation: Daily bitumen usage divided by mass of asphalt produced for each mix type.
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 1.07 - Mass of asphalt produced
label | Frequency: Once per work period for each nominal size of asphalt mix.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-001 5131(e)
label | Inspection/ Test Method: Inspection of plant digital readouts
label | Record of conformity: Production records
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
section | 2 Bitumen properties
checkpoint | 2.01 - Sampling of bitumen deliveries.
label | Frequency: Prior notice (minimum 24 hours) of the time of bitumen delivery to mixing plant and the taking of samples to be given to Contract Administrator.
label | Acceptance Criteria:
label | • One sample of not less than two (2) litres taken from each separate delivery vessel of bitumen delivered to the mixing plant.
label | • Containers are labelled appropriately so that samples are traceable to asphalt lots, manufacturing batch records and conformance reports. Samples are provided to Contract Administrator immediately after sampling.
label | Reference Documents: GHD-DD-SPC-001 5131(c) WP5131-1
label | Inspection/ Test Method: AS 2008 (Appendix B)
label | Record of conformity: ITP
label | WP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.02 - Sampling from storage tank at the asphalt mixing plant.
label | Frequency: Not more than four hours prior to the scheduled production start time for each work period.
label | Acceptance Criteria:
label | • Duplicate samples are taken from the storage tank at the asphalt mixing plant.
label | • Containers are labelled appropriately so that samples are traceable to asphalt lots, manufacturing batch records and conformance reports.
label | • One sample is provided to Contract Administrator immediately after sampling; one sample is tested as per Section 2 of this ITP.
label | Reference Documents: GHD-DD-SPC-001 5131(c)
label | Inspection/ Test Method: AS 2008 (Appendix B)
label | Record of conformity: ITP
label | IP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.03 - Viscosity at 165°C
label | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AG:PT/T111
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.04 - Torsional recovery at 25oC, 30 s
label | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AG:PT/T122
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.05 - Softening point
label | Frequency: One test prior to each work period, completed no later than 1 hour prior to start of asphalt production.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AG:PT/T131
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.06 - PG MSCR
label | Frequency: One test weekly conducted on a Monday sampled from storage tank, regardless of whether work proceeds that day or not.
label | Acceptance Criteria: To be reported.
label | Reference Documents:
label | • GHD-DD-SPC-002 5131(c)
label | • Table SP5131-3
label | Inspection/ Test Method: AASHTO T350
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 2.07 - Submission of binder test results.
label | Frequency: No later than 1 hour prior to the scheduled start of asphalt production for each work period.
label | Acceptance Criteria:
label | • Completion of the specified set of tests on polymer modified binder.
label | • Submission of test results and a statement to the Contract Administrator regarding the compliance of the binder in the tank.
label | Reference Documents: GHD-DD-SPC-001 5131(c) HP5131-2
label | Inspection/ Test Method: N/A
label | Record of conformity: ITP
label | HP
label | Responsibility: Laboratory Technician
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 Asphalt properties
checkpoint | 3.01 - Mixing efficiency
label | Frequency: Not less than once per work period.
label | Acceptance Criteria:
label | • Percentage of coating of particles in the mix, when sampled at the point of loading, must not be less than 97% and a homogeneous mixture must be obtained.
label | Reference Documents: GHD-DD-SPC-001 5116(g)
label | Inspection/ Test Method: Visual inspection as per ASTM D2489 methodology
label | Record of conformity: Inspection record
label | IP
label | Responsibility: Plant Operator
text | Date Completed:
checkpoint | 3.02 - Stability
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: ±3.0 compared to job mix but not less than 12.0 kN (for 14mm NMS) or not less than 10.0 kN (for 10mm NMS)
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-4
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.03 - Flow
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: Max 3.0 mm for unmodified binder; max ±1.0 mm compared to job mix for PMB
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-4
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.04 - Minimum voids in mineral aggregate
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: 14.0% (for 14mm NMS) or 15.0% (for 10mm NMS)
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-4
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.05 - Minimum and maximum air voids
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: 3.0-5.0%
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-4
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.06 - Minimum and maximum voids filled with bitumen
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: 70.0-80.0% (for 14mm NMS) or 75.0-85.0% (for 10mm NMS)
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-4
label | • HP5116-2
label | Inspection/ Test Method: AS/NZS 2891.5 (75 blows)
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.07 - Combined aggregate particle size distribution
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria:
label | • Within acceptable range of deviation from job mix aggregate particle size distribution:
label | 13.2: ±6 ¦¦ 1.18: ±4
label | 9.5: ±6 ¦¦ 0.6: ±3
label | 6.7: ±6 ¦¦ 0.3: ±2
label | 4.75: ±5 ¦¦ 0.15: ±2
label | 2.36: ±5 ¦¦ 0.075: ±1.5
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-7
label | Inspection/ Test Method: AS/NZS 2891.3.3
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.08 - Bitumen content in asphalt
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: Within ±0.3 of job bitumen content by mass.
label | Reference Documents:
label | • GHD-DD-SPC-001 5116(j)
label | • Table 5116-7
label | Inspection/ Test Method: AS/NZS 2891.3.3
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint | 3.09 - Maximum density
label | Frequency: Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency.
label | Acceptance Criteria: To be reported.
label | Reference Documents: GHD-DD-SPC-001 5132(a)
label | Inspection/ Test Method: AS/NZS 2891.7.1
label | Record of conformity: NATA-accredited test certificate
label | TP
label | Responsibility: Laboratory Technician
text | Date Completed:
checkpoint-no-status | Note 1: Sampling frequency
label | • Number of test sets on asphalt of each nominal size in work period:
label | Quantity of asphalt produced ¦¦ Number of sets of tests
label | First 50t (0-50t) ¦¦ 1
label | Next 100t (50-150t) ¦¦ 1
label | Next 200t (150-350t) ¦¦ 1
label | Next 250t (350-600t) ¦¦ 1
label | Every 250t thereafter ¦¦ 1
label | • Minimum number of tests per work period regardless of tonnes produced: 3
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: