## Building Breakdown
NURSE CALL SOLUTIONS - Highett Site Project - Bert Newton Village BNE Breakdown
Project Breakdown | [6 empty] | Checklists
Job Details
| Pre-Commencement |  |  |  |  | Prepopulate | Job Details (Highett Site - Bert Newton Village BNE )
| NCS Site QA |  |  |  |  | Prepopulate | Quality Assurance Pre-Commencement Checklist
B00-Basement
Stage 1- Basement
Operational-Utilities Rooms
To be provided
Village Ammenities Rooms
To be provided
Stairs/ Lift Lobbies
To be provided
Hallways/ Corridors
To be provided
Stage 2- Basement
Operational-Utilities Rooms
[5 empty] | B02 Car Park Grid A-D/6-9 |  | COMMON AREA CHECKLIST
[5 empty] | B02 Car Park Grid A-D/10-14 |  | COMMON AREA CHECKLIST
[5 empty] | B02 Carpark Grid D-F/6-13 |  | COMMON AREA CHECKLIST
Village Ammenities Rooms
[5 empty] | B02-Bike Store Grid A-B/13-14 |  | COMMON AREA CHECKLIST
[5 empty] | B02- Waste Room Grid C/11 |  | COMMON AREA CHECKLIST
Stairs/ Lift Lobbies
[5 empty] | B02- Stair 5 |  | COMMON AREA CHECKLIST
[5 empty] | B02- Lift 4 |  | COMMON AREA CHECKLIST
Stage 3- Basement
Operational-Utilities Rooms
[5 empty] | B03- Carpark Grid E-H/14-16 |  | COMMON AREA CHECKLIST
[5 empty] | B03- Carpark Grid I-L/14-16 |  | COMMON AREA CHECKLIST
Village Ammenities Rooms
[5 empty] | B03- Waste Room |  | COMMON AREA CHECKLIST
Stairs/ Lift Lobbies
[5 empty] | B03- Lift 5 |  | COMMON AREA CHECKLIST
[5 empty] | B03- Stair 6 |  | COMMON AREA CHECKLIST
Stage 4- Basment
Operational-Utilities Rooms
[5 empty] | B04- Carpark Grid F-J/11-13 |  | COMMON AREA CHECKLIST
[5 empty] | B04- CarpARK Grid J-L/9-13 |  | COMMON AREA CHECKLIST
Village Ammenities Rooms
[5 empty] | Pool Plant Grid F-H/10-11 |  | COMMON AREA CHECKLIST
[5 empty] | B04- Store Grid H-I/11 |  | COMMON AREA CHECKLIST
[5 empty] | B04-Waste Room Grid I-J/11 |  | COMMON AREA CHECKLIST
Stairs/ Lift Lobbies
[5 empty] | B04- Lift 6 |  | COMMON AREA CHECKLIST
[5 empty] | B04- Stair 7 |  | COMMON AREA CHECKLIST
Hallways/ Corridors
[5 empty] | Pedestrian Ramp Grid H-I/8-11 |  | COMMON AREA CHECKLIST
B02
Ground Level
|  |  |  | Common Areas- Utilities rooms |  |  | COMMON AREA CHECKLIST
[5 empty] | G- Lift 4 Lobby |  | COMMON AREA CHECKLIST
[5 empty] | G- Stair 5 |  | COMMON AREA CHECKLIST
[5 empty] | G- Foyer external Auto door Grid D/9 |  | COMMON AREA CHECKLIST
[5 empty] | G-Riser Cuppboads |  | COMMON AREA CHECKLIST
[5 empty] | G-Corridor Grid C/10 |  | COMMON AREA CHECKLIST
[5 empty] | G- Corridor Grid C/10-13 |  | COMMON AREA CHECKLIST
[5 empty] | G-external Prewire Cams Grid C/6 |  | COMMON AREA CHECKLIST
[5 empty] | G-external Prewire Cams Grid A-B/10 |  | COMMON AREA CHECKLIST
[5 empty] | G-external Prewire Cams Grid A-B/13 |  | COMMON AREA CHECKLIST
[5 empty] | G-external Prewire Cams Grid D-E/10 |  | COMMON AREA CHECKLIST
Independent Apartments
[5 empty] | IA G71 |  | APARTMENT CHECKLIST
[5 empty] | IA G72 |  | APARTMENT CHECKLIST
[5 empty] | IA G73 |  | APARTMENT CHECKLIST
[5 empty] | IA G74 |  | APARTMENT CHECKLIST
[5 empty] | IA G75 |  | APARTMENT CHECKLIST
[5 empty] | IA G76 |  | APARTMENT CHECKLIST
[5 empty] | IA G77 |  | APARTMENT CHECKLIST
[5 empty] | IA G78 |  | APARTMENT CHECKLIST
[5 empty] | IA G79 |  | APARTMENT CHECKLIST
Level 1
Common Areas- Utilities rooms
[5 empty] | L1- Lift 4 Lobby |  | COMMON AREA CHECKLIST
[5 empty] | L1- Staire 5 |  | COMMON AREA CHECKLIST
[5 empty] | L1- Comms Room Grid C/10 |  | COMMS ROOM BUILD
[5 empty] | L1- Corridor Grid B-C/6-9 |  | COMMON AREA CHECKLIST
[5 empty] | L1- Corridor Grid B-C/9- 13 |  | COMMON AREA CHECKLIST
Independent Apartments
[5 empty] | IA 171 |  | APARTMENT CHECKLIST
[5 empty] | IA 172 |  | APARTMENT CHECKLIST
[5 empty] | IA 173 |  | APARTMENT CHECKLIST
[5 empty] | IA 174 |  | APARTMENT CHECKLIST
[5 empty] | IA 175 |  | APARTMENT CHECKLIST
[5 empty] | IA 176 |  | APARTMENT CHECKLIST
[5 empty] | IA 177 |  | APARTMENT CHECKLIST
[5 empty] | IA 178 |  | APARTMENT CHECKLIST
[5 empty] | IA 179 |  | APARTMENT CHECKLIST
Level 2
Common Areas- Utilities rooms
[5 empty] | L2- Lift 4 Lobby |  | COMMON AREA CHECKLIST
[5 empty] | L2- Stair 5 |  | COMMON AREA CHECKLIST
[5 empty] | L2- Comms |  | COMMS ROOM BUILD
[5 empty] | L2- Corridor Grid B-C/6-13 |  | COMMON AREA CHECKLIST
Independent Apartments
[5 empty] | IA 271 |  | APARTMENT CHECKLIST
[5 empty] | IA 272 |  | APARTMENT CHECKLIST
[5 empty] | IA 273 |  | APARTMENT CHECKLIST
[5 empty] | IA 274 |  | APARTMENT CHECKLIST
[5 empty] | IA 275 |  | APARTMENT CHECKLIST
[5 empty] | IA 276 |  | APARTMENT CHECKLIST
[5 empty] | IA 277 |  | APARTMENT CHECKLIST
[5 empty] | IA 278 |  | APARTMENT CHECKLIST
[5 empty] | IA 279 |  | APARTMENT CHECKLIST
Level 3
Common Areas- Utilities rooms
[5 empty] | L3 Plant Deck |  | COMMS ROOM BUILD
|  |  | Building Commisioning |  |  |  | COMMISSIONING CHECKLIST
B03
To be provided
B04
To be provided
B01
To be provided

## Miscellaneous Checklists
type | name | values
checklist | Quality Assurance Pre-Commencement Checklist
checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Ryman
checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint | Review Access Granted to Ryman & Relevant Parties
checkpoint | Matrix/Insights Setup (if required)
type | name | values
checklist | Job Details (Highett Site)
checkpoint | Site Info |  | Dep True
label | Site Address: 32 - 40 Graham Road Highett VIC 3190
text | Builders Details: Ryman Healthcare Construction
text | Project Managers Details
text | Site Managers Details
checkpoint | latest drawings (attached or referenced) |  | Dep True
checkpoint | Scope of Works Attached |  | Dep True
checkpoint | Additional Pre-Start Docs (attached or referenced) |  | Dep True

## Common Areas checklist
type | name | values
checklist | COMMON AREA CHECKLIST
section | Prewire
checkpoint | Access available
checkpoint | Framework available
checkpoint | WIFI cabling completed (Attach Photo)
checkpoint | Repeater cabling completed (Attach Photo)
checkpoint | CCTV Cabling completed (Attach Photo)
checkpoint | Nurse call cabling completed (Attach Photo)
checkpoint | DDU- Digital Display Unit- cabled (Attach Photo)
checkpoint | Access Control cabling completed (Attach Photo)
checkpoint | Salto Gate way Cabled (Attach Photo)
checkpoint | Salto Nodes Cabled (Attach Photo)
checkpoint | Data Cabling Completed (Attach Photos)
checkpoint | PA Cabling Completed (Attach Photos)
checkpoint | MATV Cabling Completed (Attach Photos)
checkpoint | Intercom Cabling Completed (Attach Photos)
checkpoint | NBN conduit installed (Attach Photo)
checkpoint | Attach photos of Fire penetrations & specify location
holdpoint | Raise remedial / Sign Off
section | Termination and Testing
checkpoint | WIFI Fit Off (Attach Photo)
checkpoint | Repeaters fit off (Attach Photo)
checkpoint | Nurse call fit off (Attach Photo)
checkpoint | DDU- Digital Display Unit- installed (Attach Photo)
checkpoint | CCTV cameras fit off (Attach Photo)
checkpoint | Access Control doors fit off (Attach Photo)
checkpoint | Salto Gateway Installed (Attach Photo)
checkpoint | Salto Node Installed (Attach photo)
checkpoint | Data Fit off (Attach Photos)
checkpoint | PA Fit off (Attach Photos)
checkpoint | MATV Fit Off (Attach Photos)
checkpoint | Intercom Fit Off (Attach Photos)
holdpoint | Raise remedial / Sign Off

## Apartments checklist
type | name | values
checklist | APARTMENT CHECKLIST
section | Pre-wire
checkpoint | Access available
checkpoint | Framework available
checkpoint | Comms box/NBN Conduit/Lead in Cables
checkpoint | Bed NC (Attached Photo)
checkpoint | Ensuit NC (Attached Photo
checkpoint | Ensuit Shower NC (Attach Photo)
checkpoint | Bath NC (Attach Photo)
checkpoint | Bath Shower NC (Attach Photo)
checkpoint | Toilet NC (Attach Photo)
checkpoint | Nurs Press (Attach Photo)
checkpoint | ODL (Attach Photo)
checkpoint | Bed 1 Phone (Attach Photo)
checkpoint | Bed 1 TV/Data (Attach Photo)
checkpoint | Bed 2 Phone (Attach Photo)
checkpoint | Bed 2 TV/Data (Attach Photo)
checkpoint | Bed 3 Phone (Attach Photo)
checkpoint | Bed 3 TV/Data (Attach Photo)
checkpoint | Lounge Data/Ph (Attach Photo)
checkpoint | Lounge TV (Attach Photo)
checkpoint | Kitchen Data/phn (Attach Photo)
checkpoint | Study Nook Data/Phone (Attach Photo)
checkpoint | Wifi (Attach Photo)
checkpoint | Client extras (Attach Photo)
checkpoint | Attach photos of Fire penetrations & specify location
holdpoint | Raise remedial / Sign Off
section | Termination and Testing
checkpoint | Cut-out
holdpoint | Raise remedial / Sign Off
checkpoint | Comms box installed
checkpoint | Comms box fit off (Attach Photo)
checkpoint | Bed NC Fit Off Tested (Attached Photo)
checkpoint | Ensuit NC Fit Off Tested (Attached Photo
checkpoint | Ensuit Shower NC (Attach Photo)
checkpoint | Bath NC Fit Off Tested (Attach Photo)
checkpoint | Bath Shower NC Fit Off Tested (Attach Photo)
checkpoint | Toilet NC Fit Off Tested (Attach Photo)
checkpoint | Nurs Press Fit Off Tested (Attach Photo)
checkpoint | ODL Fit Off Tested (Attach Photo)
checkpoint | Bed 1 Phone Fit Off Tested (Attach Photo)
checkpoint | Bed 1 TV Fit Off Tested (Attach Photo)
checkpoint | Bed 2 Phone Fit Off Tested (Attach Photo)
checkpoint | Bed 2 TV/Data Fit Off Tested (Attach Photo)
checkpoint | Bed 3 Phone Fit Off Tested (Attach Photo)
checkpoint | Bed 3 TV/Data Fit Off Tested (Attach Photo)
checkpoint | Lounge Data/Ph Fit Off Tested (Attach Photo)
checkpoint | Lounge TV Fit Off Tested (Attach Photo)
checkpoint | Kitchen Data/phn Fit Off Tested (Attach Photo)
checkpoint | Study Nook Data/Phone Fit Off Tested (Attach Photo)
checkpoint | Wifi Fit Off Tested (Attach Photo)
checkpoint | Never Alone Sensor Installed (Attach Photo)
checkpoint | Wireless Locks installed (Salto ) Attach photo
checkpoint | NBN Conduit/Draw rope installed (Attach Photo)
checkpoint | LAN Test data cables
checkpoint | Client extras (Attach Photo)
holdpoint | Raise remedial / Sign Off

## Care Rooms
type | name | values
checklist | CARE ROOMS CHECKLIST
section | Pre-wire
checkpoint | Access available
checkpoint | Framework available
checkpoint | Lead In cables (Attached Photo)
checkpoint | Bed NC (Attached Photo)
checkpoint | Ensuit NC (Attached Photo)
checkpoint | Shower NC (Attached Photo)
checkpoint | Nurs Press (Attached Photo)
checkpoint | ODL (Attached Photo)
checkpoint | Bed Phone (Attached Photo)
checkpoint | Room Data/Ph (Attached Photo)
checkpoint | Room TV High (Attached Photo)
checkpoint | Room TV Low (Attached Photo)
checkpoint | Wifi (Attached Photo)
checkpoint | Study Nook (Attached Photo)
checkpoint | Attach photos of Fire penetrations & specify location
holdpoint | Raise remedial / Sign Off
section | Termination and Testing
checkpoint | Cut-out
checkpoint | Bed NC Fit off/Tested (Attached Photo)
checkpoint | Ensuit NC Fit off/Tested (Attached Photo)
checkpoint | Shower NC Fit off/Tested (Attached Photo)
checkpoint | Nurs Press Fit off/Tested (Attached Photo)
checkpoint | ODL Fit off/Tested (Attached Photo)
checkpoint | Bed Phone Fit off/Tested (Attached Photo)
checkpoint | Room Data/Ph Fit off/Tested (Attached Photo)
checkpoint | Room TV High Fit off/Tested (Attached Photo)
checkpoint | Room TV Low Fit off/Tested (Attached Photo)
checkpoint | Wifi Fit off/Tested (Attached Photo)
checkpoint | Study Nook Fit off/Tested (Attached Photo)
holdpoint | Raise remedial / Sign Off

## Dementia Rooms
type | name | values
checklist | DEMENTIA ROOMS CHECKLIST
section | Pre-wire
checkpoint | Access available
checkpoint | Framework available
checkpoint | Lead in Cables (Attached Photo)
checkpoint | Bed NC (Attached Photo)
checkpoint | Ensuit NC (Attached Photo)
checkpoint | Nurse Press (Attached Photo)
checkpoint | ODL (Attached Photo)
checkpoint | DCM (Attached Photo)
checkpoint | Room PIR (Attached Photo)
checkpoint | Bath PIR (Attached Photo)
checkpoint | Room Relay (Attached Photo)
checkpoint | Bath Relay (Attached Photo)
checkpoint | Door Reed Sw (Attached Photo)
checkpoint | Bed Sensor (Attached Photo)
checkpoint | Bed Phone (Attached Photo)
checkpoint | Room Data/Ph (Attached Photo)
checkpoint | Room TV High (Attached Photo)
checkpoint | Room TV Low (Attached Photo)
checkpoint | Wifi (Attached Photo)
checkpoint | Study Nook (Attached Photo)
holdpoint | Raise remedial / Sign Off
section | Termination and Testing
checkpoint | Cut-out
checkpoint | Bed NC Fit off and tested (Attached Photo)
checkpoint | Ensuit NC Fit off and tested (Attached Photo)
checkpoint | Nurs Press Fit off and tested (Attached Photo)
checkpoint | ODL Fit off and tested (Attached Photo)
checkpoint | DCM Fit off and tested (Attached Photo)
checkpoint | Room PIR Fit off and tested (Attached Photo)
checkpoint | Bath PIR Fit off and tested (Attached Photo)
checkpoint | Room Relay Fit off and tested (Attached Photo)
checkpoint | Bath Relay Fit off and tested (Attached Photo)
checkpoint | Door Reed Sw Fit off and tested (Attached Photo)
checkpoint | Bed Sensor Fit off and tested (Attached Photo)
checkpoint | Bed Phone Fit off and tested (Attached Photo)
checkpoint | Room Data/Ph Fit off and tested (Attached Photo)
checkpoint | Room TV High Fit off and tested (Attached Photo)
checkpoint | Room TV Low Fit off and tested (Attached Photo)
checkpoint | Wifi Fit off and tested (Attached Photo)
checkpoint | Study Nook Fit off and tested (Attached Photo)
holdpoint | Raise remedial / Sign Off

## COMMS ROOM BUILD
type | name | values
checklist | COMMS ROOM BUILD
section | Pre-wire
checkpoint | Reticulation cables run
checkpoint | Attach photos of Fire penetrations & specify location
section | Comms room build
checkpoint | Walls built and painted
holdpoint | Raise remedial / Sign Off
checkpoint | Install cable tray
checkpoint | Install Rack
checkpoint | Loom cables
checkpoint | Terminate Fibre
checkpoint | Terminate patch panels
checkpoint | Install nurse call head end
checkpoint | Install UPS
checkpoint | Build MATV Head end (Attach Photo)
checkpoint | Build access control head end (Attach Photo)
checkpoint | Build PA Head end
checkpoint | Ryman network gear installed
checkpoint | Patching completed (Attach Photo)

## COMMISSIONING
type | name | values
checklist | COMMISSIONING CHECKLIST
section | Comissioning
checkpoint | Common area data cables LAN tested
holdpoint | Raise remedial / Sign Off
checkpoint | Patch cables installed into rack (Attach Photo)
checkpoint | Fire alarm interface programmed
checkpoint | Fire alarm interface comissioned
checkpoint | Fire alarm Report sent to Ryman
holdpoint | Raise remedial / Sign Off
checkpoint | Nurse call system programmed
checkpoint | Nurse call system comissioned
checkpoint | Nurse call Report sent to Ryman
holdpoint | Raise remedial / Sign Off
checkpoint | CCTV Programmed
checkpoint | CCTV Comissioned
holdpoint | Raise remedial / Sign Off
checkpoint | MATV Comissioned
holdpoint | Raise remedial / Sign Off
checkpoint | Access Control programmed
checkpoint | Access Control comissioned
holdpoint | Raise remedial / Sign Off
checkpoint | PA System comissioned
holdpoint | Raise remedial / Sign Off

## Theatre Checklist
type | name | values
checklist | THEATRE CHECKLIST
section | Prewire
checkpoint | Access available
checkpoint | Framework available
checkpoint | WIFI cabling completed (Attach Photo)
checkpoint | Repeater cabling completed (Attach Photo)
checkpoint | CCTV Cabling completed (Attach Photo)
checkpoint | Nurse call cabling completed (Attach Photo)
checkpoint | Data Cabling Completed (Attach Photos)
checkpoint | PA Cabling Completed (Attach Photos)
checkpoint | MATV Cabling Completed (Attach Photos)
checkpoint | Screen Cabling Completed (Attach Photos)
checkpoint | Projector Cabling Completed (Attach Photos)
checkpoint | Theatre speakers Cabling Completed (Attach Photos)
checkpoint | Attach photos of Fire penetrations & specify location
section | Termination and Testing
checkpoint | WIFI Fit Off (Attach Photo)
checkpoint | Repeaters fit off (Attach Photo)
checkpoint | CCTV cameras fit off (Attach Photo)
checkpoint | Nurse call fit off (Attach Photo)
checkpoint | Access Control doors fit off (Attach Photo)
checkpoint | Data Fit off (Attach Photos)
checkpoint | PA Fit off (Attach Photos)
checkpoint | MATV Fit Off (Attach Photos)
checkpoint | Screen Fit off (Attach Photos)
checkpoint | Projector fit off (Attach Photos)
checkpoint | Theatre Amp install (Attach Photos)
section | Commissioning
checkpoint | Test Theatre
holdpoint | Raise remedial / Sign Off