## Sheet1
Appendix C – Pavement Rehabilitation ITP
INSPECTION & TEST PLAN
EAST WAIKATO NOC
EW-I-0010 Inspection and Test Plan: | Pavement Rehabilitation
Work Component Management Plan: | (ITP: Pavement Rehabilitation)
Project: SH25 Boat Harbour Rehabilitation (SH25 – 0156/3100-3400
Inspection & Test Plan: Pavement Rehabilitation
Product Stage or Material to be Tested or Inspected | Type | Reference or | Method/Test | How often? | Records required | Responsibility | Initial on completion
| T = Test | Specification | required
I= Inspection
H= Hold point
Daily Work Briefing, confirm scope, location, that you have all staff, materials and plant needed | H | HSMP | Brief all team members on day’s work plan | Each morning | Daily diary | Supervisor
1.0 AP 40 M4 – Raw Aggregate Testing
1.1 Sand equivalent, or | T | Design | ≥35 Unit of measure? | 1 sample per 500m3 | Test Report | Project Manager
1.2 Clay Index (passing 0.075 mm), or | T | Design | <=3 Unit of measure? |  | Test Report | Project Manager
1.3 Plasticity Index | T | Design |  |  | Test Report | Project Manager
1.4 Particle size distribution | T | Design | 100% passing 63mm 40% ≥ 65%passing 19mm ≤ 10% passing 0.425mm425µm | 1 sample per 250m3 | Test Report | Project Manager
1.5 Solid Density | T | NZTA B/2 7.5 | Unit of measure? | 1 test | Test Report | Project Manager
Tolerance?
1.6 Determination of MDD & OWC | T | NZTA B/2 7.5 | Unit of measure? | 1 test | Test Report | Project Manager
Tolerance?
2.0 Site set up
2.1 Stakeholder notifications undertaken | H | CSCMP | Stakeholder notification emails and letter drops | Each site | Evidence of notifications | Network Manager
2.2 Mark-out of services and Permits in place | H | HSMP | Physical mark-out of all services and signed permits | Each site | Signed permit | Project Manager
2.3 Job start, identify risks and mitigations, communicate to team | H | HSMP | Record all hazards on JSEA and brief team | Each morning | Job start form | Supervisor
2.4 Set up traffic management to plan | T | TMP | Perform Site audit post-set up | Each site | Daily Diary | STMS
2.5 Assess environmental requirements of site and install sediment and erosion control measures if required | I | ESMP | Identify areas at risk and install control measures | Each site | Daily diary | Supervisor
3.0 Basecourse Inlay
4.1 Cement Spread Rate | H | NZTA B/5 | ±0.5kg/m2 | Per run | Cement Sheet | Stabilizing Supervisor
Weigh mat:
Every 400m²
|  |  | Average usage test: | Upon emptying the spreader and bulk tanker | Cement Sheet | Stabilizing Supervisor
Within ±2.5% of the specified rate
4.2 Hoe and stabilise to design depth | I | NZTA B/5 | -0mm / +20mm | Per run | Cement Sheet | Stabilizing Supervisor
4.3 Overlap longitudinal joints | I | NZTA B/5 | Record hoe-depth setting |  | Stringline Sheet | Stabilizing Supervisor
4.4 Plateau density test | T | NZTA B/5 | 200mm overlap | 20m centres each side | Plateau Density Sheet | Quality Engineer
4.5 Confirm layer thickness |  |  | Nuclear Densometer | 20m alternating wheel tracks
Tolerance?
4.6 Compaction as per sample test results | H | NZTA B/5 | Mean ≥95% | Every 20m alternating wheel tracks | NDM Sheet | IANZ Accredited Lab
Minimum ≥92%
4.7 Impact hammer test | H | Spec? | ≥70 CIV | Every 20m alternating wheel tracks | Clegg Sheet | IANZ Accredited Lab
4.8 Confirm surface levels | T | NZTA B/2 5.1 | -5mm / +15mm | Every 20m, full width | Stringline Sheet/As-Builts | Project Manager
4.9 Surface Finish
4.10 Confirm surface levels | H | NZTA B/2 | On-Site Inspection | Per site | Inspection between BECA/Higgins Staff | Renewals Manager
4.11 Surface Finish
5.0 Aggregate Testing – Sealing Chip
5.1 Crushing Strength | T | NZTA M/6 3.2 | <10% fines passing 2.36mm under 230 KN load | 1 Test | Test Report | IANZ accredited laboratory
5.2 Weathering Quality | T | NZTA M/6 3.3 | AA or BA | 1 Test | Test Report | IANZ accredited laboratory
5.3 Polished Stone Value | T | NZTA M/6 3.5 | PSV Required = 52 min | 1 Test | Test Report | Accredited PSV Testing Agency
5.4 Cleanliness | T | NZTA M/6 4.1.1 | Grade 5 – 89 min Grade 3 – 87 min Grade 4 – 85 min | 1 Test | Test Report | IANZ accredited laboratory
5.5 Grading | T | NZTA M/6 4.2.1 | See NZTA M/6 4.2.1 | 1 Test | Test Report | IANZ accredited laboratory
6.0 Chipseal Control
6.1 Confirm viscosity of bitumen | T | NZTA M/1 Table 1 | Viscosity PaS at 60°C | 1 Test | Construction | IANZ accredited laboratory
6.2 Confirm penetration grade of bitumen | T | NZTA M/1 Table 1 | Penetration at 25°C,100g, five seconds | 1 Test | Construction | IANZ accredited laboratory
6.3 Spray bitumen, then place chip *and roll – refer design for chipseal Grade | I | NZTA M/1 Table 1 | Visual Check | On-Site | Visual check | Supervisor
6.4 Check for excessive “windows” | I | NZTA M/1 Table 1 | Visual Check | On-Site | Visual check | Supervisor
7.0 Site Close-out
7.1 Field Quality Review | I | QMP | Verification of Work Standards | 10% of sites | Record in Audit Field of RAMM Contractor | Supervisor
7.2 Collect RAMM Data | I | SHDOM / Data Quality Plan | L1 Accredited Personnel | All Jobs | SHDOM Specs | Foreman/ Supervisor
7.3 Verify RAMM Data | I | SHDOM / Data Quality Plan | Level 2 Accredited Personnel | All Jobs | SHDOM Specs | Renewals Manager
(The Inspection and Test Plan defines the work sequence and lists key actions, risk controls, hold or witness points, inspections, and tests)
Signature Identification Block:
Print Name | Full Signature | Initials