## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Granular Rehab | [5 empty] | ITP - Granular Rehab
section | 1.0 AP 40 M4 – Raw Aggregate Testing
checkpoint | Sand equivalent, or
note | T
note | Reference or Specification: Design
note | Method/Test required: ≥35 Unit of measure?
note | How Often? 1 sample per 500m3
note | Records Required: Test Report
note | Responsibility: Project Manager
checkpoint | Clay Index (passing 0.075 mm), or
note | T
note | Reference or Specification: Design
note | Method/Test required: <=3 Unit of measure?
note | How Often? 1 sample per 500m3
note | Records Required: Test Report
note | Responsibility: Project Manager
checkpoint | Plasticity Index
note | T
note | Reference or Specification: Design
note | Method/Test required: <=3 Unit of measure?
note | How Often? 1 sample per 500m3
note | Records Required: Test Report
note | Responsibility: Project Manager
section | 2.0 Site set up
checkpoint | Particle size distribution
note | T
note | Reference or Specification: Design
note | Method/Test required:
note | • 100% passing 63mm
note | • 40% ≥ 65%passing 19mm
note | • ≤ 10% passing 0.425mm425µm
note | How Often? 1 sample per 250m3
note | Records Required: Test Report
note | Responsibility: Project Manager
checkpoint | Solid Density
note | T
note | Reference or Specification: NZTA B/2 7.5
note | Method/Test required:
note | • Unit of measure?
note | • Tolerance?
note | How Often? 1 test
note | Records Required: Test Report
note | Responsibility: Project Manager
checkpoint | Determination of MDD & OWC
note | T
note | Reference or Specification: NZTA B/2 7.5
note | Method/Test required:
note | • Unit of measure?
note | • Tolerance?
note | How Often? 1 test
note | Records Required: Test Report
note | Responsibility: Project Manager
section | 2.0 Site set up
checkpoint | Stakeholder notifications undertaken
note | H
note | Reference or Specification: CSCMP
note | Method/Test required: Stakeholder notification emails and letter drops
note | How Often? Each site
note | Records Required: Evidence of notifications
note | Responsibility: Network Manager
checkpoint | Mark-out of services and Permits in place
note | H
note | Reference or Specification: HSMP
note | Method/Test required: Physical mark-out of all services and signed permits
note | How Often? Each site
note | Records Required: Signed permit
note | Responsibility: Project Manager
checkpoint | Job start, identify risks and mitigations, communicate to team
note | H
note | Reference or Specification: HSMP
note | Method/Test required: Record all hazards on JSEA and brief team
note | How Often? Each morning
note | Records Required: Job start form
note | Responsibility: Supervisor
checkpoint | Set up traffic management to plan
note | T
note | Reference or Specification: TMP
note | Method/Test required: Perform Site audit post-set up
note | How Often? Each site
note | Records Required: Daily Diary
note | Responsibility: STMS
checkpoint | Assess environmental requirements of site and install sediment and erosion control measures if required
note | I
note | Reference or Specification: ESMP
note | Method/Test required: Identify areas at risk and install control measures
note | How Often? Each site
note | Records Required: Daily diary
note | Responsibility: Supervisor
section | 3.0 Basecourse Inlay
checkpoint | Cement Spread Rate
note | H
note | Reference or Specification: NZTA B/5
note | Method/Test required:
note | • ±0.5kg/m2
note | • Weigh mat: Every 400m²
note | • Average usage test: Within ±2.5% of the specified rate
note | How Often? Upon emptying the spreader and bulk tanker
note | Records Required: Cement Sheet
note | Responsibility: Stabilizing Supervisor
checkpoint | Hoe and stabilise to design depth
note | I
note | Reference or Specification: NZTA B/5
note | Method/Test required: -0mm / +20mm
note | How Often? Per run
note | Records Required: Cement Sheet
note | Responsibility: Stabilizing Supervisor
checkpoint | Overlap longitudinal joints
note | I
note | Reference or Specification: NZTA B/5
note | Method/Test required: Record hoe-depth setting
note | How Often? Per run
note | Records Required: Stringline Sheet
note | Responsibility: Stabilizing Supervisor
checkpoint | Plateau density test
note | T
note | Reference or Specification: NZTA B/5
note | Method/Test required: 200mm overlap
note | How Often? 20m centres each side
note | Records Required: Plateau Density Sheet
note | Responsibility: Quality Engineer
checkpoint | Confirm layer thickness
note | T
note | Reference or Specification: NZTA B/5
note | Method/Test required: Nuclear Densometer
note | How Often? 20m alternating wheel tracks
note | Records Required: Plateau Density Sheet
note | Responsibility: Quality Engineer
checkpoint | Compaction as per sample test results
note | H
note | Reference or Specification: NZTA B/5
note | Method/Test required:
note | • Mean ≥95%
note | • Minimum ≥92%
note | How Often? Every 20m alternating wheel tracks
note | Records Required: NDM Sheet
note | Responsibility: IANZ Accredited Lab
checkpoint | Impact hammer test
note | H
note | Reference or Specification: Spec?
note | Method/Test required: ≥70 CIV
note | How Often? Every 20m alternating wheel tracks
note | Records Required: Clegg Sheet
note | Responsibility: IANZ Accredited Lab
checkpoint | Confirm surface levels
note | T
note | Reference or Specification: NZTA B/2 5.1
note | Method/Test required: -5mm / +15mm
note | How Often? Every 20m, full width
note | Records Required: Stringline Sheet/As-Builts
note | Responsibility: Project Manager
checkpoint | Surface Finish
note | T
note | Reference or Specification: NZTA B/2 5.1
note | Method/Test required: -5mm / +15mm
note | How Often? Every 20m, full width
note | Records Required: Stringline Sheet/As-Builts
note | Responsibility: Project Manager
checkpoint | Confirm surface levels
note | H
note | Reference or Specification: NZTA B/2
note | Method/Test required: On-Site Inspection
note | How Often? Per site
note | Records Required: Inspection between BECA/Higgins Staff
note | Responsibility: Renewals Manager
checkpoint | Surface Finish
note | H
note | Reference or Specification: NZTA B/2
note | Method/Test required: On-Site Inspection
note | How Often? Per site
note | Records Required: Inspection between BECA/Higgins Staff
note | Responsibility: Renewals Manager
section | 5.0 Aggregate Testing – Sealing Chip
checkpoint | Crushing Strength
note | T
note | Reference or Specification: NZTA M/6 3.2
note | Method/Test required: <10% fines passing 2.36mm under 230 KN load
note | How Often? 1 Test
note | Records Required: Test Report
note | Responsibility: IANZ accredited laboratory
checkpoint | Weathering Quality
note | T
note | Reference or Specification: NZTA M/6 3.3
note | Method/Test required: AA or BA
note | How Often? 1 Test
note | Records Required: Test Report
note | Responsibility: IANZ accredited laboratory
checkpoint | Polished Stone Value
note | T
note | Reference or Specification: NZTA M/6 3.5
note | Method/Test required: PSV Required = 52 min
note | How Often? 1 Test
note | Records Required: Test Report
note | Responsibility: Accredited PSV Testing Agency
checkpoint | Cleanliness
note | T
note | Reference or Specification: NZTA M/6 4.1.1
note | Method/Test required:
note | • Grade 5 – 89 min
note | • Grade 3 – 87 min
note | • Grade 4 – 85 min
note | How Often? 1 Test
note | Records Required: Test Report
note | Responsibility: IANZ accredited laboratory
checkpoint | Grading
note | T
note | Reference or Specification: NZTA M/6 4.2.1
note | Method/Test required: See NZTA M/6 4.2.1
note | How Often? 1 Test
note | Records Required: Test Report
note | Responsibility: IANZ accredited laboratory
section | 6.0 Chipseal Control
checkpoint | Confirm viscosity of bitumen
note | T
note | Reference or Specification: NZTA M/1 Table 1
note | Method/Test required: Viscosity PaS at 60°C
note | How Often? 1 Test
note | Records Required: Construction
note | Responsibility: IANZ accredited laboratory
checkpoint | Confirm penetration grade of bitumen
note | T
note | Reference or Specification: NZTA M/1 Table 1
note | Method/Test required: Penetration at 25°C,100g, five seconds
note | How Often? 1 Test
note | Records Required: Construction
note | Responsibility: IANZ accredited laboratory
checkpoint | Spray bitumen, then place chip *and roll – refer design for chipseal Grade
note | I
note | Reference or Specification: NZTA M/1 Table 1
note | Method/Test required: Visual Check
note | How Often? On-Site
note | Records Required: Visual check
note | Responsibility: Supervisor
checkpoint | Check for excessive "windows"
note | I
note | Reference or Specification: NZTA M/1 Table 1
note | Method/Test required: Visual Check
note | How Often? On-Site
note | Records Required: Visual check
note | Responsibility: Supervisor
section | 7.0 Site Close-out
checkpoint | Field Quality Review
note | I
note | Reference or Specification: QMP
note | Method/Test required: Verification of Work Standards
note | How Often? 10% of sites
note | Records Required: Record in Audit Field of RAMM Contractor
note | Responsibility: Supervisor
checkpoint | Collect RAMM Data
note | I
note | Reference or Specification: SHDOM / Data Quality Plan
note | Method/Test required: L1 Accredited Personnel
note | How Often? All Jobs
note | Records Required: SHDOM Specs
note | Responsibility: Foreman / Supervisor
checkpoint | Verify RAMM Data
note | I
note | Reference or Specification: SHDOM / Data Quality Plan
note | Method/Test required: Level 2 Accredited Personnel
note | How Often? All Jobs
note | Records Required: SHDOM Specs
note | Responsibility: Renewals Manager