## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Site Works - Underground Services | [5 empty] | Site Works - Underground Services
checkpoint | Cabling installed in ducting (ducting by others)
checkpoint | Light fittings cleaned and sealed against water ingress
checkpoint | Cable seal applied pre cladding
checklist-flat | Building - Apartment - Exterior Lighting | [5 empty] | Building - Apartment - Exterior Lighting
checkpoint | Exterior apartment wall lighting prewired
checkpoint | Cable seal applied pre cladding
checkpoint | Exterior apartment wall lighting installed and connected
checkpoint | Light fittings cleaned and sealed against water ingress
checklist-flat | Building - Apartment - Exterior Lighting Level 1 | [5 empty] | Building - Apartment - Exterior Lighting Level 1
checkpoint | Cable seal applied pre cladding
checkpoint | Exterior apartment wall lighting installed and connected
checkpoint | Light fittings cleaned and sealed against water ingress
checklist-flat | Containment - Communal Corridor | [5 empty] | Containment - Communal Corridor
checkpoint | Cable tray installed at high level
checkpoint | Cable tray droppers installed on ceiling
checkpoint | Seismic installed where required as per kcl certified design
checkpoint | Bonding completed and connected with correct size
checkpoint | Catenary wires installed
checkpoint | Catenary correctly supported
checkpoint | Subcircuits taped and supported
checkpoint | Subcircuits cable tied and supported
checklist-flat | Containment - Corridor/Circulation | [5 empty] | Containment - Corridor/Circulation
checkpoint | Cable runs marked and hilti fixings /catenery wires
checkpoint | Subcircuits cable tied and supported in ceiling space
checklist-flat | Distribution - Switchboards on Levels 1 - 3 | [5 empty] | Distribution - Switchboards on Levels 1 - 3
checkpoint | Installation completed and securely mounted
checkpoint | Submains terminated
checkpoint | Subcircuits terminated including labelling/ferrules to all cores
checkpoint | Earthing/bonding terminated
checkpoint | DB schedule completed
checkpoint | SB test sheet completed
checkpoint | Earthing test sheet completed
checkpoint | Distribution board test sheet completed
checkpoint | DB schedule installed
checkpoint | Clean of all debri and marks
checklist-flat | Lighting Controls/Communal Boards | [5 empty] | Lighting Controls/Communal Boards
checkpoint | Lighting prewired - incl dali
checkpoint | Lighting installed and connected
checkpoint | Emergency lighting prewired
checkpoint | Emergency lighting installed
checkpoint | Exit lighting prewired
checkpoint | Exit lighting installed
checkpoint | CBus sensors prewired
checkpoint | CBus sensors installed
checkpoint | Subcircuits prewired and tied back to DB
checkpoint | Conduit installed where required
checkpoint | Subcircuits terminated at DB
checkpoint | Power outlets isolators terminated
checkpoint | Fixed wired appliances connected and bonded accordingly
checklist-flat | Apartments - Care Suits Type 1,3 and Dementia Suits & Other Rooms | [5 empty] | Apartments - Care Suits Type 1,3 and Dementia Suits & Other Rooms
checkpoint | Setout + flushboxes installed/complete as per architectural drawings
checkpoint | Lighting prewired for dimming as per updated drawing
checkpoint | Lighting prewired
checkpoint | Lighting installed and connected
checkpoint | Subcircuits prewired and tied back to DB
checkpoint | Conduit installed where required
checkpoint | Subcircuits terminated at floor DBs
checkpoint | Switches/controls installed/connected
checkpoint | Power outlets isolators terminated
checkpoint | Fixed wired appliances connected and bonded accordingly
checklist-flat | Bathroom Pods | [5 empty] | Bathroom Pods
checkpoint | Correct cabling installed as per e cubed updated electrical drawings
checkpoint | Cabling meets install requirment
checkpoint | Cabling brought out through correct location.
checkpoint | Correct earthing cable size installed (4mm2)
checkpoint | Conduct insulation test on all pre installed cables by others
checkpoint | Conduct continuity test on all pre installed cables by others
checkpoint | Confirm all pod cables run back to provided connect point
checklist-flat | Commissioning - Switch Boards | [5 empty] | Commissioning - Switch Boards
checkpoint | Switchboard test sheet completed and added to dropbox
checkpoint | DB schedule completed, installed into DB and added to dropbox
checkpoint | Distribution board test sheet completed and added to dropbox
checkpoint | Subcircuit commissioning results sheet completed and added to dropbox
checkpoint | Distribution board check sheet completed and added to dropbox
checkpoint | Earthing test sheet completed and added to dropbox
checkpoint | Emergency lighting test sheet completed and added to dropbox
checkpoint | Timeclock test sheet completed and added to dropbox
checkpoint | Board free from debri, no marks, all accessories installed
checkpoint | Labelling completed on all field outlets, switches and isolators etc