## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | QA - Precast Walls Checklist |  |  |  |  | Yes | QA - Precast Walls Checklist | 112ff51a-7254-4d35-8559-517c88d5fc89
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast walls manufacturing completed and transported safely to the site
boolean | 3f0c9123-04cc-5f32-aa11-88b25d00d729 |  | tickbox | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Site Setout completed
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the panel checked/correct
checkpoint-status |  |  | checkpoint | Panel propping checked
checkpoint-status |  |  | checkpoint | Checked rebar requirements for any insitu stich joints
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
boolean | c727a0e4-0a22-564e-a61b-d00686786964 |  | tickbox | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Interior Timber Framing QA for Area: |  |  |  |  | Yes | QA - Interior Timber Framing | 23522a22-fc59-40b4-a8e9-d4e7e3c9832c
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked & referenced
checkpoint-status |  |  | checkpoint | All materials checked & aligning with consented design & specifications prior to install
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required)
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | QA - Interior Fitout |  |  |  |  | Yes | QA - Interior Fitout | 3bf6f283-d9ca-49a4-b962-be9fe3ccb1ea
checkpoint-group |  |  | section | Plumbing First Fix
checkpoint-status |  |  | checkpoint | Plumbing first fix complete
boolean | 389b3048-2c43-5218-80c2-d4b99746bd06 |  | tickbox | Mixers are in correct position (hole allowance to work with tiles)
boolean | 61ebd45c-8d50-5622-8f6f-5e58628f2929 |  | tickbox | All water & gas risers are complete
boolean | b86543b1-3834-5bf9-a63b-7cdfe80c7ae8 |  | tickbox | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | b32fba7c-1ca2-5c09-87cb-501dbd999986 |  | tickbox | Power points have been installed as per the electrical plans
boolean | 21fd5cfa-57e2-526c-8e68-8edc6d2e1529 |  | tickbox | All comms are installed to allow for good detailing around
boolean | 2ab90cd5-6475-5080-b61d-978515961a5c |  | tickbox | GPO's are correct for air conditioning & functional
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Mechanical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | b085abdf-8b33-52aa-bb45-3aa7cabea7cb |  | tickbox | All aircon has been roughed in & tested
boolean | 494114c5-dbd8-5484-a652-93a2816e5d1b |  | tickbox | All mech has been roughed in & completed
boolean | ce9234ea-04ad-57f2-b8d8-12e5a270f49d |  | tickbox | All services that go through fire rated walls to be treated with collars/fire rated sealant
boolean | 1e0265e2-0a58-50c7-aa67-4699def69b79 |  | tickbox | Duct work to be tear free & sealed prior to cleaning
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Passive Fire
checkpoint-status |  |  | checkpoint | Ensure all penetrations have been installed as per specifications
checkpoint-status |  |  | checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications
checkpoint-status |  |  | checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint-status |  |  | checkpoint | Ensure that suitable access is provided to mechanical fire dampers
checkpoint-status |  |  | checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in
checkpoint-status |  |  | checkpoint | Check that fire doors have been filled
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Post Wall Linings
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for insulation
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for fire rated walls
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Bathroom & Laundry Waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing completed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Tiling
checkpoint-status |  |  | checkpoint | All floors fall to wastes & don't hold water
checkpoint-status |  |  | checkpoint | Ensure all tiles are fixed correctly
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Joinery Fit Out
checkpoint-status |  |  | checkpoint | All bathroom joinery installed as per specifications
checkpoint-status |  |  | checkpoint | All kitchen joinery installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Services Fit Out
checkpoint-status |  |  | checkpoint | Plumbing fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Electrical fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Air Conditioning / Mech fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Internal Painting, Framing & Carpet
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
checkpoint-status |  |  | checkpoint | Painting completed as per specs, correct paint product and colour used
checkpoint-status |  |  | checkpoint | Carpet installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Fire System
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Sprinkler rough fit off completed
checkpoint-status |  |  | checkpoint | Sprinklers commissioned
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Scarbro Final Sign - Off
checkpoint-status |  |  | checkpoint | All apartment work is completed as per specifications / drawings. All relevant trade QA reviewed & approved
boolean | 07497d14-4b56-5b55-8ea2-192bf6384268 |  | tickbox | Scarbro - apartment final sign off
label | 03131f9b-d739-576f-bd71-6cdc6c2203d7 |  | note | Click to attach signature sign off below
checklist-flat |  |  | checklist | Footings for Area: |  |  |  |  | Yes | QA - Footings | 3ce7d06a-0e2f-458b-abb7-fe8d1b6355f1
checkpoint-status |  |  | checkpoint | Drawings photo with location
checkpoint-status |  |  | checkpoint | Set out correct
checkpoint-status |  |  | checkpoint | Boxing correct
checkpoint-status |  |  | checkpoint | Reinforcing
checkpoint-status |  |  | checkpoint | Starter setout
checkpoint-status |  |  | checkpoint | Inspect
checkpoint-status |  |  | checkpoint | Pour
checklist-sectioned |  |  | checklist | QA - Structural Steel Checklist |  |  |  |  | Yes | QA - Structural Steel Checklist | 50364988-2f7a-4796-8447-b56679e25773
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Structural steel items checked
label | 0a4551b9-a50c-529d-a2a4-d0b6d11e25eb |  | note | Type/Size Checked
label | 48cbc615-3fb8-56ee-9dc1-41e5d713e575 |  | note | Finishing checked (ie. Painted, Galvanised, etc)
checkpoint-status |  |  | checkpoint | Cast in/anchor bolts and plates installed
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels checked/correct
checkpoint-status |  |  | checkpoint | All dry packing completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Structural steel work completed within tolerance in respective area
boolean | 63a40bc1-6561-56eb-9fbe-6701f9ee3154 |  | tickbox | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Piling for Area: |  |  |  |  | Yes | QA - Piling | 572c63a5-535a-42ea-9425-bc6a55216255
checkpoint-group |  |  | section | Prepour
checkpoint-status |  |  | checkpoint | Pile diameter
text | 7b0b2241-a4ec-5a24-8b59-4f1777156812 |  | textbox | Pile diameter
checkpoint-status |  |  | checkpoint | Engineer Inspection reinforcing
checkpoint-status |  |  | checkpoint | Geotech inspection
checkpoint-status |  |  | checkpoint | Council inspection
checkpoint-status |  |  | checkpoint | ICB QA received
checkpoint-status |  |  | checkpoint | Any Issues with Pile
text | 4ea0ab1b-ea2a-5e6d-9a9d-9da3c8a69186 |  | textbox | Any issues/ collapse?
text | 9d88bd9a-3d81-5a1e-99b3-51d415fc8a4e |  | textbox | Weather conditions
checkpoint-group |  |  | section | Post pour
checkpoint-status |  |  | checkpoint | Concrete poured to the correct height
text | d8e01ebf-4f11-5484-8652-36e412990d09 |  | textbox | Date of Concrete Pour:
checkpoint-status |  |  | checkpoint | Sand filled to clay height
checkpoint-status |  |  | checkpoint | Cage centre of the hole
checkpoint-status |  |  | checkpoint | No bars damaged
checkpoint-status |  |  | checkpoint | Concrete cleaned from reinforcing
checklist-flat |  |  | checklist | QA - Waterproofing Checklist |  |  |  |  | Yes | QA - Waterproofing Checklist | 9ddc1ce9-c262-482d-92ac-ac0dddbedf91
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status |  |  | checkpoint | General photos/comments during install
checkpoint-status |  |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status |  |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
label | a845dc49-6bc7-5ca5-a82c-18277d977221 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
boolean | 89689ed9-de0c-563c-8a9a-03651f264759 |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Retaining Pole Pre-Pour Inspection |  |  |  |  | Yes | QA - Retaining Poles | ac054603-2b1b-41f5-9280-d40cabbfb327
checkpoint-status |  |  | checkpoint | Surveyor set out alignment
checkpoint-status |  |  | checkpoint | Poles spaced at 900mm centres
checkpoint-status |  |  | checkpoint | Correct diameter pole
checkpoint-status |  |  | checkpoint | Correct embedment depth
checkpoint-status |  |  | checkpoint | Top of pole above ground level
checkpoint-status |  |  | checkpoint | Parallel to boundary
checkpoint-status |  |  | checkpoint | Front of post in straight line
checkpoint-status |  |  | checkpoint | 20mpa concrete poured to correct height
checkpoint-status |  |  | checkpoint | Photos of location and placement
checkpoint-status |  |  | checkpoint | Photo of concrete dockets
checkpoint-status |  |  | checkpoint | Any additional items / observations
checkpoint-status |  |  | checkpoint | Retaining Poles completed, reviewed and approved
checklist-flat |  |  | checklist | QA - Grout |  |  |  |  | Yes | QA - Grout | da7d1712-12c7-4c32-82b4-b820e7bbf4e5
checkpoint-status |  |  | checkpoint | Grouting works completed
label | 73f0ed41-02ae-5969-a8ce-6c7c7574914d |  | note | Photos
checklist-sectioned |  |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pour | fe752d32-47cf-4c17-9f3d-9db47ecfd03d
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | 451dfd4c-8f28-589a-9ead-f7ccdf2bd341 | DataPoint is missing 'button' values | button | Size and type correct to specification
boolean | f90c578f-ec6d-5669-af63-02a4971bb8fa |  | tickbox | Reinforcing spacing and location correct | Yes, N/A
boolean | eb1fefb9-5cc1-5d0a-b796-3e16f5c64604 |  | tickbox | Specified covers checked/correct | Yes, N/A
boolean | b2295ef4-834c-59a8-b68e-d3275dfb4698 |  | tickbox | Splice laps checked/correct | Yes, N/A
boolean | 5d2f0302-42fd-5128-9902-2e5093b57fac |  | tickbox | Any starter bars are installed correctly (location, size and spacing ) | Yes, N/A
boolean | 2747bf11-1161-5b16-b769-486374add88a |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed | Yes, N/A
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | c42b5d98-4a6f-5030-957a-ec105539610d |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | 2068b14a-04c8-5baa-9a96-75c4fb5fb09e |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
boolean | 21c40f74-8d44-5efa-9f96-821a51c1222c |  | tickbox | Trades QA received & attached as applicable