## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITR 014 Sanitary Fit Off |  |  |  |  | Yes | ITR 014 Sanitary Fit Off | 02b4978d-bdd2-4937-991e-686699476e63
checkpoint-status |  |  | checkpoint | All works to be set our as per approved Architectural Drawing No.
checkpoint-status |  |  | checkpoint | Inspect for product defects.
checkpoint-status |  |  | checkpoint | Install as per manufacturer's recommendations and requirements
checkpoint-status |  |  | checkpoint | All sanitary items to be tested in accordance to specifications and manufacturers requirements
checkpoint-status |  |  | checkpoint | Check for leaks
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | ITR 013 Water Meter |  |  |  |  | Yes | ITR 013 Water Meter | 09a4aea5-1e95-4b14-9b6b-6b7de6250bbd
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All meter work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Ensure that all pipework to meters has been sealed and jointed, all capping adequately installed for testing.
checkpoint-status |  |  | checkpoint | Ensure all meters are sufficient supported and installed in correct location
checkpoint-status |  |  | checkpoint | Pass an amount of water in a container of known volume (bucket) and confirm the volume of water and meter reading are the same or within the required tolerances
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-sectioned |  |  | checklist | Inspection Test Plan |  |  |  |  | Yes | Inspection Test Plan | 1a399967-9944-4536-8757-dcd094047d7c
checkpoint-group |  |  | section | Set Out Penetrations
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Penetrations and Fire Collars to be in accordance with specification as required for each fire compartment rating and for each fire rated element.
checkpoint-status |  |  | checkpoint | Ensure Fire Collars are installed as per manufacturer’s instructions. Tabs on cast in, collars to be exposed. Photos of collar and labelling referencing fire matrix if required
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications and drawings. All certificates completed and submitted
label | 9af3d250-6970-5857-81b0-f0494891f60b |  | note | ITR 001
checkpoint-group |  |  | section | In Ground Sewer Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings
checkpoint-status |  |  | checkpoint | Inspection booked with VBA for in ground drainage. HP can sign off if inspector does not attend.
label | d0331185-9ac8-53dd-ace9-18a711d7b09b |  | note | ITR 002
checkpoint-group |  |  | section | In Ground Storm Water Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification and AS 3500
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawings No
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted.
label | b6530cbb-7322-5973-b093-ba653988c7e4 |  | note | ITR 003
checkpoint-group |  |  | section | In Ground Greasy Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | 7ee0219d-989e-56f8-b67a-b76dd382ce7f |  | note | ITR 004
checkpoint-group |  |  | section | Fire Services
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 2419 & AS 2441 or alternatively approved by CFA/MFB
checkpoint-status |  |  | checkpoint | All pipe work to be tested to 1700 kPA in accordance to specifications and requirements as per AS 2419 Hydrants & AS 2441 Hose Reels
checkpoint-status |  |  | checkpoint | Prior to handover system must be inspected & certified in accordance to drawings, code, specification, dispensation & 129 report and FER.
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted.
label | aee28dfd-ca89-54cb-ac7c-3ec5c117a385 |  | note | ITR 005
checkpoint-group |  |  | section | Suspended Sewer Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification and acoustic engineers report
checkpoint-status |  |  | checkpoint | As per AS 3500 all traps have been tested for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | 177254dd-1f95-518a-b77e-a2341783057a |  | note | ITR 006
checkpoint-group |  |  | section | Suspended Stormwater
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels, gradients & clearance levels/head height in accordance with specifications and requirements
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification and acoustic engineers report
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | 13fb5773-12d6-5a63-a549-96af85bf58b3 |  | note | ITR 007
checkpoint-group |  |  | section | Domestic Cold Water In
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 in accordance with specifications and requirements
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | 2505b1cc-087a-5c0f-b9b4-e35d559bcab8 |  | note | ITR 008
checkpoint-group |  |  | section | Gas Service
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500 or alternatively approved including road sizes, clipping configurations and methods
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
checkpoint-status |  |  | checkpoint | Prior to gas being turned on ESV must be notified, inspection arrange and approval issued (if required). HP Management must be notified at the completion of works.
label | f5b35d97-19b4-5761-b121-e4af2f2a44a1 |  | note | ITR 009
checkpoint-group |  |  | section | Hot & Cold Water Rough In
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.1.2015 & AS 3500.4.2015 or alternatively approved.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance with specifications and requirements namely 1500 kPA for 30 minutes as per AS 3500:1 clause 18.1.3.
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted.
label | f7cd022b-340f-57ea-b9a7-ac1805099887 |  | note | ITR 010
checkpoint-group |  |  | section | Hot Water Service
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples HWS.. Ensure all materials are in accordance to specification AS 3500.1.2015 & AS 3500.4.2015 or alternatively approved
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | 1fe38fdb-a836-5093-8fa7-e16dcd5399d0 |  | note | ITR 011
checkpoint-group |  |  | section | Water Meter
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of materials. Ensure all materials are in accordance to specification AS 3500.1.2015 & AS 3500.4.2015 or alternatively approved
checkpoint-status |  |  | checkpoint | All works to be set up as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings
checkpoint-status |  |  | checkpoint | All meter work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Tested and Commissioning completed by passing an amount of known volume (bucket) and confirm the volume of water and meter reading are the same or within the required tolerances
label | 2e685d54-f53f-5669-9c9d-c592714244f6 |  | note | ITR 012
checkpoint-group |  |  | section | Sanitary Fit Off
checkpoint-status |  |  | checkpoint | Submit all sanitary fixtures and tapware. Ensure all material is in accordance with specification AS 3500 and watermarked.
label | c39da493-8974-5b8f-a89d-d8a7ca56c4c5 |  | note | ITR 013
checkpoint-group |  |  | section | Backflow Test Report
checkpoint-status |  |  | checkpoint | Submit Backflow Test Report
label | 922fd125-ce7d-59fb-9ab5-22139d08e614 |  | note | ITR 014
checkpoint-group |  |  | section | Tempering Valve Test Report
checkpoint-status |  |  | checkpoint | Submit Tempering Valve Test Report
label | ba9be896-17e1-5c34-b031-af50df0dd049 |  | note | ITR 015
checkpoint-group |  |  | section | Thermostatic Mixing Valve Test Report
checkpoint-status |  |  | checkpoint | Submit Thermostatic Mixing Valve Test Report
label | f5c83801-d650-5a71-b680-f0b9613651d0 |  | note | ITR 016
checkpoint-group |  |  | section | Third Party Commissioning
checkpoint-status |  |  | checkpoint | Submit any Third Party Commissioning Reports which one are applicable:
label | d858f886-4509-5363-9d7f-0218fd8a9227 |  | note | Ie Pumps, Tanks, HWS, Fire Hydrants
label | e9339495-f564-5a9c-ac37-1ce9a0d6e568 |  | note | Report from Third Party
checklist-flat |  |  | checklist | ITR 005 Fire Service |  |  |  |  | Yes | ITR 005 Fire Service | 2dce7bb9-4784-4c56-ad6c-51b02d08f5ef
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & Standards or alternatively approved by CFA/MFB.
checkpoint-status |  |  | checkpoint | All pipework to be tested TO 1700 kPA in accordance to specifications &
checkpoint-status |  |  | checkpoint | requirements as per AS 2419 Hydrants & AS 2441 Hose Reels
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checkpoint-status |  |  | checkpoint | Prior to handover system must be inspected & certified in accordance to drawings, code, specification, dispensation, 129 report and FER
checklist-flat |  |  | checklist | ITR 007 Suspended Storm Drainage |  |  |  |  | Yes | ITR 007 Suspended Storm Drainage | 355e7043-45bf-4f44-b506-ffe9e7d165f5
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | Internal Audit Checklist |  |  |  |  | Yes | Internal Audit Checklist | 4774b83c-6a93-41b9-ab7e-62ebe0dac989
checkpoint-status |  |  | checkpoint | Drawing Register Current
checkpoint-status |  |  | checkpoint | Drawings as per Register
checkpoint-status |  |  | checkpoint | ITP Records
checkpoint-status |  |  | checkpoint | Material Specification
checkpoint-status |  |  | checkpoint | Sanitary Specification
checkpoint-status |  |  | checkpoint | Calibration records
checkpoint-status |  |  | checkpoint | Sample Register
text | 84a9b71e-de12-57fb-b889-4124ccee8e90 |  | textbox | Comments
text | 8b62b117-eb26-5c59-9c2e-bcf9bf0d85e8 |  | textbox | Items of concern
text | 6d7cf492-89e6-5ceb-8417-2a82c68df4af |  | textbox | Action required
text | aeed4337-3c7b-5338-926e-72d2463bcd21 |  | textbox | Future recommendations
checkpoint-status |  |  | checkpoint | Signed off by Highbury Plumbing Supervisor
checklist-flat |  |  | checklist | ITR 002 Sewer Drainage |  |  |  |  | Yes | ITR 002 Sewer Drainage | 4ef72eba-36a9-4500-ab80-c332e62e79c9
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Notify HP Management for inspection of drainage prior to backfill.
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage. HP can sign off if inspector does not attend.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 017 Thermostatic Mixing Valve Test Report |  |  |  |  | Yes | ITR 017 Thermostatic Mixing Valve Test Report | 4ff1a767-225b-4337-b068-c238560d8924
checkpoint-status |  |  | checkpoint | Thermostatic Mixing Valve Test
text | 91959b26-b680-50aa-83d6-de8d36388503 |  | textbox | Licence No.
text | 76227ca5-a175-5a52-b78c-701f730e9709 |  | textbox | Test kit serial No.
text | 561dbbdd-2408-5eb1-ac10-1170b05dc09d |  | textbox | Date test kit last certified:
text | ff746d6b-7fea-5f4b-b399-d568ac69e523 |  | textbox | Place of certification
text | 1953fa84-5e25-573d-9e3d-dad036bd2eda |  | textbox | Make
text | ab9bf7fa-0617-52c1-b70c-af64e83706dd |  | textbox | Model
text | 6326571c-91ea-5c4a-a12b-ce424c42e1b7 |  | textbox | Location of valve
checkpoint-status |  |  | checkpoint | Shut down test
checkpoint-status |  |  | checkpoint | Flush / Clean filters
checkpoint-status |  |  | checkpoint | Static Test
boolean | 4d8b6bb0-95d2-5964-84f2-ff7bf2ae0aa4 |  | tickbox | One outlet in use
text | 52837403-c9bc-52a6-ae7b-f35f4bd8f0b5 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Temp of warm water
text | 46c3ca90-5846-5b54-a6d6-97ef149c2c32 |  | textbox | Fixture
text | 85f4305c-fbd8-5ff8-ad94-34cbf98750ce |  | textbox | Pre Set Temp
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | 4af0c3db-f88e-558b-a7b0-aa773df4c874 |  | textbox | Parts & Materials Used
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-flat |  |  | checklist | Add Photos |  |  |  |  | Yes | Add Photos | 50cc8b50-b4bd-41e4-9a54-c6965c388758
checkpoint-no-status |  |  | checkpoint | Attach photos to show the pit has been cleaned out
text | ce817c90-f941-51ff-a797-1a66935cb548 |  | textbox | Date:
checklist-flat |  |  | checklist | Non Conformance Report |  |  |  |  | Yes | Non Conformance Report | 65bc6c5e-24ac-4eb9-88c5-71af00857647
checkpoint-status |  |  | checkpoint | Report completed
text | e767f6a7-266f-52fc-9718-973f4713e410 |  | textbox | Short description
text | f53dc87d-f1af-549f-9f73-6cd7c6cb0bdf |  | textbox | NCN NO:
text | 5d929266-a0fe-5c1e-a09f-61b33a22d5ed |  | textbox | Level / Area
text | 17612156-15cd-5e79-8235-c80965bc6ff3 |  | textbox | Grid Coord
text | 9baf8494-6c88-554b-be81-20a83cebd916 |  | textbox | Responsibility
text | 35d170e1-59d5-5d60-a868-7f8626d67489 |  | textbox | Non Conformance Details
checkpoint-status |  |  | checkpoint | Method of disposition
text | 36ccc5cb-7f71-5e03-b77a-49f449280aba |  | textbox | Approval required from
checkpoint-status |  |  | checkpoint | Repair / Use as is
text | f6321488-f765-5cb9-8bac-8baaba3ca64a |  | textbox | Customer
checkpoint-status |  |  | checkpoint | Rework / Replace
text | 66ec4bd0-4544-5c21-933a-0c4394efbb58 |  | textbox | Project Manager
checkpoint-status |  |  | checkpoint | Signed off by Highbury Plumbing Supervisor
checkpoint-status |  |  | checkpoint | Signed off by Scentre Group
checklist-flat |  |  | checklist | ITR 001 Set Out Penetrations |  |  |  |  | Yes | ITR 001 Set Out Penetrations | 79be261a-f9fa-4d01-9ee7-bb961fef1876
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings. Works set out to IFC Drawing No.
checkpoint-status |  |  | checkpoint | All penetrations and fire collars to be as per specifications or alternatively approved
checkpoint-status |  |  | checkpoint | Ensure fire collars are installed as per manufacturer’s instructions.
checkpoint-status |  |  | checkpoint | Tabs on cast in collar to be exposed.
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 006 Suspended Sewer Drainage |  |  |  |  | Yes | ITR 006 Suspended Sewer Drainage | 7cb70aab-9416-4095-964b-ac30ec61fcbf
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 009 Domestic Cold Water In Ground |  |  |  |  | Yes | ITR 009 Domestic Cold Water In Ground | 7ea3644d-53be-498d-9dad-0079fee6f95e
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 & in accordance with specifications and requirements . Ensure isolation from authority main, fixtures, tapware and appliances while undertaking testing.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | Documentation |  |  |  |  | Yes | Documentation | 82244024-f1ba-4ee6-a987-9ecb0a1eac1d
checkpoint-status |  |  | checkpoint | Attach relevant documents
checklist-flat |  |  | checklist | ITR 004 Greasy Drainage In Ground |  |  |  |  | Yes | ITR 004 Greasy Drainage In Ground | 83673e75-f4ab-4e26-bb6b-cdb49a250798
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 010 Gas Service |  |  |  |  | Yes | ITR 010 Gas Service | 8bdbfd36-27b3-41df-9963-a20a8e292b84
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS5601.1 or alternatively approved including rod sizes and clipping configurations and methods
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance with specifications and requirements & AS5601.1
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checkpoint-status |  |  | checkpoint | Prior to gas being turned on ESV must inspect and approved installation if required, including all builders work requirements IE signage, access panels, ventilation, riser shafts etc..
checkpoint-status |  |  | checkpoint | Must notify HP management on completion of works.
checklist-flat |  |  | checklist | ITR 015 Backflow Test Report |  |  |  |  | Yes | ITR 015 Backflow Test Report | 8becf26b-123e-4b2c-92d8-abaf5cc0baa3
checkpoint-status |  |  | checkpoint | Backflow Test Report Completed - Attach Document
checklist-flat |  |  | checklist | ITR 018 Safety Shower & Eye Wash |  |  |  |  | Yes | ITR 018 Safety Shower & Eye Wash | 961b0466-b0dc-4df5-b047-34e17ae392bf
checkpoint-status |  |  | checkpoint | All safety shower work to be as per specifications & AS/NZS4775-2007 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Ensure that all pipework to safety shower has been sealed and jointed.
checkpoint-status |  |  | checkpoint | Ensure safety shower is sufficiently supported and installed in correct location
checkpoint-status |  |  | checkpoint | Flow test- Pass an amount of water in a container of known volume (bucket or bin) and confirm the volume of water discharged into the bucket. AS4775-2007 requires 76 litres per minute for safety shower, 26 litres per minute for eye/face wash
checkpoint-status |  |  | checkpoint | Temperature test- AS4775-2007 requires temperature to be between 15.6°C & 37.8°C
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | ITR 003 Stormwater Drainage In Ground |  |  |  |  | Yes | ITR 003 Stormwater Drainage In Ground | ae4ef601-70d7-4158-ba62-bb6c33f2578e
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | All pits to be checked for correct invert levels & finished floor levels in accordance to specifications & requirements & IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications & requirements
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 011 Hot & Cold Rough In |  |  |  |  | Yes | ITR 011 Hot & Cold Rough In | b0fdc203-7f23-4b6f-9a22-20295ebc692f
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings and penetrations to be installed to - IFC Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 & in accordance with specifications and requirements . Ensure isolation from authority main, fixtures, tapware and appliances while undertaking testing
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 008 Suspended Greasy Drainage |  |  |  |  | Yes | ITR 008 Suspended Greasy Drainage | c757a86b-035a-4b59-ac89-5718f4d1cad7
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 016 Tempering Valve Test Report |  |  |  |  | Yes | ITR 016 Tempering Valve Test Report | c8118f4e-6cbe-493d-90f3-25f732a6d57e
checkpoint-status |  |  | checkpoint | Tempering Valve Test
text | 25d534d5-2cce-54af-acc1-773e49df0af3 |  | textbox | Licence No.
text | 43d45511-d33a-5f18-8a18-63a55eaffce3 |  | textbox | Test kit serial No.
text | 33652038-45da-5bea-8f74-82af742440f8 |  | textbox | Date test kit last certified:
text | c5689beb-a0ac-5eae-978b-7474692ba6d6 |  | textbox | Place of certification
text | 0659f40e-86f4-5c7a-9004-b200c71cd229 |  | textbox | Make
text | 8228d0b1-78c2-5306-969c-134be0a6df3f |  | textbox | Model
text | 71e1df9a-b511-5e83-b4eb-d13e40558791 |  | textbox | Location of valve
checkpoint-status |  |  | checkpoint | Flush / Clean filters
checkpoint-status |  |  | checkpoint | One outlet in use
text | ab6a8cf9-88dd-5404-9ac9-8b3fde76594d |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Temp of warm water
text | 7f5dbe41-5e6c-5b79-8675-420e37083afd |  | textbox | Fixture
text | eb70aa87-daab-513e-97fc-654954ab95f3 |  | textbox | Pre Set Temp
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | 54117874-f7b6-5a56-ba27-14e5b6c58c19 |  | textbox | Parts & Materials Used
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-flat |  |  | checklist | Passive Fire / Collars Penetration |  |  |  |  | Yes | Passive Fire / Collars Penetration | d51b34b1-4e1a-40c9-9fbe-9dbbb50a2952
checkpoint-status |  |  | checkpoint | Please take detail photos of penetration & labelling
select | 179a2978-6a9c-531f-a0e2-785e624c58e5 |  | dropdown | Drawing Ref Number | HP-PE-B2-00, HP-PE-B2-01, HP-PE-B1-00, HP-PE-B1-01, HP-PE-GF-00, HP-PE-GF-01, HP-PE-01-00, HP-PE-01-01, HP-PE-02-00, HP-PE-02-01, HP-PE-03-00, HP-PE-03-01, HP-PE-04-00, HP-PE-04-01, HP-PE-05-00, HP-PE-05-01, HP-PE-06-00, HP-PE-06-01, HP-PE-07-00, HP-PE-07-01, HP-PE-08-00, HP-PE-08-01, HP-PE-09-00, HP-PE-09-01, HP-PE-10-00, HP-PE-10-01, HP-PE-11-00, HP-PE-11-01, HP-PE-12-00, HP-PE-12-01
select | 97a6349f-05d3-5a2b-9962-a9f0158443a0 |  | dropdown | Material | PVC, HDPE, CU, PEX, GAL
select | 2026ed39-034d-5f29-87e2-7204b5415d4e |  | dropdown | Pipe size | 20, 25, 32, 40, 50, 56, 63, 65, 75, 80, 90, 100, 110, 125, 150, 160, 200, 225, 250, 300, 315, 375, 450
text | 4f957a50-82d4-5865-8ade-96c07b9e5c9d |  | textbox | Fire Matrix Ref Number
checklist-flat |  |  | checklist | ITR 012 Hot Water Service |  |  |  |  | Yes | ITR 012 Hot Water Service | db42eb39-0649-4e89-8ea1-45245a1dbce6
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance to specifications and requirements namely 1500 kPA for 30 minutes
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy