## Project Structure (2)
Folder Structure |  |  | Checklists | #NAME?
Site QA
Switchboard's
|  | Main Switchboard / MCC | Switchboards
|  | DB-A1 | Switchboards
|  | DB-A2 | Switchboards
|  | DB-A3 | Switchboards
|  | DB-UPS | Switchboards
Cable Tray
|  | Coldstore - R002 | Cable Tray
|  | ELA - R001 | Cable Tray
|  | Chiller - R005 | Cable Tray
|  | Produce - R006 | Cable Tray
|  | Drive Thru Canopy - R012 | Cable Tray
|  | Drystore - R015 | Cable Tray
First Fix
|  | R001 - ELA | First Fix Electrical
|  | R002 - Coldstore | First Fix Electrical
|  | R003 - Chiller | First Fix Electrical
|  | R004 - Meat Chiller | First Fix Electrical
|  | R005 - Chiller | First Fix Electrical
|  | R006 - Produce | First Fix Electrical
|  | R007 - Produce Office | First Fix Electrical
|  | R008 - Produce Toilet | First Fix Electrical
|  | R009 - MCC Room | First Fix Electrical
|  | R010 - Plant Room | First Fix Electrical
|  | R011 - Loading Canopy | First Fix Electrical
|  | R012 - Drive Thru Canopy | First Fix Electrical
|  | R013 - Truck Wash | First Fix Electrical
|  | R014 - Storage | First Fix Electrical
|  | R015 - Drystore | First Fix Electrical
|  | R016 - Drystore Toilet | First Fix Electrical
|  | R017 - Drystore Office | First Fix Electrical
|  | R018 - Smoke Lobby | First Fix Electrical
|  | R019 - Ripening Room | First Fix Electrical
|  | R020 - Service Corridor | First Fix Electrical
|  | R031 - Entry Lobby | First Fix Electrical
|  | R032 - Meeting Room | First Fix Electrical
|  | R033 - Open Plan Office 1 | First Fix Electrical
|  | R034 - GM Office | First Fix Electrical
|  | R035 - Server | First Fix Electrical
|  | R036 - Corridor | First Fix Electrical
|  | R037 - Dry Room | First Fix Electrical
|  | R038 - Male Lobby | First Fix Electrical
|  | R039 - Male Toilets | First Fix Electrical
|  | R040 - Female Toilets | First Fix Electrical
|  | R041 - Female Lobby | First Fix Electrical
|  | R042 - Female Toilets | First Fix Electrical
|  | R043 - Lunch Room | First Fix Electrical
|  | R044 - Kitchen | First Fix Electrical
|  | R045 - Outdoor Area | First Fix Electrical
|  | R046 - Office 2 | First Fix Electrical
|  | R047 - RWV Cupboard | First Fix Electrical
|  | R048 - Dispatch Office | First Fix Electrical
|  | R049 - Cleaners Cupboard | First Fix Electrical
|  | Sarir - 01 | First Fix Electrical
|  | Sarir - 02 | First Fix Electrical
|  | Sarir - 03 | First Fix Electrical
|  | Sarir - 04 | First Fix Electrical
|  | Sarir - 05 | First Fix Electrical
|  | Sarir - 06 | First Fix Electrical
|  | Exterior walls | First Fix Electrical
|  | R110 - Plant Room Roof | First Fix Electrical
|  | R111 - Pod | First Fix Electrical
|  | R112 - Plant Room Roof | First Fix Electrical
Second Fix
|  | R001 - ELA | Second Fix Electrical
|  | R002 - Coldstore | Second Fix Electrical
|  | R003 - Chiller | Second Fix Electrical
|  | R004 - Meat Chiller | Second Fix Electrical
|  | R005 - Chiller | Second Fix Electrical
|  | R006 - Produce | Second Fix Electrical
|  | R007 - Produce Office | Second Fix Electrical
|  | R008 - Produce Toilet | Second Fix Electrical
|  | R009 - MCC Room | Second Fix Electrical
|  | R010 - Plant Room | Second Fix Electrical
|  | R011 - Loading Canopy | Second Fix Electrical
|  | R012 - Drive Thru Canopy | Second Fix Electrical
|  | R013 - Truck Wash | Second Fix Electrical
|  | R014 - Storage | Second Fix Electrical
|  | R015 - Drystore | Second Fix Electrical
|  | R016 - Drystore Toilet | Second Fix Electrical
|  | R017 - Drystore Office | Second Fix Electrical
|  | R018 - Smoke Lobby | Second Fix Electrical
|  | R019 - Ripening Room | Second Fix Electrical
|  | R020 - Service Corridor | Second Fix Electrical
|  | R031 - Entry Lobby | Second Fix Electrical
|  | R032 - Meeting Room | Second Fix Electrical
|  | R033 - Open Plan Office 1 | Second Fix Electrical
|  | R034 - GM Office | Second Fix Electrical
|  | R035 - Server | Second Fix Electrical
|  | R036 - Corridor | Second Fix Electrical
|  | R037 - Dry Room | Second Fix Electrical
|  | R038 - Male Lobby | Second Fix Electrical
|  | R039 - Male Toilets | Second Fix Electrical
|  | R040 - Female Toilets | Second Fix Electrical
|  | R041 - Female Lobby | Second Fix Electrical
|  | R042 - Female Toilets | Second Fix Electrical
|  | R043 - Lunch Room | Second Fix Electrical
|  | R044 - Kitchen | Second Fix Electrical
|  | R045 - Outdoor Area | Second Fix Electrical
|  | R046 - Office 2 | Second Fix Electrical
|  | R047 - RWV Cupboard | Second Fix Electrical
|  | R048 - Dispatch Office | Second Fix Electrical
|  | R049 - Cleaners Cupboard | Second Fix Electrical
|  | Sarir - 01 | Second Fix Electrical
|  | Sarir - 02 | Second Fix Electrical
|  | Sarir - 03 | Second Fix Electrical
|  | Sarir - 04 | Second Fix Electrical
|  | Sarir - 05 | Second Fix Electrical
|  | Sarir - 06 | Second Fix Electrical
|  | Exterior walls | Second Fix Electrical
|  | R110 - Plant Room Roof | Second Fix Electrical
|  | R111 - Pod | Second Fix Electrical
|  | R112 - Plant Room Roof | Second Fix Electrical
FEL SM Weekly Site Checklist
| 2023-10-30 |  | FEL SM Weekly Site Checklist
| 2023-11-06 |  | FEL SM Weekly Site Checklist
| 2023-11-13 |  | FEL SM Weekly Site Checklist
| 2023-11-20 |  | FEL SM Weekly Site Checklist
| 2023-11-20 |  | FEL SM Weekly Site Checklist
| 2023-11-27 |  | FEL SM Weekly Site Checklist
| 2023-12-04 |  | FEL SM Weekly Site Checklist
| 2023-12-11 |  | FEL SM Weekly Site Checklist
| 2023-12-18 |  | FEL SM Weekly Site Checklist
| 2023-12-25 |  | FEL SM Weekly Site Checklist
| 2024-01-01 |  | FEL SM Weekly Site Checklist
| 2024-01-08 |  | FEL SM Weekly Site Checklist
| 2024-01-15 |  | FEL SM Weekly Site Checklist
| 2024-01-22 |  | FEL SM Weekly Site Checklist
| 2024-01-29 |  | FEL SM Weekly Site Checklist
| 2024-02-05 |  | FEL SM Weekly Site Checklist
| 2024-02-12 |  | FEL SM Weekly Site Checklist
| 2024-02-19 |  | FEL SM Weekly Site Checklist
| 2024-02-26 |  | FEL SM Weekly Site Checklist
| 2024-03-04 |  | FEL SM Weekly Site Checklist
| 2024-03-11 |  | FEL SM Weekly Site Checklist
| 2024-03-18 |  | FEL SM Weekly Site Checklist
| 2024-03-18 |  | FEL SM Weekly Site Checklist
| 2024-03-25 |  | FEL SM Weekly Site Checklist
| 2024-04-01 |  | FEL SM Weekly Site Checklist
| 2024-04-08 |  | FEL SM Weekly Site Checklist
| 2024-04-15 |  | FEL SM Weekly Site Checklist
| 2024-04-22 |  | FEL SM Weekly Site Checklist
| 2024-04-29 |  | FEL SM Weekly Site Checklist
| 2024-05-06 |  | FEL SM Weekly Site Checklist
| 2024-05-13 |  | FEL SM Weekly Site Checklist
FEL SM Weekly Site Checklist

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Fire rated boxes installed where necessary
checkpoint | Acoustic boxes installed where necessary
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Power cables wired from correct RCD location
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Photos

## Cable Tray
Section | Cable Tray
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Cable Tray Installed
Checkpoint | Tray Joined Correctly
Checkpoint | Hangers Sceismicly Restrained / Under 400mm drop
Checkpoint | Tray Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Tray Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard