## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Switchboards |  |  |  |  | Yes | Switchboards | 2cce86a7-3244-45da-b1f4-ad0b960dc0c0
checkpoint-group |  |  | section | Switchboard
checkpoint-status |  |  | checkpoint | Spatial certificate signed if required
checkpoint-status |  |  | checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint-status |  |  | checkpoint | All clearances sighted to ensure location is compliant
checkpoint-status |  |  | checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint-status |  |  | checkpoint | Cables neatly dressed
checkpoint-status |  |  | checkpoint | Phase tabs on chassy covered
checkpoint-status |  |  | checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint-status |  |  | checkpoint | Switchboard is clean on the inside and outside
checkpoint-status |  |  | checkpoint | Masking blanks installed
checkpoint-status |  |  | checkpoint | DB legend installed
checkpoint-status |  |  | checkpoint | Feisst label on the door installed
checkpoint-group |  |  | section | Photos
checkpoint-no-status |  |  | checkpoint | Add Photos
checklist-sectioned |  |  | checklist | FEL SM Weekly Site Checklist |  |  |  |  | Yes | FEL SM Weekly Site Checklist | 4406dc62-fb9b-4004-bdee-2789c1defa6e
checkpoint-group |  |  | section | Monday
checkpoint-status |  |  | checkpoint | Prestart Meeting with Team
checkpoint-status |  |  | checkpoint | Health Check
checkpoint-status |  |  | checkpoint | Review Tasks for the week
checkpoint-status |  |  | checkpoint | Identify Targets Including Hours
checkpoint-status |  |  | checkpoint | Approve hours by 9AM for previous week
checkpoint-status |  |  | checkpoint | Sign off Subcontractor Hours & Submit
checkpoint-status |  |  | checkpoint | Review SWMS
checkpoint-status |  |  | checkpoint | Site Toolbox Meeting
checkpoint-status |  |  | checkpoint | SSSP in Order
checkpoint-group |  |  | section | Tuesday
checkpoint-status |  |  | checkpoint | Follow up outstanding RFI's with PM
checkpoint-group |  |  | section | Wednesday
checkpoint-status |  |  | checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint-status |  |  | checkpoint | QAs up to date
checkpoint-group |  |  | section | Thursday
checkpoint-status |  |  | checkpoint | Weekly planner filled out for week ahead
checkpoint-status |  |  | checkpoint | Roadblocks identified and actioned
checkpoint-status |  |  | checkpoint | Materials organized for week ahead
checkpoint-status |  |  | checkpoint | Plans printed with any relevant notes added
checkpoint-group |  |  | section | Friday
checkpoint-status |  |  | checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint-status |  |  | checkpoint | Job Cards up to date and submitted
checkpoint-status |  |  | checkpoint | Team tasks for week ahead filled out on whiteboard
checklist-sectioned |  |  | checklist | QA - First Fix |  |  |  |  | Yes | QA - First Fix | 7ad2faa8-157b-457a-a147-651d5782f3ea
checkpoint-group |  |  | section | Flush Boxes
checkpoint-status |  |  | checkpoint | Height as per plan
checkpoint-status |  |  | checkpoint | Location as per plan
checkpoint-status |  |  | checkpoint | Fire rated boxes installed where necessary
checkpoint-status |  |  | checkpoint | Acoustic boxes installed where necessary
checkpoint-group |  |  | section | Cabling
checkpoint-status |  |  | checkpoint | Power cables installed correctly
checkpoint-status |  |  | checkpoint | Lighting cables installed correctly
checkpoint-status |  |  | checkpoint | Power cables wired from correct RCD location
checkpoint-status |  |  | checkpoint | Circuits clearly labelled
checkpoint-status |  |  | checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint-status |  |  | checkpoint | All cables secured via cable ties with ends cut
checkpoint-group |  |  | section | QA - Lights
checkpoint-status |  |  | checkpoint | Setout Correct
checkpoint-status |  |  | checkpoint | Cabling in correct location
checkpoint-status |  |  | checkpoint | Emergency/ Exit Lighting
checkpoint-status |  |  | checkpoint | Nogging installed for Electrical Services
checkpoint-group |  |  | section | Photos
checkpoint-no-status |  |  | checkpoint | Add Photos
checklist-sectioned |  |  | checklist | Cable Tray |  |  |  |  | Yes | Cable Tray | 9a228765-b975-4a9e-abe0-65c4f523da2a
checkpoint-group |  |  | section | Cable Tray
checkpoint-status |  |  | checkpoint | Unistrutt Filed & Painted
checkpoint-status |  |  | checkpoint | Hangers Spaced as Specified
checkpoint-status |  |  | checkpoint | Correct Size Cable Tray Installed
checkpoint-status |  |  | checkpoint | Tray Joined Correctly
checkpoint-status |  |  | checkpoint | Hangers Sceismicly Restrained / Under 400mm drop
checkpoint-status |  |  | checkpoint | Tray Fastened to Hangers
checkpoint-status |  |  | checkpoint | Correct Anchors used fixing to Ceiling / Walls
checkpoint-status |  |  | checkpoint | Cable Tray Bonded
checkpoint-group |  |  | section | Photos
checkpoint-no-status |  |  | checkpoint | Add Photos
checklist-sectioned |  |  | checklist | QA - Second Fix |  |  |  |  | Yes | QA - Second Fix | a383a3e4-8b06-4008-97fc-5d5ba3eea02c
checkpoint-group |  |  | section | Power Outlets
checkpoint-status |  |  | checkpoint | Correct type installed
checkpoint-status |  |  | checkpoint | Correctly installed with terminations all secured properly
checkpoint-status |  |  | checkpoint | Outlet Installed level
checkpoint-status |  |  | checkpoint | Circuit Tested and results recorded
checkpoint-status |  |  | checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
checkpoint-group |  |  | section | Light Switches
checkpoint-status |  |  | checkpoint | Correct type installed
checkpoint-status |  |  | checkpoint | Correctly installed with terminations all secured properly
checkpoint-status |  |  | checkpoint | Light switch Installed level
checkpoint-status |  |  | checkpoint | Circuit Tested and results recorded
checkpoint-status |  |  | checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
checkpoint-group |  |  | section | Light Fixtures
checkpoint-status |  |  | checkpoint | Correct type installed
checkpoint-status |  |  | checkpoint | Correctly installed with terminations all secured properly
checkpoint-status |  |  | checkpoint | Tested for operation
checkpoint-group |  |  | section | Photos
checkpoint-no-status |  |  | checkpoint | Add Photos