## Imperial Apartment Overview
Imperial Garden Apartment
Swimming Pool and Podium
Bathroom and En-suite
Kitchen Splashback
Bathroom

## Imperial Garden Apartment List
Floor Level | BATHROOM | Bathroom and En-suite | Splashback
Ground Floor
G1
G2
G3
G4
G5
G7
G9
Level -1
| 101 |  | 103
| 112 | 111 | 104
| 113 | 115 | 114
117
Level -2
| 201 | 215 | 203
| 205 | 216 | 204
| 207 |  | 214
210
Level - 3
| 301 |  | 303
| 308 |  | 304
| 320 |  | 314
321
Level - 4
| 401 |  | 403
| 402 |  | 404
| 404 |  | 414
405
406
407
| 410 | 411
| 413 | 416
419
Level - 5
| 501 |  | 503
| 508 |  | 504
| 509 |  | 514
512
Level - 6
| 601 |  | 603
| 604 |  | 604
| 613 |  | 614
| 622 | 615
618
Level - 7
701
| 704 | 711 | 703
| 706 | 715 | 704
| 709 | 718 | 714
719
Level - 8
| 801 | 811 | 803
| 807 | 818 | 804
| 810 |  | 814
Level - 9
| 901 |  | 903
| 907 | 918 | 904
| 910 |  | 914
Level - 10
| 1001 |  | 1003
| 1005 |  | 1004
| 1006 |  | 1014
1007
| 1008 | 1015
| 1009 | 1016
1014
1019
1021
Level - 11
| 1101 |  | 1103
| 1103 |  | 1103
| 1106 |  | 1114
1107
1113
1121
Level - 12
| 1208 | 1201 | 1203
1204
1214
| 62 Units | 36 Units | 35 Units

## List Combined Units
Workscope by Units and floors
Floor Level | Bathroom, En-suite and Splashback | Abbrivation
Ground Floor |  | B1 | Bathroom
| Swimming Pool | ENS | En-suite
| Entry Podium | Spl | Splashback
Exit Podium
G1-B1
G2-B1
G3-B1
G4-B1
G5-B1
G7-B1
G9-B1
Level -1
101-B1
103-Spl
104-Spl
111-B1,ENS
112-B1
113-B1
114-Spl
115-B1-ENS
117-B1-ENS
Level -2
201-B1
203-Spl
204-Spl
205-B1
207-B1
210-B1
214-Spl
215-B1,ENS
216-B1,ENS
Level - 3
301-B1
303-Spl
304-Spl
308-B1
314-Spl
320-B1
321-B1
Level - 4
401-B1
402-B1
403-Spl
404-B1
404-Spl
405-B1
406-B1
407-B1
410-B1
411-B1,ENS
413-B1
414-Spl
416-B1,ENS
419-B1
Level - 5
501-B1
503-Spl
504-Spl
508-B1
509-B1
512-B1
514-Spl
Level - 6
601-B1
603-Spl
604-B1
604-Spl
613-B1
614-Spl
615-B1,ENS
618-B1,ENS
622-B1
Level - 7
701-B1
703-Spl
704-B1
704-Spl
706-B1
709-B1
711-B1,ENS
714-Spl
715-B1,ENS
718-B1,ENS
719-B1
Level - 8
801-B1
803-Spl
804-Spl
807-B1
810-B1
811-B1,ENS
814-Spl
818-B1,ENS
Level - 9
901-B1
903-Spl
904-Spl
907-B1
910-B1
914-Spl
918-B1,ENS
Level - 10
1001-B1
1003-Spl
1004-Spl
1005-B1
1006-B1
1007-B1
1008-B1
1009-B1
1014-B1
1014-Spl
1015-B1,ENS
1016-B1,ENS
1019-B1
1021-B1
Level - 11
1101-B1
1103-B1
1103-Spl
1104- Spl
1106-B1
1107-B1
1113-B1
1114-Spl
1121-B1
Level - 12
1201-B1,ENS
1203-Spl
1204-Spl
1208-B1
1214-Spl

## Imperi Checklist Seq WBS 10AUG
CHOICE TILING NZ LTD - Project- Imperial Garden, Auckland CBD
type | name | values
checklist-flat | Pool Area- POOL
checkpoint | Pre-start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Pool Area ready for tiling work
checkpoint | Seq # 1 - Blue pool tiles removal
checkpoint | Seq # 2 - Removal of Fibreglass
checkpoint | Seq # 3 - Substrate Preparation - remove any residual of fibreglass
checkpoint | Seq # 4 - Two coat of Fibreglass - Allow of drying
Restriction | Check the fibreglass leakproof and strict compliance required for repair work
checkpoint | Seq # 5 - Apply Atlantic Blue ISO NPG Spray blue Gel Coat /flowcoat
checkpoint | Seq # 6 - Install the blue pool tiles use epoxy adhesive
Restriction | Check any corner damage installed tiles
checkpoint | Seq # 7 - Apply Epoxy Grout
Restriction | Check grout applied on acceptable quality to the client expectation
checkpoint | Seq # 8 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 9 - Final Cleaning
checkpoint | Seq # 10 - Handover
checklist-flat | Entry Podium Area - PODIUM -1
checkpoint | Pre-start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Podium Area ready for tiling work
checkpoint | Seq # 1 - Removal of damage tiles as instructed /marked
checkpoint | Seq # 2 - Substrate Preparation /grind off any residual of old adhesive
checkpoint | Seq # 3 - Levelling / Screeding if required
checkpoint | Seq # 4 - Lay Floor Tiling and install trim
Restriction | Check any corner damage insulated tiles
checkpoint | Seq # 5 - Apply Grouting
Restriction | Check grout applied on acceptable quality to the client expectation
checkpoint | Seq # 6 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 7 - Final Cleaning
checkpoint | Seq # 8 - Handover
checklist-flat | Exit Podium Area - PODIUM - 2
checkpoint | Pre-start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Podium Area ready for tiling work
checkpoint | Seq # 1 - Removal of damage tiles as instructed /marked
checkpoint | Seq # 2 - Substrate Preparation /grind off any residual of old adhesive
checkpoint | Seq # 3 - Levelling / Screeding if required
checkpoint | Seq # 4 - Lay Floor Tiling and install trim
Restriction | Check any corner damage insulated tiles
checkpoint | Seq # 5 - Apply Grouting
Restriction | Check grout applied on acceptable quality to the client expectation
checkpoint | Seq # 6 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 7 - Final Cleaning
checkpoint | Seq # 8 - Handover
checklist-flat | Bathroom
checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Bathroom ready for tiling work
checkpoint | Seq # 1 - Remove floor tiles and Skirting
checkpoint | Seq # 2 - Substrate preparation
checkpoint | Seq # 3 Install Regupol 4515 Acoustic Under Lay
Restriction | Check the acoustic lay is meet the building compliance
checkpoint | Seq # 4 - Apply Ardex WPM-002 Waterproofing - two-part component
checkpoint | Seq # 5 - Lay the floor, skirting and trim as per drawings - Shower is not included
Restriction | Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint | Seq # 6 - Apply Grouting
Restriction | Check grout applied on high standard upload the Picture-Mandatory
checkpoint | Seq # 7 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 8 - Final Cleaning
checkpoint | Seq # 9 - Install the floor finish protection (RAMBOARD)
checkpoint | Seq # 10 - Handover
checklist-flat | En-suite
checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Bathroom ready for tiling work
checkpoint | Seq # 1 - Remove floor tiles and Skirting
checkpoint | Seq # 2 - Substrate preparation
checkpoint | Seq # 3 Install Regupol 4515 Acoustic Under Lay
Restriction | Check the acoustic lay is meet the building compliance
checkpoint | Seq # 4 - Apply Ardex WPM-002 Waterproofing - two-part component
checkpoint | Seq # 5 - Lay the floor, skirting and trim as per drawings - Shower is not included
Restriction | Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint | Seq # 6 - Apply Grouting
Restriction | Check grout applied on high standard upload the Picture-Mandatory
checkpoint | Seq # 7 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 8 - Final Cleaning
checkpoint | Seq # 9 - Install the floor finish protection (RAMBOARD)
checkpoint | Seq # 10 - Handover
checklist-flat | Splashback
checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Splashback area ready for tiling work
checkpoint | Seq # 1 - Removal of existing splashback tiles
checkpoint | Seq # 2 - Prepare substrate to suitable to lay the tiles
checkpoint | Seq # 3 - Lay the tiles to splashback wall and install the trim
Restriction | Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint | Seq # 4 - Apply Grouting
Restriction | Check grout applied on high standard upload the Picture-Mandatory
checkpoint | Seq # 5 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 6 - Final Cleaning
checkpoint | Seq # 7 - Install the floor finish protection (RAMBOARD)
checkpoint | Seq # 8 - Handover
checklist-flat | Kitchen Floor | Updated 10 Aug 2023
checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint | Kitchen floor ready for tiling work
checkpoint | Seq # 1 - Remove floor tiles
checkpoint | Seq # 2 - Substrate preparation
checkpoint | Seq # 3 Install Regupol 4515 Acoustic Under Lay
Restriction | Check the acoustic lay is meet the building compliance
checkpoint | Seq # 4 - Lay the floor, as per drawings
Restriction | Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint | Seq # 5 - Apply Grouting
Restriction | Check grout applied on high standard upload the Picture-Mandatory
checkpoint | Seq # 6 - Apply Silicon
Restriction | Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint | Seq # 7 - Final Cleaning
checkpoint | Seq # 8 - Install the floor finish protection (RAMBOARD)
checkpoint | Seq # 9 - Handover

## Imperial Garden Updated 10AUG23
CHOICE TILING NZ LTD - Project- Imperial Garden, Auckland CBD
|  |  | Updated | 2023-08-10
Floor Level | BATHROOM | Bathroom and En-suite | Kitchen Floor and Splashback | Kitchen Floor only
Ground Floor
| G1 |  |  | G5
G2
G3
G4
G5
G7
G9
Level -1
| 101 |  | 103 | 111
| 112 | 111 | 104 | 113
| 113 | 115 | 114 | 115
117
Level -2
| 201 | 215 | 203
| 205 | 216 | 204
| 207 |  | 214
| 210 |  | 215
Level - 3
| 301 |  | 301
| 308 |  | 303
| 320 |  | 304
| 321 |  | 314
Level - 4
| 401 |  | 403
| 402 |  | 404
| 404 |  | 405
| 405 |  | 407
| 406 |  | 410
| 407 |  | 411
| 410 | 411 | 414
| 413 | 416
419
Level - 5
| 501 |  | 503
| 508 |  | 504
| 509 |  | 512
| 512 |  | 514
518
Level - 6
| 601 |  | 603
| 604 |  | 604
| 613 |  | 614
| 622 | 615 | 622
618
Level - 7
701
| 704 | 711 | 703
| 706 | 715 | 704
| 709 | 718 | 714
719
Level - 8
| 801 | 811 | 803
| 807 | 818 | 804
| 810 |  | 811
814
Level - 9
| 901 |  | 903
| 907 | 918 | 904
| 910 |  | 907
910
914
Level - 10
| 1001 |  | 1001 | 1006
| 1005 |  | 1003 | 1007
| 1006 |  | 1004 | 1008
| 1007 |  | 1014 | 1009
| 1008 | 1015 | 1019
| 1009 | 1016
1014
1019
1021
Level - 11
| 1101 |  | 1103 | 1113
| 1103 |  | 1104
| 1106 |  | 1106
| 1107 |  | 1107
| 1113 |  | 1114
| 1122 |  | 1122
Level - 12
| 1208 | 1201 | 1201
1203
1204
1214
| 62 Units | 18 Units | 54 Units | 9 Units
| 62+18 = 80 units | 98 bathrooms