## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 0b8a3152-98a2-411f-b5c0-3d01f696690f |  | checklist | Entry Podium Area - PODIUM - 1 |  |  |  |  | Yes | Entry Podium Area - PODIUM - 1 | 13227fe7-c3b8-471f-84b3-e1c7df8e6441
checkpoint-status | 01128f7d-c932-4743-995a-641bbae0040b |  | checkpoint | Pre-start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | 44ed71fc-7878-4567-a93e-4fa945c8961b |  | checkpoint | Podium Area ready for tiling work
checkpoint-status | b1b87b55-a3e4-47e2-8d81-c3f2a6ae22a9 |  | checkpoint | Seq # 1 - Removal of damage tiles as instructed /marked
checkpoint-status | ebd1549d-b877-43b7-a9e3-4c73a10831f6 |  | checkpoint | Seq # 2 - Substrate Preparation /grind off any residual of old adhesive
checkpoint-status | bfc98b0c-fd1c-4dba-bc1a-c9df38e4d377 |  | checkpoint | Seq # 3 - Levelling / Screeding if required
checkpoint-status | ef70d90d-bf2b-4249-ac54-869497d4091e |  | checkpoint | Seq # 4 - Lay Floor Tiling and install trim
holdpoint | 71a09152-d1a8-453c-8398-6ff275b3b8c1 |  | signoff | HOLD POINT: Check any corner damage insulated tiles
checkpoint-status | dd6526bc-8a89-40bb-b7ea-aa4e8db6d839 |  | checkpoint | Seq # 5 - Apply Grouting
holdpoint | 97eae078-89b1-465c-882b-b2b69db28bb3 |  | signoff | HOLD POINT: Check grout applied on acceptable quality to the client expectation
checkpoint-status | df8a02de-99b1-42eb-8f1f-15ee17ed1f85 |  | checkpoint | Seq # 6 - Apply Silicon
holdpoint | c07555c2-dc57-4ac8-8fb9-63fab82dc2a5 |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | 036e67c0-a7a5-45ef-969b-06c8a872e7ce |  | checkpoint | Seq # 7 - Final Cleaning
checkpoint-status | c2d4619d-86fd-4ecc-b021-ea6236a6ac45 |  | checkpoint | Seq # 8 - Handover
checklist-flat | 67c0d7fb-4141-4b4f-8807-2f1d4752df45 |  | checklist | Bathroom |  |  |  |  | Yes | Bathroom | 29619aa8-9cd1-4f07-8e8e-744ffd845ff5
checkpoint-status | 375ca9a8-476b-4152-b498-a680cda6fa4c |  | checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | 8a2063c2-b777-4cce-923e-34cdf7e75336 |  | checkpoint | Bathroom ready for tiling work
checkpoint-status | 65c41aad-b58e-4057-a7e3-392b3c262c05 |  | checkpoint | Seq # 1 - Remove floor tiles and Skirting
checkpoint-status | 1533d193-3a38-497b-9387-4df11e84a743 |  | checkpoint | Seq # 2 - Substrate preparation
checkpoint-status | f3a07947-0546-4934-b1bc-7d2cc42980d4 |  | checkpoint | Seq # 3 Install Regupol 4515 Acoustic Under Lay
holdpoint | 304d3b88-dca7-4fe0-871a-8bc6d7c1bd8b |  | signoff | HOLD POINT: Check the acoustic lay is meet the building compliance
checkpoint-status | 20c3e4c0-3d52-4850-8925-8bb92e244907 |  | checkpoint | Seq # 4 - Apply Ardex WPM-002 Waterproofing - two-part component
checkpoint-status | 36bb0826-a212-46a5-94a0-d05d6bf5a928 |  | checkpoint | Seq # 5 - Lay the floor, skirting and trim as per drawings - Shower is not included
holdpoint | 52cc981a-5ccd-48a4-a924-f873aa58d26c |  | signoff | HOLD POINT: Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint-status | 5947078e-b5fb-49d7-927b-1a293d4990ab |  | checkpoint | Seq # 6 - Apply Grouting
holdpoint | d08e3531-0146-47f8-9838-5ecfd63b5ef7 |  | signoff | HOLD POINT: Check grout applied on high standard upload the Picture-Mandatory
checkpoint-status | ab66cb57-8536-4f05-ae8d-acaf0f8f765b |  | checkpoint | Seq # 7 - Apply Silicon
holdpoint | 573d47b4-f80c-4434-b67a-3ecdf25ccba4 |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | 3c3864e8-4fed-4a17-98d7-2ed02bfc5e61 |  | checkpoint | Seq # 8 - Final Cleaning
checkpoint-status | 1a533255-3b81-4e0c-880f-884d6c99c011 |  | checkpoint | Seq # 9 - Install the floor finish protection (RAMBOARD)
checkpoint-status | 0bf1149f-3095-45e5-8e9f-31e0691f56f3 |  | checkpoint | Seq # 10 - Handover
checklist-flat | 5f0e21cf-e1e7-43fb-8315-1429a5ea4da8 |  | checklist | Exit Podium Area - PODIUM - 2 |  |  |  |  | Yes | Exit Podium Area - PODIUM - 2 | 82e260b8-7e00-4d86-8fe0-84e5401bba36
checkpoint-status | 6fbbbcae-c31c-4286-9c60-c9d439bfadee |  | checkpoint | Pre-start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | f600d7db-494d-452d-b16f-56d85cbc26d1 |  | checkpoint | Podium Area ready for tiling work
checkpoint-status | 1e7d8a8c-943c-4adf-9f75-65119186e51f |  | checkpoint | Seq # 1 - Removal of damage tiles as instructed /marked
checkpoint-status | 91f9c7ce-82e9-416c-a661-4216f75e3567 |  | checkpoint | Seq # 2 - Substrate Preparation /grind off any residual of old adhesive
checkpoint-status | b3590401-f2b4-4993-9af4-f1039cbb2253 |  | checkpoint | Seq # 3 - Levelling / Screeding if required
checkpoint-status | 887a9dc9-3866-4bec-94b8-f633f65ef8f9 |  | checkpoint | Seq # 4 - Lay Floor Tiling and install trim
holdpoint | 47c1ffe1-d789-45a5-baca-5c6e40c8993b |  | signoff | HOLD POINT: Check any corner damage insulated tiles
checkpoint-status | c5049022-ef34-42e5-b2f2-53a99cf5bef5 |  | checkpoint | Seq # 5 - Apply Grouting
holdpoint | f9e1d9de-109a-4e11-91ef-63adb92d3b72 |  | signoff | HOLD POINT: Check grout applied on acceptable quality to the client expectation
checkpoint-status | 3b4fc19b-386a-46a6-8f4d-8c212c3cdd78 |  | checkpoint | Seq # 6 - Apply Silicon
holdpoint | a112425e-7445-4e85-bbe7-2d59ff828f62 |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | 7a56be1a-a40b-4217-9689-2004e31418c0 |  | checkpoint | Seq # 7 - Final Cleaning
checkpoint-status | 77cc52f2-12d3-4673-b973-21bd25253185 |  | checkpoint | Seq # 8 - Handover
checklist-flat | 87431521-583c-45c1-9d02-5c3d76e3f553 |  | checklist | En-suite |  |  |  |  | Yes | En-suite | 96904627-492e-4bba-9a61-977afad7be46
checkpoint-status | 13847570-9909-4f83-a404-6c63d90664e9 |  | checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | 4feacc78-2867-4ccb-957b-8ed7d88756ad |  | checkpoint | Bathroom ready for tiling work
checkpoint-status | 3d5d9d14-7052-4e8b-be31-b3ca9ef9f29f |  | checkpoint | Seq # 1 - Remove floor tiles and Skirting
checkpoint-status | 4006758b-2a51-4971-bfab-3be92dd84402 |  | checkpoint | Seq # 2 - Substrate preparation
checkpoint-status | 1427cee0-ce56-485b-bc4b-8533e26f7ddb |  | checkpoint | Seq # 3 Install Regupol 4515 Acoustic Under Lay
holdpoint | 37d0ccc4-2ece-47ea-8351-b83470ade68a |  | signoff | HOLD POINT: Check the acoustic lay is meet the building compliance
checkpoint-status | c8d55627-e4b4-4532-bac3-391dc306438e |  | checkpoint | Seq # 4 - Apply Ardex WPM-002 Waterproofing - two-part component
checkpoint-status | a6c55aa3-e1d1-4e4c-82b8-980e8f39490b |  | checkpoint | Seq # 5 - Lay the floor, skirting and trim as per drawings - Shower is not included
holdpoint | 2e9dcce5-092f-40f7-a2b7-3cf21480928b |  | signoff | HOLD POINT: Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint-status | 7099d6a6-cf68-4777-be2b-1f31988943e7 |  | checkpoint | Seq # 6 - Apply Grouting
holdpoint | 3e58fa09-967c-4f32-9254-f64d50611780 |  | signoff | HOLD POINT: Check grout applied on high standard upload the Picture-Mandatory
checkpoint-status | 12ca508a-e738-4e84-91eb-55c0762754ef |  | checkpoint | Seq # 7 - Apply Silicon
holdpoint | bfd387ea-dcf3-4fc7-a79e-cb7b40ee5f79 |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | 102cd283-6e44-4cac-82f6-834ed04c5be2 |  | checkpoint | Seq # 8 - Final Cleaning
checkpoint-status | 522a727d-a2f0-41ca-9210-d9d2e1b3e8bf |  | checkpoint | Seq # 9 - Install the floor finish protection (RAMBOARD)
checkpoint-status | 3901ce9a-e67a-40ed-ba85-ee6a17c187a6 |  | checkpoint | Seq # 10 - Handover
checklist-flat | a0cbfe7e-7f15-4faa-91c4-2bd6f5f821e5 |  | checklist | Pool Area - POOL |  |  |  |  | Yes | Pool Area - POOL | bc3e6e3b-ddc9-47c6-b397-bc0527d686f0
checkpoint-status | ed1bf47e-f2a5-4374-8668-603e3564758c |  | checkpoint | Pre-start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | bdb14686-4b84-4f73-a659-5c95017fe3a6 |  | checkpoint | Pool Area ready for tiling work
checkpoint-status | 9dfd84f9-4ef5-4302-952b-a0af683ccd13 |  | checkpoint | Seq # 1 - Blue pool tiles removal
checkpoint-status | 8488e6fa-baea-4c17-8470-efb0c48b3f57 |  | checkpoint | Seq # 2 - Removal of Fibreglass
checkpoint-status | 47d16dfb-414e-41c6-a831-f236d3119d6d |  | checkpoint | Seq # 3 - Substrate Preparation - remove any residual of fibreglass
checkpoint-status | 41142d24-2473-4957-a3aa-b99d803b49bc |  | checkpoint | Seq # 4 - Two coat of Fibreglass - Allow of drying
holdpoint | c480346c-d33c-4c9e-a142-2b8d3e040c24 |  | signoff | HOLD POINT: Check the fibreglass leakproof and strict compliance required for repair work
checkpoint-status | 2ade9ad4-a7fb-41f2-9ff6-0f7ec48247c1 |  | checkpoint | Seq # 5 - Apply Atlantic Blue ISO NPG Spray blue Gel Coat /flowcoat
checkpoint-status | 9f17911d-d5e0-49f5-b47c-e7fb6455698a |  | checkpoint | Seq # 6 - Install the blue pool tiles use epoxy adhesive
holdpoint | af9deccb-8e39-4709-8829-7d0eca7cdbd3 |  | signoff | HOLD POINT: Check any corner damage installed tiles
checkpoint-status | b1a563f7-b7a1-432c-b889-5bdc3d648f8b |  | checkpoint | Seq # 7 - Apply Epoxy Grout
holdpoint | 15b049a9-7a78-46ac-aae6-017963bd2937 |  | signoff | HOLD POINT: Check grout applied on acceptable quality to the client expectation
checkpoint-status | 2b85c8ee-3197-430c-98a2-3b6ab823724e |  | checkpoint | Seq # 8 - Apply Silicon
holdpoint | 839b202e-8f9e-4669-b9a7-7023b4345001 |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | c441a3a5-6eee-4713-94da-16819d16de1c |  | checkpoint | Seq # 9 - Final Cleaning
checkpoint-status | 18996ad8-c424-41ef-be88-879aadd0c7de |  | checkpoint | Seq # 10 - Handover
checklist-flat | da84cbaa-d794-4597-9812-ba3255a99e58 |  | checklist | Splashback |  |  |  |  | Yes | Splashback | da1f7435-2d6e-4054-bbf6-b8d7601cf41e
checkpoint-status | 506f7f45-0daf-4003-b797-d4f5dfdcd185 |  | checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | b27f7e24-13aa-4002-af0b-4bde7695e456 |  | checkpoint | Splashback area ready for tiling work
checkpoint-status | 7d072f4a-c3a2-4863-a51b-0d9fe646bf49 |  | checkpoint | Seq # 1 - Removal of existing splashback tiles
checkpoint-status | 8914bb38-465e-49a2-8a06-ba4ca7d6ee5b |  | checkpoint | Seq # 2 - Prepare substrate to suitable to lay the tiles
checkpoint-status | df3ef86e-0581-4610-a7de-5c75a89665e1 |  | checkpoint | Seq # 3 - Lay the tiles to splashback wall and install the trim
holdpoint | 2032a3bd-01a4-46c6-afa5-564254932773 |  | signoff | HOLD POINT: Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint-status | 4ddd9ba6-6cda-48c8-ac06-6ea86faf8158 |  | checkpoint | Seq # 4 - Apply Grouting
holdpoint | bd9ffc50-8f60-44de-b015-4ab2a4e55b84 |  | signoff | HOLD POINT: Check grout applied on high standard upload the Picture-Mandatory
checkpoint-status | a1827de0-c333-4690-bd6f-7c987be54aa3 |  | checkpoint | Seq # 5 - Apply Silicon
holdpoint | b0aec937-a2ae-4c28-add5-32e54197e43f |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | 5cd687b9-1e65-4e17-a6b3-a89a50d60bae |  | checkpoint | Seq # 6 - Final Cleaning
checkpoint-status | 95e6a634-df0d-4c51-93d6-ddaeabbb964e |  | checkpoint | Seq # 7 - Install the floor finish protection (RAMBOARD)
checkpoint-status | a3f6f9f4-4e2f-464e-81a1-2125d0a50e73 |  | checkpoint | Seq # 8 - Handover
checklist-flat | 706d6a8c-4d2f-4897-a377-2e2d0430df11 |  | checklist | Kitchen Floor |  |  |  |  | Yes | Kitchen Floor | e489e4a0-6c83-4b01-b380-0c9ddc8b1c42
checkpoint-status | 23023563-0b6c-4343-9ea5-d9ad85805b68 |  | checkpoint | Pre-Start - Area tidy and Accessible- Free from any foreign objects
checkpoint-status | 7059b346-330b-45cb-a94e-630f5ac3239c |  | checkpoint | Kitchen floor ready for tiling work
checkpoint-status | bbeafe21-5561-42ba-93c8-3390fa456278 |  | checkpoint | Seq # 1 - Remove floor tiles
checkpoint-status | 0bbbf4ae-a4a5-4457-a5c6-71aaf809e82e |  | checkpoint | Seq # 2 - Substrate preparation
checkpoint-status | 5f3af52c-0618-4a30-b7df-1c4a8ca92c17 |  | checkpoint | Seq # 3 Install Regupol 4515 Acoustic Under Lay
holdpoint | 512fa576-ceb0-48eb-8788-bbec33c8e184 |  | signoff | HOLD POINT: Check the acoustic lay is meet the building compliance
checkpoint-status | a023f06c-8f01-4bf0-8c69-30c598a31f75 |  | checkpoint | Seq # 4 - Lay the floor, as per drawings
holdpoint | 99f435df-d360-414d-9631-7af8c43bc26a |  | signoff | Check any corner damage installed tiles- Upload the Picture-Mandatory
checkpoint-status | 725c1885-26be-4476-a761-c830292c9e89 |  | checkpoint | Seq # 5 - Apply Grouting
holdpoint | d892040d-7119-4f49-85a0-1ea9dac176d6 |  | signoff | HOLD POINT: Check grout applied on high standard upload the Picture-Mandatory
checkpoint-status | 950b076d-ee21-49d5-9a1f-f952662b5288 |  | checkpoint | Seq # 6 - Apply Silicon
holdpoint | ac7a82d2-63c9-49de-9019-73d4ac9a943d |  | signoff | HOLD POINT: Silicon finishes to meet the client requirement do not proceed to handover if QA not acceptable
checkpoint-status | c4538f17-d0b3-4ea1-bbf8-d63d185f9f65 |  | checkpoint | Seq # 7 - Final Cleaning
checkpoint-status | b3d69546-e542-4dde-ba98-89ba403c695c |  | checkpoint | Seq # 8 - Install the floor finish protection (RAMBOARD)
checkpoint-status | 0ea8dae4-f0df-4228-8c4e-855e1c306796 |  | checkpoint | Seq # 9 - Handover