## Project Structure
Summerset St Johns BuildingS C and F
QA BUILDING C
Level 1 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Cold Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP101M | Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
|  |  |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP102M | same as AP101M
|  | AP103M | same as AP101M
|  | AP104M | same as AP101M
|  | AP105M | same as AP101M
|  | AP106M | same as AP101M
|  | AP107M | same as AP101M
|  | AP108M | same as AP101M
|  | AP109M | same as AP101M
|  | AP110M | same as AP101M
|  | AP111M | same as AP101M
Bin room / cleaners room
|  |  |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 2 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP201M
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
[6 empty] | Pre line | Checklist
Apartment pre line
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP202M | same as AP201M
|  | AP203M | same as AP201M
|  | AP204M | same as AP201M
|  | AP205M | same as AP201M
|  | AP206M | same as AP201M
|  | AP207M | same as AP201M
|  | AP208M | same as AP201M
|  | AP209M | same as AP201M
|  | AP210M | same as AP201M
|  | AP211M | same as AP201M
|  | AP212M | same as AP201M
Bin room / cleaners room
|  |  |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 3 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
|  | AP301M |  |  | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
[6 empty] | Pre line | Checklist
Apartment pre line
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP302M | same as AP301M
|  | AP303M | same as AP301M
|  | AP304M | same as AP301M
|  | AP305M | same as AP301M
|  | AP306M | same as AP301M
|  | AP307M | same as AP301M
|  | AP308M | same as AP301M
|  | AP309M | same as AP301M
|  | AP310M | same as AP301M
Bin room / cleaners room
|  |  |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 4 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP401M
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Second Fix
[7 empty] | Checklist | Apartment Waste QA Checklist
|  | AP402M | same as AP401M
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
TESTING & COMMISSIONING BUILDING C
Level 1 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
|  | AP101M | Underslab drainage
Test Sheet
Apartment Water Test Sheet
Apartment Waste Test Sheet
|  | AP102M | same as AP101M
|  | AP103M | same as AP101M
|  | AP104M | same as AP101M
|  | AP105M | same as AP101M
|  | AP106M | same as AP101M
|  | AP107M | same as AP101M
|  | AP108M | same as AP101M
|  | AP109M | same as AP101M
|  | AP110M | same as AP101M
|  | AP111M | same as AP101M
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 2 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP201M
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP202M | same as AP201M
|  | AP203M | same as AP201M
|  | AP204M | same as AP201M
|  | AP205M | same as AP201M
|  | AP206M | same as AP201M
|  | AP207M | same as AP201M
|  | AP208M | same as AP201M
|  | AP209M | same as AP201M
|  | AP210M | same as AP201M
|  | AP211M | same as AP201M
|  | AP212M | same as AP201M
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 3 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP301M
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP302M | same as AP301M
|  | AP303M | same as AP301M
|  | AP304M | same as AP301M
|  | AP305M | same as AP301M
|  | AP306M | same as AP301M
|  | AP307M | same as AP301M
|  | AP308M | same as AP301M
|  | AP309M | same as AP301M
|  | AP310M | same as AP301M
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 4 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP401M
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP402M | same as AP401M
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
QA BUILDING F
Level 1 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Cold Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
|  | AP101T | Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
|  |  |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP102T | same as AP101T
|  | AP103T | same as AP101T
|  | AP104T | same as AP101T
|  | AP105T | same as AP101T
|  | AP106T | same as AP101T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 2 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP201T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
[6 empty] | Pre line | Checklist
Apartment pre line
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP202T | same as AP201T
|  | AP203T | same as AP201T
|  | AP204T | same as AP201T
|  | AP205T | same as AP201T
|  | AP206T | same as AP201T
|  | AP202T | same as AP201T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 3 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP301T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
[6 empty] | Pre line | Checklist
Apartment pre line
Second Fix
[7 empty] | Checklist | Apartment 2nd Fix QA Checklist
|  | AP302T | same as AP301T
|  | AP303T | same as AP301T
|  | AP304T | same as AP301T
|  | AP305T | same as AP301T
|  | AP306T | same as AP301T
|  | AP307T | same as AP301T
|  | AP308T | same as AP301T
|  | AP309T | same as AP301T
|  | AP310T | same as AP301T
|  | AP311T | same as AP301T
|  | AP312T | same as AP301T
|  | AP313T | same as AP301T
|  | AP314T | same as AP301T
|  | AP315T | same as AP301T
|  | AP316T | same as AP301T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 4 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP401T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Second Fix
[7 empty] | Checklist | Apartment Waste QA Checklist
|  | AP402T | same as AP401T
|  | AP403T | same as AP401T
|  | AP404T | same as AP401T
|  | AP405T | same as AP401T
|  | AP406T | same as AP401T
|  | AP407T | same as AP401T
|  | AP408T | same as AP401T
|  | AP409T | same as AP401T
|  | AP410T | same as AP401T
|  | AP411T | same as AP401T
|  | AP412T | same as AP401T
|  | AP413T | same as AP401T
|  | AP414T | same as AP401T
|  | AP415T | same as AP401T
|  | AP416T | same as AP401T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
[7 empty] | Checklist | Apartment pre line
Level 5 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP501T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Second Fix
[7 empty] | Checklist | Apartment Waste QA Checklist
|  | AP502T | same as AP501T
|  | AP503T | same as AP401T
|  | AP504T | same as AP401T
|  | AP505T | same as AP401T
|  | AP506T | same as AP401T
|  | AP507T | same as AP401T
|  | AP508T | same as AP401T
|  | AP509T | same as AP401T
|  | AP510T | same as AP401T
|  | AP511T | same as AP401T
|  | AP512T | same as AP401T
|  | AP513T | same as AP401T
|  | AP514T | same as AP401T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
Level 6 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP601T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Second Fix
[7 empty] | Checklist | Apartment Waste QA Checklist
|  | AP602T | same as AP601T
|  | AP603T | same as AP601T
|  | AP604T | same as AP601T
|  | AP605T | same as AP601T
|  | AP606T | same as AP601T
|  | AP607T | same as AP601T
|  | AP608T | same as AP601T
|  | AP609T | same as AP601T
|  | AP610T | same as AP601T
|  | AP611T | same as AP601T
|  | AP612T | same as AP601T
|  | AP613T | same as AP601T
|  | AP614T | same as AP601T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
Level 7 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP701T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Second Fix
[7 empty] | Checklist | Apartment Waste QA Checklist
|  | AP702T | same as AP701T
|  | AP703T | same as AP701T
|  | AP704T | same as AP701T
|  | AP705T | same as AP701T
|  | AP706T | same as AP701T
|  | AP707T | same as AP701T
|  | AP708T | same as AP701T
|  | AP709T | same as AP701T
|  | AP710T | same as AP701T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
Level 8 QA
Waste & Stacks
|  |  |  | Checklist |  |  |  | Common Waste & Stack QA Check
Main Water Reticulation
Cold Water
[5 empty] | Checklist |  |  | Main Cold Water QA Checklist
AP801T
Underslab drainage
|  |  |  | Checklist |  |  |  | Underslab Checklist
First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Second Fix
[7 empty] | Checklist | Apartment Waste QA Checklist
|  | AP802T | same as AP801T
|  | AP803T | same as AP801T
|  | AP804T | same as AP801T
|  | Bin room / cleaners room |  | Checklist | First Fix
Waste
[7 empty] | Checklist | Apartment Waste QA Checklist
Water
[7 empty] | Checklist | Apartment Waste QA Checklist
Pre line
TESTING & COMMISSIONING BUILDING F
Level 1 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
|  | AP101T | Underslab drainage
Test Sheet
Apartment Water Test Sheet
Apartment Waste Test Sheet
|  | AP102T | same as AP101T
|  | AP103T | same as AP101T
|  | AP104T | same as AP101T
|  | AP105T | same as AP101T
|  | AP106T | same as AP101T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 2 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP201T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP202T | same as AP201T
|  | AP203T | same as AP201T
|  | AP204T | same as AP201T
|  | AP205T | same as AP201T
|  | AP206T | same as AP201T
|  | AP202T | same as AP201T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 3 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP301T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP302T | same as AP301T
|  | AP303T | same as AP301T
|  | AP304T | same as AP301T
|  | AP305T | same as AP301T
|  | AP306T | same as AP301T
|  | AP307T | same as AP301T
|  | AP308T | same as AP301T
|  | AP309T | same as AP301T
|  | AP310T | same as AP301T
|  | AP311T | same as AP301T
|  | AP312T | same as AP301T
|  | AP313T | same as AP301T
|  | AP314T | same as AP301T
|  | AP315T | same as AP301T
|  | AP316T | same as AP301T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 4 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP401T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP402T | same as AP401T
AP403T
AP404T
AP405T
AP406T
AP407T
AP408T
AP409T
AP410T
AP411T
AP412T
AP413T
AP414T
AP415T
AP416T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 5 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP501T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP502T | same as AP501T
|  | AP503T | same as AP501T
|  | AP504T | same as AP501T
|  | AP505T | same as AP501T
|  | AP506T | same as AP501T
|  | AP507T | same as AP501T
|  | AP508T | same as AP501T
|  | AP509T | same as AP501T
|  | AP510T | same as AP501T
|  | AP511T | same as AP501T
|  | AP512T | same as AP501T
|  | AP513T | same as AP501T
|  | AP514T | same as AP501T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 6 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP601T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP602T | same as AP601T
|  | AP603T | same as AP601T
|  | AP604T | same as AP601T
|  | AP605T | same as AP601T
|  | AP606T | same as AP601T
|  | AP607T | same as AP601T
|  | AP608T | same as AP601T
|  | AP609T | same as AP601T
|  | AP610T | same as AP601T
|  | AP611T | same as AP601T
|  | AP612T | same as AP601T
|  | AP613T | same as AP601T
|  | AP614T | same as AP601T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 7 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP701T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP702T | same as AP701T
|  | AP703T | same as AP701T
|  | AP704T | same as AP701T
|  | AP705T | same as AP701T
|  | AP706T | same as AP701T
|  | AP707T | same as AP701T
|  | AP708T | same as AP701T
|  | AP709T | same as AP701T
|  | AP710T | same as AP701T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet
Level 8 TEST
Waste & Stacks
Apartment Waste Test Sheet
Main Cold Water Reticulation
Cold Water Test Sheet
AP801T
Apartment Waste Test Sheet
Apartment Water Test Sheet
|  | AP802T | same as AP801T
|  | AP803T | same as AP801T
|  | AP804T | same as AP801T
Bin room / cleaners room
Apartment Waste Test Sheet
Apartment Water Test Sheet

## Underslab Checklist
checklist | QA - Basement Underslab | COMENT
section | Area Prestart / Acceptance & Drawings
Text | Zone / Area
checkpoint | Area ready for works (grids setout, area accessible and approval to start)
checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
section | Under Slab Pipe install
checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | Start Invert
text | Finish Invert
text | Grade of Pre-Line %
text | Product Type
checkpoint | Pipe supported
checkpoint | Install Tests completed, reviewed & approved
text | Test method used
text | Duration
checkpoint | Local Authority Inspection Passed
text | Witnessed by
SIGN BOX
Text | Representing (Company)
text | Date
checkpoint | All relevant test plugs removed where applicable
checkpoint | Open ends sealed
checkpoint | General photos, comments and observations
checkpoint | Pipe Laying Completed
Text | Laid by
bool | Bedding Sound
bool | Soil Removed
bool | Trench Compacted
bool | Hard Filled
section | Area Completion/Signoff
checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint | All Measurements Double Checked
checkpoint | As-Built Drawings recorded (drawing & revision number(s)
checkpoint | All relevant under slab works completed, reviewed and approved
text | Completion Date

## Common Waste & Stacks QA Check
checklist | QA - Waste / Stacks | COMENT
section | Area Prestart / Acceptance & Drawings
Text | Zone / Area
checkpoint | Area ready for works
checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
section | Pipe install
checkpoint | IE's - Test points installed corrrect locations (ASNZS 3500)
checkpoint | Pipeout completed
Check point | Correct labels
Checkpoint | Acoustic lagging
text | Product Type
checkpoint | Correct Pipe supports completed
checkpoint | Seismic bracing completed
checkpoint | Vent installed
checkpoint | Correct fall
checkpoint | Flood Test in accordance with ASNZ 3500
text | Witnessed by
SIGN BOX
Text | Representing (Company)
text | Date
checkpoint | All relevant test plugs removed where applicable
checkpoint | Open ends sealed
checkpoint | General photos, comments and observations
checkpoint | Pipe Install Completed
Text | Installed by
section | Area Completion/Signoff
checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint | All Measurements Double Checked
checkpoint | As-Built Drawings recorded (drawing & revision number(s)
text | Completion Date
Pass,Fail,Partial Pass,N/A
Remove to waste
Remove to waste

## Hot Water Main Checklist
Checklist
checkpoint | Connections welded/crimped correctly
checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint | Lagging installed and neat
checkpoint | Labels installed
checkpoint | Correct valves fitted correctly
checkpoint | Tested

## Main Cold Water QA Checklist
Checklist
checkpoint | Connections welded/crimped correctly
checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint | Lagging installed and neat
checkpoint | Labels installed
checkpoint | Correct valves in correct locations
checkpoint | Tested
Photo&Notes | Add drawing - Highlight completed section. Include channges for As-Builts

## Apartment Water QA Checklist
Section | Water Supply | Preload apartment #'s
checkpoint | Pipe Work Secured in ceiling
checkpoint | Pipe Work Secured in wall
checkpoint | Pipe Work Siliconed
checkpoint | Check for Cross Overs
checkpoint | Pressure Test 1500 KPA or product/job spec
checkpoint | Visual check & photos attached
checkpoint | Check all joints
checkpoint | HWC water feeds
checkpoint | HWC waste
checkpoint | HWC nogs for strapping
label | Attach photos of completed area
Photo | Shower/bath outlet Crimp | Must include photo to pass
checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | Add Signature
checkpoint | Pre Line Inspection Passed - Witness
holdpoint | Add Signature

## Apartment pre line
Section | Pre-line Inspection
Checkpoint | Nogs in correct Location
Checkpoint | Cylinder siesmic nogs in place
checkpoint | Vanity, shower, toilet nogs
Checkpoint | Shower mixer - Depths allowance for tiles, nogs square to wall
Checkpoint | Mixers straight
checkpoint | Vanity Wingbacks
Checkpoint | Outlets straight
Checkpoint | Outlets correct length
checkpoint | HWC water feeds
checkpoint | Capped Off
checkpoint | Rubbish removed
checkpoint | Protective covers in place
label | Attach photos of completed area
checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | Add Signature
checkpoint | Pre Line Inspection Passed - Witness
holdpoint | Add Signature

## Apartment Waste QA Checklist
Section |  | Preload apartment #'s
checklist | First Fix - P.V.C
checkpoint | Waste Pipeout complete
checkpoint | Vent installed
checkpoint | Correct Fall
checkpoint | Correct Clipping
checkpoint | Flood Test in accordance with ASNZ 3500
checkpoint | Hydrostatic test Plug Removed
checkpoint | Inspection Cover Replaced
checkpoint | All pipe stubs & FWG's covered
checkpoint | Visual check & photos attached
label | Attach photos of completed area
checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | Add Signature
checkpoint | Pre Line Inspection Passed - Witness
holdpoint | Add Signature
Photo&Notes | Add drawing - Highlight completed section. Include channges for As-Builts

## Apartment Waste Test Sheet
Checklist | Testing - Waste / Stacks
Text | Area / Stack
checkpoint | Flood Test in accordance with ASNZ 3500 (15.2)
text | Duration
text | Notes
checkpoint | Install Tests completed, reviewed & approved
checkpoint | Local Authority Inspection Passed
text | Witnessed by
Text | Representing (Company)
Signing box
text | Date

## Apartment Water Test Sheet
checklist | Apartment Water Test Sheet
checkpoint | Connections welded/crimped correctly
checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint | Valves fitted correctly
checkpoint | Checked for crossovers
checkpoint | Lagging installed and neat
checkpoint | release TPR and CW expansion valve
checkpoint | Test overflow & safe tray
checkpoint | Set tempering valve temperature 55deg C
checkpoint | Tidy work areas
checkpoint | Pressure 1500 kpa or as per spec
text | Duration
checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
label | Attach photos of completed area
checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | Add Signature
checkpoint | Pre Line Inspection Passed - Inspector
holdpoint | Add Signature

## Pump Test Sheet
Waste Water Pump Commissioning
name | Pump Model Matches Spec
checklist | Waste Water Pump Commissioning
Checkpoint | Chain connected and secure
Checkpoint | Float Valve operating free of obstruction
checkpoint | Flow test pump
checkpoint | Visual check for leaks
checkpoint | Non return valves fitted
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date

## Apartment 2nd Fix QA Checklist
type | name
checklist | Second Fix Plumbing - Water & Waste
checkpoint | Flush all water pipes before connecting fittings
checkpoint | Correct Taps And Fittings Provided
checkpoint | Silicone Applied To Fixtures Where Required
checkpoint | Check All Tap Connectors For Leaks
checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint | Check Traps For Leaks
checkpoint | Check Cisterns For Leaks
checkpoint | Check cisterns flushing correctly
checkpoint | Check All Fixtures Function Correctly
checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint | Check HWC For Correct Valve Installation
checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint | Check Flanges Have Been Installed Where Required
checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint | Kitchen overflow working and no leaks
checkpoint | Picked Up All Left Over Material & Retumed to Office
checkpoint | All your rubbish removed or in bins provided
checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint | Temperature set point
checkpoint | Downpipe & overflow cover installed on balcony
checkpoint | Correct screws on balcony drain
checkpoint | Installers name & date works completed
text | Installers name
text | Date:
checkpoint | Tested by & date
text | Tested by:
text | Date tested:
checkpoint | Council inspector sign off and date

## HOT WATER PLANT QA_TEST
checklist | HOT WATER PLANT
checkpoint | Installation – refer to installation check list for hot and cold water.
checkpoint | Testing – Pressure tested to1500kpa or 1.5 times working pressure whichever is greater.
checkpoint | Temp relief points ran to tundishes.
checkpoint | Temperature probe from control box installed into storage tanks.
checkpoint | Check that an adequate water supply is available to the hot water system.
checkpoint | Water supply pressure shall not exceed the maximum pressure stated by manufacturer.
checkpoint | Open cold water inlet valve, hot water outlet valve
checkpoint | Exercise all valves and ensure correct operation. Ensure all valves are in open position prior turning power on.
checkpoint | Check the system is fully charged & all air is bled from the system & no leaks are evident
checkpoint | Ensure hot water heaters and storage tanks are full of water and all valves are open.
checkpoint | Ensure pressures are not greater then 750Kpa to the heaters or storage tanks.
checkpoint | Open all individual gas isolation valves & purge gas lines.
checkpoint | Test gas pipe work for leaks.
checkpoint | Check the gas supply pressure at the inlet to the water heater with the water heater and all
checkpoint | other burning appliances in the premises operating. The minimum gas supply pressure
checkpoint | range is NG: 1.13Kpa - 3.5Kpa & LPG: 2.75Kpa - 3.5Kpa
checkpoint | Clean filters and strainers once after 4 hours of use.
checkpoint | Set temperature to 65 degrees.
checkpoint | For further detailed applications refer to owners/installation manual from manufacturer