## Folder Structure
BALCONY | Building A | Level 4 | Apartment 401 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 417
|  | Level 5 | Apartment 501 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 517
|  | Level 6 | Apartment 601 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 617
|  | Level 7 | Apartment 701 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 717
|  | Level 8 | Apartment 801 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 817
|  | Level 9 | Apartment 901 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 917
| Building B | Level 5 | Apartment 501 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 502
Apartment 503
Apartment 504
Apartment 505
Apartment 506
Apartment 507
|  | Level 6 | Apartment 601 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 602
Apartment 603
Apartment 604
Apartment 605
Apartment 606
Apartment 607
|  | Level 7 | Apartment 701 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 702
Apartment 703
Apartment 704
Apartment 705
Apartment 706
Apartment 707
|  | Level 8 | Apartment 801 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 802
Apartment 803
Apartment 804
Apartment 805
Apartment 806
Apartment 807
|  | Level 9 | Apartment 901 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 902
Apartment 903
Apartment 904
Apartment 905
Apartment 906
Apartment 907
|  | Level 10 | Apartment 1001 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1002
Apartment 1003
Apartment 1004
Apartment 1005
Apartment 1006
Apartment 1007
|  | Level 11 | Apartment 1101 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1102
Apartment 1103
Apartment 1104
Apartment 1105
Apartment 1106
Apartment 1107
| Building C | Level 1 | Apartment 101 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 114
|  | Level 2 | Apartment 201 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 214
|  | Level 3 | Apartment 301 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 314
|  | Level 4 | Apartment 401 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 414
|  | Level 5 | Apartment 501 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 514
|  | Level 6 | Apartment 601 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 614
|  | Level 7 | Apartment 701 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 714
|  | Level 8 | Apartment 801 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 814
|  | Level 9 | Apartment 901 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 914
|  | Level 10 | Apartment 1001 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1014
|  | Level 11 | Apartment 1101 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1114
|  | Level 12 | Apartment 1201 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1214
|  | Level 13 | Apartment 1301 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1314
|  | Level 14 | Apartment 1401 | G. Closed Cell Foam & Saddle Flashing Checklist
Apartment 1414
Building A | Level 1 | North Elevation / GLAE ~ A8-A16 | A. Lifting Eyes Checklist
B. Baffles Checklist
| Lv. 2 |  | C. Internal Airseal Checklist
| Lv. 3 |  | D. External Airseal Checklist
| Lv. 4 |  | E. Angle Flashing Checklist
| Lv. 5 |  | F. P-Seal Checklist
Lv. 6
| Lv. 7 | South Elevation / GLAH ~ A10-A16 | A. Lifting Eyes Checklist
| Lv. 8 |  | B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | East Elevation / GLAD ~ A1-A6 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | West Elevation / GLAA ~ A1-A7 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
| Level 9 | North Elevation / GLAE ~ A8-A16 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | South Elevation / GLAH ~ A10-A16 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | East Elevation / GLAD ~ A1-A6 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | West Elevation / GLAA ~ A1-A7 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
Building B | Level 1 | North Elevation / GLB4 ~ BA-BH | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
| Lv. 2 |  | E. Angle Flashing Checklist
| Lv. 3 |  | F. P-Seal Checklist
Lv. 4
| Lv. 5 | South Elevation / GLB1 ~ BA-BH | A. Lifting Eyes Checklist
| Lv. 6 |  | B. Baffles Checklist
| Lv. 7 |  | C. Internal Airseal Checklist
| Lv. 8 |  | D. External Airseal Checklist
| Lv. 9 |  | E. Angle Flashing Checklist
| Lv. 10 |  | F. P-Seal Checklist
Lv. 11
|  | East Elevation / GLBH ~ B1-B4 | A. Lifting Eyes Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | West Elevation / GLBA ~ B1-B4 | A. Lifting Eyes Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
| Level 12 | North Elevation / GLB4 ~ BA-BH | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | South Elevation / GLB1 ~ BA-BH | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | East Elevation / GLBH ~ B1-B4 | A. Lifting Eyes Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | West Elevation / GLBA ~ B1-B4 | A. Lifting Eyes Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
Building C | Level 1 | North Elevation / GLC5-C10 ~ CA-CK | A. Lifting Eyes Checklist
B. Baffles Checklist
| Lv. 2 |  | C. Internal Airseal Checklist
| Lv. 3 |  | D. External Airseal Checklist
| Lv. 4 |  | E. Angle Flashing Checklist
| Lv. 5 |  | F. P-Seal Checklist
Lv. 6
| Lv. 7 | South Elevation / GLC1 ~ CA-CK | A. Lifting Eyes Checklist
| Lv. 8 |  | B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | East Elevation / GLCK ~ C1-C10 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | West Elevation / GLCA-CF ~ C1-C10 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
| Level 9 | North Elevation / GLC5-C10 ~ CA-CK | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | South Elevation / GLC1 ~ CA-CK | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | East Elevation / GLCK ~ C1-C10 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist
|  | West Elevation / GLCA-CF ~ C1-C10 | A. Lifting Eyes Checklist
B. Baffles Checklist
C. Internal Airseal Checklist
D. External Airseal Checklist
E. Angle Flashing Checklist
F. P-Seal Checklist

## A.Lifting Eyes Checklist
Type | Name | Value
Checklist | Lifting Eyes Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Fill lifting eyes & upstand with Sika Monotop 412 | Photo Required
Checkpoint | Apply Dryseal 107 over lifting eyes & upstand | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## B.Baffles Checklist
Type | Name | Value
Checklist | Façade Baffle & Soaker Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Install Sika Facade Battle to vertical joints | Photo Required
Checkpoint | Install S/S pin into rebate and mechanically fix to panel | Photo Required
Checkpoint | Install SS soaker - beadseal with Sikaflex 11 FC & mechanically fixed to one panel | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## C. Internal Airseal Checklist
Type | Name | Value
Checklist | Joint Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install expansion tape to vertical inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to vertical joints | Photo Required
Checkpoint | Apply primer to vertical joints | Photo Required
Checkpoint | Apply sealant to vertical joints | Photo Required
Checkpoint | Write initials and date beside each joint | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## D. External Airseal Checklist
Type | Name | Value
Checklist | Joint Sealant Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer to horizontal & vertical joints | Photo Required
Checkpoint | Apply sealant to horizontal & vertical joints | Photo Required
Checkpoint | Form drainage holes with PEF rod | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## E.Angle Flashing Checklist
Type | Name | Value
Checklist | Angle Flashing Checklist
Checkpoint | Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Install Angle Flashing - beadseal with Sikaflex 11 FC & mechanically fixed. | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## F. P-Seal Checklist
Type | Name | Value
Checklist | P Seal Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Install horizontal P seal - beadseal with Ardex CA20 & mechanically fixed. | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## G. Closed Cell & Saddle Flashin
Type | Name | Value
Checklist | Closed Cell Foam & Saddle Flashing Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Apply Sikadur 31CF Epoxy to the substrate | Photo Required
Checkpoint | Install closed cell foam to the joints | Photo Required
Checkpoint | Install Saddle Flashing - beadseal with Sikaflex 11 FC & mechanically fixed | Photo Required
Checkpoint | Installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required