## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 5758947d-36ce-42dc-8cf1-e2e5f9cb6b62 |  | checklist | Façade Baffle & Soaker Checklist |  |  |  |  | Yes | B. Baffles Checklist | 23c642d8-6506-4e31-8865-bc1b17d6edc3
checkpoint-status | 9def7b48-0d23-444a-aab8-f59a1ca9edcc |  | checkpoint | Substrate is clean, dry and ready to start
checkpoint-status | 9f8db81b-65b5-4d88-aac8-0efb65f60ec4 |  | checkpoint | Install Sika Facade Battle to vertical joints
checkpoint-status | cd6b9651-1544-47f1-bfb5-11115f8b581c |  | checkpoint | Install S/S pin into rebate and mechanically fix to panel
checkpoint-status | e4f1dc15-642c-4b02-ab4c-056bb6d8496b |  | checkpoint | Install SS soaker - beadseal with Sikaflex 11 FC & mechanically fixed to one panel
checkpoint-status | 941728ce-3401-4c44-b043-b01959562d57 |  | checkpoint | Installed correctly and as per drawings/specification
checkpoint-status | a17cf6d1-52b6-41d6-8fce-a646dafe12f5 |  | checkpoint | Work area is left clean & tidy
checklist-flat | 148c9d90-0c06-4bee-9e3a-3ed6f64da3f8 |  | checklist | Joint Sealant Checklist |  |  |  |  | Yes | D. External Airseal Checklist | 2490441c-e5a2-4509-9e9e-b7a20a172d1f
checkpoint-status | 791764c4-0758-4b0a-8e58-cca68806ab91 |  | checkpoint | Substrate is clean, dry and ready to start
checkpoint-status | da2cb125-d8aa-40af-955c-fb68645bac64 |  | checkpoint | Record product batch numbers
checkpoint-status | 19cd64ce-4168-4118-b462-2bc662a6fc45 |  | checkpoint | Install PEF backing rod to horizontal & vertical joints
checkpoint-status | 2dc04c26-6a88-4849-af86-b2f94bd91557 |  | checkpoint | Apply primer to horizontal & vertical joints
checkpoint-status | 5b9185a8-3a3f-415d-994a-48a9f938349d |  | checkpoint | Apply sealant to horizontal & vertical joints
checkpoint-status | 3a79d308-669e-4830-81da-62ab914b78a3 |  | checkpoint | Form drainage holes with PEF rod
checkpoint-status | 5155ade2-ecea-4de1-9b3d-6be18f30faa1 |  | checkpoint | Joint sealant installed correctly and as per drawings/specification
checkpoint-status | 49c7e716-bb97-4532-a661-6b21b7e23033 |  | checkpoint | Work area is left clean & tidy
checklist-flat | c1a6270c-344d-47fa-8244-3dc5478719be |  | checklist | Joint Sealant Checklist |  |  |  |  | Yes | C. Internal Airseal Checklist | 35d44a3e-e91e-4d7e-9215-ae91369bfbf7
checkpoint-status | fb9ff7a4-2260-4273-838b-ff59844cfef1 |  | checkpoint | Substrate is clean, dry and ready to start
checkpoint-status | 05683d7b-02dd-4c6d-a469-4be85af04772 |  | checkpoint | Record product batch numbers
checkpoint-status | f45ecde3-e41f-4288-b87a-c8e98245aeaa |  | checkpoint | Install expansion tape to vertical inaccessible areas
checkpoint-status | 9b91bc02-d3b0-4712-9a6e-3ce8e3d98304 |  | checkpoint | Install PEF backing rod to vertical joints
checkpoint-status | ab5ea609-601e-4ae6-8328-a017ce98218e |  | checkpoint | Apply primer to vertical joints
checkpoint-status | 6b63fe49-09b4-43d5-8a11-58474e63104b |  | checkpoint | Apply sealant to vertical joints
checkpoint-status | b4910cd5-b1cc-4372-8018-d02be53e85ce |  | checkpoint | Write initials and date beside each joint
checkpoint-status | a23d6ee2-9580-4b00-885e-484853aa62aa |  | checkpoint | Joint sealant installed correctly and as per drawings/specification
checkpoint-status | 5f003e35-b921-46f2-8538-aa1112420888 |  | checkpoint | Work area is left clean & tidy
checklist-flat | 98b8bd5a-f60c-4184-a1cc-5754ea794917 |  | checklist | P Seal Checklist |  |  |  |  | Yes | F. P-Seal Checklist | 91bb3b4b-6b9b-40f7-9539-9234d05dee64
checkpoint-status | b6260db7-2531-4acf-ab39-20dcf644c5ef |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
checkpoint-status | db93d433-e5b6-409b-be5c-d211771099af |  | checkpoint | Install horizontal P seal - beadseal with Ardex CA20 & mechanically fixed.
checkpoint-status | 55ee318d-50d1-431a-8aa4-c0e2a3106e13 |  | checkpoint | Installed correctly and as per drawings/specification
checkpoint-status | 01a48b9e-08bc-411d-bede-cf16f9ddcf66 |  | checkpoint | Work area is left clean & tidy
checklist-flat | 90d0fb39-b871-4963-aee0-e5f2dc35b403 |  | checklist | Lifting Eyes Checklist |  |  |  |  | Yes | A. Lifting Eyes Checklist | 9353c44d-b213-48ed-87e1-5b6260799cb1
checkpoint-status | 9950704d-1a90-45e6-bc2e-77b21a8c8283 |  | checkpoint | Substrate is clean, dry and ready to start
checkpoint-status | 6ae09d34-f80a-4983-a17f-0f69cb528ef2 |  | checkpoint | Record product batch numbers
checkpoint-status | 92e5f659-f898-4f6e-b80a-0640218d13ba |  | checkpoint | Fill lifting eyes & upstand with Sika Monotop 412
checkpoint-status | f0832c25-4678-4069-887f-987e812e577f |  | checkpoint | Apply Dryseal 107 over lifting eyes & upstand
checkpoint-status | 52d36fdc-c414-4da2-a0c3-d977d36d2773 |  | checkpoint | Installed correctly and as per drawings/specification
checkpoint-status | f8b1e424-889b-4375-b29b-174e92783e8f |  | checkpoint | Work area is left clean & tidy
checklist-flat | d7fea427-62c4-4147-9092-2a15f9543ae8 |  | checklist | Angle Flashing Checklist |  |  |  |  | Yes | E. Angle Flashing Checklist | eae80ecc-4d31-4475-b8da-e25f07c23edf
checkpoint-status | a290d93b-725f-4ffe-a975-f16116a45002 |  | checkpoint | Substrate is clean, dry and ready to start
checkpoint-status | b2576da2-5814-4328-a78d-82f0d76b459f |  | checkpoint | Install Angle Flashing - beadseal with Sikaflex 11 FC & mechanically fixed.
checkpoint-status | e7c669e4-b887-41bd-8166-fa802b2cf1d9 |  | checkpoint | Installed correctly and as per drawings/specification
checkpoint-status | 6c77d25b-b397-4c7c-ae5e-4947ae1fb4af |  | checkpoint | Work area is left clean & tidy