## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 0cc25f8c-8f0f-4bd6-a61a-5226c6bf5303 |  | checklist | Voltex to GB. Date/Area: |  |  |  |  | Yes | QA - Voltex to Ground Beams | 3066148c-4b5f-475d-b552-c23b3d39a48e
checkpoint-status | 6ba67195-3f87-4a78-ba86-5f99af7df671 |  | checkpoint | Substrate acceptable
checkpoint-status | 10f23f72-9a8a-4a73-9cac-84959d1832c6 |  | checkpoint | Form work acceptable
checkpoint-status | e02be2b0-9474-44ab-b6a7-4d571aa896f0 |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status | 1767750a-9414-4f6d-9a8d-1a7526c75f9e |  | checkpoint | Penetration(s) detailed and photo(s) taken of each
checkpoint-status | e89437ab-7e1e-4025-98a2-1b9a45882923 |  | checkpoint | Area left clean, tidy and rubbish removed
checkpoint-status | a01722f8-8ec5-4a77-9cb7-90b659fa905e |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-sectioned | 3e44e0de-6c3b-4802-9414-2bcda241fefd |  | checklist | Volclay Waterproofing Warranty Request |  |  |  |  | Yes | Warranty Req - Volclay Waterproofing | 40242019-43d9-4596-ab9f-aa271f01b139
checkpoint-group | 5cdd2af4-5658-448a-832a-cb301e12bdf1 |  | section | Project Info
checkpoint-status | 0f1dfeff-a0cb-4613-bb1b-2b0e8a9a6c4a |  | checkpoint | Project Info
text | 985899ca-5d13-53f9-9886-5cd63b9b17b6 |  | textbox | PROJECT ADDRESS:
text | 2bbbc9ed-2a61-591f-adc8-015b11c3c50b |  | textbox | PROJECT SIZE (sq m):
text | a4e1c0e4-2f5c-535c-9734-20c6b59d5259 |  | textbox | PROJECT START DATE:
text | dfeada96-48ff-5587-89bc-c91cdd339ea8 |  | textbox | COMPLETION DATE:
radio | 8e5106b5-e755-5158-8f11-d343c70785ad |  | radio | HYDROSTATIC HEAD (select one “x”): | No,Yes
text | 2bfba684-ed36-5952-b21a-3a6d721ce861 |  | textbox | If yes, how many metres?
radio | 40458e8a-4005-55af-abe4-1fd7a1010435 |  | radio | WARRANTY TYPE (select one “x”): | Product,System
checkpoint-group | 93bb0ca2-6098-40d8-855e-834ef5b8ac11 |  | section | OWNER/BUILDER INFORMATION
checkpoint-status | 33ac443a-4f28-49c5-95de-7714ec421b0f |  | checkpoint | OWNER/BUILDER INFORMATION
radio | 287ce15c-0d83-53e4-aa5a-1e27d70e9d5e |  | radio | OWNER/BUILDER INFORMATION (Please indicate which) | Builder,Owner
text | b14909ae-46f7-543e-aaca-432508e80887 |  | textbox | NAME:
text | d4375383-a979-5ae4-9cb8-149141aa6441 |  | textbox | CONTACT:
text | aa5ae38b-0fd8-576e-838e-9c6446b7702c |  | textbox | ADDRESS:
text | 584f2a19-c1b5-56f7-b74c-d77eb9145536 |  | textbox | PHONE:
text | 1d0213b9-f439-518d-9dbb-aad7f185cf6a |  | textbox | FAX:
text | 13a629e4-60b9-5575-8155-f438552be6c0 |  | textbox | EMAIL:
checkpoint-group | e64a0c21-f4b1-4511-aa67-cce495b428e5 |  | section | APPLICATOR INFORMATION
checkpoint-status | 4d9aa94c-f3f8-4b27-a422-822b4ffb5ed5 |  | checkpoint | APPLICATOR INFORMATION
text | 08db5e9c-4191-5c51-bb46-0efb155efbdd |  | textbox | APPLICATOR:
text | a50422d6-2eaa-5b6a-9a6b-def65567731a |  | textbox | CONTACT:
text | 0c3de058-268d-5fd7-846d-c83a730467ed |  | textbox | ADDRESS:
text | d0fab130-35c0-5dc6-9d40-e23bbfb3e533 |  | textbox | PHONE:
text | 1084e6a6-eeb7-503c-ae9a-293f2d26c938 |  | textbox | FAX:
text | a4ec1ddc-0e73-5f4a-9433-e2f17a4decaf |  | textbox | EMAIL:
checkpoint-group | 52288543-a8e7-4f9d-a5d0-b230f669d7e9 |  | section | LIST QUANTITY OF FOLLOWING PRODUCTS USED:
checkpoint-status | 720e1124-0bc5-4c78-b185-bc42ae9265c6 |  | checkpoint | LIST QUANTITY OF FOLLOWING PRODUCTS USED:
label | 82e5accc-a7b7-5b0f-96fb-46180e37a166 |  | note | (Provide sq m, linear metres, litres used) MUST BE COMPLETED
checkpoint-status | ec373b23-5fb6-42b9-9f54-e1f8dd953276 |  | checkpoint | STRATASEAL
boolean | b3e077b1-a4de-5724-9649-e4261ac19c6e |  | tickbox | Hot Rubber
checkpoint-status | e6ce31b5-abdb-4d2c-bbe4-60f3d070b038 |  | checkpoint | SWELLTITE
boolean | de469fa3-8afe-5c5d-a835-ce520a0a13a9 |  | tickbox | Swelltite
checkpoint-status | fdc27cf2-983b-4633-a25e-46842e757315 |  | checkpoint | VOLTEX
boolean | 71e0e0f7-f8f3-5651-a8cb-ba37f17accb0 |  | tickbox | Reg
boolean | df39d6e2-ce34-5691-b6dd-9401b4e5be97 |  | tickbox | DS
boolean | 1ec45f59-2f77-565b-ba38-93246604d70c |  | tickbox | DS/SWR
checkpoint-status | cf5916aa-4fea-4dd5-b78e-3b628a0d7e7b |  | checkpoint | WATERSTOP-RX
boolean | 2a575ffa-8801-5eef-8674-e8ca91e585a6 |  | tickbox | RX-101
boolean | a01a2d3a-065c-5050-9df0-d07c47df9565 |  | tickbox | RX-101T
boolean | 26d975c5-65d2-5780-bfed-993d1a20422a |  | tickbox | RX-102
boolean | 444fe6ee-76cb-525c-bc5d-cdc2a3e8f2da |  | tickbox | Cetseal
boolean | 406bbc48-1d5c-5173-aa0b-eb32e3dee949 |  | tickbox | Revofix (Mesh)
checkpoint-status | 0ea228ca-aea0-475b-836e-4196672ca638 |  | checkpoint | AQUADRAIN
boolean | 14f3d8f2-c634-5bc3-9a2f-c62fe8bfe22c |  | tickbox | 15x
boolean | 47c95381-187d-577d-8db4-092975fcef17 |  | tickbox | GS310
checkpoint-status | 160228de-9015-412a-a762-401e92a33093 |  | checkpoint | ULTRASEAL
boolean | b8c4ebda-f2ca-5978-8146-4bc03989d827 |  | tickbox | BT
boolean | 9bffeefa-91d8-53a0-a831-1e14d1ec1eab |  | tickbox | SP
checkpoint-status | dbea5f13-592d-4a79-bbb7-077264ff3cc6 |  | checkpoint | ACCESSORIES
boolean | 8c054e5f-4d42-5649-8dd7-e8eb5cc43262 |  | tickbox | AKWASEAL
boolean | 4d50a17e-ff21-53e4-8590-a35946b85455 |  | tickbox | AKWASTOP
boolean | d5f4d2c5-9a1b-5709-b430-ddd10b23c441 |  | tickbox | BENTOGROUT
boolean | b825c27b-6a50-5b5b-bed5-e17327be1683 |  | tickbox | BENTOSEAL
boolean | 057c3c64-c320-596e-a2db-f456d1531204 |  | tickbox | CETCOAT
boolean | 7ed256dc-0f08-50a9-8e90-325cd4e98001 |  | tickbox | ENVIROSHEET
boolean | 9b907af9-2c89-54af-8832-5e6f31f6b920 |  | tickbox | ENVIROSHEET LT
boolean | d5a0448f-6984-5ecc-b036-8aa296c9bd9e |  | tickbox | HYDROBAR TUBES
boolean | 55ae270b-a041-5f80-a10d-b77e8f869c65 |  | tickbox | WATERSTOPPAGE
checkpoint-status | 87005300-caa5-4aa5-a32b-d9b097896d81 |  | checkpoint | “x” PROJECT TYPE:
boolean | 63f61117-4f35-5265-a113-82d4f5845878 |  | tickbox | Residential
boolean | 39d1cd48-8b6b-5b4a-af35-fbdab45589d3 |  | tickbox | Apartment
boolean | 816fce82-a7be-5ca1-a385-58b4939f3cb5 |  | tickbox | Commercial Bldg
boolean | 200a3e3b-fbc4-5516-947a-9242b2898e2d |  | tickbox | Roading
boolean | 28d46e11-02da-5cbb-b362-f5a08de10506 |  | tickbox | Educational
boolean | d127be2d-773d-5589-a390-ae6768d64ab4 |  | tickbox | Civil
boolean | 7994f92d-5960-5776-9761-cee6e5829a1e |  | tickbox | Sports facility
boolean | 8dc5d33a-4b03-5813-92d4-ca471cd320a6 |  | tickbox | Hospital
boolean | 903bb69f-dd00-522f-9fed-caf0d96449cb |  | tickbox | Hotel
checkpoint-status | c4b6f640-333b-4151-aff4-caf684e34c42 |  | checkpoint | “x” CONSTRUCTION APPLICATION(S): (Tick as many as apply) MUST BE COMPLETED
boolean | d069b7ba-a061-5b1d-9cae-bc67548607b8 |  | tickbox | Backfilled Walls
boolean | 3fbd9271-ad90-5014-a47d-9a4418722367 |  | tickbox | Precast Panel
boolean | a8f6e5fb-013f-5af8-b199-44fcc3399792 |  | tickbox | Contiguous Pile Shotcrete
boolean | fb649d11-df73-5748-99c0-e81c1118829f |  | tickbox | Insitu Poured Concrete
boolean | 97516521-0c13-59f6-9f82-29c8a6038da1 |  | tickbox | Grout Injection
boolean | 7ab0c7f1-1c9a-530a-8539-cd9ffdeab265 |  | tickbox | Injection (urethane)
boolean | 14e59786-9d3e-5bf1-b1ce-e323128f67c5 |  | tickbox | Footings
boolean | 779cc54d-03f4-5437-872a-8ed77a82a1d3 |  | tickbox | Lift pits
boolean | be7a9727-e44a-5b1f-b8c6-1d830197bf2f |  | tickbox | Masonry Block Wall
boolean | 7e641474-f261-5ea1-80d4-3a9992c08e3d |  | tickbox | Foundations
boolean | 3c1cfaa3-5962-57a1-8bfb-f041b366cc42 |  | tickbox | Plaza Deck
boolean | b855ac96-2d25-51e8-9ba8-c76c809560ef |  | tickbox | Green Roof
boolean | 6d004166-8ad5-553c-8a78-a703acdeca13 |  | tickbox | Secant Pile
boolean | 6d87238f-fbc3-537d-8cf1-4367e05c97a6 |  | tickbox | Sheet Piling
boolean | 2918360d-df5d-53a2-b513-133df7db0462 |  | tickbox | Underslab
boolean | 8a248273-4c9b-50c2-a227-20c8cfb18e14 |  | tickbox | Shotcrete Piled Wall
boolean | dbdf6a92-fd4c-581d-a36f-0833dcba3711 |  | tickbox | Split Slab
boolean | 47342001-3529-500c-a806-7e38d45b1d5b |  | tickbox | Tunnel
boolean | efb9e575-cf26-576a-978b-d66f2f2b0bac |  | tickbox | Underslab
text | 443b6ff8-e078-5ce5-a999-8a89bf94fecb |  | textbox | OTHER (Please state)
label | 843fa1b9-6874-5f81-8ce2-78f344bc3860 |  | note | *** Please remember to attach all relevant Quality Assurance photographs*** *** Please note areas on the request that must be completed***
checklist-flat | 737a6941-2a95-4edb-b95a-b0f5c43e3f1d |  | checklist | Voltex to Wall Checklist |  |  |  |  | Yes | QA - Voltex to Wall Checklist | 4a757ca6-497a-4181-ae92-3ba751487e0e
checkpoint-status | a3ecf379-5c40-4896-b613-42690d351dfa |  | checkpoint | Substrate acceptable
checkpoint-status | 68f95399-faff-44cf-b631-df916cdd82e2 |  | checkpoint | Is lap from capping beam accessible/acceptable
checkpoint-status | 1a62e5e9-5f35-418f-8c9c-313473286d27 |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status | 230f88cd-58f5-4fde-b498-c062b4d68ef8 |  | checkpoint | Rx Waterbar 101t/bentoseal installed to piles/capping beam
checkpoint-status | 4e2095d9-7e03-4067-afc9-dbe5cb540927 |  | checkpoint | Penetration(s) detailed?
boolean | b814ab5a-e6c2-5126-b6d4-1acda5719979 |  | tickbox | Photo taken of each
checkpoint-status | d4817a2e-2b8d-4290-96ed-6e9a08be1a22 |  | checkpoint | Area left clean, tidy and rubbish removed
checklist-flat | 2aa2a7ed-2364-4deb-ba20-22d94b115844 |  | checklist | Document: |  |  |  |  | Yes | Document Attach | 51248b57-8650-4d29-9f30-92a8cd43da5d
checkpoint-status | 12c8ad85-0133-4af1-948a-ad327307b0f9 |  | checkpoint | Document Attached
checklist-sectioned | 1be3c28a-6b2e-4c76-9057-a68e56e805e1 |  | checklist | Concrete Repair Checklist |  |  |  |  | Yes | QA - Concrete Repair Checklist | 9efff8fe-9a08-4c70-a4ca-9ca22816e951
checkpoint-group | fee00e50-3958-4b79-a663-6fa647967173 |  | section | SB1 Dicore Supports
checkpoint-status | 97b95b7d-1301-492b-9dbb-9539fb79b59d |  | checkpoint | Marking holes
checkpoint-status | 687ceda9-19b8-4ed5-b5ae-bcdafd3f1900 |  | checkpoint | Drilling 150mm deep
checkpoint-status | d15301e1-36b6-4371-a0ff-661a8625bfa4 |  | checkpoint | Cleaning holes
checkpoint-status | 2af0efd8-c8d5-4fd2-b82e-da594ad5888e |  | checkpoint | Fitting bolts
checkpoint-status | d98e0549-43dd-486f-9fb8-aaffd6cdd1c4 |  | checkpoint | Fitting plate
checkpoint-status | 257ee064-d598-4fa4-9122-ef61bdf03378 |  | checkpoint | Bolt tension
checkpoint-group | 05827e6d-950b-493d-ae77-5789762f2247 |  | section | M12 Hangers
checkpoint-status | f8b49ba9-31db-4204-a9a1-496b7a12c83d |  | checkpoint | Hole location
checkpoint-status | 5a6494f3-ce0c-4b70-89d0-a10b513b15bb |  | checkpoint | Hole depth 380mm
checkpoint-status | 8421cc68-8681-4000-a4ab-57f7e3c4aea4 |  | checkpoint | Cutting 380mm
checkpoint-status | e5b2c94e-bf59-4266-bfbd-b09311dcb0a1 |  | checkpoint | Chip out 20mm deep
checkpoint-status | e7e66b97-60d4-4004-847b-440164c25e31 |  | checkpoint | Fit bolt, washer, nut, pour epoxy under plate, tighten nut
checklist-sectioned | ce501018-7a86-4b35-8e51-c1e1fab89214 |  | checklist | Preprufe Tanking Underfloor - |  |  |  |  | Yes | QA - Preprufe Tanking Underfloor Checklist | a13bf3f4-6c21-4bc4-8969-b98bb7388c03
checkpoint-group | 42fb288c-2c8b-4e27-88a2-9ebda5fc286d |  | section | Pre Start
checkpoint-status | 963b26f6-5433-455b-8550-4ff74e469d3a |  | checkpoint | Work area clear, tidy and accessible
checkpoint-status | 570e1148-bde6-4d3d-856f-460d7af052f0 |  | checkpoint | Previous substrate/opening acceptable
checkpoint-group | 43142905-8d2a-4160-97a0-c0d7d76efed9 |  | section | Install QA
checkpoint-status | ca473746-51d0-4a23-8bfc-012b7130bb13 |  | checkpoint | Area (grid lines)
checkpoint-status | 9167ce90-44c8-4c72-b66f-422590c1e136 |  | checkpoint | Pile tops sealed with epoxy
checkpoint-status | 3a614a17-f14b-464f-b564-925e91258776 |  | checkpoint | Preprufe placed and laps taped with Preprufe bedded into LM 3000 on top of piles
checkpoint-status | 946e6605-2950-4130-8bcd-cdf0b35a953c |  | checkpoint | Adcor 500 T placed around top of pile
checkpoint-status | b05a4d6b-cdf8-4737-b194-836fa2aeb2ec |  | checkpoint | Swell seal WA placed around all pile bars
checkpoint-status | cce585c6-d07c-4879-8ccd-28d6f081282d |  | checkpoint | CJ tape placed at construction joint locations
checkpoint-status | a504488d-a485-4f13-88bc-2223b43579de |  | checkpoint | Preprufe lapped and taped to the DPM
checkpoint-group | 852d4f5e-e199-4481-8ea1-3585d17ed278 |  | section | Handover
checkpoint-status | 8df12188-f17e-433f-b1a0-7dd811f3f6d1 |  | checkpoint | Area and item left clean and tidy
checkpoint-status | bc25c7c1-c107-445b-b8e7-d1868ac692fd |  | checkpoint | Final Sign Off
checklist-flat | 9461573b-647b-4f8b-8ac2-6b23b65ac440 |  | checklist | Voltex - Area: |  |  |  |  | Yes | QA - Tanking Voltex | cb44b3b9-9953-4466-9a3c-3d0f6df83229
checkpoint-status | 64bd6d35-882a-4747-aefb-8fce065faeee |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 9b2ad16f-4db6-40b0-bfe1-6fcb5e2e0925 |  | checkpoint | Form work acceptable
checkpoint-status | 70ac0545-c20e-4ab6-b8ad-e12586f886c4 |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status | 859be09c-6532-439c-b549-df69f6c4fd7c |  | checkpoint | Penetration(s) detailed and photo(s) taken of each
checkpoint-status | 64cfd265-c97c-4e9c-8a04-76314b3d1cea |  | checkpoint | Photo of highlighted drawing showing locations of work