## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Underpass Construction - 103 - Rev C | itp |  |  |  | Yes | ITP - Underpass Construction - 103 - Rev C
checkpoint-group |  |  | section | 4.21 Underpass Materials
checkpoint-status |  |  | checkpoint | 4.21.01 - Concrete Plant
label |  |  | note | Acceptance / Conformance Criteria - All plants supplying concrete to the project shall hold and maintain a current quality Certificate of Audit in accordance with NZS 3104 throughout the duration of their supply of concrete for the contract. A copy of each plant’s current Certificate of Audit shall be submitted to the Engineer prior to their initial supply of concrete.
label |  |  | note | Standard / Specification - PS 19.7.1
label |  |  | note | Verifying Document - Audit Cert
label |  |  | note | Frequency - Prior to their initial supply of concrete
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.21.02 - Blinding Concrete
label |  |  | note | Acceptance / Conformance Criteria - Blinding concrete shall have a minimum 28 days compression strength of 10 MPa and comply with the requirements for Prescribed Mix concrete specified by NZS 3104.
label |  |  | note | Standard / Specification - PS 19.5.1, PS 19.7.10
label |  |  | note | Verifying Document - Approved Mix Design
label |  |  | note | Frequency - Submitted to and approved by the Engineer prior to concreting
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.21.03 - Underpass Entrances Concrete
label |  |  | note | Acceptance / Conformance Criteria - The Underpass Entrances (insitu) concrete shall be a Normal 40MPA 19mm Mix.
label |  |  | note | Standard / Specification - PS 19.6.1, PS 19.7.9
label |  |  | note | Verifying Document - Approved Mix Design
label |  |  | note | Frequency - Submitted to and approved by the Engineer prior to concreting
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.21.04 - Precast Mild steel fixings
label |  |  | note | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
label |  |  | note | Standard / Specification - PS 19.15.6
label |  |  | note | Verifying Document - Datasheet / Mill Certs
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.21.05 - Precast Stainless steel
label |  |  | note | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
label |  |  | note | Standard / Specification - PS 19.15.7
label |  |  | note | Verifying Document - Datasheet / Mill Certs
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.21.06 - Reinforcement cover spacer blocks
label |  |  | note | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
label |  |  | note | Standard / Specification - PS 19.7.8
label |  |  | note | Verifying Document - Datasheets
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 4.22 Underpass Materials – Associated Works
checkpoint-status |  |  | checkpoint | 4.22.01 - uPVC Pipe
label |  |  | note | Acceptance / Conformance Criteria - Pipes and fittings shall comply with the requirements of AS/NZS 1254:2010 for uPVC pipes
label |  |  | note | Standard / Specification - PS 19.27
label |  |  | note | Verifying Document - Datasheets
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.02 - Anti-Graffiti Product
label |  |  | note | Acceptance / Conformance Criteria - Permanent (not sacrificial) anti-graffiti coatings shall be applied to the exposed faces of all concrete surfaces including wingwalls. The coatings shall have a design life of not less than 10 years. The Contractor shall submit the proposed extent of application for authorisation by the Engineer.
label |  |  | note | Standard / Specification - PS 19.24.1, PS 19.24.2
label |  |  | note | Verifying Document - Details of prequalified Product
label |  |  | note | Frequency - Prior to Application
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.03 - Anti-Graffiti Label
label |  |  | note | Acceptance / Conformance Criteria - At least two weeks prior to the applicable works, the Contractor shall submit details of the label to the Engineer for authorisation.
label |  |  | note | Standard / Specification - PS 19.24.4
label |  |  | note | Verifying Document - Label Details
label |  |  | note | Frequency - At least two weeks prior to the applicable works
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.04 - Steelwork Fabrication Notice
label |  |  | note | Acceptance / Conformance Criteria - To allow for the provision of inspection and verification, the Contractor shall, in writing, notify the Engineer at least one weeks prior to commencement of the workshop fabrication work.
label |  |  | note | Standard / Specification - PS 19.26.6
label |  |  | note | Verifying Document - Notice
label |  |  | note | Frequency - At least one weeks prior to fabrication
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.05 - Steelwork Shop and Erection Drawings
label |  |  | note | Acceptance / Conformance Criteria - The Contract Drawings show the design intent. The Contractor shall submit shop and erection drawings to the Engineer for approval a minimum of 10 days prior to fabrication.
label |  |  | note | Standard / Specification - PS 19.26.7
label |  |  | note | Verifying Document - Drawings
label |  |  | note | Frequency - 10 days prior to fabrication
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.06 - Welding Plan
label |  |  | note | Acceptance / Conformance Criteria - The Welding Plans shall comply with AS/NZS 5131, Section 7.
label |  |  | note | Standard / Specification - PS 19.26.8
label |  |  | note | Verifying Document - Welding Plan
label |  |  | note | Frequency - Prior to Welding
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.07 - Welder Qualiications
label |  |  | note | Acceptance / Conformance Criteria - Welder Qualiications shall comply with AS/NZS 5131, Section 7.
label |  |  | note | Standard / Specification - PS 19.26.8
label |  |  | note | Verifying Document - Qualifications
label |  |  | note | Frequency - Prior to Welding
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.08 - Supply of Non-slip Coating
label |  |  | note | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150.
label |  |  | note | Standard / Specification - PS 19.23.1
label |  |  | note | Verifying Document - Datasheet
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.09 - Joint Sealing and Waterproofing Sealant
label |  |  | note | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
label |  |  | note | Standard / Specification - PS 19.22.1, PS 19.22.7
label |  |  | note | Verifying Document - Datasheet
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.10 - Debonding tape / Backing Rod
label |  |  | note | Acceptance / Conformance Criteria - A polyethylene bond breaker tape, or a closed cell, polyethylene backing rod shall be used in movement joints unless joint sealant is natureally bond breaking.
label |  |  | note | Standard / Specification - PS 19.22.3
label |  |  | note | Verifying Document - Datasheet
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.11 - Compressible filler board
label |  |  | note | Acceptance / Conformance Criteria - Details of the Compressible filler board proposed to be used shall submitted to the Engineer for acceptance at least 1 week prior to installation.
label |  |  | note | Standard / Specification - PS 19.22.6
label |  |  | note | Verifying Document - Datasheet
label |  |  | note | Frequency - prior to installation.
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.12 - Reinforcement bars
label |  |  | note | Acceptance / Conformance Criteria - All Reinforcement bars shall be of New Zealand origin unless otherwise accepted, grade 500 ductility class E and shall be manufactured by the micro-alloy process. Quenched and tempered reinforcement shall not be permitted.
label |  |  | note | Standard / Specification - PS 19.16.12
label |  |  | note | Verifying Document - Mill Certs
label |  |  | note | Frequency - Each Item
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.14 - Reinforcement Welding Approval
label |  |  | note | Acceptance / Conformance Criteria - Steel reinforcement shall not be welded, except where specified on the Drawings or approved by the Engineer. In either case, welding of reinforcement shall comply with AS/NZS 1554.3.
label |  |  | note | Standard / Specification - PS 19.16.15
label |  |  | note | Verifying Document - Engineers Approval
label |  |  | note | Frequency - Before Welding
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.15 - Welding TPI Inspections
label |  |  | note | Acceptance / Conformance Criteria - The welding shall be inspected by the Contractor’s Third Part Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3 with the following additional requirements: All welding shall undergo visual scanning. Welding shall be non-destructively tested to the extent and standards of acceptance of AS/NZS 1554.1 Appendix F, for SP welds. All welds shall be visually scanned by the steel fabricator. 30% of the welds shall undergo visual examination in accordance with Table 6.2.2 and 5% of the welds shall be subjected to radiography or ultrasonic testing in accordance with Table 6.2.1 of AS/NZS 1554.1.
label |  |  | note | Standard / Specification - PS 19.16.16
label |  |  | note | Verifying Document - TPI Report
label |  |  | note | Frequency - 100% Visual Scanning
label |  |  | note | ○ 30% Visual Examination
label |  |  | note | ○ 5% Radiography / Ultrasonic Tesing
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 4.22.16 - Bar Schedule
label |  |  | note | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
label |  |  | note | Standard / Specification - PS19.16.20
label |  |  | note | Verifying Document - Bar Schedule
label |  |  | note | Frequency - At least 14 days before the start of placing
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.17 - Reinforcing Mill Certs
label |  |  | note | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of ay work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
label |  |  | note | Standard / Specification - PS19.16.23
label |  |  | note | Verifying Document - Mill Certs
label |  |  | note | Frequency - At least one week before the programmed commencement of ay work incorporating these materials
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.22.18 - Corrosion Protection
label |  |  | note | Acceptance / Conformance Criteria - Unless otherwise shown on drawings, all steel members, bolts, nuts and washers, excluding any stainless-steel components shall be hot dip galvanized after fabrication in accordance with AS/NZS4680.
label |  |  | note | Standard / Specification - PS 19.17.1
label |  |  | note | Verifying Document - Datasheet
label |  |  | note | Frequency - Each Item
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 10.01 Concrete Pours
checkpoint-status |  |  | checkpoint | 10.01.1 - Construction Joint Locations
label |  |  | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
label |  |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label |  |  | note | Verifying Document - Approval
label |  |  | note | Frequency - Prior to Pour
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.01.2 - Dry Pack Mortar
label |  |  | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
label |  |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label |  |  | note | Verifying Document - Pre pour
label |  |  | note | Frequency - Before Works
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.3 - Blinding Concrete Subgrade Inspection
label |  |  | note | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
label |  |  | note | Standard / Specification - PS 19.5.1
label |  |  | note | Verifying Document - Pre Pour Checksheet
label |  |  | note | Frequency - Prior to Pour
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.01.4 - Reinforcement Pre Pour Inspection
label |  |  | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label |  |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label |  |  | note | Verifying Document - Pre pour
label |  |  | note | Frequency - Each Pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.5 - Pre-Pour Inspection
label |  |  | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label |  |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label |  |  | note | Verifying Document - Signed Pre-Pour
label |  |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.01.6 - Delivery Dockets
label |  |  | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label |  |  | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
label |  |  | note | Verifying Document - Dockets
label |  |  | note | Frequency - Each Pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.7 - Slump Testing
label |  |  | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
label |  |  | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label |  |  | note | Verifying Document - Pre Pour
label |  |  | note | Frequency - Each Pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.8 - Compression Testing Insutu Concrete
label |  |  | note | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
label |  |  | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
label |  |  | note | Verifying Document - IANZ Test Results
label |  |  | note | Frequency - One Set Daily consist of at least six field specimens
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.01.9 - Compression Testing Precast Concrete
label |  |  | note | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label |  |  | note | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
label |  |  | note | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
label |  |  | note | Verifying Document - Plant Test Results
label |  |  | note | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-group |  |  | section | 10.02 Post Pours
checkpoint-status |  |  | checkpoint | 10.02.1 - Post Pour Inspection
label |  |  | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label |  |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
label |  |  | note | Verifying Document - Post Pour
label |  |  | note | Frequency - Each Pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.2 - Construction joints
label |  |  | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
label |  |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
label |  |  | note | Verifying Document - Post Pour
label |  |  | note | Frequency - Each Pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.3 - Concrete Curing
label |  |  | note | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
label |  |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.12
label |  |  | note | Verifying Document - Post Pour
label |  |  | note | Frequency - At least 7 days after pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.4 - Stripping
label |  |  | note | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
label |  |  | note | Standard / Specification - PS 18.2, PS 19
label |  |  | note | Verifying Document - Post Pour
label |  |  | note | Frequency - At least 3 days after pour
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.5 - Protection of Completed Works
label |  |  | note | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
label |  |  | note | Standard / Specification - PS 18.2, PS 19
label |  |  | note | Verifying Document - Post Pour
label |  |  | note | Frequency - During the remainder of the construction period
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - PE
checkpoint-status |  |  | checkpoint | 10.02.6 - Defective Concrete Finishes
label |  |  | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label |  |  | note | Standard / Specification - PS 18.2, PS 19, PS 19.13
label |  |  | note | Verifying Document - NCR
label |  |  | note | Frequency - Prior to non Minor Repair
label |  |  | note | Verification Activity: Activity - V
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.01 Undercut to Drying Site and Backfill with Compacted GAP65
checkpoint-status |  |  | checkpoint | 12.01.01 - Excavations
label |  |  | note | Acceptance / Conformance Criteria - All excavations/cuts shall be carried out in fully drained conditions with no free water on the working surface.
label |  |  | note | Standard / Specification - PS 19.4.1
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - During Works
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.01.02 - Foundations
label |  |  | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
label |  |  | note | Standard / Specification - Downer
label |  |  | note | Verifying Document - Scala Report
label |  |  | note | Frequency - 10m
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.01.03 - GAP65
label |  |  | note | Acceptance / Conformance Criteria - The imported granular Material shall be GAP65 with the grading envelope given in Table 15-3 and have the following geotechnical parameters after placement and compaction Angle of internal friction = 35° and Cohesion = 0kPa
label |  |  | note | Standard / Specification - PS 19.4.5.3
label |  |  | note | Verifying Document - IANZ Test Reprots
label |  |  | note | Frequency - Prior to use
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.01.04 - GAP65 Layer Compaction
label |  |  | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
label |  |  | note | Standard / Specification - PS 19.4.5.4
label |  |  | note | Verifying Document - NDM Report
label |  |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.01.05 - GAP65 Layer thickness.
label |  |  | note | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness. The GAP65 layers shall be constructed in accordance with NZTA B/2. The maximum lift thickness shall be 200mm.
label |  |  | note | Standard / Specification - PS 19.4.5.4
label |  |  | note | Verifying Document - Survey / Level Checks
label |  |  | note | Frequency - 1 test per 20m
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.01.06 - Proof Rolling
label |  |  | note | Acceptance / Conformance Criteria - The GAP65 layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
label |  |  | note | Standard / Specification - PS 19.4.5.5
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Prior to Concreting
label |  |  | note | Verification Activity: Activity - W
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.02 Concreting
checkpoint-status |  |  | checkpoint | 12.02.02 - Insitu Concreting Methodology
label |  |  | note | Acceptance / Conformance Criteria - The Contractor shall submit the proposed handling and placing methods, sequence and timing of pours and location on construction joints for the Engineer's consent before concrete placing commences. Where a placing diagram, construction joint location diagram or equivalent is included in the drawings, the requirements thereof shall be followed unless changes are specifically agreed by the Engineer in writing.
label |  |  | note | Standard / Specification - PS 19.9.1
label |  |  | note | Verifying Document - Methodology
label |  |  | note | Frequency - Before concrete placing commences
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 12.03 Precast Concrete
checkpoint-status |  |  | checkpoint | 12.03.01 - Precast Methodology
label |  |  | note | Acceptance / Conformance Criteria - Details of the proposed method of casting, curing, storing, transportation, and erection shall be submitted to the Engineer before commencing manufacture of the mould and precast units.
label |  |  | note | ○ The Engineer shall be informed 24 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units.
label |  |  | note | Standard / Specification - PS 19.15.1
label |  |  | note | Verifying Document - Methodology
label |  |  | note | Frequency - Before commencing manufacture of the mould and precast units.
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.03.02 - Precast Shop Drawings
label |  |  | note | Acceptance / Conformance Criteria - The Contractor shall make available the shop drawings to the Engineer for review, at least 14 days prior to manufacture. Any variations between the Drawings and shop drawings shall be clearly identified and brought to the attention of the Engineer.
label |  |  | note | Standard / Specification - PS 19.15.16
label |  |  | note | Verifying Document - Shop Drawings
label |  |  | note | Frequency - At least 14 days prior to manufacture
label |  |  | note | Verification Activity: Activity - HP
label |  |  | note | Verification Activity: By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 12.04 Installation and Bolt Tightening
checkpoint-status |  |  | checkpoint | 12.04.01 - Structural steelwork fixed to the concrete surfaces Dry Packing
label |  |  | note | Acceptance / Conformance Criteria - All structural steelwork fixed to the concrete surfaces shall be bedded against the concrete surfaces using a layer of dry pack mortar, plastic bedding mortar or grout with a minimum compressive strength at 28 days of at least the specified compressive strength of the element being bedded against.
label |  |  | note | Standard / Specification - PS 19.18.1
label |  |  | note | Verifying Document - Pre Pour
label |  |  | note | Frequency - All structural steelwork fixed to the concrete surfaces
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.04.02 - Bolt, threaded rod, and stud connections
label |  |  | note | Acceptance / Conformance Criteria - All bolt, threaded rod, and stud connections shall be installed in accordance with AS/NZS 5131 Section 8.2. Tightening shall be to the snug tight condition as specified in Section 8.3 of AS/NZS 5131 after the mortar packing or grout has hardened. Where shown on the drawings, lock nuts shall be fitted, and snug tightened against the nut.
label |  |  | note | Standard / Specification - PS 19.18.2
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Bolt
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.05 Underpass and Wingwall Backfill
checkpoint-status |  |  | checkpoint | 12.05.01 - Polythene Sheet above Underpass
label |  |  | note | Acceptance / Conformance Criteria - Two layers of polythene sheet shall be placed across the full width and length of all underpass precast concrete units. The polythene sheet shall have a nominal thickness of 0.25mm and comply with the requirements of the New Zealand Building Code.
label |  |  | note | ○ Polythene sheet shall be lapped by a minimum of 150mm at all joints.
label |  |  | note | Standard / Specification - PS 19.19.1
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Sheet
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.05.02 - Minimum cover over Underpass
label |  |  | note | Acceptance / Conformance Criteria - The minimum cover to the underpass within all traffic lanes is to be 600mm to the top of the pavement.
label |  |  | note | Standard / Specification - PS 19.19.1
label |  |  | note | Verifying Document - Survey Records
label |  |  | note | Frequency - During Backfilling
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SV
checkpoint-status |  |  | checkpoint | 12.05.03 - AP40 Backfill alongside Underpass
label |  |  | note | Acceptance / Conformance Criteria - Fill shall be spread in horizontal layers not exceeding 200mm loose depth. Backfill shall be compacted in accordance with TNZ B/2. The maximum lift thickness shall be 200mm. Backfill shall be carried out in unison on both sides of the box underpass such that the level of backfill on one side is not more than 500mm different from the other side, at all times. and testing shall be completed on each lift.
label |  |  | note | Standard / Specification - PS 19.19.2
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each lift
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.05.04 - AP40 Backfill Compaction Testing
label |  |  | note | Acceptance / Conformance Criteria - Clegg testing shall be carried out and recorded for each lift (200mm Maximum) to be carried out once per 10m length of the 300mm wide AP40 strip. A CIV value of 40 shall be achieved for each test.
label |  |  | note | Standard / Specification - PS 19.19.2
label |  |  | note | Verifying Document - Clegg Results
label |  |  | note | Frequency - Each lift to be carried out once per 10m length of the 300mm wide AP40 strip
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.05.05 - Polythene sheet at Culvert
label |  |  | note | Acceptance / Conformance Criteria - The polythene sheet between the precast culvert and the structural fill, or site concrete layer. The polyethene sheet shall be a single continuous sheet with no joins. The sheet is to be laid flat with folds or wrinkles prior to the placement of material on top.
label |  |  | note | Standard / Specification - PS 19.20.2
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Culvert Entrance
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.06 Joint Sealing and Waterproofing
checkpoint-status |  |  | checkpoint | 12.06.01 - Preparation
label |  |  | note | Acceptance / Conformance Criteria - The joints surfaces should be accurately formed and must be thoroughly dry, clean, and free from frost. Remove all laitance, curing compounds, form release agents, loose material, and any contaminating foreign matter from joint faces by grinding, grit blasting or wire brushing. The prepared sealing slot should be blown out with dry, oil-free compressed air. The sealant may be applied in joints up to a maximum of 30mm wide. All moving joints should be designed to an optimal width to depth ratio of 2:1, with a minimum joint size of 12mm sealant depth.
label |  |  | note | Standard / Specification - PS 19.22.2
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Joint
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.06.02 - Movement joints
label |  |  | note | Acceptance / Conformance Criteria - In movement joints, the sealant must not be allowed to bond to the back face of the joint.
label |  |  | note | Standard / Specification - PS 19.22.3
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Joint
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.06.03 - Concrete Age
label |  |  | note | Acceptance / Conformance Criteria - New concrete must be allowed to cure for a minimum of 28 days before sealant installation.
label |  |  | note | Standard / Specification - PS 19.22.4
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - 28 days post pouring
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.07 Supply and Install of Non-slip Coating
checkpoint-status |  |  | checkpoint | 12.07.01 - Install of Non-slip Coating
label |  |  | note | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150 applied after the installation of the box culvert segments. The thickness of this is to be between 3 and 5mm. The application of the product must be done in accordance with the manufacturer’s specifications.
label |  |  | note | Standard / Specification - PS 19.23.2
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Underpass
label |  |  | note | Verification Activity: Activity - I
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.08 Anti-Graffiti Finish
checkpoint-status |  |  | checkpoint | 12.08.01 - Anti-Graffiti Application
label |  |  | note | Acceptance / Conformance Criteria - The anti-graffiti coatings shall be applied and maintained in accordance with the manufacturer's requirements.
label |  |  | note | Standard / Specification - PS 19.24.3
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Application
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.08.02 - Anti-Graffiti Label Application
label |  |  | note | Acceptance / Conformance Criteria - A self-adhesive label shall indicate all areas of anti-graffiti coatings on site.
label |  |  | note | Standard / Specification - PS 19.24.4
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Structure
label |  |  | note | Verification Activity: Activity - R
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.09 Steelwork Fabrication and Installation
checkpoint-status |  |  | checkpoint | 12.09.01 - Welding
label |  |  | note | Acceptance / Conformance Criteria - Welding shall comply with AS/NZS 5131, Section 7.
label |  |  | note | Standard / Specification - PS 19.26.8
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Weld
label |  |  | note | Verification Activity: Activity - S
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.09.02 - Holing
label |  |  | note | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131, Section 6.7.
label |  |  | note | Standard / Specification - PS 19.26.9
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Hole
label |  |  | note | Verification Activity: Activity - S
label |  |  | note | Verification Activity: By - SE
checkpoint-status |  |  | checkpoint | 12.09.03 - Installation
label |  |  | note | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131
label |  |  | note | Standard / Specification - PS 19.26
label |  |  | note | Verifying Document - Site Records
label |  |  | note | Frequency - Each Item
label |  |  | note | Verification Activity: Activity - S
label |  |  | note | Verification Activity: By - SE
checkpoint-group |  |  | section | 12.10 uPVC Pipe
checkpoint-status |  |  | checkpoint | 12.10.01 - Plastic Pipe Trench Backfill
label |  |  | note | Acceptance / Conformance Criteria - Plastic Pipe Trench Backfill
label |  |  | note | Standard / Specification - Except as shown otherwise on the drawings, or directed otherwise by the Engineer, support material shall be as per AS/NZS 2566.2.2002 “Buried flexible pipelines – installation” corresponding to the relevant pipe support type as detailed. All materials in bedding zones, side zones and haunching zones shall comply with the grading specification in the aforementioned AS/NZS 2566.2.2002.
label |  |  | note | Verifying Document - PS 19.27.4