## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-170-CIV-BRUNT-Concrete Pavement Construction Rev 0 | itp |  |  |  |  | ITP-170-CIV-BRUNT-Concrete Pavement Construction Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-170-CIV-BRUNT-Concrete Pavement Construction
label | ITP Description: Concrete Pavement Construction
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 28/05/2024
label | ITP created by: Jon De Castro
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 304 August 2013
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 703 April 2019
checkpoint | 1.3 - Non Dependent
label | Reference - Council EDCM 401
checkpoint | 1.4 - Non Dependent
label | Reference - Council EDCM 501
checkpoint | 1.5 - Non Dependent
label | Reference - Council EDCM 502
checkpoint | 1.6 - Non Dependent
label | Reference - Council EDCM 503
checkpoint | 1.7 - Non Dependent
label | Reference - AS 1379-2007
checkpoint | 1.8 - Non Dependent
label | Reference - VicRoads Section 812 July 2016
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Bedding Material Placement & Compaction
label | Reference - IFC Drawings: 812.04, 703.21
label | Acceptance Criteria - Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
label | ○ SUP: SIZE 20mm CLASS 3 CRUSHED ROCK
label | ○ Driveways PT-08 and PT-08A: SIZE 20mm CLASS 3 CRUSHED ROCK
label | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Concrete Mix
label | Reference - IFC Drawings: 703.05 (a), 703.07
label | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | – Footpaths: 25Mpa
label | – SUP: VR330/32
label | – Driveway PT-08: 25MPa
label | – Driveway PT-08A: 25MPa
label | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Reinforcement
label | Reference - IFC Drawings: 703.16
label | Acceptance Criteria - Reinforcement shall comply with AS4671.
label | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | Following steel mesh requirements shall apply as per IFC Drawings:
label | – Driveway PT-08: SL72 Continously Lapped
label | – Driveway PT-08A: SL82 Contniously Lapped
label | – Footpaths, Residential driveways and Median islands infills: SL72
label | – Industrial Crossovers: SL82
label | – Traffic Islands: SL72
label | – SUP: SL82
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Evaporative Retardant
label | Reference - 703.09, 610.17 (f)
label | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Curing Compound
label | Reference - 703.10 (a), 610.23 (d)
label | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Documents
checkpoint | 3.1 - Survey Set-out
label | Reference - IFC Drawings 703.17
label | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | ○ The Nominated Authority will review and confirm the set out.
label | Attach: Survey Report
label | Method - Document Review, Measure, Visual
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/PE, Surveyor
label | Verifying Documents - This ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Lot Map
label | Reference - MRPA Lot Management Plan
label | Acceptance Criteria - Attach Marked drawing indicating the location of this Lot
label | Attach: Lot Map
label | Method - Document
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Site Clearing & Grubbing
label | Reference - IFC Drawings
label | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 4.2 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that all employee and sub contractors are:
label | – Using the correct and complete set of drawings
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
section | 5. Construction Activities
checkpoint | 5.1 - Excavation
label | Reference - 703.20 IFC Drawings
label | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | Method - Visual, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
label | Reference - IFC Drawings: Relevant Council Drawings
label | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | Method - Visual, Measure
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.3 - Bedding Material Placement & Compaction
label | Reference - 703.21 IFC Drawings
label | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
label | ○ Footpath: 100mm compacted thickness
label | ○ SUP: 150 mm compacted thickness
label | ○ PAVEMENT TYPE PT08: DRIVEWAY (IN ACCORDANCE WITH EDCM 502): 50mm compacted thickness
label | ○ PAVEMENT TYPE PT08A: COMMERCIAL DRIVEWAY (IN ACCORDANCE WITH EDCM 503): 100mm compacted thickness
label | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | Attach: Bedding Material Delivery Dockets
label | Method - Visual, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.4 - Compaction Testing
label | Reference - 703.21, 304.08 (a) & (b), 304.11 (a)
label | Acceptance Criteria - Compaction shall meet the following requirements:
label | ○ Scale of Surface Level Measurement = Scale C
label | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
label | Attach: Moisture Content Test Results
label | Attach: Mean Value of Density Ratio
label | Method - Document Review, Visual
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.5 - Proof-rolling
label | Reference - 703.21, 304.08 (b)
label | Acceptance Criteria - Bedding material to be compacted and proof rolled before any construction.
label | ○ Withstands Test rolling without visible deformation or springing.
label | Method - Visual
label | Frequency - Where applicable, each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Formwork Construction & Placement
label | Reference - IFC Drawings 703.12
label | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | Method - Visual, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.7 - Construction Joints & Matching Existing Surfaces
label | Reference - IFC Drawings 703.24, Relevant Council Standard DrawingsRelevant Council drawings:
label | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | Consult the relevant Council Standard drawings for the joint detail, these may require:
label | i. Concrete cutting of a shear-key
label | ii. Surface roughening
label | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | iv. Cutting a groove for sealant
label | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | ○ Transitions between different profiles shall be made in accordance with the drawings.
label | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | Method - Visual, Measure
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.8 - Isolation Joints
label | Reference - IFC Drawings 703.26 (c), Relevant Council Standard Drawings
label | Acceptance Criteria - Where applicable, isolation joints shall be placed:
label | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | ii. at any location marked on the drawings
label | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | Method - Visual, Measure
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.9 - Expansion Joints
label | Reference - IFC Drawings 703.26 (a) (ii) & (b) (i), Relevant Council Standard Drawings
label | Acceptance Criteria - Where applicable, expansion joints shall be placed:
label | i. on either side of vehicle crossings
label | ii. at junctions with existing footpaths and shared use paths
label | iii. at junctions with bridges
label | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | Method - Visual, Measure
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.10 - Reinforcement Placement
label | Reference - IFC Drawings 703.13
label | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
label | – Footpaths, Residential driveways and Median islands infills: SL72
label | – Industrial Crossovers: SL82
label | – Traffic Islands: SL72
label | – SUP: SL82
label | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | ○ Any splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.11 - Pre-pour Survey
label | Reference - IFC Drawings 703.15
label | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | Erected formwork and base layer within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from alignment = ±10mm
label | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
label | ○ Irregularities in alignment = 5mm in 3m
label | ○ Section dimensions = ±5mm
label | ○ Section dimensions (less than 25mm) = ±3mm
label | ○ Width of pavement = -5mm, +15mm
label | Attach: Survey Report
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.12 - Pre-pour Inspection
label | Reference - Section 703.09, Section 703.21 Section 610.17a), b) & c)
label | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.13 - Weather Conditions & Evaporation Limits
label | Reference - 703.09, 610.17 (a - f) Table 610.171
label | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | Record: Required information on the Concrete Pour Record.
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.14 - Concrete Testing - Sampling Frequencies-Footpath
label | Reference - 703.11, AS 1379-2007 Cluse 6.2
label | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | ○ Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.15 - Concrete Testing - Sampling Frequencies
label | Reference - 703.11, 610.16 (b)
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | Shared User Path:
label | – 0m³ to 10m³ = 1 sample
label | – 10m³ to 25m³ = 2 samples
label | – 25m³ to 50m³ = 3 samples
label | – 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Footpaths:
label | – 0m³ to 50m³ = 1 sample
label | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 2 no. 28 day strength.
label | ○ Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.16 - Concrete Testing - Slump
label | Reference - 703.11, 610.16 (c)
label | Acceptance Criteria - Slump testing tolerances =
label | ○ <60mm = ±10mm
label | ○ ≥60mm to ≤80mm = ±15mm
label | ○ >80mm to ≤110mm = ±20mm
label | ○ >110mm to ≤150mm = ±30mm
label | ○ >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample
label | Category - IP
label | Responsibility - Concrete Tester
label | Verifying Documents - This ITP
checkpoint | 5.17 - Placement & Compaction
label | Reference - 703.08
label | Acceptance Criteria - All concrete batches are traceable.
label | Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | Record: Required information on the Concrete Pour Record.
label | Attach: Concrete Pour Record
label | Attach: Concrete Dockets
label | Method - Visual
label | Frequency - Each load
label | Category - SP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.18 - Surface Finishes
label | Reference - IFC Drawings, Relevant Council Drawings 703.25
label | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.19 - Footpaths - Crack-control Joints / Weaken Plane Joints
label | Reference - IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
label | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | Method - Visual
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.2 - Curing
label | Reference - 703.1
label | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
section | 6. Post-construction Activities
checkpoint | 6.1 - Crack-control Joints / Weaken Plane Joints
label | Reference - IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
label | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | ○ <20°C = within 24 hours of finishing operations
label | ○ ≥20°C - 35°C = within 4 hours of finishing operations
label | Method - Visual
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 6.2 - Protection of Newly Poured Concrete
label | Reference - 703.27
label | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | Method - Visual
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 6.3 - Stripping Formwork
label | Reference - 703.12 AS3610 Table C2
label | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | i. 2 days for vertical formwork on external surfaces; and
label | ii. 1 day for vertical forms on permanently hidden surfaces
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 6.4 - Backfilling & Pavement Restoration
label | Reference - 703.29
label | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | Method - Visual, Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 6.5 - Surface Inspection - Cracks
label | Reference - 703.3
label | Acceptance Criteria - No cracks greater than 0.2mm.
label | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | Method - Visual, Measure
label | Frequency - Where applicable, each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 6.6 - Surface Inspection - Surface Finish
label | Reference - IFC Drawings, Relevant Council Drawings 703.25, 703.10 (a) AS3610 Clause 3.2
label | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
label | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | Class of finish:
label | – Permanently hidden surfaces = Class 4
label | – All other surfaces = Class 3
label | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP
checklist | ITP-172-CIV-BRUNT-Landscaping - Ground Preparation & Planting Rev 0 | itp |  |  |  |  | ITP-172-CIV-BRUNT-Landscaping - Ground Preparation & Planting Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-172-CIV-BRUNT-Landscaping-Ground Preparation & Planting
label | ITP Description: Landscaping-Ground Preparation & Planting
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 1
label | Revision Date: 28/05/2024
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads 720
checkpoint | 1.2 - Non Dependent
label | Reference - AS 4454
checkpoint | 1.3 - Non Dependent
label | Reference - AS 4419
checkpoint | 1.4 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Submission and records
label | Reference - Section 720.03
label | Acceptance Criteria - Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
label | Following information shall be provided to the NA:
label | Samples
label | – Mulch
label | – Imported topsoil
label | Records
label | – Details of suppliers
label | – Soil tests on imported topsoil
label | – Copies/Photos of fertiliser labels
label | Attach: Records and Certs as Hold Point onto TeamBinder and write the Reference No.
label | Method - Document Review
label | Frequency - Prior to Commencement of works
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Supply of topsoil
label | Reference - Section 720.04, Table 720.042 IFC Drawings
label | Acceptance Criteria - Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
label | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings.
label | Attach: Material Conformance Docs / Test Reports as Material Approval onto TeamBinder and write the Reference No.
label | Method - Verify, Doc. Review if applicable
label | Frequency - Prior to Commencement of works
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Supply of Mulch
label | Reference - Section 720.04, Table 720.044, AS4454 IFC Drawings
label | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
label | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
label | ○ Imported Wood Mulch shall comply with Table 720.044.
label | Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
label | Method - Verify, Doc. Review if applicable
label | Frequency - Prior to Commencement of works
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Supply of Plant
label | Reference - Section 720.041
label | Acceptance Criteria - All Plants have been inspected and comply with Sec 720.041
label | Attach: Landscape Architect Approval
label | Method - Verify
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Supply of grass seed
label | Reference - VicRoads Spec.
label | – Cl.720.04
label | – Table 720.045
label | Acceptance Criteria - Grass seed shall comply with Table 720.045
label | Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
label | Method - Verify
label | Frequency - Prior to Commencing works
label | Category - HP
label | Responsibility - NA
label | Verifying Documents - ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - Check for correct documentation
label | Reference - Drawings and drawing registers
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – Using the correct and complete set of IFC drawings
label | – All drawings are the latest revision
label | Method - Document Review
label | Frequency - Prior to Commencement of works
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - ITP Signed Off
checkpoint | 3.2 - Subcontractor ITP
label | Reference - Subcontractor ITP
label | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
label | Method - Document Review
label | Frequency - Each Lot
label | Category - WP
label | Responsibility - SE/PE
label | Verifying Documents - ITP Signed Off
section | 4. Ground Preparation
checkpoint | 4.1 - Soil Additives
label | Reference - Section 720.07 a) AS 4419
label | Acceptance Criteria - Refer to Subcontractor ITP
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Sign ITP, Attach Test Report, Attached Delivery Docket (if applicable)
checkpoint | 4.2 - Ripping of subsoil
label | Reference - Section 720.07 Table 720.071
label | Acceptance Criteria - Rip Subsoil to min 250mm at 500mm spacing
label | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - HP
label | Responsibility - SE/NA
label | Verifying Documents - Sign ITP, Attach Lot Map/Marked Up Area Inspected
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Topsoil application
label | Reference - Section 720.07
label | Acceptance Criteria - Topsoil to be installed at 150mm depth with no air pockets, weeds, rocks, and other debris. Finish surface should be smooth and uniform
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Subcontractor ITP
checkpoint | 4.4 - Mulching
label | Reference - Section 720.08 a) IFC Drawings
label | Acceptance Criteria - Mulch to be installed at 100mm and to finish 50mm below pavement.
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
checkpoint | 4.5 - Weed and Erosion Control Mat
label | Reference - Section 720.04 i) IFC Drawings
label | Acceptance Criteria - Refer to Subcontractor ITP
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
checkpoint | 4.6 - Jute Matting Installation
label | Reference - Section 720.071 IFC Drawings
label | Acceptance Criteria - Pre-slit Jute Matt installed as per specification
label | ○ Lay Matting into a trench of min 150mm wide and depth, pin and backfill
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
section | 5. Planting
checkpoint | 5.1 - Plant Installation
label | Reference - Section 720.041 IFC Drawings
label | Acceptance Criteria - Plants to be removed from Pot and Roots Tickled
label | ○ Ensure Mulch does not overly cover stem of plant
label | ○ Ensure plants to be watered within the same day
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE, Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
checkpoint | 5.2 - Fertiliser Application
label | Reference - Section 720.041 IFC Drawings
label | Acceptance Criteria - Tubestock: 10gms (approx. 1 teaspoon) of fertiliser been added to base of plant
label | ○ 15-30cm Pots: 40gms (approx. 4 teaspoons) of fertiliser been added to base of plant
label | ○ 45L Trees: 80gms (approx. 8 teaspoons) of fertiliser been added to top of root ball
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE, Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
checkpoint | 5.3 - Tree Installation
label | Reference - Section 720.041 IFC Drawings
label | Acceptance Criteria - Installation on Grade:
label | – Hole to be 100mm deeper and 600mm wider than pot size
label | – Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
label | Installation on Garden Beds/Turf:
label | – Tree Pit Inspected and Minimum 3 times the root ball width
label | – Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE, Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
checkpoint | 5.4 - Soil Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - 75mm depth topsoil & 100mm min in swales consolidated as approved
label | Method - Verify
label | Frequency - Each Applicable Lot
label | Category - IP
label | Responsibility - SE, Site Supervisor
label | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
section | 6. Post Construction
checkpoint | 6.1 - NCR Closeout
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot/element/Work Area that this ITP covers, have been closed
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot/element/work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP
checklist | ITP-175-STR-BRUNT-Cast In-Situ Stairs Rev 0 | itp |  |  |  |  | ITP-175-STR-BRUNT-Cast In-Situ Stairs Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-175-STR-BRUNT-Misc Structures Cast In-Situ Stairs
label | ITP Description: Cast In-Situ Stairs
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 27/05/2024
label | ITP created by: Derek Collins
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 602 October 2007
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 610 February 2020
checkpoint | 1.3 - Non Dependent
label | Reference - VicRoads Section 611 November 2018
checkpoint | 1.4 - Non Dependent
label | Reference - VicRoads Section 614 June 2017
checkpoint | 1.5 - Non Dependent
label | Reference - AS3810.1 2018
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Concrete Mix
label | Reference - 610.07 Table 610.071 IFC Drawings
label | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | Reference - 611.05 (a)
label | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Hold Point Ref Number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days of award of contract
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | Reference - 610.26 (a)
label | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | ○ Concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12%. Bar chairs and spacers made of wood, metal, plastic coated metal and site made concrete shall not be used.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Hold Point Ref Number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Evaporative Retardant
label | Reference - 610.17 (f)
label | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Hold Point Ref Number
label | Method - Document Review
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Curing Compound
label | Reference - 610.23 (d)
label | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Hold Point Ref Number
label | Method - Document Review
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | Reference - 610.18
label | Acceptance Criteria - Concrete placement and compaction to be in accordance with Section 610.18.
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | Reference - 610.16
label | Acceptance Criteria - Concrete sampling and testing to be in accordance with Section 610.16.
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 3.3 - Hot and/or Cold Weather Concreting Procedure
label | Reference - 610.17
label | Acceptance Criteria - Hot and/or cold weather concreting to be in accordance with Section 610.17.
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 3.4 - Curing Methodology (for Concrete and Grout)
label | Reference - 610.23
label | Acceptance Criteria - Curing methodology and procedure to be in accordance with Section 610.23.
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 3.5 - Concrete Drilling Procedure
label | Reference - 610.46
label | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. Refer to Section 610.46
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
section | 4. Pre-construction Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.2 - Survey Set-out
label | Reference - IFC Drawings 610.47 (a) Table 610.472
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.3 - Concrete Blinding
label | Reference - IFC Drawings
label | Acceptance Criteria - Blinding concrete shall be in accordance to IFC Drawings.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Formwork Design and Construction
label | Reference - IFC Drawings 614.04, 614.05, 614.06
label | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | Attach: Temp Works Design, Proof Engineer Approval
label | Method - Document Review, Visual, Measure
label | Frequency - Each type of element
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | Reference - 614.08
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | Attach: Temp Works Design, Proof Engineer Approval
label | Method - Document Review, Visual, Measure
label | Frequency - Each element (where greater than 2m)
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | Reference - 614.08
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | Method - Document Review, Visual, Measure
label | Frequency - Each element (where 2m or less)
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Pre-pour Survey
label | Reference - 610.47 (a) Table 610.472
label | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - HP*
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Reinforcement Placement
label | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.6 - Cast-in Items
label | Reference - IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
label | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | Method - Measure, Visual
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.7 - Pre-pour Inspection
label | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ○ All foreign material has been completely removed from the forms.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Weather Conditions & Evaporation Limits
label | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | Record: Required information on the Concrete Pour Record.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.9 - Concrete Testing - Sampling Frequency
label | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | – 0m³ to 10m³ = 1 sample
label | – 10m³ to 25m³ = 2 samples
label | – 25m³ to 50m³ = 3 samples
label | – 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each element
label | Category - IP
label | Responsibility - Concrete Tester, Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.10 - Concrete Testing - Slump
label | Reference - 610.16 (c)
label | Acceptance Criteria - Slump testing tolerances =
label | ○ <60mm = ±10mm
label | ○ ≥60mm to ≤80mm = ±15mm
label | ○ >80mm to ≤110mm = ±20mm
label | ○ >110mm to ≤150mm = ±30mm
label | ○ >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample of Standard or Superplasticised Concrete
label | Category - IP
label | Responsibility - Concrete Tester, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
label | Reference - Site Sampling & Testing Procedure
label | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample
label | Category - IP
label | Responsibility - Concrete Tester, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.12 - Placement & Compaction
label | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | Acceptance Criteria - All concrete batches are traceable.
label | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ Concrete is not dropped freely from a height exceeding 2m.
label | ○ Concrete is not moved horizontally by use of vibrators.
label | ○ Adequate compaction is ensured
label | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | ○ Concrete layers are not more than 350mm
label | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | Record: Required information on the Concrete Pour Record.
label | Attach: Concrete Pour Record
label | Attach: Concrete Dockets
label | Method - Visual
label | Frequency - Each load
label | Category - SP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.13 - Surface Finishes
label | Reference - IFC Drawings 610.31, 610.20
label | Acceptance Criteria - Surface finish as per IFC drawings.
label | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.14 - Curing after formwork removal
label | Reference - IFC Drawings
label | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Early Age Compressive Strength Test Results - Removal of Formwork
label | Reference - IFC Drawings
label | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | Method - Document Review
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - Foreman, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Surface Inspection - Cracks
label | Reference - 610.24
label | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | Method - Visual, Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.3 - Surface Inspection - Surface Finish
label | Reference - IFC Drawings 610.31 (a) - (n), 610.32
label | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.4 - Measurement of Concrete Cover
label | Reference - 610.34
label | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | ○ Minimum 10 no. measurements recorded in each area.
label | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | Attach: Covermeter Check Record
label | Method - Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.5 - Compressive Strength Test Results
label | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each cylinder
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.6 - As-built Survey
label | Reference - IFC Drawings 610.47 Table 610.472
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.7 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP
checklist | ITP-176-CIV-BRUNT-Line Marking Rev 0 | itp |  |  |  |  | ITP-176-CIV-BRUNT-Line Marking Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-176-CIV-BRUNT-Line Marking
label | ITP Description: Line Marking
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 27/05/2024
label | ITP created by: Jon De Castro
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - VR Section 721
checkpoint | 1.2 - Non Dependent
label | Reference - VR Section 175
checkpoint | 1.3 - Non Dependent
label | Reference - VR Section 853
checkpoint | 1.4 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Type of marking material as shown on design drawings and shall conform to the Standard
label | Reference - Vicroads 721.A05
label | Acceptance Criteria - Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
label | ○ Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
textbox | Enter: TeamBInder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Per Material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Raised Pavement Markers
label | Reference - Vicroads 721.A05
label | Acceptance Criteria - Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175.
label | (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material.
textbox | Enter: TeamBInder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Per Material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Adhesive
label | Reference - Vicroads 721.A05
label | Acceptance Criteria - Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
label | ○ Other types of adhesive materials shall only be used with the approval of the Superintendent
textbox | Enter: TeamBInder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Per Material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Line marking and Road marking Paint
label | Reference - Vicroads 721.A05
label | Acceptance Criteria - All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
textbox | Enter: TeamBInder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Per Material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Glass beads
label | Reference - Vicroads 721.A05
label | Acceptance Criteria - Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
textbox | Enter: TeamBInder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Per Material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Pristine glass beads (Type B-HR)
label | Reference - Vicroads 721.A05
label | Acceptance Criteria - Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | ○ Pristine glass beads (Type B-HR)
label | ○ Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M
textbox | Enter: TeamBInder Material Approval Ref No.
label | Method - Document Review
label | Frequency - Per Material
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Accreditation to Painting Contractors Certification Program
label | Reference - Vicroads 721.D01
label | Acceptance Criteria - Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
label | Attach: PCCP Accreditation
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Surface preparation
label | Reference - Vicroads 721.A06, Vicroads 721.A09
label | Acceptance Criteria - The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | ○ The area around making area is also clean to avoid tracking into the marking area
label | ○ Removal of existing unsound, obsolete or redundant pavement markings
label | ○ Removal of any foreign materials and debris within reasonable limits.
label | Method - Measure, Visual, Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.2 - Redundant pavement / unsuitable marking markers removal
label | Reference - Vicroads 721.A12, Vicroads 721.A06, Vicroads 721.A08
label | Acceptance Criteria - Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.3 - Set out the works for installation of pavement markings / raised markers
label | Reference - Vicroads 721.B05
label | Acceptance Criteria - Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | Method - Survey, Document Review
label | Frequency - Per Lot
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Application of pavement marking / markers
label | Reference - Vicroads 721
label | Acceptance Criteria - Check conditions for application of marking paint & materials.
label | (i) Paints and markers installed as per manufacturer’s recommendations.
label | (ii) The same materials used with those nominated in the certifications.
label | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
label | (iv) Verify markings are straight or with smooth, even curves where intended.
label | (v) Edges are clean sharp cut off.
label | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
label | (viii) Markings are neat & free from traffic damage or other defects
label | (ix) Marking protected from traffic until hardened
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Tolerances for new marking/marker installations
label | Reference - Vicroads 721.A10 Table 721.A101
label | Acceptance Criteria - Pavement marking:
label | ○ Distance between the centreline of the marking and the centreline of the set out mark-<30 mm
label | ○ Distance between the centreline of the completed marking and the centreline of the previous marking-<15 mm
label | ○ Width of completed painted markings-±10 mm of the specified dimensions
label | ○ Width of completed markings for long life materials0 mm to +10 mm
label | ○ Length of completed stripes and blocks-0% to +10% of the specified length
label | ○ Gap between double lines--10 mm to +0 mm of the required 100 mm gap
label | Raised Pavement Markers:
label | (i) Markers in line with broken segments
label | – Transverse position-±25 mm of the centreline of segments
label | – Longitudinal position-±0.5 m of the specified position
label | (ii) Markers in a longitudinal group
label | – Transverse position-±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | – Longitudinal position-±0.5 m
label | – Spacing of markers within the group-50 mm of specified spacing
label | (iii) Markers adjacent to an unbroken line
label | – Clearance to edge line-±5 mm of the specified dimensions
label | – Longitudinal mismatch between markers in transverse pairs-<25 mm
label | – Longitudinal position-Lesser of: 0.5 m or 10%
label | (iv) Orientation of reflective markers-Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
label | – Thermoplastic profiled lines
label | (i) Tolerances on dimension
label | – Line width-+20 mm, -5 mm
label | – Line height-+2 mm, -0 mm
label | – Extrusion breadth-+10 mm, -0 mm
label | – Extrusion spacing-±15 mm
label | – Extrusion shape-±25 mm at any point from rectangular shape
label | (ii) Tolerances on position
label | – Distance between the centreline of the marking and the centreline of the set out-<30 mm
label | – Length of the completed lines--0% to +5% of the specified length
label | – Longitudinal position of individual extrusions-±50 mm of any previously applied profiled lining
label | Method - Visual /Site Inspection & Document Review
label | Frequency - Per Lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Retroreflectivity Report
label | Reference - Vicroads 721.B06 (b)
label | Acceptance Criteria - Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
label | Method - Document Review
label | Frequency - Per lot
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Job Completion Report
label | Reference - Vicroads 721.B06 (a)
label | Acceptance Criteria - For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings).
label | Method - Document review
label | Frequency - Per lot When applicable
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP