## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-152-STR-SSB-Post and Panel Retaining Walls-Precast Panels installation
ITP Description: |  | SSB-Post and Panel Retaining Walls-Precast Panels installation
Discipline (e.g. CIV/STR/RAIL: |  | 152-STR
Revision Number: |  | 0
Revision Date: |  | 2024-05-28
ITP created by: |  | VM
ITP approved for use by: |  | VM
Special Notes to ConQA Team : |  | ITP for Station Street
Inspection & Test Plan -Post and Panel Retaining Walls - Precast Panel installation
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-05-28
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 610 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 620 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VicRoads Section 606 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materils
2.1 | Precast Elements | IFC Drawings 610.46 (a), Table 610.463 610.47 (a) Table 610.473 | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.473 Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) | Document Review | Each element | IP | PE/SE/SPE | This ITP
2.2 | Grout | MRPA Quality Management Plan | Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP | Nominated Authority | This ITP
3 | Preliminaries-Procedures
3.2 | Materials Inspection Checklist | 620.06 620.07 MRPA Quality Management Plan | General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable). Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
4 | Pre-installation Activities
4.1 | Survey Set-out | IFC Drawings VR 606.08 | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances. Survey Activities to ensure bearing plates are in correct level Where steel posts are cast in to the concrete, ensure that these are within tolerance. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5 | Installation Activities
4.2 | Bearing Shims or Bearing Strip Placement | IFC Drawings | Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances. Gap between the panels and top of piles shall accommodate for the grout depth as specified in IFC Drawing | Measure Visual | Where applicable, each installation location | IP | Surveyor SE/PE | This ITP
| Elastomeric rubber - Face of the Panel | IFC Drawing | 15x50mm elastomeric rubber is installed to to the steel post (Epoxy adhesive) | Visual | Each Panel | IP | SE | This ITP
5.1 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | IP | SE/PE | This ITP
5.2 | Precast Placement | IFC Drawings Temporary Works Design 610.27 | Precast elements shall be placed into location or and not released from the crane until sufficiently braced, wedged or restrained by bolted connection, in accordance with the approved Temporary Works Design and/or IFC drawings. Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance. The nominal gap between elements is as per the IFC Drawings. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP
| Plastic Packer - Back of the panel | IFC Drawings | Continuous Plastic packer or equivalent is installed to ensure panel is firm against the face of the flange. | Visual | Each Panel | IP | SE | This ITP
5.4 | Drainage | IFC Drawings | Dranage shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists. Drainage is to be installed as per manufacturers instruction. Slotted pipe wrapped in geotextile installed to drain to the low point. | Measure Visual | Where applicable, each installation location | IP | Foreman SE/PE | This ITP
5.6 | Precast Traceability | 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report ATTACH: Lot Map | Visual | Each element | IP | SE/PE/SPE | This ITP
6 | Post-installation Activities
6.1 | Joint Sealant Application | IFC Drawings | The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod. | Visual | Where applicable, each element | IP | Surveyor SE/PE/SPE | This ITP
4.2 | Bearing Shims-Packing Grout | IFC Drawings | Gap Between Panels and top of piles shall be filled with Packing Grout. Packing Grout Depth shall be according to IFC Drawings | Visual | Where applicable, each installation location | IP | Surveyor SE/PE | This ITP
6.4 | As-built Survey | IFC Drawings | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.5 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /