## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-151-STR-SSB-Shotcrete | itp |  |  |  | Yes | ITP-151-STR-SSB-Shotcrete Rev 0 | 0f0cb2af-52dd-46db-8956-16f038533a20
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b58a43fa-499a-5f50-a996-541b6216375f |  | note | Document Title: ITP-151-STR-Shotcrete-SSB
label | 5b760dbd-361e-5e00-a0eb-505445322b45 |  | note | ITP Description: Shotcrete-SSB
label | 3decbe3a-d9d4-5ea5-aee8-0c7d628c2255 |  | note | Discipline (e.g. CIV/STR/RAIL): 151-STR
label | 1b364ea3-68d7-5eb2-9342-b683d0cd7be6 |  | note | Revision Number: 0
label | ce55b006-c87f-5d33-8074-edf83aa187f4 |  | note | Revision Date: 19/04/2024
label | a50c4f8e-c7fb-50ee-9780-28768d18905b |  | note | ITP created by: Mike Freeman
label | a37fc78d-dd8d-52ea-b3c5-f9359c56027a |  | note | ITP approved for use by: Mike Freeman
label | 7e5e99b7-b26b-56d6-8f7b-0c7c22e0c604 |  | note | 1.1 Non Dependent
label | 9c1ea9d8-ec35-57e0-9c2d-669a825e0eda |  | note | Reference: VicRoads Section 610 June 2019
label | ee6e7f01-0353-544e-933e-cb204d982209 |  | note | 1.2 Non Dependent
label | 89cfd349-5ccc-572e-a057-ee5ad65fcf5c |  | note | Reference: VicRoads Section 611 November 2018
label | 94e28892-1391-5503-9cba-b1c67fb51bda |  | note | 1.3 Non Dependent
label | b7cd0ba1-33b3-50c7-9b53-11df51bbb7e2 |  | note | Reference: VicRoads Section 684 April 2019
label | a0fa93fe-1c1b-5c7d-82c7-14704e47f6ad |  | note | 1.4 Non Dependent
label | ca560439-0c93-5b01-93b7-66d053b31bb1 |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 9df0f71d-8046-5a00-92cb-b783d2508836 |  | note | REFERENCE: 684.04 (a), 684.04 (d) (i & ii), 684.05 (a) (i & ii) Table 684.051, 684.05 (b) Table 684.052, 610.07 Table 610.071
label | 87b20736-7398-5125-ac26-29cd0d17e732 |  | note | – – – – – – – – – – – – – – – – –
label | 46d3809d-1a29-5d0a-bbda-2122932cd579 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | be43c41d-f982-5697-b194-d0ff6b124912 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
label | 9bb03520-64ef-5577-8f64-4443f8d09f25 |  | note | ○ Maximum drying shrinkage shall meet the values shown on table 684.052.
label | db39f867-2627-5a6f-9898-4d4e76938b78 |  | note | Where applicable, steel fibres shall:
label | 64166414-9463-5af8-89c3-04a8c06a5d5f |  | note | i. be deformed
label | 81cfab48-8931-5b9e-8327-faf429302fe8 |  | note | ii. have a minimum tensile strength of 800MPa
label | 9d7ee70d-30ce-5354-bc25-722bd2c6e4b7 |  | note | iii. have an aspect ratio between 40 and 70
label | e007839e-9a49-5ec7-bb70-3789f0d70fea |  | note | iv. have a minimum dosage rate as per table 684.051
text | 7d3fd1ab-160c-5f05-a713-a00d9137bc38 |  | textbox | Enter: Teambinder Material Approval number
label | e4a93f48-4ce9-5719-815f-642998044aa0 |  | note | – – – – – – – – – – – – – – – – –
label | 6f4f20ce-ddd2-5231-96d1-273393a05b80 |  | note | METHOD: Document Review
label | bf6a9b96-275e-51e3-bf10-e3b7eeffc1cb |  | note | – – – – – – – – – – – – – – – – –
label | 4580905d-6642-571d-980e-bd060d95b873 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 9aa5e8c9-f44b-59be-8a49-8bc1fa3aaedd |  | note | – – – – – – – – – – – – – – – – –
label | a6041449-204a-5bea-856d-7280a72c7d5b |  | note | CATEGORY: HP
label | ff69eea8-da32-58c9-8e7e-140a9675c07c |  | note | – – – – – – – – – – – – – – – – –
label | ea793249-e5f6-58b5-8717-df3ecf6c7e73 |  | note | RESPONSIBILITY: Nominated Authority
label | 439dd05a-f137-562c-b256-892d08fa511e |  | note | – – – – – – – – – – – – – – – – –
label | 72819043-16b6-5908-970d-cee8ada43673 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f9821b5a-ed0f-5ccd-af17-3b2848e93eb5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 6c7361d7-f267-526d-80c7-fe71812473e0 |  | note | REFERENCE: 684.04 (c), 611.05 (a)
label | bcccba9c-640c-5437-9ac2-dbd739017062 |  | note | – – – – – – – – – – – – – – – – –
label | 9e3e96bd-38f9-5bc6-879f-02adf7ea3d9e |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | e30dc0c6-b040-5c75-bb05-7c6ef4202c35 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | f015e0aa-3841-5844-9110-716855b3a4a4 |  | textbox | Enter: Teambinder Material Approval number
label | faa9c760-4bff-53d1-b51c-1dded6c93d54 |  | note | – – – – – – – – – – – – – – – – –
label | cf4aab33-89ed-59b5-a10e-627cf0787f1b |  | note | METHOD: Document Review
label | 33ea7257-61c9-5405-a766-f8390cd04887 |  | note | – – – – – – – – – – – – – – – – –
label | 1f665e0f-83e6-52c7-8885-e1421a0956d6 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 54c92f9e-4026-521b-a2c4-a3ecdc5625ad |  | note | – – – – – – – – – – – – – – – – –
label | edc0b383-fd84-5849-a3f2-0340352dfa2b |  | note | CATEGORY: WP
label | eb102c54-4635-5cbb-979c-9fc344f1c949 |  | note | – – – – – – – – – – – – – – – – –
label | f8ae51ec-b9b9-52ea-998d-1a2208969cfa |  | note | RESPONSIBILITY: Nominated Authority
label | e30dd8ff-b32e-5be1-9f1d-076fe0b2d303 |  | note | – – – – – – – – – – – – – – – – –
label | 39181bff-b650-563c-aa30-3afeca3194cb |  | note | VERIFYING DOCUMENTS: This ITP
date | a18df07c-1f9d-5bd7-9979-ce4b223d3af2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Galvanising (for Reinforcement)
label | c26fc4ad-d404-5621-92e0-c7162b97bee0 |  | note | REFERENCE: 684.04 (c)
label | b0502845-44b1-5553-a040-8008fa766284 |  | note | – – – – – – – – – – – – – – – – –
label | 692a01af-eaa8-52f6-98db-09154ad2ee85 |  | note | ACCEPTANCE CRITERIA: All reinforcement and tie wire used in the Works shall be hot-dipped galvanised in accordance with AS4680.
label | 9078cf65-01cd-5582-a3c5-0768d39aaf6a |  | note | Attach: Galvaniser's Certificate of Compliance
label | 392b448a-2bf8-59b5-9b92-5c768e8d8dd7 |  | note | – – – – – – – – – – – – – – – – –
label | 422938a1-e7af-515d-b945-958c0a503785 |  | note | METHOD: Document Review
label | c4cca00b-d969-5467-a712-98259e7b89fe |  | note | – – – – – – – – – – – – – – – – –
label | 54bd3a8b-b142-56bb-8dd1-5ad3deac4364 |  | note | FREQUENCY: For each reinforcement delivery from each galvaniser
label | ef2485db-67dd-57d0-9fb2-01d69a27b99a |  | note | – – – – – – – – – – – – – – – – –
label | 36da5664-8f06-5e19-a29a-3ddaedaabe6d |  | note | CATEGORY: WP
label | 1b14ad45-8804-509e-ab66-1b4ca59075c4 |  | note | – – – – – – – – – – – – – – – – –
label | be16d354-c7f2-5d6d-8c33-a99fe99e70d2 |  | note | RESPONSIBILITY: Nominated Authority
label | c4bc3b25-2917-58c6-ac7a-e4be144f59ba |  | note | – – – – – – – – – – – – – – – – –
label | ed21a64c-b5a5-536e-abd3-29c1217c646d |  | note | VERIFYING DOCUMENTS: This ITP
date | 8cfb987b-15d1-58e1-9ef1-49dff6c6f11b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Bar Chairs/Aspros Certification
label | 94fbad4f-536c-5cd5-85ce-8ebab61c9f21 |  | note | REFERENCE: 610.26 (a)
label | 6ef456d4-4424-594b-be48-009ce257ba82 |  | note | – – – – – – – – – – – – – – – – –
label | 4ba9dcb1-a834-5372-ba37-8dd915463c51 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 1fc1dfd5-c750-58a6-9c48-8e32c5fa9b75 |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | e727ca1f-7277-595d-b774-0c22fa3ef72e |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 34ceff72-fede-5a95-8a40-17057a7072ba |  | textbox | Enter: Teambinder Material Approval number
label | 39f8d090-e63b-51aa-b019-9d9cb6fc2423 |  | note | – – – – – – – – – – – – – – – – –
label | 5caa25e8-9721-5006-a294-895d391c4ff0 |  | note | METHOD: Document Review
label | 3a3d806b-35c5-5119-9ad0-344619967b2b |  | note | – – – – – – – – – – – – – – – – –
label | 8f0d7e97-40e0-53c2-94ef-5eb49c73a582 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 66fcbd2d-e724-5a53-82b1-774cb3b31e64 |  | note | – – – – – – – – – – – – – – – – –
label | 2192a39c-194f-5756-9e72-994e50e33c6c |  | note | CATEGORY: WP
label | cda16fe6-07c6-5141-98bf-44fcd7bc232c |  | note | – – – – – – – – – – – – – – – – –
label | 7aea55ed-c26a-56e8-b782-5ada61dd9397 |  | note | RESPONSIBILITY: Nominated Authority
label | 7defe3b0-5880-5983-ae94-5cbfe481f643 |  | note | – – – – – – – – – – – – – – – – –
label | f79da547-33ba-570b-b7ef-760ae8b80cd0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9d89de54-088c-54cc-a4ee-ba19e4a954f3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Evaporative Retardant
label | b87a7aca-7c83-575e-8fee-5d377cb7f283 |  | note | REFERENCE: 684.10 (b), 684.11, 610.17 (f)
label | 79eac654-1f18-5011-acae-dcd53feb5257 |  | note | – – – – – – – – – – – – – – – – –
label | 0fc65582-9f60-57be-8cd0-bb8c8d4edb3d |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 419cb2e5-4a37-5697-879b-ee9d78f21f0f |  | textbox | Enter: Teambinder Material Approval number
label | 0c47913a-58dc-5098-b2b1-db6b327978b2 |  | note | – – – – – – – – – – – – – – – – –
label | ab720aa5-2612-5e7e-b686-1fedc0d849ab |  | note | METHOD: Document Review
label | 7a729b26-f608-531c-a484-0ef520776956 |  | note | – – – – – – – – – – – – – – – – –
label | b5fee518-c224-5707-9dd7-4dd48467f13f |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | e13f1e0f-33e0-500c-8bfd-d756032b32df |  | note | – – – – – – – – – – – – – – – – –
label | a3500e6b-d04c-56a7-80f2-5d26e23cbbef |  | note | CATEGORY: WP
label | 1351d24d-a8a7-54f5-8654-2811982d5243 |  | note | – – – – – – – – – – – – – – – – –
label | 76cb9921-726f-5132-aee8-804649c04e90 |  | note | RESPONSIBILITY: Nominated Authority
label | c9115606-e21a-5dcf-9ea2-cfe265df9d79 |  | note | – – – – – – – – – – – – – – – – –
label | af3163ef-c946-5535-9ea3-aa7c72bc2ab6 |  | note | VERIFYING DOCUMENTS: This ITP
date | cb3de2ba-1b41-52a2-be5b-eb1bd510b7a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Curing Compound
label | ae6b96b8-fa54-5e36-b942-9b908547a15d |  | note | REFERENCE: 684.12, 610.23 (d)
label | 9df54dfe-8aa1-57de-a54d-5209e7bf7be3 |  | note | – – – – – – – – – – – – – – – – –
label | 83f95aba-70ac-5034-81dd-f511795c6f40 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | a7ae6c71-1498-5c03-9f83-2b334cf9c0c5 |  | textbox | Enter: Teambinder Material Approval number
label | a1b3988d-9842-5df3-8c87-5cbf7c37ff38 |  | note | – – – – – – – – – – – – – – – – –
label | 89ad8e0e-7c43-58ab-be47-d0ad34bf5f05 |  | note | METHOD: Document Review
label | 7c63f5ce-91c2-54c3-bbe6-346190adc2a5 |  | note | – – – – – – – – – – – – – – – – –
label | 82c2df8b-2c45-59eb-962e-96a5ae77ea18 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | f5dda133-75d0-52b9-9111-97ca24f8032a |  | note | – – – – – – – – – – – – – – – – –
label | 37616d08-6931-55fd-94e3-25b848400ff6 |  | note | CATEGORY: WP
label | 3a8fded5-8d49-5212-8442-e3726e80e842 |  | note | – – – – – – – – – – – – – – – – –
label | 6fc2d2e5-0eda-5b0f-9bd1-3922f95f5675 |  | note | RESPONSIBILITY: Nominated Authority
label | 963a71d7-3ea6-520a-acc7-7e32d21c7ff2 |  | note | – – – – – – – – – – – – – – – – –
label | 87619553-744c-5ae2-bfcf-cf2f07d40b02 |  | note | VERIFYING DOCUMENTS: This ITP
date | 424333e4-afa4-52bb-bc19-986fb8983647 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Shotcrete Work Method Statement
label | afe5f1a4-aaca-5f0d-92fc-88caafeb117c |  | note | REFERENCE: 684.07 (a), 684.07 (d) (i), 684.07 (d)
label | fd722161-8b63-5fa2-9f68-cfd6b4b64dd2 |  | note | – – – – – – – – – – – – – – – – –
label | 4cd92e7e-60cd-5898-9eb0-c5d8663d581d |  | note | ACCEPTANCE CRITERIA: Shotcrete WMS, detailing the proposed equipment and preparation works, to be submitted for review to the Nominated Authority.
label | fa40e011-a25d-5bd5-b0ee-8810c05b9d93 |  | note | ○ Any changes to the approved WMS shall be deemed a new Hold Point.
text | 738b78d6-7469-5ea5-a38e-54298a1999d1 |  | textbox | Enter: Teambinder Approval number
label | e69eb363-bf9a-5cf4-a807-e6766e1e30b5 |  | note | – – – – – – – – – – – – – – – – –
label | 08b79882-917e-5291-84a2-f348f7e14ccb |  | note | METHOD: Document Review
label | ac518f59-2de9-5136-92b5-dd682e9427fd |  | note | – – – – – – – – – – – – – – – – –
label | cdae47ed-3427-5685-8b04-a8216b56cc71 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 40433b88-b21d-5ac1-9248-e078292569d3 |  | note | – – – – – – – – – – – – – – – – –
label | 421dc724-1d7c-5459-aded-7257fca2705f |  | note | CATEGORY: HP
label | 3278f25c-fd93-56f3-b2e3-37870b78f32f |  | note | – – – – – – – – – – – – – – – – –
label | 1630297d-cfc7-55b5-9e04-a6d150c91d28 |  | note | RESPONSIBILITY: Nominated Authority
label | c0de13c6-b194-522c-92a9-3310ed62807d |  | note | – – – – – – – – – – – – – – – – –
label | 8d632451-5ee2-588a-b120-d422289109ba |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | b6344f35-9402-59ab-8526-a6ba9eaceda9 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Contractor Competency
label | 068625ce-980d-58d4-970a-d7a8f9f2252b |  | note | REFERENCE: 684.06, 684.07 (a), 684.07 (d)
label | f107c4df-ca2b-5eeb-9d44-47c12f6c7878 |  | note | – – – – – – – – – – – – – – – – –
label | 955bdabc-8d12-505e-9fa3-4d2625f5fd0d |  | note | ACCEPTANCE CRITERIA: Personnel undertaking the shotcrete works, including the nozzle operator, supervisor and finisher, shall have a minimum of 5 years experience in shotcrete application.
label | 0e01a23a-acb3-52d3-80cb-a21566341da6 |  | note | ○ Any changes to personnel shall be deemed a new Hold Point.
text | a3c3c695-68fb-5723-b62c-3249073cb72f |  | textbox | Enter: Teambinder Approval number
label | c89f0ca3-87df-5383-a0fd-6db46167c737 |  | note | – – – – – – – – – – – – – – – – –
label | 3a1556a4-99c4-57d9-a570-4574c9aa42b0 |  | note | METHOD: Document Review
label | 544afb22-6240-56d7-8465-0a09f215f463 |  | note | – – – – – – – – – – – – – – – – –
label | 06bbea13-ce64-54c8-aee0-9dd9d74b66d0 |  | note | FREQUENCY: Once, 4 weeks prior to commencement of works and for any personnel changes
label | 52b43fd4-d073-514e-908c-d5b576685bb2 |  | note | – – – – – – – – – – – – – – – – –
label | c61dc202-3c8e-5d82-98aa-3d4b3103cb23 |  | note | CATEGORY: HP
label | d059220b-43a0-5b12-b556-74082c2dfe93 |  | note | – – – – – – – – – – – – – – – – –
label | 7eb7f6a8-0ae7-5642-ac6b-2d1eebf33594 |  | note | RESPONSIBILITY: Nominated Authority
label | c233aa54-3038-5a43-b3ee-e22e120fc19d |  | note | – – – – – – – – – – – – – – – – –
label | 444646a8-98cb-5434-8d70-a85c27aac343 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | b4ca0ebb-d1c3-51a6-991d-fee0d0631174 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Test Panels
label | 6a7350b7-8acd-55d2-9c1b-eb729731ec38 |  | note | REFERENCE: 684.07 (b - d), 684.07 (d) (i), 684.10 (a)
label | 6ba5917b-6b84-5743-8ffb-11ec1cbb8e33 |  | note | – – – – – – – – – – – – – – – – –
label | b5ce5c2b-cf6c-589a-8005-7630e9b12601 |  | note | ACCEPTANCE CRITERIA: For each combination of nozzle operator, concrete mix and spraying equipment, 2 no. test panels (750mm x 750mm x the maximum design thickness or 150mm min.), shall be cast.
label | 409e4ec2-bc47-58cb-94a2-363c93728225 |  | note | – The panels shall be cast using the same reinforcement design and in the same orientation as the Works - panels shall not be cast horizontally on the ground.
label | abb80fb7-e1f9-58d7-b019-46f075db919d |  | note | – For each test panel, 8 no. core samples shall be taken, perpendicular to the surface, no closer than 125mm from the edge and after 48 hours minimum.
label | 16adc6bf-cb75-5e7e-b92d-971f288e6718 |  | note | Core samples shall be tested for:
label | 4237ce29-8edc-5176-96e2-a9fe2ff285cb |  | note | ○ 1 no. 3 day compressive strength
label | 090528d6-f73f-52b3-aebb-653a1f2fef3d |  | note | ○ 1 no. 7 day compressive strength
label | fce9f4f5-0a6a-5265-b215-cdf9b0e2d5a5 |  | note | ○ 2 no. 28 day compressive strength
label | b60c7d6f-fbb6-5ab9-9d90-3ccc29934eaf |  | note | ○ 2 no. VPV tests
label | b62547cf-5000-5169-868f-f80b56534c43 |  | note | ○ 2 no. visual inspection showing reinforcement encasement in concrete
label | d60e246d-19f6-5017-a0eb-9d8b660c62e8 |  | note | – Any changes to approved test panel combinations is deemed a new Hold Point.
label | 35340154-be4d-52c0-9dc7-13825de66bee |  | note | – Where existing test results for the same combinations exist, this is considered to be a pre-qualification and new test panels are not required.
text | 9bfec23d-7a70-5147-8f3a-1ac2cdf9f5c8 |  | textbox | Enter: Teambinder Approval Number
label | 70ad285f-0ec6-5616-80a2-44dc217433e0 |  | note | – – – – – – – – – – – – – – – – –
label | 8ef80510-905b-5828-9fb8-aefc8166c504 |  | note | METHOD: Document Review
label | 62af3624-a916-51a5-9331-3d7766250864 |  | note | – – – – – – – – – – – – – – – – –
label | 8c868545-474f-5c65-9935-8f78e0bd1883 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete, for each combination of personnel, concrete mix and equipment
label | b0a3fd47-8bcc-5628-97f2-0b58c797db3b |  | note | – – – – – – – – – – – – – – – – –
label | dd01138a-fbab-5031-afd6-8a86b938c9f8 |  | note | CATEGORY: HP
label | cd0f7c0b-a88d-56eb-9f87-7e52e854e899 |  | note | – – – – – – – – – – – – – – – – –
label | 65c96565-0182-5936-9e06-0fdc1199b258 |  | note | RESPONSIBILITY: Nominated Authority
label | 9dff91af-7cd0-59eb-89c1-aefc84bdb518 |  | note | – – – – – – – – – – – – – – – – –
label | 9a039d52-bc72-518c-902a-36f4f798553d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 86ea054d-4834-5ad3-a527-3663b7a51e00 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Concrete Sampling and Testing Procedure
label | 50080a53-5c72-5120-82c9-c2b6bc87c6a2 |  | note | REFERENCE: 684.08 (a), 610.18 (a) (v)
label | ad619734-e051-548c-b1ad-113807671b1e |  | note | – – – – – – – – – – – – – – – – –
label | b7e75692-9b29-5998-8d8a-e321eda133fb |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 9ffe508e-ae67-52c0-b5b5-3860ff85b02a |  | textbox | Enter: Teambinder Approval number
label | deb1eef0-6e07-5613-98f9-cc2aa5acd4c0 |  | note | – – – – – – – – – – – – – – – – –
label | 59f361d1-4aad-5771-98a9-a6d9906acb4b |  | note | METHOD: Document Review
label | 2e8de8ee-a59d-567a-adc0-ffe7319a8f6d |  | note | – – – – – – – – – – – – – – – – –
label | 276411a9-f8bb-5bba-8847-d35d3169d056 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 1fc5d4a2-eb75-50f5-8bbc-5c5b58f9aabe |  | note | – – – – – – – – – – – – – – – – –
label | ad9593d9-8a37-591c-ba75-d4a48f6fdc1c |  | note | CATEGORY: HP
label | 85aa96e9-57b0-5e4f-90ee-5b0310f66d0b |  | note | – – – – – – – – – – – – – – – – –
label | 3b754ae3-e62b-52da-91a1-5e4809cefe0c |  | note | RESPONSIBILITY: Nominated Authority
label | a8b30256-dbbd-590f-a8e7-b31b22a07f64 |  | note | – – – – – – – – – – – – – – – – –
label | 59f75502-839b-5b65-92f4-0904645bd9b5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 453f3e18-6645-5df9-a9c6-eb5c42309a93 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Shotcrete Prequalification Toolbox Meeting
label | fbc1d2d5-1d11-57d7-b3a1-b8e18d974130 |  | note | REFERENCE: 684.07 (d) (ii)
label | 8a27b34a-d4a0-5c43-831a-68e20470e9c9 |  | note | – – – – – – – – – – – – – – – – –
label | ad5ed471-913e-5c9b-98c9-edeb7897c3f3 |  | note | ACCEPTANCE CRITERIA: Shotcrete prequalification toolbox meeting held to discuss the quality requirements.
label | 019b9039-fb2b-5e14-8f1f-177f1327adc0 |  | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
text | bb92db1f-df28-5f02-84e5-8ef7295e1f74 |  | textbox | Enter: Teambinder Approval number
label | 34dc10bf-7325-5fd6-b649-a7a2a61065b0 |  | note | – – – – – – – – – – – – – – – – –
label | 6d77cbea-6ade-55c1-b051-ff824c3e2375 |  | note | METHOD: Document Review
label | 5cae4618-adcb-50e0-8678-5b2714230759 |  | note | – – – – – – – – – – – – – – – – –
label | c757efd7-2b5d-557f-8d5f-9600ddf8ceda |  | note | FREQUENCY: Once, prior to placement of concrete
label | 1cb6e8e6-c4bc-57a3-a0ae-bccfcfa61be8 |  | note | – – – – – – – – – – – – – – – – –
label | 4dbb6e69-ea92-5976-bf4c-97ba818694ab |  | note | CATEGORY: HP
label | b4e1d1e6-62f4-530d-9875-8ac56118863e |  | note | – – – – – – – – – – – – – – – – –
label | 5c28401e-d43e-5633-87e7-d0e77137e25a |  | note | RESPONSIBILITY: Nominated Authority
label | b5408dfd-9491-5abd-aa8f-e4bbdd17d702 |  | note | – – – – – – – – – – – – – – – – –
label | 797f0350-cf55-5cd0-ad19-469ea5f5ffbe |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 395cebb0-c8c6-5794-abc3-5a7e02517e9d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Hot and/or Cold Weather Concreting Procedure
label | 7cfc56b2-e161-5fa2-8239-3967bfc9e2dd |  | note | REFERENCE: 684.10 (b), 610.17 (a)
label | c228c623-fd97-54ff-81c2-64b6c8bfae6f |  | note | – – – – – – – – – – – – – – – – –
label | 4867d063-c2dc-55dc-b511-5c2fc6cb708d |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 2fe21378-224e-59f1-b64d-c0a6a89e1d18 |  | textbox | Enter: Teambinder Approval number
label | 989cfdf6-aa6e-55de-a647-c58a88985a59 |  | note | – – – – – – – – – – – – – – – – –
label | b25dc6a1-264e-5226-b70c-fc5b223fad51 |  | note | METHOD: Document Review
label | 98f07f1d-92da-5373-8005-4c000c049dea |  | note | – – – – – – – – – – – – – – – – –
label | 2dda1c3b-0d3a-578e-99c0-05ef8f2ea10a |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | 5da6f983-ee26-5c26-bffc-d83eccf1871f |  | note | – – – – – – – – – – – – – – – – –
label | 5bd52cf4-7706-5f22-a4da-ed874ce63c8b |  | note | CATEGORY: WP
label | cfffa956-8979-56ff-bd77-73892cf2a88d |  | note | – – – – – – – – – – – – – – – – –
label | c4244a79-b964-5b8c-8b6e-df2565ad44ec |  | note | RESPONSIBILITY: Nominated Authority
label | 7fdb27e0-a733-5889-ad2f-b9fc17765205 |  | note | – – – – – – – – – – – – – – – – –
label | 179e448f-c3cb-591d-9a62-be8e336b0daf |  | note | VERIFYING DOCUMENTS: This ITP
date | 44029c85-d561-561a-a9b7-e6c7d7e44aa4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Curing Methodology (for Concrete and Grout)
label | 5065707c-e88b-5dd4-aa19-41ddb9b94f41 |  | note | REFERENCE: 684.12, 610.23 (a)
label | 32274d53-ca32-56dd-941b-801c47a6e1ab |  | note | – – – – – – – – – – – – – – – – –
label | 4be075c4-3bb7-5606-b128-683e5cd229d7 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | c45f34d5-b748-5318-96d2-760e57492ed2 |  | textbox | Enter: Teambinder Approval number
label | 9efca5a8-2a0c-5215-966c-41e9b2f4bb6c |  | note | – – – – – – – – – – – – – – – – –
label | b6485254-b170-5580-a4ef-e24f027b7620 |  | note | METHOD: Document Review
label | f756c4db-a07d-54e5-a01a-28dfca96fe88 |  | note | – – – – – – – – – – – – – – – – –
label | e704e244-bd64-5302-8b0d-991f75de9cd4 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 2d43187c-e211-510d-bdad-85a1d3143ea8 |  | note | – – – – – – – – – – – – – – – – –
label | 245d99c6-44ca-5a90-a030-af991c4a7a5e |  | note | CATEGORY: HP
label | bbda7962-3818-5dbb-91b7-a8488d0bd52a |  | note | – – – – – – – – – – – – – – – – –
label | fe93d5f3-a413-515e-b321-b6515608bdfd |  | note | RESPONSIBILITY: Nominated Authority
label | 4dff10cb-5ba6-5029-bfc9-b9c005183f47 |  | note | – – – – – – – – – – – – – – – – –
label | 7d614731-c711-5002-bcaa-0ecde2f1396a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | e270b087-ac40-5e48-86a5-2cf889f4ebdd |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | b3e87a10-2b94-526a-aa8a-f7c399470fc0 |  | note | REFERENCE: MRPA Quality Management Plan
label | 89ea3363-18e0-5207-abee-55635cac2c35 |  | note | – – – – – – – – – – – – – – – – –
label | bb409bd6-1490-5fdb-9728-2b8707ae2bcc |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 416677a2-482d-5a00-ac49-43b92bf6d1b4 |  | note | – – – – – – – – – – – – – – – – –
label | 10830ece-ea7b-550c-a53a-f6bc790c6ea4 |  | note | METHOD: Document Review
label | c56e7c5f-9904-5bc5-b562-7043bf0f8242 |  | note | – – – – – – – – – – – – – – – – –
label | 75527c0e-e33c-514b-95fa-7fc944df97d2 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 53431f26-07d7-5980-9d88-98d2d7fcc58a |  | note | – – – – – – – – – – – – – – – – –
label | e4f95e87-1cba-52d9-8202-97def824bcd6 |  | note | CATEGORY: HP*
label | 47038905-8266-5fcf-ae18-2135dd0ee206 |  | note | – – – – – – – – – – – – – – – – –
label | adecdb1a-882e-5605-8bc7-2269086aa478 |  | note | RESPONSIBILITY: All
label | 59d07c34-944a-50ce-a38c-83113c57e90c |  | note | – – – – – – – – – – – – – – – – –
label | d698124a-a706-5b22-aa6e-b3f3d07fc32b |  | note | VERIFYING DOCUMENTS: This ITP
date | 1db64cee-05cc-53d1-9622-50c8804a75cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Substrate Preparation
label | 3d4f8d79-2c33-5312-ac0d-24acefd75769 |  | note | REFERENCE: IFC Drawings, Shotcrete WMS, 684.09 (a - c)
label | d8f50cd7-37b7-5435-aae7-2e54eb177d18 |  | note | – – – – – – – – – – – – – – – – –
label | ff9b51be-ced6-5dfb-8804-cb92ee59df89 |  | note | ACCEPTANCE CRITERIA: Substrate shall be formed to the correct line and grade to provide adequate thickness for the works and shaped (or repaired - for concrete) to prevent any abrupt changes in thickness of the shotcrete.
label | 019312c6-e6e4-5b87-9356-b1bf15ca223a |  | note | ○ Any loose materials, oils, grease and coatings of any description shall be removed.
label | dfbad5ea-4a99-518c-976f-c70d3334c8a4 |  | note | ○ Smooth concrete substrates shall be roughened to create a construction joint.
label | f8f84b47-f5d1-5f55-9868-879294b5c429 |  | note | – – – – – – – – – – – – – – – – –
label | 74de6d07-5112-5711-805c-db9df05697b8 |  | note | METHOD: Measure, Visual
label | 4f81cb0a-8244-5341-9184-835f74b560cb |  | note | – – – – – – – – – – – – – – – – –
label | 7739c733-e3cb-589a-9660-38799a78581e |  | note | FREQUENCY: Each lot
label | ef13ba74-0c8d-543e-8bbe-8fba21f0d15d |  | note | – – – – – – – – – – – – – – – – –
label | eebae0a1-7392-5899-935f-49e6b29529b1 |  | note | CATEGORY: IP
label | d550fd24-5308-5879-9cc7-3ff659a73360 |  | note | – – – – – – – – – – – – – – – – –
label | a4c0d236-466d-5f26-b94a-becea72add8f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | a102c48b-2a22-5554-9c62-bff0490c0a0e |  | note | – – – – – – – – – – – – – – – – –
label | 7c5441f7-51fa-526a-8a8d-a756fcc5ec98 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6ee0ba11-330c-56f9-abd5-73c695246b70 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Subsurface Drainage
label | 4abdd9dc-7f2a-58a8-875b-099738edf8bb |  | note | REFERENCE: IFC Drawings 684.09 (a), 702.03, 702.06, 702.07, 702.09 (f)
label | ce3d0ac8-d86a-5b01-8845-9542b78a639c |  | note | – – – – – – – – – – – – – – – – –
label | 6f70b1a2-e6c9-54a1-ab48-798ee8598b06 |  | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
label | c58ab7ef-eaa9-5507-8a93-a2e15f76694f |  | note | ○ The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings against the substrate to prevent encasement in concrete.
label | 6c5a0128-9c6b-5db7-9588-7a346e98be86 |  | note | ○ Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
label | a586126f-2bb4-5add-9b8d-3315fbb1d276 |  | note | – – – – – – – – – – – – – – – – –
label | 5beab188-1969-5280-9aae-c165b520744b |  | note | METHOD: Measure, Visual
label | 9d86c3b3-7bdd-5af4-8868-726823070c46 |  | note | – – – – – – – – – – – – – – – – –
label | 3a1c5ae4-fa91-5d31-9cfc-fa026fd8ecb6 |  | note | FREQUENCY: Where applicable, each lot
label | fab60858-3ff2-5486-9733-dcac698bb906 |  | note | – – – – – – – – – – – – – – – – –
label | cbaee9e1-19eb-510c-af65-2a5f5634c930 |  | note | CATEGORY: IP
label | ea16be8a-3fa2-5f5a-b265-735ee1668d60 |  | note | – – – – – – – – – – – – – – – – –
label | d6146c58-e73d-544f-812e-b87de8011530 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 98943ada-07c2-5156-a80d-ff982e8a1de2 |  | note | – – – – – – – – – – – – – – – – –
label | a3e43997-9983-56d9-92b3-a60c38818807 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2c1c5ea8-33e4-5c04-884e-31d2a5bf1a50 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Waterstop Seals, Compressible Seals & Isolation Joints
label | bf9c67f7-b3b4-5967-b2a4-2d87cc8a6aa6 |  | note | REFERENCE: IFC Drawings, Product TDS
label | 9cf66ff2-50ad-5ca9-adc5-4dd94ce04e18 |  | note | – – – – – – – – – – – – – – – – –
label | bdfc100f-4c4b-5ebc-ac4e-4033ff774187 |  | note | ACCEPTANCE CRITERIA: Waterstop seals, compressible seals and isolation joints shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
label | 7b2aa106-1af8-5e8a-acd5-62210205eda3 |  | note | ○ Seals and isolation joints must be full height of the structural element(s) and located as per the IFC drawings.
label | 4e1de026-a134-5609-8284-583d58ab006e |  | note | – – – – – – – – – – – – – – – – –
label | 288bc9a4-e0b3-5002-8733-2f17c2888279 |  | note | METHOD: Measure, Visual
label | d5f7149f-2219-5b4b-b697-b03d5a0a5bd3 |  | note | – – – – – – – – – – – – – – – – –
label | a75214ec-0320-59f4-ac97-650acbee3d26 |  | note | FREQUENCY: Where applicable, at each existing structural element
label | 62dde248-8ec9-573b-b7dc-8ca0139cec96 |  | note | – – – – – – – – – – – – – – – – –
label | 80b3c0dd-d186-5826-a059-f077bb194ad9 |  | note | CATEGORY: IP
label | ac2a9959-9313-58ce-8d2f-a286be4b758e |  | note | – – – – – – – – – – – – – – – – –
label | 85cc7399-0bc4-5898-8822-c796ca74ecfe |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e6903149-969f-5f49-ac7b-62c856c02dd3 |  | note | – – – – – – – – – – – – – – – – –
label | e7d82da7-f2d1-5ae1-8880-05aca89d384b |  | note | VERIFYING DOCUMENTS: This ITP
date | bf78f6a0-2d84-5a3c-b561-3a2c9788421a |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement Placement
label | 4ac6331c-ed82-5f0a-8107-61c56c2d81f8 |  | note | REFERENCE: IFC Drawings 684.04 (c), 684.09 (c), 611.06, 611.09, 611.10, 611.11, 611.12
label | c3b61017-4ee3-5e3c-ac83-fccfb81a0872 |  | note | – – – – – – – – – – – – – – – – –
label | 9cef3854-9e55-5a5f-99ea-54e110125875 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 9864b2d7-7ceb-58c7-b682-19dfc32f4c05 |  | note | ○ Tie wire is to match the reinforcement it is securing, with contact between dissimilar metals isolated with zinc-rich spray paint, electrical tape or have a minimum gap of 10mm.
label | 4bdd7da4-d6f2-5c11-b5c4-4f2bf147f1d1 |  | note | ○ Layers are spaced apart using bent reinforcement, not bar chairs.
label | 31e1f601-c881-53d6-8053-2e06211d1e44 |  | note | ○ Projecting reinforcement is the correct length and location.
label | 30be9767-338c-5457-8a5c-3d8c8c02cf48 |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | 413f4898-67d3-55b0-9ff2-b60c51f81e25 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | a2056456-4299-535a-9dc6-43786498a4e6 |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the shotcrete application.
label | c4ac3cbc-e4ed-508a-b686-439b99b151ee |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | 5887e86c-2540-536e-9957-4b505d05c860 |  | note | – – – – – – – – – – – – – – – – –
label | e9fa0aaf-3766-55bf-a704-12960a645f1f |  | note | METHOD: Measure, Visual
label | 87646bc8-b8e7-5829-bdfc-8d7508fc9515 |  | note | – – – – – – – – – – – – – – – – –
label | 014e1c87-0978-5ade-9ebd-e0c08fc1b3f1 |  | note | FREQUENCY: Each lot
label | b798e074-36a9-5efb-8466-39014b7017c4 |  | note | – – – – – – – – – – – – – – – – –
label | ac06655e-b678-53be-9d51-7c3654b1c2ed |  | note | CATEGORY: IP
label | b6f36953-a6e7-57dc-a2cb-7341fcecb4e8 |  | note | – – – – – – – – – – – – – – – – –
label | d0f1cde5-b5a6-5315-8222-a6e00b7ddae6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | ffe8b4d8-791c-5db6-9107-4884e1c12feb |  | note | – – – – – – – – – – – – – – – – –
label | 12cc6b4e-9d38-5f44-b103-3b918fb61f57 |  | note | VERIFYING DOCUMENTS: This ITP
date | 96d418b8-68da-5339-9d01-c64b3c47bc50 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Cast-in Items
label | 5513d90b-7747-5a07-9c44-2dd2334f5851 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
label | c40b22b8-c3fe-5844-8205-73fe1abea2ba |  | note | – – – – – – – – – – – – – – – – –
label | 28b51c68-af7a-5b86-ab85-0f23f327411d |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 91a01d8f-d45e-5184-83a8-d1b8fb4947fc |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 1b4534d1-92f7-5c86-8479-f899b2cf5729 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 5a18b200-46a2-5619-92f3-14bd31b16fdb |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 8caacb5b-f153-54fb-8035-a37f56e54a59 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 25161706-75ea-5da9-acb7-61537b79cac6 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | a1488597-807d-5587-a903-3f3d3b5d2c7f |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 5b97b929-2367-5569-a460-8ad85025cf4d |  | note | iii. Ducts and conduit location = ±12mm
label | 0a884b8e-e1b9-5e03-a3c1-6d0332ae65fa |  | note | iv. Diameter of ducts and conduits = ±3mm
label | f2980443-55cc-5ea9-b0e8-3344bfa53332 |  | note | – – – – – – – – – – – – – – – – –
label | 41a50191-f332-5bbe-9eb0-1318b110a7b8 |  | note | METHOD: Measure, Visual
label | c13e2588-80af-57ff-ba55-fb4901512bc4 |  | note | – – – – – – – – – – – – – – – – –
label | 2004649f-7eae-5051-9eff-fca231f0e117 |  | note | FREQUENCY: Where applicable, each element
label | 721647df-967c-50b9-a77d-bbe31cba787c |  | note | – – – – – – – – – – – – – – – – –
label | 5d79473f-1b07-5f64-acf7-eb11aa45b161 |  | note | CATEGORY: IP
label | 4b6083f2-66b6-5310-b396-20f55572c321 |  | note | – – – – – – – – – – – – – – – – –
label | 34037a69-5327-50d1-90ce-e57f55568fbe |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 4047cb0c-7909-5856-b433-fdadc39e88a2 |  | note | – – – – – – – – – – – – – – – – –
label | 2b497c3b-b4f8-5a24-905e-9c8d42448663 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0be0c936-d70a-59eb-ab4f-c00480fbd3cb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pre-pour Inspection
label | d4176b23-89be-5a6d-90b1-a460333df9ea |  | note | REFERENCE: IFC Drawings, Bonded Anchors ITP 684.10 (b)
label | bf31c5f8-53ba-56c5-a0c2-541f85c76a06 |  | note | – – – – – – – – – – – – – – – – –
label | 0fcdf0bf-d1e9-5ed7-8df7-d83ade9c8f35 |  | note | ACCEPTANCE CRITERIA: All preparation works on the substrate have been completed and the surface moistened without free-standing water to prevent premature drying of the shotcrete.
label | 4da1fb46-d36b-5b1c-8469-0b1011ebed3d |  | note | ○ Evidence that the reinforcement and embedments are conforming to the requirements of the specifications and the IFC drawings.
label | d25d5909-074c-5e73-9f40-c2aef3660bc0 |  | note | – – – – – – – – – – – – – – – – –
label | 0ca8db37-0aa6-5b36-bd30-3d88b14548a8 |  | note | METHOD: Measure, Visual
label | 4c8348a5-82c9-5b36-80c0-407925146cdb |  | note | – – – – – – – – – – – – – – – – –
label | 862e4927-05d8-5a90-81e8-4ee3ccdc7545 |  | note | FREQUENCY: Each lot
label | 56cb202e-c711-58fd-b31b-acd54ea61867 |  | note | – – – – – – – – – – – – – – – – –
label | 9da65e91-728c-51af-936d-f230ef85762d |  | note | CATEGORY: HP
label | 89fd5992-a968-5933-94fe-787cc8c8eab9 |  | note | – – – – – – – – – – – – – – – – –
label | c721f071-2652-514f-8ca1-9fec50663725 |  | note | RESPONSIBILITY: Nominated Authority
label | a6b02a8d-789f-521a-a2f7-40e72b3337dd |  | note | – – – – – – – – – – – – – – – – –
label | 16acc145-68c5-5044-8140-756250b90415 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 305be4f2-d681-5427-9a9b-ac04f57f76fb |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Weather Conditions & Evaporation Limits
label | c17ed9a1-17d7-5db5-aee0-64132eee04c2 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 684.10 (b), 610.17, 610.17 (a) & (e) Table 610.171
label | 5ff2c03b-7e01-57b1-b728-2ae186cc5753 |  | note | – – – – – – – – – – – – – – – – –
label | 5e313ce8-0030-5739-8190-253971f65e46 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 5461e051-c765-52fe-958e-6e2752572c23 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 8a6f4fcd-7659-5882-b5fd-0379bfef6600 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | d659eb7e-1794-5dbe-a183-99d98006bca2 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 12aed29c-4ae1-5364-8c4d-1d5511ab0e68 |  | note | Record: Required information on the Concrete Pour Record.
label | 6db7a8db-b6a2-50f1-9c4d-e63f67f47247 |  | note | – – – – – – – – – – – – – – – – –
label | 959dd4d3-efbc-5eb8-8139-6946b650f15e |  | note | METHOD: Measure, Visual
label | df2aa1a2-1951-52f2-9b8b-1b516c01556f |  | note | – – – – – – – – – – – – – – – – –
label | d6771eea-4f36-5813-8ff1-84bd90045591 |  | note | FREQUENCY: Each lot
label | 4c87dcfd-8240-5d17-b0a9-8ae78e1c5bff |  | note | – – – – – – – – – – – – – – – – –
label | 0116a619-54b8-569d-b1f3-7c1c7bfde3b7 |  | note | CATEGORY: IP
label | e9bd898d-b09b-52bd-944e-74f918682159 |  | note | – – – – – – – – – – – – – – – – –
label | bd512b81-63de-54a4-b8e0-dbe401989f7e |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fb0661a7-6888-5e06-b640-4cc67b9569cb |  | note | – – – – – – – – – – – – – – – – –
label | e4014dfb-6ead-5a85-986f-249ab7c9f680 |  | note | VERIFYING DOCUMENTS: This ITP
date | c568262e-ed38-5081-b7b7-020e976b4747 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Concrete Testing - Sampling Frequency
label | a936dba7-93b8-598b-84ec-3b156c85d4c8 |  | note | REFERENCE: Site Sampling & Testing Procedure 684.08 (a), RC 377.01, 610.16 (b)
label | a8e3ee37-adf0-5dca-a59c-e59673d41b8b |  | note | – – – – – – – – – – – – – – – – –
label | f6603bc9-450d-52ef-a755-4fcec920c26c |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 2a0bcc9d-4880-5f12-8ac0-503ce9c8c3a7 |  | note | ○ 0m³ to 10m³ = 1 sample
label | fb3cda54-8b1b-51ed-b02a-7ad865692179 |  | note | ○ 10m³ to 25m³ = 2 samples
label | 35a9156b-3bb4-5612-8edb-9cde62d4367e |  | note | ○ 25m³ to 50m³ = 3 samples
label | 3e0264c3-b809-59f6-a11e-ffc6cf4ec359 |  | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 5ff78e78-144b-5f69-85d0-4a3a4bd7ea45 |  | note | – For each additional 50m³ and additional sample shall be taken.
label | e8a011c1-ea28-5334-ac71-436cb92e9e21 |  | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | c53b1d93-39ec-5052-bee1-631114a122ce |  | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 62a3770b-e74d-536e-819f-97596f04f2bd |  | note | – Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
label | fcaa2e3e-724b-55f9-9d9d-8d7b6b73d1a4 |  | note | Record: Required information on the Concrete Pour Record.
label | 80fba312-e78e-510a-9f06-db46c7a8f897 |  | note | – – – – – – – – – – – – – – – – –
label | 6bc11daa-892f-5fa5-b96c-401f5b1da1db |  | note | METHOD: Test
label | 4958b72b-8ba9-50b4-a3fc-eb0a748f848f |  | note | – – – – – – – – – – – – – – – – –
label | 917b06d4-8a67-5a02-9822-77cd1c88a638 |  | note | FREQUENCY: Each lot
label | fe6f315b-55e3-525a-856d-c4042575a973 |  | note | – – – – – – – – – – – – – – – – –
label | d4780ade-7cbc-54c4-aa7c-06399cb1f25b |  | note | CATEGORY: IP
label | 13ddd55d-970d-57eb-a778-583b0195b117 |  | note | – – – – – – – – – – – – – – – – –
label | c6da7c91-4f25-5f01-b989-ff9561c3270c |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 04cae994-70e5-5e09-ab25-750e812ba524 |  | note | – – – – – – – – – – – – – – – – –
label | 46a7aa76-c167-56c7-b3ee-b5712c659b32 |  | note | VERIFYING DOCUMENTS: This ITP
date | 54dae2c4-dfce-57c9-aae7-a682b79cf53c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Concrete Testing - Slump
label | 5da4be55-24a5-50ec-b697-12807bc1ee78 |  | note | REFERENCE: 684.08 (a), 610.16 (c)
label | a0b0c74e-ff0a-597d-b108-16c67266f716 |  | note | – – – – – – – – – – – – – – – – –
label | 836807dd-1592-5a1a-b025-c4fb000e01ad |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | 032eb7ff-c3aa-54b2-b73f-36039f80015b |  | note | ○ <60mm = ±10mm
label | 816c0664-0313-5629-922b-ae0acc4fa54f |  | note | ○ ≥60mm to ≤80mm = ±15mm
label | a28a8bc5-98f4-528a-bc73-c5d074ee3da7 |  | note | ○ >80mm to ≤110mm = ±20mm
label | 9fecc294-5206-5727-a5ba-c83a1dcc2895 |  | note | ○ >110mm to ≤150mm = ±30mm
label | 7e36bb3d-7197-5e3f-b967-d2f86f72c3f2 |  | note | ○ >150mm = ±40mm
label | f653c9c3-97dc-5248-9759-499bcdda6a58 |  | note | Record: Required information on the Concrete Pour Record.
label | 0efd11dd-2529-596e-814d-4016cfd40eef |  | note | – – – – – – – – – – – – – – – – –
label | 69c8923e-e1d5-55b5-b676-48ee96099d18 |  | note | METHOD: Test
label | 61696456-4567-5401-a98f-263c0322392a |  | note | – – – – – – – – – – – – – – – – –
label | da114f82-cb94-5f82-bbb1-d518aa341edf |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | 01172c0b-761d-5122-b891-2803d15083da |  | note | – – – – – – – – – – – – – – – – –
label | fa26cbb9-b8d0-5f80-9d1b-9110d646bcac |  | note | CATEGORY: IP
label | 0029f9a0-7e7e-5cde-a0d9-2d915be335c7 |  | note | – – – – – – – – – – – – – – – – –
label | e0d66d5b-8291-5fb4-86a4-be397ebb4835 |  | note | RESPONSIBILITY: Concrete Tester
label | 5c922122-5e0a-5c1b-9240-cf7f8dd64a36 |  | note | – – – – – – – – – – – – – – – – –
label | d168c838-eebd-54fc-9944-6c5b25f56ab3 |  | note | VERIFYING DOCUMENTS: This ITP
date | beaa273c-6ea4-5bf5-8b3d-ab38762a2736 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Compressive Strength Cylinders
label | d0ba5579-e5ea-53a8-842c-65d91f16674c |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 9ecbbfa7-9c52-5131-a82f-5ebff888678b |  | note | – – – – – – – – – – – – – – – – –
label | 7b9d6f3c-ffc5-5fb9-8a30-cfd2f3549976 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 06bb274b-6dc8-58d1-9a1a-596d19de00af |  | note | Record: Required information on the Concrete Pour Record.
label | 2892189a-5ed3-50da-b762-9a40c0510b31 |  | note | – – – – – – – – – – – – – – – – –
label | e7d5553e-bdf6-53d6-bfc7-c90282f4692d |  | note | METHOD: Test
label | 2ec36d3f-1699-5555-9b6a-37de2496471b |  | note | – – – – – – – – – – – – – – – – –
label | 9f30742a-c413-54f4-8df5-e47f9b000088 |  | note | FREQUENCY: Each sample
label | ac6045d4-55f5-5d75-ac55-d53f9c502b69 |  | note | – – – – – – – – – – – – – – – – –
label | 2c5c8d92-ccac-58d3-b5ab-7e8d9aca3064 |  | note | CATEGORY: IP
label | b7381c66-f9e5-5155-a988-0af959d633ae |  | note | – – – – – – – – – – – – – – – – –
label | 3255988e-b505-5393-8a87-29496eec97a2 |  | note | RESPONSIBILITY: Concrete Tester
label | 378bc96b-ec40-54f5-83c3-cbf956025996 |  | note | – – – – – – – – – – – – – – – – –
label | f30682a6-cd2d-5fdf-83e0-8df586a97af8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6ddb4569-0dd5-5984-a1d2-b9c4bee4b882 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Supply & Discharge Rates
label | 02a56564-8168-5631-821f-f3b1bd809e0c |  | note | REFERENCE: 684.05 (c), 610.13 (a) & (f)
label | d37a6a04-53dc-59cb-a445-de101dfb899b |  | note | – – – – – – – – – – – – – – – – –
label | 01b7a59e-60a3-599b-8091-383801e5d94c |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 520d18ee-2bf1-51f8-8ebd-11f6dd2bbefa |  | note | ○ No water is to be added once discharge commences.
label | c129a668-27ad-5302-b6f4-3159fa8ca1fc |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | 948240b7-3c83-5671-ab0b-0b0842420811 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | 17ba5c87-cc51-5b66-ae17-25faf438a3c4 |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | b61d95a0-1b46-5a80-9530-1690b7fca015 |  | note | Record: Required information on the Concrete Pour Record.
label | 53dbc419-1d0b-59b3-af65-202b4ac7980f |  | note | – – – – – – – – – – – – – – – – –
label | 739761b4-7cb3-5c35-a878-447fe8a0653e |  | note | METHOD: Measure, Visual
label | ad45acd5-1c2d-5aca-a572-e74d0d0c958a |  | note | – – – – – – – – – – – – – – – – –
label | 5efaf0fd-e4d4-5831-9456-6438f638363a |  | note | FREQUENCY: Each load
label | 1a394d2a-6aa3-5918-9b2f-7035155ab7eb |  | note | – – – – – – – – – – – – – – – – –
label | b012832f-4cb9-5121-878a-6105e9f4000f |  | note | CATEGORY: IP
label | af66aa6c-6c89-5a47-b46c-2dd074ee9981 |  | note | – – – – – – – – – – – – – – – – –
label | 175c9487-e500-5620-b406-39c22f3b1c8f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8c99bb8a-c628-55ba-a8fd-5ff38543e83c |  | note | – – – – – – – – – – – – – – – – –
label | 83594105-d613-527a-b0bc-66daae3621ce |  | note | VERIFYING DOCUMENTS: This ITP
date | c719d80a-1d5d-550b-90bd-04ca0ec167aa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Application Process
label | ca1da848-fb53-5b7c-99b1-a07288c9bd35 |  | note | REFERENCE: Shotcrete Work Method Statement 684.10 (b), 684.13, 610.18 (a) & (b)
label | 64b0a043-d158-5be1-84ca-a13fc22b84f5 |  | note | – – – – – – – – – – – – – – – – –
label | d6b21ae5-54f1-5267-a402-a776f859318d |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | d88b9e3c-e027-5426-9937-9593c17f728f |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 56f0cfdb-16cb-53c2-8cd9-a9199bafbe13 |  | note | ○ Probes or non-corrosive thickness indicators shall be used during the application to determine the actual application thickness.
label | a4e48138-2749-5c5f-91df-55a4b5301c86 |  | note | ○ The spray nozzle shall be held to ensure placement of concrete behind and around all steel reinforcement.
label | 6689a182-2cac-507d-bdb0-fe5da421aa52 |  | note | ○ For vertical surfaces, application shall commence at the bottom and overhead surfaces shall be applied from the shoulder to the crown.
label | cc98b33f-acc4-5890-9269-8410fb522280 |  | note | ○ Each layer of the sprayed concrete shall be built up by making several passes over the working area with a maximum layer thickness of 150mm.
label | 8ba50113-82f7-5c16-a0cd-3d225cc0f0c3 |  | note | ○ Concrete shall not be sprayed through more than one layer of reinforcement in one application.
label | 3ee7e510-f0cb-508f-8390-fc5272fa448b |  | note | ○ Where a layer of sprayed concrete is to be covered by succeeding layers, it shall be allowed to set prior to application of the succeeding layer without the need for curing compounds.
label | 91389199-66f0-5a01-a376-d90e15783b03 |  | note | ○ The surface shall be checked for soundness, segregated, loose or otherwise uncompacted sprayed concrete removed, repaired as specified, cleaned, and wetted using a blast of air and water, leaving a dense, homogenous monolithic layer.
label | 280f8149-d715-5b76-ad50-864543201bbd |  | note | Record: Required information on the Concrete Pour Record.
label | 7a5eb97f-7e47-5678-9f22-7167e2b2fc62 |  | note | Attach: Concrete Pour Record
label | ee060396-6c11-506f-8bd4-1dc4d5a630cc |  | note | Attach: Concrete Dockets
label | fb4a990c-5e75-52e4-bbcf-dd1256c77990 |  | note | – – – – – – – – – – – – – – – – –
label | 1cbb3cd6-9eeb-5db8-87cf-277a3cd457cd |  | note | METHOD: Visual
label | 61f4804d-c08e-52e3-b741-ffbd1614d0bf |  | note | – – – – – – – – – – – – – – – – –
label | 4c61d068-4d77-5b6d-963c-14ea43f4894b |  | note | FREQUENCY: Each load
label | b1342a29-d08c-5de4-8bcd-ccfd4765d95d |  | note | – – – – – – – – – – – – – – – – –
label | 7cb14d15-a218-5f61-af86-6a86657470c7 |  | note | CATEGORY: SP
label | 5ad38243-9c82-5451-8f21-0dd18bdb1c31 |  | note | – – – – – – – – – – – – – – – – –
label | 97b7ff97-8837-57a5-a606-9edab17d92e5 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | c09883eb-d4fb-5b9e-8a92-0ab190898a6e |  | note | – – – – – – – – – – – – – – – – –
label | 2cb911bd-d2fe-50f8-819c-31ac7ee15ac6 |  | note | VERIFYING DOCUMENTS:
date | a960fb11-fcb3-51d6-a2bb-3a53056fc412 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Surface Finishes
label | 445243de-df21-5141-817d-7887e92d6de4 |  | note | REFERENCE: IFC Drawings 684.11, 684.14, 610.31, 610.20
label | 30e026a9-c608-53cb-8a26-fd67a1155960 |  | note | – – – – – – – – – – – – – – – – –
label | 5c1d17b3-a809-5a37-8f0b-5a7fdf85dec5 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 31eae22e-475f-508e-8877-6470e9b29693 |  | note | ○ Where surface finish is not detailed, structural concrete retaining walls, soil nail walls, tunnel linings, CP Overlay and other structural components forming part of permanent Works shall have a class 2 finish to reduce the chance of cracking.
label | e8347923-d1b7-5755-8700-277ebb857ee5 |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 7bc7f37f-70a0-5ac0-a559-c9ca1f0d9263 |  | note | – – – – – – – – – – – – – – – – –
label | 6824382b-5afb-57cc-a54b-234be098755c |  | note | METHOD: Visual
label | be728479-6789-5693-879f-912535daff1e |  | note | – – – – – – – – – – – – – – – – –
label | 7f5d2af2-c6bb-5235-a1e6-403786e2d54b |  | note | FREQUENCY: Each element
label | b3d465c4-6e78-582f-9679-16047f8cadf1 |  | note | – – – – – – – – – – – – – – – – –
label | dda030f4-53b2-524f-9a41-1543ac6a7330 |  | note | CATEGORY: IP
label | 597582a1-fffe-5d54-a071-6e439349be29 |  | note | – – – – – – – – – – – – – – – – –
label | 9e273683-fce1-538e-b38b-82fab97ece70 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | efb71991-105b-5b2c-965d-387888a063df |  | note | – – – – – – – – – – – – – – – – –
label | f8cc2fcb-367d-56f8-8d67-a6ad2402f656 |  | note | VERIFYING DOCUMENTS: This ITP
date | d6e17a52-d284-5f96-adf1-252e34b5b6d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Curing
label | c36e12b3-8a15-5a97-a9f9-3898126da1b2 |  | note | REFERENCE: Curing Methodology 684.10 (b), 610.23 Table 610.231
label | 6651571f-5cf4-5065-ad00-7020d19a9d04 |  | note | – – – – – – – – – – – – – – – – –
label | cf1a66ec-3952-5861-8f0f-e5ddc2eef344 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | f7b63601-ab23-5b9b-b0e8-838d52105afc |  | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 71d1c437-130c-5346-8cbf-323334f632de |  | note | – – – – – – – – – – – – – – – – –
label | fa54faa8-d356-51e9-a3b0-ce9812280fe1 |  | note | METHOD: Visual
label | 326926f2-5d42-5489-8cc2-7e78b23d51c3 |  | note | – – – – – – – – – – – – – – – – –
label | e35d4816-2081-5ffa-bde4-261e39a542b6 |  | note | FREQUENCY: Each lot
label | c8b53a8f-35f4-5abf-931d-cdfdfe71a7f3 |  | note | – – – – – – – – – – – – – – – – –
label | c5b46fdc-425c-5de7-8c45-124ad3d18ba0 |  | note | CATEGORY: SP
label | 7e0e4804-32b9-502b-9cc9-c930a291ebd6 |  | note | – – – – – – – – – – – – – – – – –
label | a5fef641-10e4-5bfb-9adb-32c3fd53905f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | da38b0a5-56d0-518e-a2a9-d16cfa26cd8d |  | note | – – – – – – – – – – – – – – – – –
label | fac596c3-6bd1-5484-8c69-f59e01ab8860 |  | note | VERIFYING DOCUMENTS: This ITP
date | 29588fef-8022-5839-b9e9-7bf35850a924 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Concrete Testing - Core Sample Frequency
label | 24c4f9d1-2707-586f-9bfd-633ffa3a9ea3 |  | note | REFERENCE: Site Sampling & Testing Procedure 684.04 (d) Table 684.041, 610.16 (b)
label | 6a8aceb8-8b0f-5707-9fe9-d0ac80af14ad |  | note | – – – – – – – – – – – – – – – – –
label | 53668e60-29cd-57a6-a0fa-9aeb49dba3d3 |  | note | ACCEPTANCE CRITERIA: 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
label | fb882b14-09a1-525d-9ccc-bef6bc17e9e5 |  | note | ○ 0m³ to 25m³ = 1 sample
label | 9b04b934-dc4a-58be-ad2a-a43b8d0513ea |  | note | ○ 25m³ to 50m³ = 2 samples
label | 47715760-7933-5cc6-ab29-8e1019f8ab29 |  | note | – For each additional 50m³ an additional sample shall be taken.
label | d4e697cb-2499-5dd6-b16e-ba046c60ebeb |  | note | – Each sample shall consist of 5 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
label | b2eba7a9-3d73-55bf-8536-4dbf2b981b6a |  | note | Core samples shall be tested for:
label | 63e4440c-8c7c-59f8-9ee2-2435c248c761 |  | note | ○ 1 no. 7 day compressive strength
label | 6ef14fc9-f363-5e8b-b215-f9fd53d183fb |  | note | ○ 2 no. 28 day compressive strength
label | 0d701025-e4ad-5fa7-b180-447f3d30573d |  | note | ○ 2 no. VPV tests
label | 00747d17-4fbf-53cd-8f38-b8b00ea35271 |  | note | Note: MRPA has D.o.T acceptance to remove the 3 day core and take core samples on test panels in lieu of completed Works
label | 087be043-e582-58ad-93bf-427c981e5941 |  | note | See:
label | 07c31104-bbbe-59b6-949f-719fa1299b58 |  | note | ○ MRP-MRPA-GNC-XCN-0096
label | 61c0660f-bdb2-5448-b540-77d977f74ba4 |  | note | ○ E-mail from D.o.T 7.06.2021
label | b9d4f185-0906-5006-afed-4d3c8773d3ff |  | note | – – – – – – – – – – – – – – – – –
label | 9ae8ef78-966b-5d97-9086-a6f175d41cd7 |  | note | METHOD: Test
label | 7e5b056c-e8c6-5e30-b9ad-f2a9242f2502 |  | note | – – – – – – – – – – – – – – – – –
label | b560ac78-f813-5089-be84-80ceba01cca8 |  | note | FREQUENCY: Each lot
label | 2e9a6690-74bc-5947-ab6e-f2f7327e9235 |  | note | – – – – – – – – – – – – – – – – –
label | eac0f01f-fd2c-54f6-b8c4-c4ddd1d1d816 |  | note | CATEGORY: IP
label | 4bb77af0-7cd4-57d0-a786-e17eb96b26f3 |  | note | – – – – – – – – – – – – – – – – –
label | 9f7cf537-f8d8-525e-87c7-fee1a0808aad |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | be599154-24b0-546d-be6e-8b82c0d7f4ac |  | note | – – – – – – – – – – – – – – – – –
label | 3b6893eb-3f0d-51ce-89e8-39f500595c0a |  | note | VERIFYING DOCUMENTS: This ITP
date | 7b53787a-789e-525d-ab2b-e6c435b1df0b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength & VPV Test Results
label | 35ddc551-0b27-568c-aba4-dfde52b8b3e1 |  | note | REFERENCE: IFC Drawings 684.08 (e) (i - iii) Table 610.051, Table 610.061, 610.16 (g)
label | 00e28513-ceb2-5f3e-85bd-9e19223aa261 |  | note | – – – – – – – – – – – – – – – – –
label | e63df0b4-555d-5e52-9269-590742f721c5 |  | note | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 6a8bf5c7-10d1-54ed-bfc1-4afad6928805 |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
label | bb8afcae-d127-56fd-a5ab-a51ac9f704c6 |  | note | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
label | 31589206-e010-5356-b6c3-88c5b1ba09b9 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 99b814ec-b444-535e-aa5a-21bf7cd5e9d0 |  | note | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
label | 523f5e24-b6c1-5e10-8db7-da1ff9d890c7 |  | note | Attach: Compressive Strength Test Results
label | 308a0b50-3f64-5e3a-bd19-28193047e092 |  | note | Attach: Core Sample Compressive Strength Test Results
label | fbe493f2-5d2f-54c0-8a8c-ff52e78266ff |  | note | – – – – – – – – – – – – – – – – –
label | 7f605aff-5cc5-5ed5-9ec1-18d8631833f5 |  | note | METHOD: Document Review
label | a0f8ab2b-6dcf-5df5-8959-767fa1b307c5 |  | note | – – – – – – – – – – – – – – – – –
label | 0a25376b-0070-5f44-8844-330691e34fdc |  | note | FREQUENCY: Each cylinder and core sample
label | e338d642-7800-5041-bed7-0bc77cb17704 |  | note | – – – – – – – – – – – – – – – – –
label | 61833915-650f-514f-aa49-ecb5239ba1a0 |  | note | CATEGORY: IP
label | cbc59c88-4a88-5189-9a87-8e6d12bbe6ea |  | note | – – – – – – – – – – – – – – – – –
label | d49d2cd9-a502-5776-a92a-523365ccedf4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ae569fab-4fa0-55cc-b0e9-d49f36115717 |  | note | – – – – – – – – – – – – – – – – –
label | d27c5264-9f28-5b9e-83f0-a5e0f09e8fc4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 210be3ea-65a7-54c7-98e2-917f9be1f9d8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection
label | 06960ae1-8b04-55a3-b647-9bd329348265 |  | note | REFERENCE: IFC Drawings 684.08 (b), 684.15, 684.16, 610.31 (a) - (n), 610.32, 610.24
label | c1131f21-6175-5c78-a38d-44dbb3803ec2 |  | note | – – – – – – – – – – – – – – – – –
label | 53744354-cd9d-5919-9283-77e84dfcf4c2 |  | note | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
label | c16fa879-ef15-545c-931c-ce5e5e7de681 |  | note | ○ Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
label | 4eb9e20d-2c4a-5a54-9f69-3a1dbdfb6018 |  | note | ○ For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
label | 0d094c1c-2ed3-5ba4-b059-464cab22558a |  | note | ○ No cracks greater than 0.2mm (exposure classification B1)
label | 0ccf6d38-5216-5511-9a5d-01ed50902453 |  | note | ○ If cracking is observed, complete the Structural Concrete Crack Repair ITP for investigation and repair.
label | 14ebab71-50cd-5595-8a80-ff36bc2b3523 |  | note | – – – – – – – – – – – – – – – – –
label | b3af13dd-684b-5bae-a5fc-31365e7e9ae3 |  | note | METHOD: Visual, Measure
label | f63e661b-219c-5f18-a805-6cdba816f2cb |  | note | – – – – – – – – – – – – – – – – –
label | 18288cd4-4cda-5c2e-965b-5841a041de7f |  | note | FREQUENCY: Each element
label | 0e0ab124-067b-5a15-b10f-d7756edc6ac3 |  | note | – – – – – – – – – – – – – – – – –
label | b3cad2ac-5fdc-5754-8aac-ec865fb08ccb |  | note | CATEGORY: IP
label | fcb1ca40-b800-5d8b-b46c-ea921c5519c0 |  | note | – – – – – – – – – – – – – – – – –
label | a9ebb14c-900c-593f-b5a2-d854b70061d5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2b1e9147-5124-5120-86d4-516d0592cc3b |  | note | – – – – – – – – – – – – – – – – –
label | 3dacdbed-6c1d-5d52-80fc-cd3f752d338d |  | note | VERIFYING DOCUMENTS: This ITP and/or Structural Concrete Crack Repair ITP
date | 40a0bacc-75d6-55d6-aa9f-020eb769cb49 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Fibre Wash-out Test Results
label | 9ac25a4c-94e0-569b-8a27-42581ec26f55 |  | note | REFERENCE: 684.08 (c)
label | 36c37f22-64d3-5439-8dba-7a3392bb5cc2 |  | note | – – – – – – – – – – – – – – – – –
label | 6f26b33a-d975-5331-b418-b775764b8a9b |  | note | ACCEPTANCE CRITERIA: Fibre wash-out test results shall be within 1% of the concrete mix design fibre dosage rate.
label | ac9f6aca-fee9-50ac-a4f7-00c9c8018f7d |  | note | Attach: Fibre Wash-out Test Results
label | 7421480d-f926-5781-9254-879ac8faa377 |  | note | – – – – – – – – – – – – – – – – –
label | 34cc081c-c719-5619-9d5d-1067f86129a2 |  | note | METHOD: Document Review
label | d6c3310c-1de2-5441-9f27-0eb56d850e9a |  | note | – – – – – – – – – – – – – – – – –
label | 82509180-c7b8-58b2-9bdf-ff3891c5843c |  | note | FREQUENCY: Where applicable, each test
label | cb6a145d-4f8a-59d5-9a1d-912251070d0f |  | note | – – – – – – – – – – – – – – – – –
label | 3aa9c63e-2955-5f6d-bab5-6fe0eaa2c6f1 |  | note | CATEGORY: IP
label | d1e48a51-b41d-59f0-9f7d-b67a36fdde5d |  | note | – – – – – – – – – – – – – – – – –
label | 61ba2f7a-f619-5dea-a258-637607bc31cd |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6cbdf6f9-7a77-5322-a0ec-dca8e2e6f38c |  | note | – – – – – – – – – – – – – – – – –
label | 1f3c914e-d2f3-5487-9fed-cd7d896fbfea |  | note | VERIFYING DOCUMENTS: This ITP
date | e242fb32-e762-5c61-93a5-5db6f6f679c5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 As-built Survey
label | d5464442-9ab1-563b-bc5c-1ba4db3e9bb5 |  | note | REFERENCE: IFC Drawings 684.13, 610.47 Table 610.472
label | 014cb766-aa0f-523a-8561-e4aaa0d12186 |  | note | – – – – – – – – – – – – – – – – –
label | b0343076-88a1-5994-a57e-555c9ff9c5a9 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | 436fc4e5-a1dc-5b29-8450-6e037c3eeec1 |  | note | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
label | 44ce43f3-5d64-52cf-873e-2cc442cd6339 |  | note | Attach: Survey As-builts / Survey Report
label | d2808bf0-5858-5218-be34-cd24e5a66230 |  | note | – – – – – – – – – – – – – – – – –
label | d8db774f-9a72-5905-84e5-8f523fcd6bfc |  | note | METHOD: Document Review
label | f2397620-1ef6-5cd7-9fbb-7cb63203dff6 |  | note | – – – – – – – – – – – – – – – – –
label | f32140de-5b2a-5c67-b2e5-419133b3b8a3 |  | note | FREQUENCY: Each element
label | d00395b0-b649-59ea-a995-ecee1be668c9 |  | note | – – – – – – – – – – – – – – – – –
label | 4acf36cc-2422-5f16-a5eb-d36837e7c735 |  | note | CATEGORY: IP
label | e54ed46d-b511-5bfc-96b7-ce3d4538b67a |  | note | – – – – – – – – – – – – – – – – –
label | c70b3878-8a6f-5890-bce4-9b8b15ad9ad6 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 74136cab-b1f7-5ac9-a7e3-d9785f8a7877 |  | note | – – – – – – – – – – – – – – – – –
label | bbe92c4f-dc75-5227-abfa-a5191e83cced |  | note | VERIFYING DOCUMENTS: This ITP
date | 00c0753f-ffa4-5106-8680-ac06ae126d34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 853c6ba2-6060-5043-a1c0-0078a659b4ff |  | note | REFERENCE: MRPA Quality Management Plan
label | 827b4977-193c-5b39-8969-fb749127fcea |  | note | – – – – – – – – – – – – – – – – –
label | 8d26db77-0385-5de1-96c7-c471b8012c80 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | c2dd510f-667b-52d2-91dd-1c0e5a8bb64e |  | note | – – – – – – – – – – – – – – – – –
label | a2182702-deba-58a8-8130-7245fec25c94 |  | note | METHOD: Document Review
label | 94f0347a-a1bd-57a8-85e2-7d1bcbd539c0 |  | note | – – – – – – – – – – – – – – – – –
label | 244bf96c-90ed-58d2-a30f-170e1d311b4f |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0c4e13b8-0128-576c-90b4-5edf8121e8f4 |  | note | – – – – – – – – – – – – – – – – –
label | e78e2425-a260-5a96-b61d-d02bf0777ed9 |  | note | CATEGORY: HP*
label | a8183012-ac07-5dd1-8b40-e98b55f29dd8 |  | note | – – – – – – – – – – – – – – – – –
label | 53d12d7d-4e7d-5d4b-b7f2-bbe9a999201b |  | note | RESPONSIBILITY: SE/PE/SPE
label | d4888eca-e2b1-51e2-a4ad-7ab62864a9e3 |  | note | – – – – – – – – – – – – – – – – –
label | ea0d7d6a-bce0-5aed-8775-a3c7293f1e00 |  | note | VERIFYING DOCUMENTS: This ITP
date | e16bcbd4-58b8-55c3-a282-a78a76ff1422 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 127da40c-333e-5c09-bc85-34e1e9b94ff1 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8ee6a6d0-0092-5082-858c-11deed5ffdf2 |  | textbox | Name:
text | b7f24529-373d-548a-9cea-794315aac08d |  | textbox | Position:
date | f8d2b640-fdd9-5fdf-bd8a-171649069132 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-107-RAIL-SSB-OHLE Installation | itp |  |  |  | Yes | ITP-107-RAIL-SSB-OHLE Installation Rev 0 | 0f719e80-7a79-4546-8381-66f9242bab1a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f5c48fde-3c25-50e8-b1bf-59cc052e5712 |  | note | Document Title: ITP-107-RAIL-SSB-OHLE Installation
label | 8a6e91ce-bed3-5ec5-8eee-2485ffbd8da6 |  | note | ITP Description: OHLE Installation
label | 08914925-1468-5ecf-9514-489f6f9bc90a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 2fda529e-521d-5d89-907b-b5ac4fdfbfd4 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 4815e592-e6f9-5052-ace9-5fc5db0fda3c |  | note | Revision Number: 0
label | 113b297d-106a-53a2-a7f2-68e12a1ca366 |  | note | Revision Date: 26/06/2023
label | 80ff0387-a9fa-5aac-a5c2-673cc0d97262 |  | note | ITP created by: Nikhil Siram
label | 39233005-88ea-5c29-ac4a-75b5cbec119f |  | note | 1.1 Overhead Line Electrification
label | 176dd747-ed18-5a73-9470-61f2cfc9fddf |  | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
label | 3381191d-8d69-5a0d-a6aa-553c96923249 |  | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 01d92440-c86a-5f12-bf55-7947c702eed2 |  | note | Reference: VRIOGS 001 AS 4100
label | 071e02ad-c894-567c-9441-7082e39664ce |  | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
label | 10b98818-a889-5dff-bcbb-8c8137d756ed |  | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1
label | 71f3ba6a-df9a-5aec-a9a8-22eef501a124 |  | note | 1.4 Fabrication of Steelwork
label | 8ce225b9-ad39-5101-a05b-ac39074a5106 |  | note | Reference: VicRoads Section 630 January 2023
label | f87025be-1cc4-5839-80d4-da3a67d40f65 |  | note | 1.5 Electrical Networks Standard Electrical Networks Principles and Performance
label | 09338ec5-c832-5a93-84c9-6aff002a086d |  | note | Reference: Structural Steel Work - Fabrication and Erection
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components and Fasteners
label | 7f48b0e5-a05c-5e69-bbd8-7fb54e76d029 |  | note | REFERENCE: IFC Drawings
label | 00933c54-31bc-5952-982d-e7c48bd68d5d |  | note | – – – – – – – – – – – – – – – – –
label | 56d18367-3d59-5932-b91b-bd7426e435d7 |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | d3796ec1-7fe9-58fa-b856-04b7afdaa620 |  | note | ○ Typically this consists of but not limited to:
label | b4022e53-fca6-5658-a83b-0b252120c4f8 |  | note | i. Completed fabrication ITP
label | 1ce6e042-a72e-5b3d-a5e6-1922ce316e68 |  | note | ii. Weld Procedure Specifications
label | 6fdec736-7b88-5750-aef7-d8e9ab5d8ba3 |  | note | iii. Weld Procedure Qualifications
label | d242421e-deb3-50a7-8383-c1ac535ae9ea |  | note | iv. Welder Qualifications
label | 7b4ff8cd-4ba0-5964-bfa3-0d58350cbd3b |  | note | v. Material Certificates
label | bdcf8ba9-56c1-53c1-b756-6728462d2f0b |  | note | vi. Coating certificate(s)
label | d24cd7dd-235d-5070-80c8-149249417d3c |  | note | vii. Non-destructive Testing (NDT) Reports (if any)
label | 61925f5d-bcc6-5155-a106-c0eab1814d32 |  | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 0079e540-8b83-5ba3-bd63-4105bf53fd59 |  | note | ○ Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
label | 78287339-16fa-5a29-9fc3-0ca4aae85c4a |  | note | ○ Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
label | 71d132c1-0e6d-5f8d-b6f7-90da3817d9e4 |  | note | ○ All bolts nuts and washers are hot-dipped galvanized.
label | 1c6d773d-eacb-57ec-9708-c94336a351df |  | note | Collate: Structural Steel Quality Assurance Documentation.
label | 97ad8655-139d-584d-9483-8bc806287015 |  | note | Attach: Collated QA documents in ConQA
label | 22db6e69-ecb5-5f21-b61b-cf59eaccc384 |  | note | – – – – – – – – – – – – – – – – –
label | d6862f54-7f02-5a05-bb7e-c36094dc549d |  | note | METHOD: Document review
label | 5d98d8f7-a452-597f-a8d2-14627b1f7aa0 |  | note | – – – – – – – – – – – – – – – – –
label | 87acce17-c919-5fa7-885c-76630bbe905a |  | note | FREQUENCY: Where applicable/ Each element
label | 4547958a-38a7-53d3-8cf5-df14b3afa004 |  | note | – – – – – – – – – – – – – – – – –
label | 91c02744-1e3f-54cf-aa31-3eddc35ac389 |  | note | CATEGORY: HP
label | 8ada2bff-a197-5d82-93e2-2be7d406a0e0 |  | note | – – – – – – – – – – – – – – – – –
label | 2e790551-8b94-58d4-9e5d-233a389a2501 |  | note | RESPONSIBILITY: PE
label | 08b32966-6e9e-5f79-a5d3-c694cf3e181d |  | note | – – – – – – – – – – – – – – – – –
label | 172603bb-f0a9-5a52-a5dc-f89f45dbd3dd |  | note | RESPONSIBLE PERSON:
label | 25803825-3f79-5c41-bb0f-fc8eb531e7f0 |  | note | – – – – – – – – – – – – – – – – –
label | 947e00e2-2a18-5dbc-80a2-ad1e237bafd7 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | c6f46720-490f-5b81-a774-a5a26f83e34c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Bolted Connections Using Direct Tension Indicators (DTIs)
label | 4db1b464-aa00-5075-b7f6-f00be9ccb1db |  | note | REFERENCE: AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
label | 52669e31-a66e-5b21-8099-b6ca16b92cd5 |  | note | – – – – – – – – – – – – – – – – –
label | f845548c-2311-5d45-81ab-5fcbb1048745 |  | note | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 6681e48c-3121-5b5f-a75d-5fdd0ae1e729 |  | note | i. technical data sheet or information on the product
label | c40d2749-e791-54b8-8e85-8f9712d6a7c5 |  | note | – – – – – – – – – – – – – – – – –
label | 9b97709c-b4ba-5651-8c3c-2912c261c9d7 |  | note | METHOD: Document Review
label | f6d2733e-da09-53ce-94bd-7ff867a0a2ea |  | note | – – – – – – – – – – – – – – – – –
label | 8ba368e0-803b-55f2-8d54-e18552b14ae3 |  | note | FREQUENCY: Where applicable/ Each element
label | 20282071-3896-567c-9c5a-ed7894a1a286 |  | note | – – – – – – – – – – – – – – – – –
label | b99a4a83-4b40-5c57-bcaa-de4dd5d18a72 |  | note | CATEGORY: HP
label | e4dffe7d-5012-51f4-8915-d8d49a51a87e |  | note | – – – – – – – – – – – – – – – – –
label | 3cea4ccc-44e2-5f31-b532-6d8ee80a4d91 |  | note | RESPONSIBILITY: PE
label | 3f481267-29f5-5b20-b202-3c5119f9ff11 |  | note | – – – – – – – – – – – – – – – – –
label | b040a363-089a-52f8-ab58-08caf5364ff4 |  | note | RESPONSIBLE PERSON: MRPA Engineer
label | 07e41947-f445-55e7-ae0f-be5d912ba697 |  | note | – – – – – – – – – – – – – – – – –
label | 28bfff6a-19d1-525c-bbc0-22a1b800edc0 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | b2b18a3c-2dc6-5b02-840b-7f8cd0de85f8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Overhead Wiring Small Parts Steel and conductor wires
label | 7ec7c784-0d5f-55e9-b0dc-d990b9413187 |  | note | REFERENCE: Relevant MTM Standard Drawings
label | af0f832a-494d-5b7a-80e3-cc10fee4d509 |  | note | – – – – – – – – – – – – – – – – –
label | f62663fe-5197-51dc-a8b5-4149ef131d3d |  | note | ACCEPTANCE CRITERIA: Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
label | 5add9b89-e1d5-56fe-9dbc-e1ac13a53cfe |  | note | ○ Deliveries are to be inspected to match the purchase order
label | f4a781d2-e239-5ee4-9592-bc20bc84f8f7 |  | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
label | f03739a6-0fb9-5e06-a89e-54f16f877097 |  | note | – – – – – – – – – – – – – – – – –
label | 5d7d804e-f7a6-59c7-bc3d-160c6d540482 |  | note | METHOD: Visual Inspection and measurement
label | 94f9e43d-d45d-55bc-a735-7dbd08c8206b |  | note | – – – – – – – – – – – – – – – – –
label | 880de731-27e0-5cef-b95b-cafae84bf766 |  | note | FREQUENCY: Upon delivery
label | b71bd415-b1b4-5906-afbd-cb1a7a190422 |  | note | – – – – – – – – – – – – – – – – –
label | ee7086c4-7c92-51d9-b9c6-4c0716e7bc33 |  | note | CATEGORY: IP
label | 3ffa9fab-83e6-5176-87ab-7f4a34c31bab |  | note | – – – – – – – – – – – – – – – – –
label | 9c05a891-78df-59f0-b291-4505d0677208 |  | note | RESPONSIBILITY: PE
label | 8e52345c-e6f7-5b5b-815b-78ab79e4db4b |  | note | – – – – – – – – – – – – – – – – –
label | e763123f-3b3f-5479-9ba2-0546c71a6824 |  | note | RESPONSIBLE PERSON: MRPA
label | c87d283d-4a06-55b1-a169-286a774a41f4 |  | note | – – – – – – – – – – – – – – – – –
label | 789c61d5-dfab-548a-8fca-d905d1f624b5 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | a2bcd3ef-c709-53df-8094-372c67252d14 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Grout
label | 8cbec756-ffcb-5e1e-bc37-72cee335bbeb |  | note | REFERENCE: IFC drawings
label | b6e0237c-2b3d-5921-af23-5e85ee179411 |  | note | – – – – – – – – – – – – – – – – –
label | 2592bc8f-30f5-5b26-b178-73dd19272c8f |  | note | ACCEPTANCE CRITERIA: All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
text | 59918e31-9962-51eb-9303-6bbbf5823426 |  | textbox | Enter: Teambinder Material Approval number
label | 0eb4fd4d-968f-5b55-b094-639ceb753554 |  | note | – – – – – – – – – – – – – – – – –
label | bce2337f-7fca-5c30-bb68-a00b474940ba |  | note | METHOD: Document Review
label | ec7e4b40-7807-5cd6-925a-3a1003159608 |  | note | – – – – – – – – – – – – – – – – –
label | bdd22932-43e9-56c1-a3fe-ed2720bc22f6 |  | note | FREQUENCY: Where applicable/ Each element
label | 3a89f8b9-db13-511d-9a1a-5a1904c8ce5c |  | note | – – – – – – – – – – – – – – – – –
label | a0feacb8-3c68-5b7b-a35a-e3f2c7c1621b |  | note | CATEGORY: HP
label | e834f7e8-7cec-5fd2-b7ce-4cc670890ec9 |  | note | – – – – – – – – – – – – – – – – –
label | dccf37e8-c7da-54b7-8ef8-72425965afff |  | note | RESPONSIBILITY: PE
label | 29f77572-f0cd-5d85-a995-e8d381e63064 |  | note | – – – – – – – – – – – – – – – – –
label | 0c33f82c-a0cf-5368-b97a-813e37ccc2c0 |  | note | RESPONSIBLE PERSON: MRPA
label | b64ae4f0-8309-5ac6-beae-84527b3baba2 |  | note | – – – – – – – – – – – – – – – – –
label | 646a91c3-e6ca-5fa7-867c-4612eb20527c |  | note | VERIFYING DOCUMENTS: This ITP/ Material Approval
date | 607fd64a-fd95-5552-bc20-f101e27fcdd8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Installation Methodology & Works Method Statement
label | 06b87b39-b938-596e-9321-8e403cf57f97 |  | note | REFERENCE: AS5131 Clause 11.2.3
label | 48f20d59-fd7a-5d42-8b5d-02fb6d200c07 |  | note | – – – – – – – – – – – – – – – – –
label | 37ff175d-2934-514f-a960-15769eacc79a |  | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 40ad14c5-3ef3-5c3d-8d94-12c56986d644 |  | note | – Transported to site;
label | 5c163383-84b3-515d-9912-2e4901dd64c7 |  | note | – Handled on site;
label | 1dfbef54-4b81-5147-830b-4015ca392aa5 |  | note | – Installation Procedure (subcontracor ITP's);
label | 08abbfa4-c3c4-54b4-9c0f-9de2833eb84a |  | note | ○ Submission of Work Package Plan and MRPA approval and acceptance.
text | cd35c9d6-b307-58a9-a2c1-d8c88ef6b6cd |  | textbox | Enter: WAP number
label | e544f331-3e6c-5ddc-a627-2d9be45c75a5 |  | note | – – – – – – – – – – – – – – – – –
label | 4e12ea3f-6e11-5515-8890-e067e9314b03 |  | note | METHOD: Document Review
label | b3b2deb4-5f13-5207-bd52-b41177191892 |  | note | – – – – – – – – – – – – – – – – –
label | bea95289-5fe9-5e1a-976e-6e22e87d6502 |  | note | FREQUENCY: Prior to Works Start
label | d36b72c5-a9ca-5810-b78d-f7a428c728a8 |  | note | – – – – – – – – – – – – – – – – –
label | c966f8e6-2634-5da6-9bd0-0b3b368eb0f6 |  | note | CATEGORY: HP
label | aae3543e-3a4a-5514-bbdb-5680d264a22e |  | note | – – – – – – – – – – – – – – – – –
label | df3ce3e0-f979-5e2e-a959-3dba3c7c6b79 |  | note | RESPONSIBILITY: MRPA/CAT5
label | cdfdafd3-96b9-5765-b057-9dee4a8365c2 |  | note | – – – – – – – – – – – – – – – – –
label | 03a40938-10d7-527d-8b40-4be2c68694bf |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 27fa005f-f52e-5efb-bc16-911556e8d138 |  | note | – – – – – – – – – – – – – – – – –
label | b4ca5da0-8f0e-5e8a-ae4f-cecefac9a6fa |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 8f1de70a-1110-55bb-bc02-1b9c6cce1a0c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Approval of IFC drawings
label | 03726548-a028-59b2-bcda-9129ad3a0256 |  | note | REFERENCE: Contractor Design Management procedure.
label | 80f6003a-756e-5ad0-8b2a-98289d1b0b95 |  | note | – – – – – – – – – – – – – – – – –
label | 48dbc9e2-692e-5f94-b2e8-f043e8a731b0 |  | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 5e567a32-445b-53f7-bf70-57f7c7b2534f |  | note | – – – – – – – – – – – – – – – – –
label | 0e1f38c5-61c5-5709-b3d8-bbfaaea13d8f |  | note | METHOD: Document/Drawings Review
label | cffcb202-799a-53ba-9cfc-d1232efc2fea |  | note | – – – – – – – – – – – – – – – – –
label | acedcaa6-86be-5398-839f-cdc90bd6960a |  | note | FREQUENCY: Prior to Works and at regular intervals.
label | 7db8c5b3-0682-5ab5-9ded-0240dbd52567 |  | note | – – – – – – – – – – – – – – – – –
label | 2d9ccd84-c15d-5a80-9836-dfab72db52dd |  | note | CATEGORY: HP
label | 213a3a08-5961-5bd9-9256-ae3d4c507e34 |  | note | – – – – – – – – – – – – – – – – –
label | 23e993d6-81f4-59b9-aafe-45ce7cf6e160 |  | note | RESPONSIBILITY: MRPA/CAT5
label | ee6936d4-378f-5607-a399-b2c1eeaa99be |  | note | – – – – – – – – – – – – – – – – –
label | 743d1855-a3e2-5b1b-b885-b88fa60f4450 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 06e730f3-19f5-5366-a52a-cf743b1e7ebe |  | note | – – – – – – – – – – – – – – – – –
label | 029c51df-c5f7-5d86-90ae-4e85f30dc737 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | cc0e6ffc-3da0-5255-8203-464d873dee77 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Cantilever assembled.
label | daeb9e86-0c20-5572-ad60-b9a07c463071 |  | note | REFERENCE: Cantilever assembled as per IFC design.
label | 1888c66c-e1e9-511c-8004-523fee4912e2 |  | note | – – – – – – – – – – – – – – – – –
label | c668f5c3-7120-5354-a07a-bc361cf78088 |  | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | ae6c7d48-d5bf-565f-a12a-c8ed5fa415ac |  | note | – – – – – – – – – – – – – – – – –
label | 80012fcd-ffb9-5f9f-934b-115dd36f6587 |  | note | METHOD: Visual, Document Review
label | bd6f4b22-7ee8-5653-848c-3d48be06f3a5 |  | note | – – – – – – – – – – – – – – – – –
label | 470ddab8-b23c-5fca-8e5b-00fbd3790630 |  | note | FREQUENCY: Each Task prior to works start.
label | 2507c14a-c766-53a7-84b1-be065cd92b61 |  | note | – – – – – – – – – – – – – – – – –
label | d197c8b2-0d31-50fb-af67-be3e1bbba8a9 |  | note | CATEGORY: IP
label | eb5c3db2-f4df-571b-9cd1-35e64bac6d1b |  | note | – – – – – – – – – – – – – – – – –
label | b6e246cd-2103-562d-b224-4582a1174862 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 5d3de08b-51c0-5a0f-bd74-dae92dd024c3 |  | note | – – – – – – – – – – – – – – – – –
label | 6301e623-44a5-598e-baf5-44ec96908fe3 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | dfe398d2-bb3c-5b0f-8ec1-e96e92e21eef |  | note | – – – – – – – – – – – – – – – – –
label | 20ea961f-a2e2-5337-bd91-c47b37f12a21 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 56f082f9-1dc3-5866-9677-0989d3bfa7c7 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Mast Installation
label | f836838d-5917-5ad3-9ee2-90240535423c |  | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 68c217af-d910-5478-9efa-19bfc35836dc |  | note | – – – – – – – – – – – – – – – – –
label | f9678e6a-2f79-51d7-bd8a-03bf55e62cdc |  | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
label | 037314b6-5081-520d-b99f-21faf8c83299 |  | note | – – – – – – – – – – – – – – – – –
label | 3e0815a3-04b5-5400-abdd-289767b6dc79 |  | note | METHOD: Measure, Visual
label | f4e25d06-666b-5281-9236-abf99b71f042 |  | note | – – – – – – – – – – – – – – – – –
label | 4980fdcb-d940-5c5a-8ec9-138410f4f7d8 |  | note | FREQUENCY: Each OHLE Structure
label | 507d6d56-c89d-55de-adb7-f8b8ef37974d |  | note | – – – – – – – – – – – – – – – – –
label | 7e02f24e-93b7-5cb5-9d76-ab073d43984a |  | note | CATEGORY: IP
label | 54ec0c94-6f99-5d10-8480-78367384473a |  | note | – – – – – – – – – – – – – – – – –
label | cef86f02-446d-554b-9013-1eefb4bb2dfe |  | note | RESPONSIBILITY: CAT5/MRPA
label | 2b3feba3-cb56-5882-834e-3a5bccc09705 |  | note | – – – – – – – – – – – – – – – – –
label | aaa02d86-fb6f-5f7b-8b96-7612ecd4b7b2 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 704023ca-530b-5995-921b-c2777a64404a |  | note | – – – – – – – – – – – – – – – – –
label | 62802c72-180c-5c29-a35c-291303fedc1c |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | ed1dee77-fbc9-5f86-8f70-bce51fe42fcb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Cantilever installed.
label | 63d96ecf-1fbb-59d5-8961-81573cd45d63 |  | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | ba36bfb7-1225-5af7-8a8f-68cc12af69ad |  | note | – – – – – – – – – – – – – – – – –
label | bd6ea88d-50ca-5b65-a5f9-9e611a153754 |  | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
label | b8c1f307-9831-55a2-bee5-79e4e0e6a71e |  | note | – – – – – – – – – – – – – – – – –
label | b6409d62-2499-53ca-af92-3f9dab2ea4e7 |  | note | METHOD: Measure, Visual
label | 8adbfca9-da64-5043-bc16-7722def07645 |  | note | – – – – – – – – – – – – – – – – –
label | fd71d78b-82a5-5b24-b33f-a362b37effbb |  | note | FREQUENCY: Each OHLE Structure
label | 098db34e-7b9e-5093-bb69-2b79727519dc |  | note | – – – – – – – – – – – – – – – – –
label | 6aa2bda7-cc38-5bad-bbca-1ebbea093180 |  | note | CATEGORY: IP
label | 4cb4b7d7-87bd-5158-a5e2-44e49af7d4e1 |  | note | – – – – – – – – – – – – – – – – –
label | 824f6fc9-1337-5ab6-962b-f62214d32b35 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 14d4c480-973a-588b-a232-e4d248a51cc1 |  | note | – – – – – – – – – – – – – – – – –
label | 9230be26-a0c6-5611-bb52-710bbd53826b |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | cffc2974-a7d6-51ff-8265-3b008ca5e886 |  | note | – – – – – – – – – – – – – – – – –
label | 63cc700a-bc8e-53e3-8483-d679f2787207 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | a582ff00-aa80-58b8-a13a-49bd30f52774 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Bearing type Joints TB Friction type joints TF
label | 6db97c23-c0fa-5fb1-be9c-70968f6cbe4d |  | note | REFERENCE: IFC Drawings
label | d2aebb1b-5445-5b62-b8db-e2f7746e15a2 |  | note | – – – – – – – – – – – – – – – – –
label | a99ab9c1-b1fa-5766-a4c0-8c5d5a6473bb |  | note | ACCEPTANCE CRITERIA: BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
label | fc48ca2e-57d4-5cff-a4ef-e90bb19b30f8 |  | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
label | bbb1dd51-6e75-52f6-9b9e-ea8b0860391b |  | note | – DTI squirts are to be visible for inspection
label | 9ad37ab9-3e69-5320-8b85-1ce7155597de |  | note | – – – – – – – – – – – – – – – – –
label | 97ed00a7-e45e-5b7f-a415-2407f14520ad |  | note | METHOD: Visual
label | 2f94ea13-5f1b-5b16-b3a3-9cd6a0b20513 |  | note | – – – – – – – – – – – – – – – – –
label | e574ca61-f92a-5dbc-8067-fb7673ddc1e2 |  | note | FREQUENCY: Where applicable/ Each element
label | 8e4f2c72-e42c-5b30-91a2-6270bbd989ae |  | note | – – – – – – – – – – – – – – – – –
label | ff7e206b-380f-58b3-925f-91183260d963 |  | note | CATEGORY: IP
label | 95464445-1f82-5f32-8ddf-cd5c306c32f7 |  | note | – – – – – – – – – – – – – – – – –
label | 9d1ec060-98ea-5f52-b58a-87dad30ad5bf |  | note | RESPONSIBILITY: PE
label | 8f3a639a-3e9c-5133-bdd9-6e35bf2942fe |  | note | – – – – – – – – – – – – – – – – –
label | 6d1a3669-e41b-5fc5-b4cc-d7a31bb276b2 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 09fc2020-7d73-5db0-a24c-380464188db8 |  | note | – – – – – – – – – – – – – – – – –
label | f6014d24-465f-5d18-8510-6a382b46a667 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | d9b97650-44c8-53b7-8e9d-d6d88d90c790 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Install SPS to correct height / position relative to track
label | 1aa57f7e-da97-5849-9950-95863f415a77 |  | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 746ec6b0-b0c9-5821-82d7-39d4f4ea371d |  | note | – – – – – – – – – – – – – – – – –
label | 24d36fd1-927a-5922-830c-6b2fab3b7b21 |  | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | 2273c080-059d-5b4b-b950-0e9834558eb0 |  | note | – – – – – – – – – – – – – – – – –
label | 3e946535-ced9-5d18-8f04-767201e12455 |  | note | METHOD: Measure, Visual
label | 63f7aa02-4d16-5f7c-8990-cd03d7c1975f |  | note | – – – – – – – – – – – – – – – – –
label | 60002949-78cb-5169-bab2-5ef97543c714 |  | note | FREQUENCY: Each OHLE Structure
label | d7c91213-0dfb-5197-be3d-ee5b864bbe91 |  | note | – – – – – – – – – – – – – – – – –
label | 48c4eb36-f553-56cf-8815-81a3e2fbbf0c |  | note | CATEGORY: IP
label | 6f61e8df-9787-59cc-a65f-d9d85f86c271 |  | note | – – – – – – – – – – – – – – – – –
label | 9e6c836c-06e6-52a6-b10c-e45f85450158 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 29c48d56-e44b-5f29-a66d-8a74f3506a8f |  | note | – – – – – – – – – – – – – – – – –
label | f5b08423-6c6c-5c91-b104-a09e63a80a34 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 9f2723cb-97cd-56f5-9908-d1fc06d47362 |  | note | – – – – – – – – – – – – – – – – –
label | aa92441f-e490-58a2-a0a5-969bc3bbee51 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | f5182cb1-f181-5513-9d3d-441600c2c660 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Cantilever checked once installed.
label | 40c753a0-58ab-5b44-808f-dddcb5e7e4e8 |  | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
label | da60ed6f-c936-5bcc-a57f-9b4678482921 |  | note | – – – – – – – – – – – – – – – – –
label | a8eb0c5a-3caf-5aac-8d3a-66d8852fcc35 |  | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
label | 7fdd5fe8-768c-5619-997c-c71bbc5de732 |  | note | – – – – – – – – – – – – – – – – –
label | 83973b5d-f32d-52ce-bf3b-e888ef4d37ac |  | note | METHOD: Measure, Visual
label | e364e8ec-52a9-5899-b31e-d3e6b1450e58 |  | note | – – – – – – – – – – – – – – – – –
label | 1c47c9af-6eb8-5e5e-a111-c235fa38654e |  | note | FREQUENCY: Each OHLE Structure
label | 314b524d-9443-576e-8c02-70bc26f951e2 |  | note | – – – – – – – – – – – – – – – – –
label | a381d6fd-6e75-5ff7-8d8b-4308a9f89154 |  | note | CATEGORY: IP
label | 28589d8b-8b15-5633-a26b-b30d86da68c3 |  | note | – – – – – – – – – – – – – – – – –
label | a9bba10a-93fb-56ef-a3aa-d1a54a4ccbe7 |  | note | RESPONSIBILITY: CAT5/MRPA
label | d1ddbac9-a08e-5ec1-a6a2-165325626726 |  | note | – – – – – – – – – – – – – – – – –
label | ea37a33a-2397-5ca6-8a43-e29c5d83565a |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 42abe06a-f106-5ee8-a54c-b0b4454cdc05 |  | note | – – – – – – – – – – – – – – – – –
label | ab4afdc7-79f3-5948-8dd7-877f8cc91cb3 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 7be22012-1704-5bc2-8afd-e167b8680a59 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Base Plate Grout
label | 472f013c-4a6b-5a85-be79-2404a48328fd |  | note | REFERENCE: IFC Drawings
label | 26622f3f-3cf4-5b4f-bc6f-97d06b70d8c7 |  | note | – – – – – – – – – – – – – – – – –
label | 9a50a172-1b43-583c-93d5-05ada46d320d |  | note | ACCEPTANCE CRITERIA: Grout to be mixed as per manufacturer TDS.
label | 2994292e-ee6f-5db6-8e15-94832a57b902 |  | note | ○ Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
label | e97e2710-d7a5-5163-a6ae-ce8e0b3fc093 |  | note | – – – – – – – – – – – – – – – – –
label | 2656c8c8-57ee-5718-9449-0806de149355 |  | note | METHOD: Visual
label | 507c3fdb-f67c-5bf1-a3e8-5980839eec4a |  | note | – – – – – – – – – – – – – – – – –
label | 7dc93e0d-4fbc-58f2-b55a-9e3492fab876 |  | note | FREQUENCY: Where applicable/ Each element
label | 52858881-4be0-5782-aa3d-3da75ccb6e0e |  | note | – – – – – – – – – – – – – – – – –
label | 970487a6-9901-59af-b0dc-916480ca581a |  | note | CATEGORY: IP
label | d702fe00-4911-5d06-9208-4f382d322edb |  | note | – – – – – – – – – – – – – – – – –
label | f5597ac9-ce74-5cc1-9db0-a993d667a75a |  | note | RESPONSIBILITY: PE
label | 0324028f-6096-5299-904d-33535fb67fba |  | note | – – – – – – – – – – – – – – – – –
label | f7d779ba-797f-5c7c-ad40-339c51808db4 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 599c726e-cf27-557d-bc32-9c46fb003506 |  | note | – – – – – – – – – – – – – – – – –
label | b5014127-7ee4-54e4-94e6-fc4455b14681 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | cd80f9fc-2443-5d68-864d-c9830f0bac1f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Installation of wire supports at the correct height and stagger
label | fcc96006-b7d9-5045-9c6a-bff44f0e8475 |  | note | REFERENCE: Install as per design
label | 280a2a25-f8e9-5df3-b7a5-98e751d24fd6 |  | note | – – – – – – – – – – – – – – – – –
label | 4a69bea1-4ceb-550c-80a6-a754f6269740 |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | 7828dbf0-83cc-5fda-a221-0cbe8a96dc6c |  | note | – – – – – – – – – – – – – – – – –
label | 2d7e927e-9eb7-5dcd-b79e-143c5caa97af |  | note | METHOD: Visual
label | 46e231e1-2f7a-5fdd-89b0-1a5f494773f3 |  | note | – – – – – – – – – – – – – – – – –
label | a12c7f09-1e0a-5ffe-b878-fc9fd1a5ea08 |  | note | FREQUENCY: Each OHLE BWA Structure
label | 9e2ca214-4204-58f7-9b2f-c7bd8467f5c0 |  | note | – – – – – – – – – – – – – – – – –
label | 1452ba88-12e4-5ed7-8212-891b7a379d29 |  | note | CATEGORY: IP
label | 5fc422d0-e59a-581c-aec0-647c1ebe39af |  | note | – – – – – – – – – – – – – – – – –
label | a3dc6e6e-d59b-5498-bf0d-7897a5aeeb43 |  | note | RESPONSIBILITY: CAT5/MRPA
label | f129c705-a3f6-5445-be75-3d39bd50eeca |  | note | – – – – – – – – – – – – – – – – –
label | f22bcfc8-7f72-52ae-8e9c-7a8127b93758 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 441bdb42-d37c-5f43-b9b8-b5c7af05983e |  | note | – – – – – – – – – – – – – – – – –
label | 62286e36-3d2f-5e5b-bad2-aa533677321b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 5f80cca7-6405-570a-a7b9-260670117718 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Install to correct tension
label | 4abace70-0f8e-5acd-bc8f-55a4e7fb68f6 |  | note | REFERENCE: Install as per design
label | e54dbcee-131d-5800-8db2-dbff56ba7e62 |  | note | – – – – – – – – – – – – – – – – –
label | 23aa9df0-9f15-501f-9b90-d8fd20150036 |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | 4f6b6484-4507-5ae1-92fe-998447d3f299 |  | note | – – – – – – – – – – – – – – – – –
label | 8c9f5641-8693-5460-b218-5409bdfb95fc |  | note | METHOD: Visual
label | bd8714e4-62b2-5e33-b69f-402515d09f22 |  | note | – – – – – – – – – – – – – – – – –
label | e1b74f73-e958-5e50-8312-2359030d10c1 |  | note | FREQUENCY: Prior termination
label | 08ab6b8e-c616-5561-8fb1-02f455c366cf |  | note | – – – – – – – – – – – – – – – – –
label | 3d22de95-1796-5a89-b20e-2eb3b553c309 |  | note | CATEGORY: IP
label | cc42afe4-d31b-513c-9082-ec464cf53a9e |  | note | – – – – – – – – – – – – – – – – –
label | e7e154a3-ecdc-5d10-aaa5-95b26004aeee |  | note | RESPONSIBILITY: CAT5/MRPA
label | 886784fe-6e30-5603-8a38-159aa7bd6778 |  | note | – – – – – – – – – – – – – – – – –
label | aa28529a-6d96-5f42-8175-17544065b37e |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 26388024-0aa3-5153-aed0-6dcce5b74fb3 |  | note | – – – – – – – – – – – – – – – – –
label | 9a717416-0a02-5029-84b1-2f955d03b8c0 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 073ee182-b453-551e-aefb-0cc230428632 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Defects/Temporary Works
label | 8e5b20f0-aedd-50e0-8837-4cfda6888ff9 |  | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
label | aad3ad53-f78a-527d-adca-8165b43469e7 |  | note | – – – – – – – – – – – – – – – – –
label | 81985eee-e375-5967-be50-c81a1e62f180 |  | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
label | e48dc262-11c3-5c99-9c97-0d216689ff91 |  | note | ○ Defect list to be provided at the end of Occo identifying planned work to rectify
label | 5977aa75-3312-56c1-9e8e-5924f6be181a |  | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | 76220dc5-f144-5a51-bd04-3a784d59af62 |  | note | – – – – – – – – – – – – – – – – –
label | 5481a2c3-3c24-5d8b-98c5-c862f8431513 |  | note | METHOD: Document Review, Visual
label | 521da5ab-6de0-5266-9cc1-a78c2cae07b3 |  | note | – – – – – – – – – – – – – – – – –
label | 778add88-1405-5cef-bcca-10f2c4e36c96 |  | note | FREQUENCY: Each OHLE Structure
label | 532b9e49-a50b-5724-aa64-903f33276c7b |  | note | – – – – – – – – – – – – – – – – –
label | 1f9914fa-6f8e-50cf-8a61-8d3c02373bf8 |  | note | CATEGORY: IP
label | 90b4d32f-bfae-59d8-a589-b6b32fc559b2 |  | note | – – – – – – – – – – – – – – – – –
label | e4f0aefb-32cf-544d-9375-84f3aed21a98 |  | note | RESPONSIBILITY: CAT5/MRPA
label | cf49f667-b651-5b46-95fe-a85df82be67b |  | note | – – – – – – – – – – – – – – – – –
label | f217e66a-1eb5-551c-9e7c-73249d974583 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 324d62a5-257d-5c04-afd2-97e7d48ce97d |  | note | – – – – – – – – – – – – – – – – –
label | 8e1a2245-0360-5a7f-b8c3-162450aa96c9 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | c5bd15a4-3b3d-510b-bdc3-3cab8e683e9b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
label | 5dcd57a0-6070-5d1f-a40d-2e8287bbeefc |  | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
label | 6bf6fc30-c69a-539c-9977-691915cd71f0 |  | note | – – – – – – – – – – – – – – – – –
label | 66f07e6c-8a1a-556a-8a60-4594e4b6ca7f |  | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client. As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | af95d27b-b40c-5708-bf58-5a79d926b22d |  | note | – – – – – – – – – – – – – – – – –
label | 73bd7905-e7fd-5468-acd7-610163b1f206 |  | note | METHOD: Document Review, Visual
label | 606ab702-d632-54a7-ba38-87bb95c74aa8 |  | note | – – – – – – – – – – – – – – – – –
label | 3acabf6d-d016-5cf0-abbb-fc5e2376d428 |  | note | FREQUENCY: Each OHLE Structure
label | 659b7a70-476a-5377-81ba-24dca963c751 |  | note | – – – – – – – – – – – – – – – – –
label | b0755c96-53de-56a6-9e35-e4ced03522de |  | note | CATEGORY: IP
label | 9198c3c8-6f66-5089-ad81-82e29ff048d7 |  | note | – – – – – – – – – – – – – – – – –
label | 7c01eef9-c55b-5073-9513-04da0545460d |  | note | RESPONSIBILITY: CAT5/MRPA
label | a87b5892-a74c-58ad-8554-38ee502e4c51 |  | note | – – – – – – – – – – – – – – – – –
label | ff182eaf-28a9-5501-b252-a12e7a88e9f0 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 362d1d17-b1dc-54fb-84ce-01367bc2a177 |  | note | – – – – – – – – – – – – – – – – –
label | 1b5e274e-d16e-523e-ade3-a5495354be6b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | faf34a72-f863-5153-9589-feae71cf3c71 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 8a14dcbe-13dd-5762-b42e-25623c030c34 |  | note | REFERENCE: MTM Quality Management Plan
label | fc3d709a-0024-51a0-a488-6f35e7c200da |  | note | – – – – – – – – – – – – – – – – –
label | b2c3584c-44fa-5af6-b2ca-411c815a4a96 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | bea11cc4-ac13-586a-b23b-7329051824d9 |  | note | – – – – – – – – – – – – – – – – –
label | d99adc94-5f27-569c-91f1-ce9adeff5f65 |  | note | METHOD: Document Review
label | c5a4b39b-6769-5b01-bd79-90983f5042e6 |  | note | – – – – – – – – – – – – – – – – –
label | 6b1bd36a-19a8-5c12-8fc8-354eb196ee61 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d89b08ad-7e65-5677-aee8-4cce4a857b8b |  | note | – – – – – – – – – – – – – – – – –
label | 9654a071-8b23-59bd-b53f-e73e99005098 |  | note | CATEGORY: HP
label | c76cde6e-a315-5a6c-9327-6e31d8472957 |  | note | – – – – – – – – – – – – – – – – –
label | d715b7ee-c420-58b8-a7ee-614bc43702b4 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 93e256e9-51ff-54f5-a119-ba3760940847 |  | note | – – – – – – – – – – – – – – – – –
label | a3ecd573-b018-5142-b35e-b69e64ef6e4a |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 801195e6-7702-52c8-bcb7-63f41c80acfd |  | note | – – – – – – – – – – – – – – – – –
label | 4a321a0c-270a-5f45-b033-cbb5966179b5 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 63eefb72-6924-57f0-a28a-3782188b04b0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | d384d2f2-544a-5d4a-ba72-f04de1f3313c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8fbbd0bd-8390-59a5-a60d-2f60d26ffa81 |  | textbox | Name:
text | 34994f68-105f-560d-a385-9882e1ec343f |  | textbox | Position:
date | 98aa1362-5e33-54cf-8864-cdad148ed63d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-154-STR-SSB-Precast Super T Installation | itp |  |  |  | Yes | ITP-154-STR-SSB-Precast Super T Installation Rev 0 | 113118e7-9644-4857-a493-18b33cb40350
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 2daedeab-3acb-5d7a-a07e-7fc627f8c23a |  | note | Document Title: ITP-154-STR-SSB-Precast Super T Installation
label | 4780b3ef-d1c6-522d-bb75-8f31c4634f67 |  | note | ITP Description: SSB-Precast Super T Installaton
label | 7c9cace8-4110-5c33-8e9a-f32024562f18 |  | note | Discipline (e.g. CIV/STR/RAIL): 154-STR
label | ad433f81-7bbe-51a7-9c85-5a6a750760d7 |  | note | Revision Number: 0
label | d081902d-743d-5d69-a4e0-d0d9403cf30f |  | note | Revision Date: 1/05/2024
label | c4ac9f6a-cd32-530b-8a42-5184ccbd04a1 |  | note | ITP created by: Dan O'Brien
label | afbc0b4f-42d4-578d-8312-ab047e342178 |  | note | ITP approved for use by: Victor Mira
label | b7a43951-e928-51b5-a934-36771c8af4cc |  | note | 1.1 Non Dependent
label | 5ffcf502-b840-5ee1-b6b1-bbf188d441df |  | note | Reference: VR 652 June 2010
label | fb24bbc2-4a6c-5738-80ce-928a649f75f8 |  | note | 1.2 Non Dependent
label | a765f196-0423-574a-b73b-a8941f808827 |  | note | Reference: VR 656 June 2010
label | c7a431f5-3122-5281-8441-d156bc4bbb7a |  | note | 1.3 Non Dependent
label | d6b7d420-8edf-57aa-b4df-38e05545301a |  | note | Reference: VR 610 February 2020
label | 02a2935f-758d-53af-b6ef-c077ddaaf908 |  | note | 1.4 Non Dependent
label | 1b207aa2-2172-5452-9613-81f18b934157 |  | note | Reference: VR 620 May 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Epoxy bedding
label | 2d353e9d-1984-5b6f-9cfb-f00e6fd36068 |  | note | REFERENCE: IFC Drawings
label | 37f1de1f-e15d-55c1-a0b7-3f44641cf5c2 |  | note | – – – – – – – – – – – – – – – – –
label | 835198e7-9647-5be6-a3b0-b1152ef67f3d |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 2929e4b6-2ed7-5e53-a112-c02fbdde06a7 |  | note | i. Have a minimum compressive strength equal to or greater than substrate
label | 4abc8512-5171-5692-871a-347744016787 |  | note | Ii. Can be applied in IFC specified nominal thickness (1mm)
text | 4141b257-b188-5177-8a2a-8d0ebb8fe1a7 |  | textbox | Enter: Teambinder Material Approval number
label | b06d0bcc-990a-55c2-808f-f86b4f7e3ae4 |  | note | – – – – – – – – – – – – – – – – –
label | 9d71e830-6db8-5586-8231-8656c06f91c2 |  | note | METHOD: Document Review
label | 605e9ba8-9e6f-50eb-b042-95cdb4a408ec |  | note | – – – – – – – – – – – – – – – – –
label | 1d92bb17-571a-54d2-ab2c-308227979eef |  | note | FREQUENCY: When applicable
label | 7371ad9c-7d94-505f-86ee-df8dc608b2a4 |  | note | – – – – – – – – – – – – – – – – –
label | b9e3a8cc-54bf-550f-aa51-bc2c6f3e675e |  | note | CATEGORY: HP
label | 615e28e0-c727-59a4-9799-60d8e3e05aac |  | note | – – – – – – – – – – – – – – – – –
label | 961bf312-04b8-5ffb-a6f7-a0b48ec2f7eb |  | note | RESPONSIBILITY: Nominated Authority
label | 51cd0bf0-a1ae-56e0-a7e6-743841cbecc5 |  | note | – – – – – – – – – – – – – – – – –
label | 6d89b180-1ce8-56b8-8a7c-64fcbe927bfe |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | fdff2274-507a-5752-ac90-03a8b7863f6d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Bolts
label | 794489b0-ef82-5c21-a576-147757b20fd5 |  | note | REFERENCE: IFC Drawings
label | 097a8e22-b990-572f-b4df-d7dff771f01f |  | note | – – – – – – – – – – – – – – – – –
label | 3db30cea-e901-5ffc-bc22-6047a86b6a90 |  | note | ACCEPTANCE CRITERIA: M16 grade 4.6/S countersunk socket cap screw
text | f24aa3c1-587a-5687-9c11-f6db600ea014 |  | textbox | Enter: Teambinder Material Approval number
label | f7cef8fd-5792-558a-95a9-b468faed9f1a |  | note | – – – – – – – – – – – – – – – – –
label | 61515735-9dad-5caf-a019-e1e9be489909 |  | note | METHOD: Document Review
label | c35e0d56-38b7-545a-8a6f-f9689ed41faa |  | note | – – – – – – – – – – – – – – – – –
label | cfe21c81-bf8b-5aa0-a4af-6253ca859b1f |  | note | FREQUENCY: When applicable
label | 21ccd3d5-b16e-5a87-a3c0-8e7ba852564b |  | note | – – – – – – – – – – – – – – – – –
label | 0098a4a4-2129-5136-842c-dcfe20ff5f0c |  | note | CATEGORY: HP
label | d8daecdb-6b70-57a8-99cb-551e101dc83a |  | note | – – – – – – – – – – – – – – – – –
label | 29b854b0-27fb-5a3f-a153-b66bea686d98 |  | note | RESPONSIBILITY: Nominated Authority
label | 10ab9497-6c2f-54e0-9a97-8214ecaf3649 |  | note | – – – – – – – – – – – – – – – – –
label | 5abf272b-5150-5b8e-bc91-54bde562eb63 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 45d0f450-5a39-5927-ba54-aa6e25c4771c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 577c696c-ad21-5630-ba0e-77f6159d7b2f |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.473 (March/June 2019), 620.03
label | b432582b-346c-5d0e-b90c-7f6d0fa5071e |  | note | – – – – – – – – – – – – – – – – –
label | 737527b2-97ed-55cb-9652-64e070788650 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 2c433ef8-b854-5040-86ab-656cf8dcf73c |  | note | i. Certificate of Compliance / Birth Certificate
label | 7108b8d3-bec1-5a89-9590-1bbbce6025c1 |  | note | ii. Compressive strength test results
label | ce816d75-69dd-5076-9a7a-e724a85e1e3b |  | note | iii. Precast Lifting Design
label | 7ca97125-deec-5fde-acbd-56d97201f69a |  | note | iv. Pre-pour check sheet / ITP
label | 4e76e859-4446-50c0-9a4d-451820642479 |  | note | v. Pre-stressing check sheet / ITP
label | 72d1464f-161b-5845-bbfa-567256cb73e8 |  | note | vi. Post-pour check sheet / ITP
label | 1ae5db3d-fecf-57c2-82a5-6ae1c0fadc3e |  | note | vii. Covermeter check record
label | ec5c4958-72d9-591c-b3af-255eb6181c96 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
label | c63b2cdb-18fe-5824-8292-5045e4dbe127 |  | note | Note: Different revisions of 610 have different clause numbers
label | 52cdaca8-c2d5-5122-af23-3db81e99f9f4 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
text | 0d9ab90a-55ed-548d-8ec1-867aa67b595c |  | textbox | Enter: Teambinder MDR Lot number
label | f7ba8785-b298-5909-9b16-6d6ef64607e1 |  | note | – – – – – – – – – – – – – – – – –
label | be7e4033-d2e0-517e-ad80-fc28fffb1db8 |  | note | METHOD: Document Review
label | d3165e0f-f499-57f7-b712-e93073a8c932 |  | note | – – – – – – – – – – – – – – – – –
label | 3aa4328d-e3af-58ea-9e71-82cfce265165 |  | note | FREQUENCY: Each element
label | 41a5f6b4-5106-58b0-9628-d22c5e63323a |  | note | – – – – – – – – – – – – – – – – –
label | 287be56d-7208-5a3b-8dff-bfd5c2c0fee9 |  | note | CATEGORY: HP*
label | daa41b0d-5542-5e67-83ad-35327a95aba6 |  | note | – – – – – – – – – – – – – – – – –
label | 39ad6b56-9426-504d-9e68-943b45d49cee |  | note | RESPONSIBILITY: PE/SE/SPE
label | d61e4819-3b86-5408-be8c-5749f9775df5 |  | note | – – – – – – – – – – – – – – – – –
label | 2c46a065-2dd5-5eeb-ae16-703dc1864d40 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9b0cbceb-99ce-5945-8b11-d8f69aedd761 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Elastomeric Bearings-crosshead and restraining blocks
label | 0c6f1b8b-96e5-5954-8797-c43abee9816c |  | note | REFERENCE: IFC Drawings 652.02, 652.03, 652.04 AS5100.4
label | 3d328fe2-6cd5-5ad9-9291-922b06967882 |  | note | – – – – – – – – – – – – – – – – –
label | 0aca2049-957e-5a71-aa86-1059509f5fda |  | note | ACCEPTANCE CRITERIA: Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
label | b679bb88-cdb3-52b9-aabc-a5143ef4cd64 |  | note | Tolerances:
label | ada7da69-9767-5140-a18e-1962302f8025 |  | note | Dimensions in plan = +4mm, -2mm
label | 57940320-9c86-5e05-a8f4-0cda43dc8598 |  | note | Thickness =
label | 5860c073-9b15-5473-b388-a88b699aa328 |  | note | ○ ≤100mm = ±2mm
label | 69adc0ef-792b-593e-8cd5-ef22d4fa3af1 |  | note | ○ >100mm ≤ 150mm = ±3mm
label | 0ced8879-725c-55fd-91ea-f3908b820804 |  | note | ○ > 150mm = ±4mm
label | 2f925334-f587-5d15-9435-63140cb37b36 |  | note | Testing:
label | 61cbbeb2-35b2-5693-9166-4efa48e8751a |  | note | ○ Each bearing tested under compression
label | 80c33ab3-f77c-5e3c-8465-da5d6d8ac11f |  | note | ○ Batch tested for shear stiffness
label | f462e438-2a5e-56e5-b085-c5bb25320b8b |  | note | Attach: Elastomeric Bearing Test Reports
label | d7da37c8-bac8-53b9-b704-f9aaa781f1cb |  | note | Attach: Elastomeric Dimensional Records
label | a6dfa0d8-07ae-50c4-880a-5d0dabdf2d23 |  | note | – – – – – – – – – – – – – – – – –
label | 79fd4b40-de87-5c92-9f19-0360e2db7c53 |  | note | METHOD: Document Review
label | 765e373e-e2fe-5a5e-b618-6a5f5f813f5d |  | note | – – – – – – – – – – – – – – – – –
label | 8f18810e-3092-54be-ba4d-7a58f5e72357 |  | note | FREQUENCY: Each element
label | 9540db40-c2b2-59cc-9986-11422d13e3d9 |  | note | – – – – – – – – – – – – – – – – –
label | 2102b0b8-7457-5be1-8632-45454e3aa070 |  | note | CATEGORY: HP
label | 66970808-cbaf-5848-a925-7f572caf6b82 |  | note | – – – – – – – – – – – – – – – – –
label | 69bd4513-4b54-5758-924e-26dc02cf35a3 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 12cdfacf-fa02-5f44-93ec-6a22de2a43cd |  | note | – – – – – – – – – – – – – – – – –
label | f179fc51-141c-56f9-833b-87bb2a5e765b |  | note | VERIFYING DOCUMENTS: This ITP
date | 554550d9-7835-5e1a-a2b4-1ca14aa07036 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Tapper plates / Keeper Plates
label | bf536a25-0f6a-5ae6-81d3-d9f12858dc6b |  | note | REFERENCE: VR 620.05
label | 91602662-2f26-5b76-b8e8-f366b2619332 |  | note | – – – – – – – – – – – – – – – – –
label | 8730f0f0-39ac-592b-9cf1-8bb2e9932fe0 |  | note | ACCEPTANCE CRITERIA: Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
text | 7e2d02b7-19cc-5d3a-8104-3e78d64f6df5 |  | textbox | Enter: Teambinder MDR Lot number
label | 0ec01da7-4f16-5361-9286-2ac9cd59d71d |  | note | – – – – – – – – – – – – – – – – –
label | 62120c67-255f-5a02-a9d3-446fae61aed9 |  | note | METHOD: Document Review
label | 9d707118-46b7-5001-b808-25043f252a9a |  | note | – – – – – – – – – – – – – – – – –
label | 3f5c5091-1be0-5d92-bdaa-870eb9cc6bf3 |  | note | FREQUENCY: Each Plate
label | 5b8a643c-785d-533b-9e7d-7807e9d5a79c |  | note | – – – – – – – – – – – – – – – – –
label | bfade325-420a-54d8-bf57-31cd9172ac7a |  | note | CATEGORY: IP
label | d7d0d864-6575-54ba-8e88-a8c6112b0397 |  | note | – – – – – – – – – – – – – – – – –
label | ed8bee67-cdc2-5b2e-987d-9b372f7fbb81 |  | note | RESPONSIBILITY: SE/PE
label | 466804e3-11d5-5615-8bef-090ecafbbe26 |  | note | – – – – – – – – – – – – – – – – –
label | 90040ab7-f9a8-5859-9ab8-37ec6b1b440d |  | note | VERIFYING DOCUMENTS: This ITP
date | 84e5e88b-22b3-5afd-801e-ef513fe88fad |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Bearing Plates-Check
label | 39ec4bb2-2dbe-5b93-96ab-0c0f6bde13f1 |  | note | REFERENCE: IFC Drawing
label | ba095c83-d904-5865-9613-35a72d5b2612 |  | note | – – – – – – – – – – – – – – – – –
label | 0f9dcec7-b044-5ac9-b56c-8aeaeff54b6a |  | note | ACCEPTANCE CRITERIA: Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders. Ensure the plate and bearing orientation are correct.
label | 6e711fbd-5a0f-5654-990c-b8d857690125 |  | note | – – – – – – – – – – – – – – – – –
label | 90973d43-6e6d-5114-baa5-4f643ff5bee0 |  | note | METHOD: Visual
label | 9edbefcc-a49d-58b1-9d64-d4b8c51105fc |  | note | – – – – – – – – – – – – – – – – –
label | 8b9e3a5e-99de-5880-bb95-4f6bfce12c82 |  | note | FREQUENCY: Each Tapper plate
label | 6e1ed9b9-6daa-55fc-be4e-29ebd9db1cb9 |  | note | – – – – – – – – – – – – – – – – –
label | 2b1d73c3-7c1e-553b-9000-3073ae3bcbcb |  | note | CATEGORY: IP
label | 6c1bb52f-9e27-5e8f-84ce-9da506d779b4 |  | note | – – – – – – – – – – – – – – – – –
label | 2805df6c-f731-56a7-9186-a9f1ce7dbda7 |  | note | RESPONSIBILITY: SE/PE
label | 10412eba-8788-505c-80b1-3eeaa9938da5 |  | note | – – – – – – – – – – – – – – – – –
label | 7d909814-24e7-5558-96f9-343b44520536 |  | note | VERIFYING DOCUMENTS: This ITP
date | ac322d61-aef4-5a27-b9ae-78b96744c06c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Crosshead / Pedestal Tolerances
label | f8cd068e-466a-570a-ad3b-ad31a9962326 |  | note | REFERENCE: Survey As-builts / Survey Report
label | c90732fc-3c13-566d-8ebe-bc760bd907ae |  | note | – – – – – – – – – – – – – – – – –
label | a1f5618f-c618-5aa8-906f-a99cdee19861 |  | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
label | 31619191-35b2-53ed-9812-52896c4d5fd2 |  | note | ○ Reduced level ±2.5mm
label | 9f24ab78-c75c-5bc3-90a7-91261f49e29e |  | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | b17ab9ad-6fa4-53f0-b1c9-5c1179e3cd5e |  | note | ○ Deviation from flat surface ±1mm
label | f495391d-1ff0-5416-89ec-d2c9c050c892 |  | note | – – – – – – – – – – – – – – – – –
label | 25ba0038-7d0d-5bb6-9bf3-6d4f9c924518 |  | note | METHOD: Document Review
label | c344bfd2-e17b-5758-9522-c0d7124a02c2 |  | note | – – – – – – – – – – – – – – – – –
label | 0a35cd5a-ed2b-56ca-b14f-537feee8ea0b |  | note | FREQUENCY: Each element
label | f9de3bb4-47f3-568f-b39d-8c8e111e705d |  | note | – – – – – – – – – – – – – – – – –
label | 9372c74a-a490-551e-9651-4b78866dd998 |  | note | CATEGORY: IP
label | 0d4e7bfd-5378-59da-972e-45d17d2273a8 |  | note | – – – – – – – – – – – – – – – – –
label | 8fcc01ea-7fea-53e7-858e-fb533236bd0d |  | note | RESPONSIBILITY: PE/SE/SPE
label | f1a68786-8585-53e3-9c01-526e899467db |  | note | – – – – – – – – – – – – – – – – –
label | 6f8707e6-4d7c-5851-857e-4978336b9b73 |  | note | VERIFYING DOCUMENTS: This ITP
date | b7baf0ee-5ffd-541e-8409-a9acfe975e1c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Precast Beam Inspection
label | aca2ae01-f3cb-5217-9db4-40514522d3e6 |  | note | REFERENCE: IFC Shop Drawings, IFC Drawings
label | 62061305-0e7c-5a82-b57d-bec97d0eedbd |  | note | – – – – – – – – – – – – – – – – –
label | 2c82d620-5b0a-5cbd-a5be-f62158542651 |  | note | ACCEPTANCE CRITERIA: Check that material inspection checklist has been completed for each beam.
label | 1216c602-ead9-5bee-ad83-091a821f28ee |  | note | ○ Engineer to check that each beam has been loaded with each end at the specified position (truck or jinker end)
label | c855a3d6-7987-5d37-82a4-93e9af9688bd |  | note | – – – – – – – – – – – – – – – – –
label | d15d8033-7cce-52db-9dba-f6d35177bb95 |  | note | METHOD: Document Review
label | 5a745ac6-500b-5778-bdaf-3e80d0a29296 |  | note | – – – – – – – – – – – – – – – – –
label | 114eb123-599c-5abf-917e-4e65cac5b67e |  | note | FREQUENCY: Each element
label | 1c17dd56-4738-5231-b943-7c4185fa9456 |  | note | – – – – – – – – – – – – – – – – –
label | fb1f7a3b-5632-5718-9e7b-4c6b841b3391 |  | note | CATEGORY: IP
label | 6514a593-a481-5498-bfbf-f254d1ca68ce |  | note | – – – – – – – – – – – – – – – – –
label | f6c0fd73-424c-5357-9aa5-f0d6e62d5d50 |  | note | RESPONSIBILITY: SE/PE
label | 5bfc3797-afbc-5ca4-959c-89b9656bda4b |  | note | – – – – – – – – – – – – – – – – –
label | 541cd2a2-9a9b-5b52-ba88-b76e9bb07df8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 72094af6-4239-59e7-8d0c-018d8666896a |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Elastomeric Bearing Placement
label | 31a8a4fe-0b40-5a22-96d5-21c13dcbca79 |  | note | REFERENCE: IFC Drawings VR 656.05
label | bb49503a-ab98-58fa-bf20-69e88f7973ef |  | note | – – – – – – – – – – – – – – – – –
label | e0e505ca-88e8-5ab6-83b1-af0fdfc179f6 |  | note | ACCEPTANCE CRITERIA: Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
label | d952b1a4-4742-5043-9880-e0f3eb57d087 |  | note | Tolerances:
label | 8e5742ca-8a99-5de6-b834-be49c519ba69 |  | note | ○ Plan position: ±2mm in any direction
label | 8e95b4ba-977b-599e-96c5-91a5c5666bbc |  | note | ○ Level: ±2mm
label | 6e41e120-e401-54bb-81cb-765016c1c44e |  | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
label | 03b7ecc4-ab14-52d6-8b1f-9efb8cfdb5e4 |  | note | – – – – – – – – – – – – – – – – –
label | 7a17a6ef-0575-5da5-879f-9bd6be94ff56 |  | note | METHOD: Measure, Visual
label | 03f593ea-7a5d-5de9-b956-2410199bfdc1 |  | note | – – – – – – – – – – – – – – – – –
label | 1323f2e6-73a0-5319-9b0e-053b86b16b36 |  | note | FREQUENCY: Where applicable, each bearing location
label | ba491f5a-94f4-5de2-ba39-6f11895a2cf7 |  | note | – – – – – – – – – – – – – – – – –
label | 5eba0b99-8f97-50e4-8ee8-1a451f86b2ce |  | note | CATEGORY: IP
label | 15a55514-c51f-53b1-a8b8-98f961c1c54c |  | note | – – – – – – – – – – – – – – – – –
label | 70d48710-7792-5341-a686-8974172a808e |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 876b13fd-e643-5e50-a749-dfdab4ab8942 |  | note | – – – – – – – – – – – – – – – – –
label | 56fa7987-de1f-5631-8cea-d6efafab7f0b |  | note | VERIFYING DOCUMENTS: This ITP
date | 2b6d9aa5-ee7d-5a50-8fb3-3a9f1c153c02 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Restraining Blocks-Bearings
label | 72bcfbef-cfad-542d-aaa8-9a8e3758e693 |  | note | REFERENCE: IFC Drawing
label | 9f6bb03b-5058-53dd-be54-63937c5476b8 |  | note | – – – – – – – – – – – – – – – – –
label | 9857ff72-1504-5b3c-9886-33c0cc3cba15 |  | note | ACCEPTANCE CRITERIA: 230x150x35mm elastomeric bearings are to be installed in designated recesses on restraining blocks.
label | d58b8b97-c7e4-5006-8e71-9993181e2ee6 |  | note | ○ Base plate 260x170x10mm cast flush into lateral restraint block with 2 x 10mm diameter, 75mm long dowels (grade 250R) cast into restraint block (4mm CFW all around to base plate)
label | c1e1daf9-cf70-5404-926c-662a4d5c9d3e |  | note | – – – – – – – – – – – – – – – – –
label | 40351494-b6a8-5769-a732-e53129966040 |  | note | METHOD: Visual
label | cb8f0e47-e914-50b9-8934-0551209c732c |  | note | – – – – – – – – – – – – – – – – –
label | 3842ecd1-5767-5792-bf72-9cc6b3ea4f74 |  | note | FREQUENCY: Each restraining block
label | 6d01e91a-b9a6-51dd-a22f-39934248df54 |  | note | – – – – – – – – – – – – – – – – –
label | 8880d05d-fe29-5b0c-971d-e7e3fabac40c |  | note | CATEGORY: IP
label | dbb10497-f2db-51fd-80ba-7c3bcf59719d |  | note | – – – – – – – – – – – – – – – – –
label | 3b7f73a4-d27a-5e41-a39f-ac04f13ab17d |  | note | RESPONSIBILITY: SE/PE
label | 00ca790e-0bcf-5ff3-9aca-2018df1a98f3 |  | note | – – – – – – – – – – – – – – – – –
label | bcfcb262-4efa-582d-98e1-7018651df410 |  | note | VERIFYING DOCUMENTS: This ITP
date | a48954be-5bd2-5d17-97d8-a3b6d7f0761b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Precast Handling
label | 34d3b1ef-4b66-57d4-9a6d-849d27c3863c |  | note | REFERENCE: 620.07 Crane Lift Study
label | 2935a8d1-5e80-5e00-8eba-f4ed72ad82de |  | note | – – – – – – – – – – – – – – – – –
label | 1b74f324-bafe-5708-93c1-ceade2632abf |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | e4d15c65-bf86-5e58-a9b8-c79cb0dffac0 |  | note | – – – – – – – – – – – – – – – – –
label | 8e272f1d-1093-586f-8a69-a942cd61254e |  | note | METHOD: Visual
label | a27f3c20-796b-5b64-a286-6bef274fda52 |  | note | – – – – – – – – – – – – – – – – –
label | b0d0f9ef-695a-549a-bab3-d3ec00931007 |  | note | FREQUENCY: Each element
label | d2600fc8-773c-5831-b885-6768bcbc0129 |  | note | – – – – – – – – – – – – – – – – –
label | 005002b0-044c-59b7-a5ad-da16e16ca817 |  | note | CATEGORY: IP
label | 0247cd61-d5b7-52d8-a85e-2746e9e191ad |  | note | – – – – – – – – – – – – – – – – –
label | 95d5a623-19a7-5e9a-a66d-9a56095af69c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 25bde931-32c6-5820-8dff-63ecc1ce272a |  | note | – – – – – – – – – – – – – – – – –
label | c245b9b4-bb85-50b7-b16a-1b993485a94c |  | note | VERIFYING DOCUMENTS: This ITP
date | 5e7f0103-41bd-5e6a-8f9e-d432ad7a6ad9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Precast Placement
label | 8be7d1bc-be80-57ef-8073-6ad4425e4b8c |  | note | REFERENCE: IFC Drawings 610.27 Temporary Works Design Drawings (IFC)
label | eab261a7-31db-5243-b777-b1bdac88ee12 |  | note | – – – – – – – – – – – – – – – – –
label | fe15d4a1-a5ee-501e-af42-1c7b323c4c7b |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 88b9ece9-5ba8-547d-9c7b-e0f1546ad17b |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 3c2609dc-4d5b-5cb2-9ef5-8226b06eaf26 |  | note | – – – – – – – – – – – – – – – – –
label | 544e027b-5572-5f72-8cbc-02437eb269f0 |  | note | METHOD: Measure, Visual
label | 9cfe212b-21a4-58d6-8102-c2d748bb7941 |  | note | – – – – – – – – – – – – – – – – –
label | eb980d0a-4613-517e-99dc-c21580f6c72a |  | note | FREQUENCY: Each element
label | c426b807-7609-5b64-9ff5-db623dcb06d3 |  | note | – – – – – – – – – – – – – – – – –
label | 2a909130-664d-502f-961e-6754a7e76089 |  | note | CATEGORY: IP
label | d2e95443-cb85-51c3-ac49-3d6b42f3035f |  | note | – – – – – – – – – – – – – – – – –
label | 3c25b821-ff60-5e1a-8c43-76b113ff227e |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | fa8095b2-36aa-558d-a6ad-a1932c73dee3 |  | note | – – – – – – – – – – – – – – – – –
label | 6e7f78f4-f60f-5e3d-9c59-1ecb5d566167 |  | note | VERIFYING DOCUMENTS: This ITP
date | 244088de-e04c-510f-8a84-7382f6855e64 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Precast Traceability
label | b6db26c4-f3bf-5e39-8a12-857be7075b71 |  | note | REFERENCE: 620.09
label | 2c80a696-eabe-55b9-847a-0ab38fd4b1a2 |  | note | – – – – – – – – – – – – – – – – –
label | 3d931b52-fa09-516c-b934-6f50cb2b06ca |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | e552bdf9-5b9e-5d20-8e27-be6fec873db2 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 43de5f6d-59f3-5beb-80f8-099ace121495 |  | note | – – – – – – – – – – – – – – – – –
label | dfea21cf-206a-5e7b-8655-8ce1c3c888b5 |  | note | METHOD: Visual
label | 5313b84b-4e06-5aae-9a29-2d96ef1600f6 |  | note | – – – – – – – – – – – – – – – – –
label | ad3ed215-80e5-5533-8c47-8988a05b4597 |  | note | FREQUENCY: Each element
label | bcde8cca-7fe8-55dc-8943-40b69cdae208 |  | note | – – – – – – – – – – – – – – – – –
label | 09ba7f2a-e3ff-5714-b4fd-395d51b76cdc |  | note | CATEGORY: IP
label | 8d27c61b-7925-5993-835a-d2bbd14eda86 |  | note | – – – – – – – – – – – – – – – – –
label | 523d39e8-47ee-5eea-a766-8fff6beaee95 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1227c860-3022-5333-a65a-e339c9293816 |  | note | – – – – – – – – – – – – – – – – –
label | b260bd3d-c4c4-542e-9fe9-7d22fb820dff |  | note | VERIFYING DOCUMENTS: This ITP
date | 741634f7-3ccf-5503-989c-d172b452edc7 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 1a74fb78-55ab-59c8-887c-b6af1e6022e4 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 (March/June 2019)
label | 1a845510-3605-5526-a406-90360084d5cf |  | note | – – – – – – – – – – – – – – – – –
label | aeee1abb-49c5-5bb0-b3e9-06ecedbc147b |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | b2d82d9c-2614-5b32-b87f-63c3653f1fcc |  | note | Attach: Survey As-builts / Survey Report
label | 801a40f9-ca52-5eaf-8f8c-4aaf0e338748 |  | note | – – – – – – – – – – – – – – – – –
label | c544ba7c-cae2-5ced-86ec-240d5640e5b4 |  | note | METHOD: Document Review
label | f7fcbb52-336b-5249-a55d-cd9f549ff9bd |  | note | – – – – – – – – – – – – – – – – –
label | a24526ec-4e8d-5365-b1a8-2b4e5956ee55 |  | note | FREQUENCY: Each element
label | a0690489-6181-520d-9856-d2ec863b08da |  | note | – – – – – – – – – – – – – – – – –
label | 72345dc0-cb41-5a8c-9de4-682c89d2caad |  | note | CATEGORY: IP
label | 0a447d53-951b-5a4e-ac24-6b97cbc94715 |  | note | – – – – – – – – – – – – – – – – –
label | 2d13583e-44a1-55b3-bb2b-c1268a79da28 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 7a07d905-90cd-593a-96c4-256ae9979eec |  | note | – – – – – – – – – – – – – – – – –
label | f5095f4a-8a22-51aa-b858-ad8c7e4abf04 |  | note | VERIFYING DOCUMENTS: This ITP
date | fc2388ff-b7f3-58e2-b90b-7695a12fe1b3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | 5932c691-4373-564f-b64d-d0903a05e05f |  | note | REFERENCE: MRPA Quality Management Plan
label | 65cf6ab8-8ed0-57f9-a8f1-f5085c44114c |  | note | – – – – – – – – – – – – – – – – –
label | 3531ac38-03c4-53f2-bc28-f3a34f25247b |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 653d7060-1c5f-56e5-a86a-2095d26874ee |  | note | – – – – – – – – – – – – – – – – –
label | 75310a30-9c4f-51d9-ad7d-5b74d2644fd4 |  | note | METHOD: Document Review
label | d4fecb5f-877c-5325-81a4-22ca9146da4a |  | note | – – – – – – – – – – – – – – – – –
label | 10b590d1-303f-5b77-be61-04b3c522f17a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 6a4917f7-7a29-517e-b9d8-ebe15599046d |  | note | – – – – – – – – – – – – – – – – –
label | 0f814a3b-5467-597f-8894-c7d0f8da2733 |  | note | CATEGORY: HP*
label | f7576878-5af1-5c50-9318-30ccb08e3b2a |  | note | – – – – – – – – – – – – – – – – –
label | 233aa0c8-e792-58cd-9d39-38a26f13e0e2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 04ab15c0-8d07-56c0-ae5a-2651e6cdb425 |  | note | – – – – – – – – – – – – – – – – –
label | 147e1244-60b3-5201-9243-d45dca4b8f2a |  | note | VERIFYING DOCUMENTS: This ITP
date | e67300f1-5d4b-58d2-ba77-70837d8b9a9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 42e373b7-6de8-54a8-9a83-a4e7c4fa571e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | baa23426-0c64-5c22-abc0-4c0b1e974a90 |  | textbox | Name:
text | 4dcbbe5e-a182-59e1-b2b6-9e930b15780e |  | textbox | Position:
date | 0b4783ef-1a47-5243-a257-7fea795dffc0 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-155-STR-SSB-Misc Steel Structure installation | itp |  |  |  | Yes | ITP-155-STR-SSB-Misc Steel Structure installation Rev 0 | 2ec5f430-260f-4092-95d7-d108d7e91d9a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | a625f9d4-5dbb-5240-805a-f67b4c8f13b2 |  | note | Document Title: ITP-155-STR-SSB-Misc Steel Structures Installation
label | 24fe5185-247e-53ce-9e68-dcb137d30e9c |  | note | ITP Description: SSB-Misc Steel Structures Installation
label | cca595b9-fcd0-52a1-a843-bfc6417ac43c |  | note | Discipline (e.g. CIV/STR/RAIL): 155-STR
label | ca898afe-ac25-5afd-829d-1f3a005e369c |  | note | Revision Number: 0
label | f24c8577-6ff8-590a-bf34-7b5c4f2d7228 |  | note | Revision Date: 1/05/2024
label | 844e5a8c-7fce-51f1-8ae9-53f8712751fe |  | note | ITP created by: VM
label | 5a9b3164-0ba5-5836-a9f6-b279c75feaac |  | note | ITP approved for use by: VM
label | 7e936023-9e62-5bed-9375-e4b11489a8a3 |  | note | 1.1 Non Dependent
label | 7cf79d5e-da88-5664-9ddf-6ba3efa3a1f2 |  | note | Reference: VicRoads Section 610 June 2019
label | cf22a2aa-b08c-5c1c-b471-2eef654c93d6 |  | note | 1.2 Non Dependent
label | 66d21da9-2a94-5bbf-9ef3-29a41d3dfc30 |  | note | Reference: VicRoads Section 630 October 2013
label | eb33115b-e1ec-5cd6-b45a-d25bb63117f3 |  | note | 1.3 Non Dependent
label | fdc51747-4771-518e-8d86-26e88fd1144d |  | note | Reference: VicRoads Section 631 February 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 5da01cfd-4a57-5316-99bb-b799b98a1d06 |  | note | REFERENCE: IFC Drawings MRPA Quality Management Plan
label | a45098ee-1523-532d-a2c5-3364046d9792 |  | note | – – – – – – – – – – – – – – – – –
label | 57a25a3f-ab4f-5b1d-a5a9-5828a42bb630 |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 02ab29ef-64e3-53f4-b091-3201adb9f768 |  | note | Typically this consists of but not limited to:
label | fb891e4d-df6a-5282-9bca-7a2e3d218a72 |  | note | i. Certificate of Compliance
label | 9a9f010d-2e3e-5fb1-a1fc-ae0ca790a9ad |  | note | ii. Completed ITP
label | b5b24806-89cd-5f47-9226-5671de05e829 |  | note | iii. Weld Procedure Specifications
label | ad31be04-c819-5593-b992-2a929e3a6cf2 |  | note | iv. Weld Procedure Qualifications
label | 57c06f3e-2511-5b4e-a0e6-b6623e7c07d8 |  | note | v. Welder Qualifications
label | f61f8fa7-2391-5510-9b5b-25037c14bce6 |  | note | vi. Material Certificates and traceability
label | f17a6951-47f1-56e6-b2ce-ba82d59a25c6 |  | note | vii. Quality Assurance check sheets
label | ed46e376-94dd-5208-94b2-16aed262bb8d |  | note | viii. Welding Consumable batch certificates
label | f6d9b5fd-2ac1-59db-96b4-217f27fb3156 |  | note | ix. Coating certificate(s)
label | d696a7a5-b985-56fe-acbb-187e6caf0eb2 |  | note | x. Non-destructive Testing (NDT) Reports
label | bf6b97ce-aae7-5d66-ac08-7c1490d3f4bc |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | eb604379-031b-54c9-9bfc-96537d16cdba |  | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
text | ae1a3e93-0e30-51ba-96d3-9dd4e6992ce8 |  | textbox | Enter: Teambinder Material Approval number
label | d980874c-6186-50c9-b698-fcd3c14be96c |  | note | – – – – – – – – – – – – – – – – –
label | adac66c1-8e36-5540-938c-714eb1f5314b |  | note | METHOD: Document Review
label | c5fc8f96-b290-58ad-805c-772fee83c0ee |  | note | – – – – – – – – – – – – – – – – –
label | 2a2de5e9-045a-5cfd-8a03-d7583a3eb7cf |  | note | FREQUENCY: Each component
label | 70c60af8-779e-5602-9c98-da6e59393b71 |  | note | – – – – – – – – – – – – – – – – –
label | cdc28a7a-17f9-542a-962d-4ccee639e95d |  | note | CATEGORY: IP
label | 09cfb55f-68b7-52ad-a8de-364fbd663411 |  | note | – – – – – – – – – – – – – – – – –
label | e60efae5-05ae-55e2-a491-f71b2784f62a |  | note | RESPONSIBILITY: PE/SE/SPE
label | bd498147-864d-5929-8015-fdc0b54648fd |  | note | – – – – – – – – – – – – – – – – –
label | 1ac2e6a9-d654-5422-a9c9-07ac1bce4031 |  | note | VERIFYING DOCUMENTS: This ITP
date | 14b0bf87-c090-5393-b15e-8938637157f7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Fasteners
label | 4c88220b-1ab2-5dc5-ac12-d4f497af1a1e |  | note | REFERENCE: 630.20 IFC Drawing
label | ebe6eaab-e02a-5e1a-9799-f0ee02ad5aef |  | note | – – – – – – – – – – – – – – – – –
label | 73368496-99ae-56fd-aaf5-984f37d8ed06 |  | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
text | a345490e-2a97-50f1-9102-e8968270dab4 |  | textbox | Enter: Teambinder Material Approval number
label | 4219fc0f-2a26-5668-8a54-7cf940d78dc5 |  | note | – – – – – – – – – – – – – – – – –
label | 09205496-0219-54db-bbb2-655ddb08f98c |  | note | METHOD: Document review
label | 852b66bd-bf6e-58a4-aac0-3c75c0f73f92 |  | note | – – – – – – – – – – – – – – – – –
label | 3f76b6f7-899f-5aa4-9dda-285fc26bd720 |  | note | FREQUENCY: Where applicable
label | 849f90d3-bd8a-5957-8521-b6827d01ccc5 |  | note | – – – – – – – – – – – – – – – – –
label | c23d3fae-dc4e-5d91-80a0-92dc75c4a1dd |  | note | CATEGORY: IP
label | c268397a-2cd4-5785-91d8-21ead9182d46 |  | note | – – – – – – – – – – – – – – – – –
label | 1491fb7d-d6f8-5a03-b038-3e4bdc5d4584 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | df3cc2f0-e6e3-50e4-a6ce-eb62f691f61b |  | note | – – – – – – – – – – – – – – – – –
label | bc78e381-8537-5341-b0c3-0c20485db16c |  | note | VERIFYING DOCUMENTS:
date | 5c48cf62-128c-5eeb-b6f6-61d8e7e469af |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | 1cff9767-e358-559e-b761-75e3c306f6b9 |  | note | REFERENCE: IFC Drawings 610.33
label | b80274ff-2fbd-5c3e-a422-131705bcc136 |  | note | – – – – – – – – – – – – – – – – –
label | 3fd1eb78-2039-5d81-b612-6a93e9d96c10 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 10103e57-9985-5858-991c-db1a4dcbb754 |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | 9fb799d6-01f7-5ade-b949-00de7902b6ba |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | f26fea5f-270c-5661-99d3-515de07479dc |  | note | iii. have a flowable consistency
label | ee21d4cc-ac12-5ee7-b370-fb880e342c7e |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | d6f51d63-f4ae-5ca0-956c-71f194108444 |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
text | c339732e-ce0c-5ae0-bb01-3dc8462c0409 |  | textbox | Enter: Teambinder Material Approval number
label | 4392c0f8-ffbf-5eab-9973-ab1381058458 |  | note | – – – – – – – – – – – – – – – – –
label | c7b34fa1-fe4a-5868-8d90-07ac8dbcdde1 |  | note | METHOD: Document Review
label | 847d816b-a6fe-55c1-9d12-5d05c034a3ab |  | note | – – – – – – – – – – – – – – – – –
label | f708b59e-7a9c-56cc-8a75-b69b8c60c9f0 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 2ace9b33-9ec3-5e3f-89f6-b390a15fac42 |  | note | – – – – – – – – – – – – – – – – –
label | eb46b472-d2f9-54c6-a70a-dfd1e9c6fd22 |  | note | CATEGORY: HP
label | c3771dae-a2cd-5b05-bf8f-e27ffb11c935 |  | note | – – – – – – – – – – – – – – – – –
label | c754d497-73a5-5d7c-b780-ea8c0127c8f7 |  | note | RESPONSIBILITY: Nominated Authority
label | 0a64b587-0ad8-51e8-8899-0df4b5b88dba |  | note | – – – – – – – – – – – – – – – – –
label | 0523bcea-7da4-53de-8f2d-1c8b4caa2df5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9989d4bb-5be3-5c2b-aa27-4701b21856f6 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | e0b8daef-0d47-507a-9fc6-63c4d270d7ed |  | note | REFERENCE: 610.23 (d)
label | 8f166148-a550-59ae-ab31-20863a137956 |  | note | – – – – – – – – – – – – – – – – –
label | 3b8a3de1-365a-5210-ae65-805ebc64bb02 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 7b9eeccb-b445-52dd-8abe-a3a135e84ca3 |  | note | Note: This may be the same product used for the concrete curing
text | b8dd58c6-26ee-5eaf-bb21-d38a1b14e117 |  | textbox | Enter: Teambinder Material Approval number
label | 7cd3943a-ed6c-5ecc-b7f9-3b464044f880 |  | note | – – – – – – – – – – – – – – – – –
label | 431c98d1-24cd-57ef-9345-27c1e07db657 |  | note | METHOD: Document Review
label | 335f5b59-c08d-583c-8d50-a5e64c5b7f8c |  | note | – – – – – – – – – – – – – – – – –
label | fc63d64d-b4f0-55c9-ae2f-82bd5ed5b6e4 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | d4083b26-5e90-52c2-a34f-db0ecba6ec92 |  | note | – – – – – – – – – – – – – – – – –
label | 47ccdd45-e9ac-5050-880b-49a06b728af7 |  | note | CATEGORY: HP
label | 08006a15-378a-569f-976b-5e5f0bd20901 |  | note | – – – – – – – – – – – – – – – – –
label | 7babeed3-67f0-5c9d-907f-c513d9978e13 |  | note | RESPONSIBILITY: Nominated Authority
label | 7dbe4a97-82d8-5b89-9af2-8f944ad7ccfa |  | note | – – – – – – – – – – – – – – – – –
label | 600f32c6-f5d0-5169-8e18-c1029408a933 |  | note | VERIFYING DOCUMENTS: This ITP
date | 28561b99-bebc-58dc-b80f-125d0caabd16 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Installation Methodology & Works Method Statement
label | 5497412b-2efd-557f-88e6-1e58a9afad7f |  | note | REFERENCE: 630.20 AS5131 Clause 11.2.3
label | 2da0ee51-cc38-52eb-b00c-d45f19864cec |  | note | – – – – – – – – – – – – – – – – –
label | 4a4ec67b-61c6-56bf-baec-20a44cbd5091 |  | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | 606b2aee-59e4-596c-938b-6af409b9e34a |  | note | ○ Transported to site;
label | c5ecd785-2d44-5889-9e7a-456c485d67b9 |  | note | ○ Handled on site;
label | c039f3fd-a80f-51f5-b8dd-43766974e8fa |  | note | ○ Installation Procedure (subcontracor ITP's);
label | f01ba61e-b383-55a3-980a-87d5893f7b46 |  | note | Attach: Subcontractor ITP
text | 5940587c-44be-5867-9857-f6c9163bde8b |  | textbox | Enter: Teambinder Approval number
label | 56148cde-ab55-550f-9dac-c7a15d09aed2 |  | note | – – – – – – – – – – – – – – – – –
label | a02af8a3-eefa-5c3e-a870-078685cef460 |  | note | METHOD: Document Review
label | 047300e1-39fd-57cf-aaf3-d542c57cd4a0 |  | note | – – – – – – – – – – – – – – – – –
label | f28f739b-85df-5343-bd2a-d2811c0997da |  | note | FREQUENCY: Where applicable, once, 14 days prior to use of devices
label | bfe3489e-751e-5d1b-9c07-a0dfa909742e |  | note | – – – – – – – – – – – – – – – – –
label | e76dcffa-0ec3-5b68-aac1-c15eef40041f |  | note | CATEGORY: HP
label | 74c4ba48-bba7-50c6-a69d-97f25daa9f00 |  | note | – – – – – – – – – – – – – – – – –
label | b5295e24-9860-5854-b110-6509c73928db |  | note | RESPONSIBILITY: PE/Nominated Authority
label | c54865ef-4034-5bfc-9b45-7cb00834e491 |  | note | – – – – – – – – – – – – – – – – –
label | 982c8805-ba04-5d8e-b192-15232f0f5f21 |  | note | VERIFYING DOCUMENTS: Subcontractor ITP, ConQA Hold Point Release
date | 450bb1d2-a9f3-5816-b74d-15ff1e0e3256 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 355c7835-7893-5bfb-b825-602e2c7a8d0d |  | note | REFERENCE: MRPA Quality Management Plan
label | 477c406f-ba43-5370-92ef-e400f34edb3a |  | note | – – – – – – – – – – – – – – – – –
label | 061c7e32-c8e3-59b5-b85a-f3f9309536bc |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b814fd24-2db5-5da8-aa0c-7f05b7909b97 |  | note | – – – – – – – – – – – – – – – – –
label | e9ef90e3-b081-55ec-b505-6bde8e1c8cec |  | note | METHOD: Document Review
label | e3570541-d9ac-5429-99fc-b8c63b6e9f42 |  | note | – – – – – – – – – – – – – – – – –
label | 8dc1183b-19b6-5eb9-a201-25792e144a20 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 80b3c85b-aca0-55ea-a304-9feedab2db27 |  | note | – – – – – – – – – – – – – – – – –
label | 5219b563-8480-5070-b4f7-240d17f4e758 |  | note | CATEGORY: HP*
label | 8ebaa06d-e094-5e73-9a45-96a973611853 |  | note | – – – – – – – – – – – – – – – – –
label | a8f02d87-fcec-5901-8a93-56d26fca5b55 |  | note | RESPONSIBILITY: All
label | 83d41b60-9d5b-5e1b-87c6-70b9a4a4c6da |  | note | – – – – – – – – – – – – – – – – –
label | 7fdc3c26-1fa1-549a-81eb-17a4bc21dd77 |  | note | VERIFYING DOCUMENTS: This ITP
date | e0498479-b963-59c9-b30e-dedc107b002a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection
label | 435a5b5d-08f9-5f4c-a39b-3d4a5262c256 |  | note | REFERENCE: IFC Drawings VR 630
label | 78b6be4c-3c95-5821-b7e2-9f4628f56564 |  | note | – – – – – – – – – – – – – – – – –
label | 34a8cd84-dbe9-543a-b02f-c42e3e19418b |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | 71e9836f-a54a-518a-9842-92855f52006e |  | note | – – – – – – – – – – – – – – – – –
label | b456c106-57cd-58a9-b886-3ae249619f30 |  | note | METHOD: Visual
label | 068107f0-69b1-5040-a226-cb432938f14d |  | note | – – – – – – – – – – – – – – – – –
label | 954e7f54-c41d-5fab-9784-846d28e40365 |  | note | FREQUENCY: Each component
label | 31ac532c-1027-56e4-8787-0546c401c411 |  | note | – – – – – – – – – – – – – – – – –
label | 3ecfe6f6-290f-5b4f-a31b-2e1109956ff1 |  | note | CATEGORY: IP
label | a7020a27-0dd2-5c8e-bb44-a1e73997ee4a |  | note | – – – – – – – – – – – – – – – – –
label | d1709cff-95d8-533a-aa3f-5b1c660c8644 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a06a3ccc-0d1d-5312-a591-f3d1eef4cb0e |  | note | – – – – – – – – – – – – – – – – –
label | 36efe8b7-15d9-5e06-ad1a-0c0e1efc3657 |  | note | VERIFYING DOCUMENTS: This ITP
date | 000d1e3c-6916-5d44-9444-9b18e652d75d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Materials Inspection
label | 02c74bab-7e03-5aee-9440-b63f38bcf521 |  | note | REFERENCE: IFC Drawings VR 630
label | af5863bd-8ba4-54a9-b0b4-73c9bf69c2f3 |  | note | – – – – – – – – – – – – – – – – –
label | 2c084065-aa8e-5bdd-aeca-9f0492668522 |  | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | 0f051f49-9307-50c5-8b16-fd16b70cc302 |  | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | ecba117d-512d-5fa2-85bd-c9ac8a5b7204 |  | note | – – – – – – – – – – – – – – – – –
label | 12da203d-582d-51e2-b779-2c801185611b |  | note | METHOD: Visual
label | 427edb7c-e4c1-5481-ba1e-732bc0ce6052 |  | note | – – – – – – – – – – – – – – – – –
label | eafd6caa-242f-5707-8baf-2f11671dff1b |  | note | FREQUENCY: Each component
label | d2131386-cf63-5ca0-9eb3-00ef0984a41a |  | note | – – – – – – – – – – – – – – – – –
label | b21fa651-b8e8-504c-8889-dfeaee343413 |  | note | CATEGORY: IP
label | 33fed794-a37d-57a3-b565-950875e5e173 |  | note | – – – – – – – – – – – – – – – – –
label | a656d96c-f426-5a30-9f54-58a7721177de |  | note | RESPONSIBILITY: SE/PE/SPE
label | b95bea7c-ae11-5aa5-81f2-495541f5d62a |  | note | – – – – – – – – – – – – – – – – –
label | 8b3479d9-ff0a-56a0-93f2-3c7ffc1c7b8d |  | note | VERIFYING DOCUMENTS: This ITP
date | 2a64135d-8455-5f5e-aad7-ca9e1ecb54b7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Materials Inspection
label | 700bf814-5389-58a8-b62c-791073b59790 |  | note | REFERENCE: IFC Drawings VR 631
label | d2253a71-75c8-5a38-8ee5-8d23fef0e6dd |  | note | – – – – – – – – – – – – – – – – –
label | 678bce47-ccd1-5bae-9c56-2ea8ec4d6767 |  | note | ACCEPTANCE CRITERIA: Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | c442c009-8c73-550d-9a82-7ef963a1108a |  | note | – – – – – – – – – – – – – – – – –
label | c9814072-60b7-5c6a-be60-57198c9bb88a |  | note | METHOD: Visual
label | 0f8b44cc-d5e6-563c-a650-38211a1ecfec |  | note | – – – – – – – – – – – – – – – – –
label | fe2ea460-aa86-546a-aece-5a7d71561d58 |  | note | FREQUENCY: Each component
label | 3c8faadc-495d-5e48-8a29-f91dde124ba3 |  | note | – – – – – – – – – – – – – – – – –
label | c179d682-2bc1-50d2-a88d-2ff7c93b7744 |  | note | CATEGORY: IP
label | f1c08457-6d1f-5357-9170-52860e35c4ec |  | note | – – – – – – – – – – – – – – – – –
label | 9406a37c-6d1a-50ec-b0aa-0a4f381200a9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cfc34b7b-b256-5d6c-9954-741e5badcc59 |  | note | – – – – – – – – – – – – – – – – –
label | e1712359-4248-5245-8931-119ccd7b751d |  | note | VERIFYING DOCUMENTS: This ITP
date | b77d32c3-f9e8-559a-a068-bc2fa40138b1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Materials Inspection
label | 10a05708-9754-54ed-919d-a5800774ac76 |  | note | REFERENCE: IFC Drawings VR 631
label | 50538c78-9f75-5824-905b-9c7c2bb7f556 |  | note | – – – – – – – – – – – – – – – – –
label | 65d2f768-afb8-580b-a8e8-146598b5a236 |  | note | ACCEPTANCE CRITERIA: Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | bad66442-f130-5321-825d-d661f92c0d17 |  | note | – – – – – – – – – – – – – – – – –
label | c8fad7c7-9880-5d88-abb3-e6a087f10398 |  | note | METHOD: Visual
label | eae84acc-eec8-578e-ac88-5f325f8e3486 |  | note | – – – – – – – – – – – – – – – – –
label | 2207ba82-36fc-59b6-a01d-73a4327014c0 |  | note | FREQUENCY: Each component
label | 5d0e708a-40c0-51fb-9fd4-6b20c9305696 |  | note | – – – – – – – – – – – – – – – – –
label | c4f575a3-837a-5ab5-85fc-2c77b16b61ed |  | note | CATEGORY: IP
label | cde6012b-ed4d-5ffe-b2f4-64fe47723f06 |  | note | – – – – – – – – – – – – – – – – –
label | ecfdfd5f-5727-5a22-bd6d-a8847a8bcb9b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2c2d8375-e222-56ae-a032-d1d0850dcf8e |  | note | – – – – – – – – – – – – – – – – –
label | a913ccfe-d0b5-5624-8d1e-b71fa9c21eff |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f37f985-af7f-5fa8-abbf-c27e2ac8c030 |  | date | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | 7abf6b15-5c55-5ca5-ab6c-a515ec920009 |  | note | REFERENCE: IFC Drawings, Product TDS
label | 22391361-9c17-5927-921a-4e221df2b17d |  | note | – – – – – – – – – – – – – – – – –
label | 9ac418ec-3adb-5f60-b803-32886ad115e8 |  | note | ACCEPTANCE CRITERIA: Ensure the bearing surface clean and free from loose particles that will prevent solid seating of the parts
label | 4061ed76-be6b-5d45-9787-a7150d7a9e00 |  | note | – – – – – – – – – – – – – – – – –
label | 307f142f-1616-5e29-a1dd-67e93d9d42c9 |  | note | METHOD: Visual
label | c70781d3-f3b3-5da7-b1e1-82875529a2ff |  | note | – – – – – – – – – – – – – – – – –
label | 85faa7d5-7c1f-5d1c-9c1f-78dc89474075 |  | note | FREQUENCY: Where applicable, each installation location
label | 14fa5f4e-c805-5887-82cc-4fd0e07d7b03 |  | note | – – – – – – – – – – – – – – – – –
label | 49d87b66-6c6f-5f32-b6f5-050d97c59858 |  | note | CATEGORY: IP
label | a21c0753-82a5-5e0c-948e-a25e4fe742d7 |  | note | – – – – – – – – – – – – – – – – –
label | a5320812-6a4f-5093-87a0-c5bb01d1e73e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8aa617e8-dc32-58da-909a-45d111fcb476 |  | note | – – – – – – – – – – – – – – – – –
label | eabe59ee-216b-5d84-8e78-fd18041091b0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 438d458f-739f-51b9-b9ef-f67bfba67f3b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 38b93087-d76e-5984-83ee-0b55de2a75db |  | note | REFERENCE: 630.09, 631.14
label | d87abdd8-a2fa-590c-a083-f9973461e9a0 |  | note | – – – – – – – – – – – – – – – – –
label | dfd47fdb-09d6-5349-9cde-4400a0aa17e3 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 5414012d-9265-5c1e-9259-775211ddf575 |  | note | – – – – – – – – – – – – – – – – –
label | 55638e3f-0ac7-51f3-a971-30fc87289ee8 |  | note | METHOD: Visual
label | 9c3e2639-9621-5bfc-b42e-c30e1c75b64c |  | note | – – – – – – – – – – – – – – – – –
label | e450aa02-da11-5b30-9a24-ed24b9fcb5d2 |  | note | FREQUENCY: Each component
label | 67ef74fc-de57-5777-933c-7a46ab1a42e2 |  | note | – – – – – – – – – – – – – – – – –
label | 6d4a2a9d-80e9-5df3-9615-ddcd6a068c76 |  | note | CATEGORY: IP
label | 586fe7fa-02be-56fe-9e4a-d01e9f34af26 |  | note | – – – – – – – – – – – – – – – – –
label | 422f1813-8e67-540e-969a-07755619b284 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0facfe05-a886-50f2-b973-ca6cdd9d35b7 |  | note | – – – – – – – – – – – – – – – – –
label | 97da19df-1813-5148-af38-bea19a58588c |  | note | VERIFYING DOCUMENTS: This ITP
date | 1596e7e5-8a23-5da2-ba22-17edcdea0e11 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | ac272e6c-f552-5f22-8eca-9fe76112e94d |  | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | 06a799eb-49f8-55d5-8f35-2d34caf971e4 |  | note | – – – – – – – – – – – – – – – – –
label | c0a28742-65a3-51c9-8ff8-7aff75b38ceb |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | 719bb433-b88e-541d-9aa3-c92a6bc3b837 |  | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | b6b9873a-43cc-538e-905d-c63802e16a38 |  | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | 0a6b8f39-e301-5fab-8119-170b50d19fac |  | note | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
label | ce619503-fb48-5ccb-95c3-e3434e4f6d7f |  | note | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 19b52686-7357-5e40-8310-35b42e5ee471 |  | note | – – – – – – – – – – – – – – – – –
label | 0106ea88-6054-57f2-aa5c-e24d3030d209 |  | note | METHOD: Measure, Visual
label | 975b0a05-0424-50de-b676-77173130dbc2 |  | note | – – – – – – – – – – – – – – – – –
label | 223cff2c-2580-50ff-9c1a-dcc153b7c3bf |  | note | FREQUENCY: Each component
label | c8cffc54-fcec-501b-bd6d-48fedca6c2eb |  | note | – – – – – – – – – – – – – – – – –
label | a5067551-d83c-5b71-981a-c8b6a6ceffa9 |  | note | CATEGORY: IP
label | d063cbea-f2c0-55bb-9836-95d8f6ee7145 |  | note | – – – – – – – – – – – – – – – – –
label | 20e4ec96-acd8-5f7f-8267-d61dfbd47354 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 15159d12-d9c9-5f23-8747-e32cdce016c8 |  | note | – – – – – – – – – – – – – – – – –
label | 34e5826d-53f5-5a03-b60f-0dee34ab5d16 |  | note | VERIFYING DOCUMENTS: This ITP
date | bf93df97-843d-53b2-9e89-a52456c0d538 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition
label | 87474308-5f3e-5e7c-80c7-fd148e96800e |  | note | REFERENCE: IFC Drawings VR 630
label | 2319a018-541a-5799-bf04-82f761ec73e8 |  | note | – – – – – – – – – – – – – – – – –
label | 999bc4a7-86ff-5d9d-8d1c-28959105f770 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 7bbebd75-b213-5c09-b5c5-3a545d55d763 |  | note | For posts base plates, the arrangement is to be (from the base plate):
label | 443142cd-85e0-5bba-80f0-8200fcbe3194 |  | note | – Base Plate
label | cc417c99-b00f-5cc9-8a51-0e441305a392 |  | note | – Washer as specified
label | adfffd4a-f905-5d08-b519-350ee5a1a51b |  | note | – Lock Nut as specified
label | 36db655b-8186-5db2-86b1-36c2d605920c |  | note | – Nut
label | 60c3baa7-6b1c-5a69-a0c2-a2141d261677 |  | note | – Bolt protrusion (1 clear tread)
label | 3d28d322-0941-5d09-94f6-80315587bd01 |  | note | – – – – – – – – – – – – – – – – –
label | 3ea8c8e0-6782-50bc-9522-c777027046c0 |  | note | METHOD: Visual
label | cb0573b3-ac09-5fb8-a192-1636183243a5 |  | note | – – – – – – – – – – – – – – – – –
label | 23074794-ef30-5a05-8ed2-ccdfba09b7bd |  | note | FREQUENCY: Where applicable, each bolted connection
label | 10a4dd43-56b4-5450-b291-b33335f4ce03 |  | note | – – – – – – – – – – – – – – – – –
label | 864eae73-d6b5-5e9e-80f6-cddf5fdbc0ca |  | note | CATEGORY: IP
label | d4b55161-6356-518c-a447-47d777f96744 |  | note | – – – – – – – – – – – – – – – – –
label | 460a4458-2af1-559a-8f18-c4d7bdac1df7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 19f6d0d8-ecf3-5fd6-8aeb-2d25ebc7e34c |  | note | – – – – – – – – – – – – – – – – –
label | 24b23190-0b57-5ad3-8901-57173c5e83e3 |  | note | VERIFYING DOCUMENTS: This ITP
date | f3c184c6-9d06-5548-9f0e-50794544dca7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Fastener Tightening - Snug Tight Condition
label | d2b57c7a-df65-51cd-ad8b-b5c88da482d9 |  | note | REFERENCE: IFC Drawings VR 630
label | e2462959-1380-52ea-b1ed-ed37eb7a601c |  | note | – – – – – – – – – – – – – – – – –
label | 6bf5342f-21f4-5ef8-94e4-430c0d3a93e9 |  | note | ACCEPTANCE CRITERIA: Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter.
label | c68f65f1-a425-555c-b14c-496cdb9800c5 |  | note | ○ Tapered washers shall be positioned if specified.
label | a7908a75-5ab0-5e73-b0be-373569c68766 |  | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 176e7a98-1db5-5ca6-998c-19b43f7c895c |  | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 40e3f500-eb74-5e61-9852-2213bb467a83 |  | note | – – – – – – – – – – – – – – – – –
label | 880fa3fc-76e3-5c9c-8e93-183df15f2dd7 |  | note | METHOD: Measure, Visual
label | dc53047c-d9c0-5d31-9a02-5aa439e069bd |  | note | – – – – – – – – – – – – – – – – –
label | 89d194c5-0473-51fb-abbd-3914763cc65f |  | note | FREQUENCY: Where applicable, each bolted connection
label | 2f07fb7c-3c68-5f32-9d36-398f8e1a7d3d |  | note | – – – – – – – – – – – – – – – – –
label | 83edf216-e8eb-539d-afa7-4b01fb28f9d5 |  | note | CATEGORY: IP
label | f9c0861f-12dd-552f-b26b-8ae9a2378dc2 |  | note | – – – – – – – – – – – – – – – – –
label | 072df4a5-5003-5041-813e-193890ea29ed |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9a6ba226-0053-5e7e-9a4a-c7eb6a4a2b81 |  | note | – – – – – – – – – – – – – – – – –
label | 413bff5c-f1e1-559a-a86b-dc7e6d29e83a |  | note | VERIFYING DOCUMENTS: This ITP
date | bd0e4285-2524-5894-9ca5-4d553a562a31 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Survey Conformance
label | 6cf960c3-c5cd-5c16-97d4-3fa1e34ac074 |  | note | REFERENCE: IFC Drawings AS4100 Clause 15.3.1 - 7, AS5131 Appendix F, Table F3
label | 1d2b066c-4f48-5a56-a5c5-bfa8bbd32340 |  | note | – – – – – – – – – – – – – – – – –
label | e5c7ada4-a4be-5d2c-91f6-8dbf7681c6ac |  | note | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | b24f8e25-f8ec-5a40-9456-fd3baaa96f73 |  | note | ○ Departure from RL = ±10mm
label | 84054f75-37bc-59ca-ba29-581ba51cbaa7 |  | note | ○ Departure from plan position = ±6mm
label | 99d43e20-ce47-5ff3-8172-5bd59eca20e4 |  | note | ○ Departure from alignment = ±6mm
label | 4c23b9ba-9ba4-5406-a30f-61e9efabeda8 |  | note | ○ Irregularities in alignment = 25mm in 30m
label | b7d07182-6382-5742-9de0-c48861635508 |  | note | ○ Projection of bolt = +25mm, -5mm
label | 3a4b9e9f-105b-5117-8ee7-6f24587e9c0f |  | note | ○ Location of beam = ±3mm
label | 08457c39-6cdc-54e4-8e6c-0bc3df719a93 |  | note | ○ Location of column = height/500
label | 5a85e06a-9575-5af1-8b03-48dde4d16086 |  | note | – – – – – – – – – – – – – – – – –
label | 7dba61e1-af16-51e8-85f0-f1dc5f6ceabf |  | note | METHOD: Measure, Visual
label | efc9ce97-c90c-58f6-9ffc-44fc197b3ddc |  | note | – – – – – – – – – – – – – – – – –
label | 8e13cdf5-7372-5751-a1c0-017b5b985b20 |  | note | FREQUENCY: Each element
label | 2d85e5ca-63bc-55ff-8d21-b5e03c52568f |  | note | – – – – – – – – – – – – – – – – –
label | c69c8269-d6bc-577e-9bcf-e6ef93decab6 |  | note | CATEGORY: HP*
label | cf79ba19-eb4a-5ead-94a1-cee8ab74fd91 |  | note | – – – – – – – – – – – – – – – – –
label | 2cffe64d-2e17-56e9-a2d2-27ae74436f1a |  | note | RESPONSIBILITY: PE/Surveyour
label | 86e79f55-8c5e-59e3-b987-2e19f6979ebf |  | note | – – – – – – – – – – – – – – – – –
label | 5ffa5c1c-8ef3-5400-8a40-920a0a7a686c |  | note | VERIFYING DOCUMENTS: This ITP
date | 8f1cfd19-559d-5842-8395-c70e85f681c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Base Plate Formwork Construction & Placement
label | 23562188-8a01-5f14-a286-854e695fe8c1 |  | note | REFERENCE: IFC Drawings
label | c86f1183-14e1-536a-951b-57b5406a8136 |  | note | – – – – – – – – – – – – – – – – –
label | 6e43eb63-d36f-5f05-a439-de9981c40307 |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
label | 04b96603-a775-5a6c-9756-1b519ef2779a |  | note | ○ Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | b57117d5-fed1-589e-9491-87b3efe2ac50 |  | note | – – – – – – – – – – – – – – – – –
label | 53802d49-709e-57e8-94da-7b87940dfb99 |  | note | METHOD: Measure, Visual
label | d67d49e9-284b-53f6-8381-813c4b6c9f14 |  | note | – – – – – – – – – – – – – – – – –
label | 5c2b9738-b606-56d9-96ca-9764969e504e |  | note | FREQUENCY: Each post location
label | d1719b50-1a7a-5ca5-a1d1-265af9af3b2b |  | note | – – – – – – – – – – – – – – – – –
label | 83cf1e25-a6e6-5d41-a4c8-40369528b80d |  | note | CATEGORY: IP
label | d9a9007c-23e2-5ec0-b285-70edba42f8b4 |  | note | – – – – – – – – – – – – – – – – –
label | 33f61635-5a46-53f2-88c0-0d950dfa3cb2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 36726093-081d-5a11-bd9e-b17e5441fcf6 |  | note | – – – – – – – – – – – – – – – – –
label | 4f862518-15ae-5d53-a690-e36c43ca03a7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9f4328dd-b797-5462-ae0d-477371f39a51 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-soaking Concrete Surface
label | bd833f7d-71d2-5fdd-807c-f3bb24c29203 |  | note | REFERENCE: Product TDS
label | 61302fe3-c258-5284-9caa-eee7e3d278c5 |  | note | – – – – – – – – – – – – – – – – –
label | 675a1955-9eca-5fe3-89a8-3b5cea87d5dd |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | f187aa99-c384-51e2-b93d-c8bdf6cfc602 |  | note | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | b09c61be-14a2-5734-98d5-2971e16df349 |  | note | – – – – – – – – – – – – – – – – –
label | 52941c6c-8654-5ef7-897b-0f12cc9d6e81 |  | note | METHOD: Visual
label | 050e5f2a-efbd-59e1-a690-cfa917b4e436 |  | note | – – – – – – – – – – – – – – – – –
label | 7f22f79e-95a0-57d1-afd2-e58759ca5840 |  | note | FREQUENCY: Each post location
label | e1c73ffe-4576-5a70-a7f9-180bd31ec9d8 |  | note | – – – – – – – – – – – – – – – – –
label | 824f3ad1-5912-5b46-9920-164a2ffe73a9 |  | note | CATEGORY: IP
label | 32d8285c-d535-51cc-b704-aba28286c7a0 |  | note | – – – – – – – – – – – – – – – – –
label | 8260f04e-bb42-5666-b785-0aa4b8fb0633 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f17097b9-6e9f-5dc5-bfd9-8bdeca41d275 |  | note | – – – – – – – – – – – – – – – – –
label | 59e1c9c9-1e34-5553-97e5-320430f55b6b |  | note | VERIFYING DOCUMENTS: This ITP
date | 6daf59c0-d113-5334-8290-6ae2fe3ced66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions
label | e0a57724-85c8-51e7-a4b8-ed076c7e4396 |  | note | REFERENCE: 610.17 Table 610.171
label | 9713ed69-2def-51d7-97bb-311ec32c12f8 |  | note | – – – – – – – – – – – – – – – – –
label | efb52f29-8a8d-5535-87a1-4f1286fc0584 |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | 0d51e4e0-6cd3-5bb3-8b8f-ab5421fe4361 |  | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 052aa883-8061-5e4e-b3c9-4d3e361da5de |  | note | Record: Required information on the Grout Pour Record.
label | be86540a-56e4-5ddf-a461-43304c302c29 |  | note | – – – – – – – – – – – – – – – – –
label | 1fbe3851-f410-5c72-af66-db54aa112e2b |  | note | METHOD: Measure, Visual
label | 3f7618c7-f990-593d-970d-167091f6e3f8 |  | note | – – – – – – – – – – – – – – – – –
label | 24e32d4a-3c63-50b6-89aa-36b189a868cc |  | note | FREQUENCY: Each lot
label | 2707b480-3089-5739-8d4f-c156663b801d |  | note | – – – – – – – – – – – – – – – – –
label | 3f83f359-b911-51b8-9fab-0cd7f42dca52 |  | note | CATEGORY: IP
label | 84770239-a699-55f1-8ed1-025e0a6c968e |  | note | – – – – – – – – – – – – – – – – –
label | 5495a49e-2f8f-5df2-95de-4165f7d954cf |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | eb3ccae6-3391-5bc1-b7dc-ed620dec46e0 |  | note | – – – – – – – – – – – – – – – – –
label | 8edd06b6-a6c4-59f7-9821-19f9f8e1a206 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5e379abc-c40e-5c1b-b162-7cbdb26abe7c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Mixing Product
label | 986d044b-0f55-545f-88b5-fbe2b8ac0845 |  | note | REFERENCE: Product TDS 610.28
label | b1cfbae4-6370-5be4-bc49-9407dc9e3078 |  | note | – – – – – – – – – – – – – – – – –
label | c5d4f277-05c1-5dec-8b77-f9845ad4757a |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 6392e226-1a6e-54ca-9c51-2157efd95430 |  | note | ○ Only whole bags to be mixed with potable water.
label | f64a80b1-7b12-538a-ba7c-fdc886a7b3e0 |  | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | 6a01520b-ea05-567f-a50c-c24a409d776a |  | note | ○ Product poured into the mixer slowly.
label | 86876427-c608-56fd-a7e1-2f7b91640004 |  | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
text | ac616716-b4f6-53f0-ad70-804849ec3c49 |  | textbox | Enter: Required information on the Grout Pour Record.
label | c5759e68-2298-5caa-a299-649e83d3021d |  | note | – – – – – – – – – – – – – – – – –
label | 71f26aea-d6d5-5595-a1a4-8c1c115c5bed |  | note | METHOD: Measure, Visual
label | 43e7443f-b737-5e2e-b684-731152b0fb71 |  | note | – – – – – – – – – – – – – – – – –
label | b2c15f44-4e3b-586d-841a-5eee7cf54062 |  | note | FREQUENCY: Each batch
label | feb002ea-28e0-5ad6-bbd3-e63e014f8098 |  | note | – – – – – – – – – – – – – – – – –
label | 3665e4ab-d3fd-5536-b64c-a3d85967a3d7 |  | note | CATEGORY: IP
label | 139848fe-80ed-58fe-aaf9-fd75039972b7 |  | note | – – – – – – – – – – – – – – – – –
label | c5ae8533-40c7-5db7-82cd-e5210dc0eca5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 77c373a0-7b61-54c9-9008-79b39dc93db3 |  | note | – – – – – – – – – – – – – – – – –
label | 83339b52-a428-551f-a060-c289b0891269 |  | note | VERIFYING DOCUMENTS: This ITP
date | ac6b606f-4c81-5633-99fd-077b1c2534fa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Product Testing - Compressive Strength Cubes
label | 9c7724d6-7477-58c8-a42c-df25edc1e4c0 |  | note | REFERENCE: 610.28, 610.33
label | 3b88b0f2-2bc0-5777-a0c5-8ecbb576f1cf |  | note | – – – – – – – – – – – – – – – – –
label | 56b7c1ff-ece0-5a6e-9146-b1eb0b8f62ff |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | d02147aa-ce09-5149-99fa-e6012f4bb084 |  | note | ○ Testing is be in accordance with the following frequencies:
label | c6abf53b-69c5-58d5-a403-ae96e64e4cb3 |  | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 974c6229-0cb3-5e85-bd45-def08ed4b941 |  | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | f8415fff-c3e2-5328-b9d3-6bd3bb23402f |  | textbox | Enter: Required information on the Grout Pour Record.
label | 12d1f69e-3bb9-5cbf-b27f-99f6dc33dce7 |  | note | – – – – – – – – – – – – – – – – –
label | 41f21175-cc2e-54b9-b091-a4165c11c4d2 |  | note | METHOD: Test
label | 69de4133-01ef-55a2-8bdd-235771a6fc76 |  | note | – – – – – – – – – – – – – – – – –
label | 6df9ad82-ca1f-58e3-a65e-9c803406229a |  | note | FREQUENCY: Each lot
label | f1b727e2-7974-5bdd-a6fb-a4029a6ffe1c |  | note | – – – – – – – – – – – – – – – – –
label | aa62d24b-fd88-5f08-97c9-f3edf5190a10 |  | note | CATEGORY: IP
label | 28c05559-7593-5fe0-a4db-50b39db0e3c2 |  | note | – – – – – – – – – – – – – – – – –
label | 0dc251cf-e8bb-5b87-b26c-2dc397fab66e |  | note | RESPONSIBILITY: Tester, SE/PE/SPE
label | 9182e25b-2e42-5731-8a0f-707521f92f0c |  | note | – – – – – – – – – – – – – – – – –
label | e769b8cf-036f-52c0-858b-c1874fb88098 |  | note | VERIFYING DOCUMENTS: This ITP
date | 817c8a5b-1cce-5434-bc7e-b3a7c2c0687e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction
label | 80a56adb-3649-5db4-928b-bcb51e527dd9 |  | note | REFERENCE: Product TDS
label | 8e3e9e26-be76-5499-ba30-d50a77da3279 |  | note | – – – – – – – – – – – – – – – – –
label | fcc2210c-f209-50bf-b0eb-d2eb0a8fc496 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | 4e53bc4d-a41c-5af0-8b13-32c1b7000061 |  | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | b92aba03-37a7-5cef-8a34-9fb88ed0bcee |  | note | ○ Product should flow to all areas and self consolidate.
label | 7b71bb9f-db70-51f3-b157-ad0cff50e02e |  | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
text | 266d4040-831c-5da4-95c6-99a983b801ec |  | textbox | Enter: Required information on the Grout Pour Record
label | 882376b2-e47c-57f5-af13-b9235a3f31db |  | note | – – – – – – – – – – – – – – – – –
label | 6c9367b3-2cdf-55e4-9ac9-a1e0e1f5105f |  | note | METHOD: Visual
label | d5b1d200-00df-54cb-a65a-2237ecc9ab31 |  | note | – – – – – – – – – – – – – – – – –
label | 97561005-a8b9-5dfe-864b-359bd455a905 |  | note | FREQUENCY: Each post location
label | 629b3d3c-210e-5448-8c66-9961ef7f94fd |  | note | – – – – – – – – – – – – – – – – –
label | 97c52eb6-c48a-527f-87fa-ce14dcf8d8bd |  | note | CATEGORY: IP
label | fba35a17-1bc9-52d6-9613-0ca5fcaec24c |  | note | – – – – – – – – – – – – – – – – –
label | 2d194a58-80fe-5f03-8619-3d2b713b0fd4 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8acf0f57-4bc2-52ab-8de2-81adf46a406b |  | note | – – – – – – – – – – – – – – – – –
label | c334fc00-40a4-58be-aa02-d3358d3748ca |  | note | VERIFYING DOCUMENTS: This ITP
date | 2373c380-5d3c-5709-827f-cd92829e997c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes & Protection of Works
label | 62f1d1d6-a6ae-53a9-9cdc-a37f233ed97d |  | note | REFERENCE: IFC Drawings 610.17
label | e775980f-aec6-566e-8a3e-cfb7a550a563 |  | note | – – – – – – – – – – – – – – – – –
label | 715e90c4-7a86-514b-951c-b740c793be87 |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | b966924e-f688-522e-9207-adee97c3c30c |  | note | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 1a2519a3-4b5d-5f3c-b541-fc453030871a |  | note | – – – – – – – – – – – – – – – – –
label | 5d74fedd-3ad2-5646-94de-10c15e6a6175 |  | note | METHOD: Visual
label | 28856fc1-659d-5be3-a986-6e52c8cab56c |  | note | – – – – – – – – – – – – – – – – –
label | 0e641d11-28c8-5b0c-ac76-eeb37956024a |  | note | FREQUENCY: Where applicable, each post location
label | 7288a30a-31a6-5e37-b101-35ef1eceec1a |  | note | – – – – – – – – – – – – – – – – –
label | 5f32c1eb-91ab-508c-9454-f5f0d6407cff |  | note | CATEGORY: IP
label | ac0742b3-963d-5ece-b3a7-c6731c441c5b |  | note | – – – – – – – – – – – – – – – – –
label | 2c68f6f5-8df1-5e6b-850e-9340ec6571c5 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 10dd66b8-e379-5267-9600-1763d81566e9 |  | note | – – – – – – – – – – – – – – – – –
label | e90c2da5-a891-5439-be33-679d073ddec6 |  | note | VERIFYING DOCUMENTS: This ITP
date | e8523e2d-4403-589f-a6d6-5c6eb7b18602 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Curing
label | 372747e4-00bb-53a6-99f8-9c446fb5d265 |  | note | REFERENCE: Curing Methodology 610.23 Table 610.231
label | b0eaf003-48c4-512d-b034-8e8309dcbc25 |  | note | – – – – – – – – – – – – – – – – –
label | 66d57a97-5e32-5c43-b64c-c343d1614048 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | b8c7e06e-5fd6-5f5e-b936-7823a5760bac |  | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 05418791-9402-57e6-ab30-91f82282a268 |  | note | – – – – – – – – – – – – – – – – –
label | 30c737cb-b3a9-5296-87a9-69c67b88b859 |  | note | METHOD: Visual
label | e6311a5d-047b-53f4-b48c-91285db81d84 |  | note | – – – – – – – – – – – – – – – – –
label | 0ba50b34-b712-5c2c-8ca9-45f08bc87837 |  | note | FREQUENCY: Where applicable, each post location
label | 13bab647-f741-51c2-bd51-72f570958e47 |  | note | – – – – – – – – – – – – – – – – –
label | fe57251b-58c0-5115-b4dc-761ec0461adc |  | note | CATEGORY: IP
label | 457b6493-6644-5464-8fba-46e99dcf9007 |  | note | – – – – – – – – – – – – – – – – –
label | deece8d3-4666-5e0b-af02-eadda98b1c9c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fa3c8874-321f-5bdf-9c83-d563eb1d3b90 |  | note | – – – – – – – – – – – – – – – – –
label | 53150924-cb3f-50f2-8c15-bd1e6aab72d4 |  | note | VERIFYING DOCUMENTS: This ITP
date | d663854a-9982-5b50-870a-ceabc6ed279c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Architectural Steel Erection
label | cd24e8b1-deb0-583a-9bf0-be735ec9d5ff |  | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | 3a26fc22-7844-5d3c-85e8-2f3acdef4255 |  | note | – – – – – – – – – – – – – – – – –
label | 9af45f0b-e2bc-532e-bc13-0891e5db55be |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level and square
label | 48cd99e7-5017-51e7-898e-73862a0a7d6f |  | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
label | 1e9ea324-ba7b-5e48-add9-37b6bfad8c36 |  | note | – – – – – – – – – – – – – – – – –
label | 1956fb79-a785-5327-ace0-1491265cfc54 |  | note | METHOD: Measure, Visual
label | 01bbf5a8-8510-5e71-8a20-c2fd52588509 |  | note | – – – – – – – – – – – – – – – – –
label | a3dccf7f-e156-5644-90bf-6f746d20a89a |  | note | FREQUENCY: Each component
label | 2deda90d-a231-5e06-b307-7ef842a7c614 |  | note | – – – – – – – – – – – – – – – – –
label | 62936bba-fc02-5a17-85b3-715d540300aa |  | note | CATEGORY: IP
label | b0de3267-9860-5a76-8aa8-36d8719dc73f |  | note | – – – – – – – – – – – – – – – – –
label | 1fff160f-7ddb-5847-b351-48d83df7f9a7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 56993b4d-9e24-5f7d-8338-d533872bb7c0 |  | note | – – – – – – – – – – – – – – – – –
label | 7e59b585-4bf2-5b67-baf7-f49cd156a636 |  | note | VERIFYING DOCUMENTS: This ITP
date | f0cbe122-9114-599f-834a-f09bd5cbd5fc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Architectural Steel Erection-Fasteners
label | ee85d6a3-55f1-5eec-83b2-36acb077e403 |  | note | REFERENCE: IFC Drawings VR 630
label | 3c4764a4-f0d2-5d58-a190-5c42e0d5e02c |  | note | – – – – – – – – – – – – – – – – –
label | f2c45cf7-0a71-5d05-99c1-9b09e892b683 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | c4b02b34-42c1-533b-bfef-822d7822680a |  | note | For architectural/Security screens, the arrangement is to be (from themounting post):
label | 6fae05b1-7d9c-5a31-9f32-63cf18a8c924 |  | note | – Post
label | 6e1aae0e-c6a7-5c60-b9d0-abea9833c2df |  | note | – Washer (s) as specified
label | c5c2298c-03d3-5f7f-86c7-996f60650115 |  | note | – insulating washer
label | 2e933884-110b-5402-83cd-6d99926a40b5 |  | note | – insulating bush
label | 1cf4d1e4-31c4-55da-adb0-7a5fcc0302a6 |  | note | – Insulating washer
label | 7f7ddc0b-8632-55e1-a11b-fb9a9cab2f02 |  | note | – washer as specified
label | 18f77903-e38a-522d-a20e-bc4f401ae2ba |  | note | – Lock nut
label | 6c909769-9e9b-5a1b-b39c-fb5f311bbce7 |  | note | – Nut
label | f2ed21ee-978f-5743-a564-956b3cf0cd9d |  | note | – Bolt protrusion (1 clear tread)
label | 4e91c446-865a-5015-8e2b-f1d802fb130c |  | note | – – – – – – – – – – – – – – – – –
label | 48459789-7104-5f2c-8dda-e4c64925d458 |  | note | METHOD: Measure, Visual
label | 9e0765e6-74da-58bf-bda6-2bc14f23db89 |  | note | – – – – – – – – – – – – – – – – –
label | 0dece7ee-c8f5-52ef-9408-35125e243e77 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 5ec67322-9426-537d-9680-507c5eb1d8dc |  | note | – – – – – – – – – – – – – – – – –
label | 2f8674fa-1121-59c3-84e0-9a495f15282e |  | note | CATEGORY: IP
label | 3647cdf0-19c3-564d-a17e-30f17b768315 |  | note | – – – – – – – – – – – – – – – – –
label | 950bb3ee-42c0-5e1b-b9df-6d83ef5860e0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b87ef16b-e3bb-59fe-a46f-5ba6831e1583 |  | note | – – – – – – – – – – – – – – – – –
label | 120e5806-9dd8-51b1-aed5-1efb613ac812 |  | note | VERIFYING DOCUMENTS: This ITP
date | fd05da25-07b0-5a4c-a8f9-1f43cf59e39c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Installation of Electrical Isolation Materials
label | e9a53e29-b621-5a3c-a968-e344d34b229b |  | note | REFERENCE: IFC Drawings
label | dfcf5539-ddcc-5e35-acf3-ed42d8520715 |  | note | – – – – – – – – – – – – – – – – –
label | 24667508-44e9-56fe-821c-fe59db616765 |  | note | ACCEPTANCE CRITERIA: Installation of Electrical Isolation Material in locations specified on the IFC drawings.
label | efbabcc7-466d-5b68-9187-9efe8a24c96f |  | note | – – – – – – – – – – – – – – – – –
label | 896c40ec-aa6b-53e1-b679-7d7eb012bb6d |  | note | METHOD: Visual
label | 8521a3aa-5d29-54d2-8541-01f79e8abf51 |  | note | – – – – – – – – – – – – – – – – –
label | 26671333-d1d5-5a79-9a01-3652487efec9 |  | note | FREQUENCY: Each component
label | 8428c5a5-6c15-50d5-8efa-70e341d152f5 |  | note | – – – – – – – – – – – – – – – – –
label | f873b1d6-081d-5507-8212-243b8afb9118 |  | note | CATEGORY: IP
label | 99801890-c7f7-51e4-ab26-a5f4ebd76df7 |  | note | – – – – – – – – – – – – – – – – –
label | 4a943141-d72a-58ed-baf0-7f42ba81ef56 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a0f3a114-0638-5cba-a23a-0d19cfa72e7f |  | note | – – – – – – – – – – – – – – – – –
label | 91e1c30d-19fc-5223-9a3b-01a4a89ab4ad |  | note | VERIFYING DOCUMENTS: This ITP
date | e6081f97-b28e-53f3-907c-0830f064802d |  | date | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | a2e3df91-50f4-5b56-a7f2-083be31cf0b4 |  | note | REFERENCE: IFC Drawings VR 630
label | 64598970-bb46-5701-92cc-82f104d19581 |  | note | – – – – – – – – – – – – – – – – –
label | a55a3996-d2f8-5580-91f9-12999bed03b4 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | 1e99be68-d26a-5d28-ab09-6e8d68703ea7 |  | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | 3b786f2d-5e26-5599-a5eb-ae7796f82857 |  | note | – – – – – – – – – – – – – – – – –
label | 7e4341ba-cebd-5c7d-ac30-20bf2d98014d |  | note | METHOD: Visual
label | 31bc6639-9ab3-543c-bda3-75ce0e618f7f |  | note | – – – – – – – – – – – – – – – – –
label | 3f058c40-29cf-5937-a2ae-12c5eb44e8ae |  | note | FREQUENCY: Each component
label | 7a37d74a-e7d4-5ca0-a0ae-60ff68db9009 |  | note | – – – – – – – – – – – – – – – – –
label | 5c9c4488-2d0e-5890-a677-80e65384b30e |  | note | CATEGORY: IP
label | 48b40435-5550-5e1b-a7ba-9dd3a7d7e675 |  | note | – – – – – – – – – – – – – – – – –
label | 4cf2f07a-951c-5c4f-9f2f-a16688bbd45f |  | note | RESPONSIBILITY: SE/PE/SPE
label | e62b7cd4-27e8-5ce1-bd8e-8b7204fb9d4f |  | note | – – – – – – – – – – – – – – – – –
label | 5d3aaf78-f083-531b-9217-65f4d3f29415 |  | note | VERIFYING DOCUMENTS: This ITP
date | ffa50e35-73f3-5a2a-9dcd-04a4ebe359df |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | f537c6c8-e0d7-55f5-9af0-812b1fc1dfd9 |  | note | REFERENCE: IFC Drawings, Product TDS 610.28, 610.33
label | 41c64bde-0370-53df-a67b-27386dec4674 |  | note | – – – – – – – – – – – – – – – – –
label | 0d605e87-30c5-5f07-b690-b1a3ef5d49a1 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | cc200bd0-8b7e-5633-8f13-80059439100e |  | note | ○ 28 day compressive strength per sample comply with the design strength.
label | 1bfb837d-eb69-5858-bd7a-d5f371ec6335 |  | note | Attach: Compressive Strength Test Results
label | 4be45c64-16a9-590b-9298-d50893a79c87 |  | note | – – – – – – – – – – – – – – – – –
label | 6bc8f0ca-ef69-5405-bf64-1846b8a09a74 |  | note | METHOD: Document Review
label | c35cb2d0-710f-5fdb-a1a9-01e07cf0162c |  | note | – – – – – – – – – – – – – – – – –
label | ce8465a3-ffe7-5258-8154-6a056c6bba37 |  | note | FREQUENCY: Each cube
label | dd2cd5c2-4e13-5b3c-a811-b49b7e430bce |  | note | – – – – – – – – – – – – – – – – –
label | 1656d823-72e7-5cb2-90d6-9b6b956b546f |  | note | CATEGORY: IP
label | c3e4e051-f51a-5f28-9873-4cf992da04fb |  | note | – – – – – – – – – – – – – – – – –
label | 525a3a6d-020b-5b02-89e6-10f41f04a20b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 94b34c88-3652-5d2a-aa07-8f4a003a0ee8 |  | note | – – – – – – – – – – – – – – – – –
label | e0e01d54-a33d-5feb-b9f8-8896b03e52f5 |  | note | VERIFYING DOCUMENTS: This ITP
date | f4724151-cf98-5d4d-bedb-122b820c4330 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | f2ec6ef4-6ea2-54df-a0e7-413576f7fe0c |  | note | REFERENCE: IFC Drawings AS5131 Appendix F, Table F3
label | c03bfb58-708d-55e8-8870-c11d68d88b26 |  | note | – – – – – – – – – – – – – – – – –
label | 7655f221-1dad-5008-bf86-d919c1b8a2d9 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 5b197d18-33ae-5afc-8c6d-00e0dda4bd27 |  | note | ○ Departure from RL = ±10mm
label | ccce2029-2f76-5543-845d-1df926611945 |  | note | ○ Departure from plan position = ±6mm
label | 0bbede1f-830e-5631-8f8e-0d6a7d5adc79 |  | note | ○ Departure from alignment = ±6mm
label | fc44d600-b06a-502b-bebf-c07c2208e1c0 |  | note | ○ Irregularities in alignment = 25mm in 30m
label | ccb8e311-a6fe-50f3-af31-072b1c0b28bd |  | note | ○ Projection of bolt = +25mm, 5mm
label | 87ec1a68-6cb7-5bf6-8209-b24f8cced04d |  | note | ○ Location of beam = ±3mm
label | e8eb1d72-9709-56e4-b83e-9e2ce2b66801 |  | note | ○ Location of column = height/500, 10mm max.
label | 3836b889-a985-5e79-8970-0c7e17ab5681 |  | note | Attach: Survey As-builts / Survey Report
label | d8cf2cc5-d889-573f-b8a7-2a59e8858c1d |  | note | – – – – – – – – – – – – – – – – –
label | 0b5d2d68-8731-5b34-9399-9c55d2b2fe44 |  | note | METHOD: Document Review
label | 11f12f8c-28c3-565e-af01-88e4c50b7271 |  | note | – – – – – – – – – – – – – – – – –
label | 4c7926d1-047f-5ab7-83a3-9f4b59b5b4a2 |  | note | FREQUENCY: Each element
label | ea790092-5f4e-55c6-b264-1b3645d91c53 |  | note | – – – – – – – – – – – – – – – – –
label | f973d39a-ea5d-5c3c-bd1d-c1efbe7dc92d |  | note | CATEGORY: IP
label | 6d164d3c-880d-52ee-a9f1-edbb3c990928 |  | note | – – – – – – – – – – – – – – – – –
label | df60a693-f3ca-5204-b1e6-8f8b4d460ced |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 19f8e62e-5d20-5aaf-817d-2edb26893710 |  | note | – – – – – – – – – – – – – – – – –
label | 53457dc3-30aa-598b-b102-89ced69ade9c |  | note | VERIFYING DOCUMENTS: This ITP
date | 4e33047c-9a16-5b20-bdfe-2c7ac5604fdf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 29c04a38-120f-55b8-97f3-f09b8fb82acf |  | note | REFERENCE: MRPA Quality Management Plan
label | eb9813af-bf12-56a7-977b-df420c8cd09e |  | note | – – – – – – – – – – – – – – – – –
label | 37661999-45b9-5c07-9223-4b662c7d29c4 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 94872680-8034-5153-a4d4-0b128965947b |  | note | – – – – – – – – – – – – – – – – –
label | 5d24fdf4-3be8-5987-8324-281f890f072e |  | note | METHOD: Document Review
label | 922dab42-e2c1-5f56-8f79-eeda6b8b1b81 |  | note | – – – – – – – – – – – – – – – – –
label | f5d832bb-aa02-51ad-b250-11ad5753ebc0 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | a77facec-1798-5fd7-adfa-457f735c9360 |  | note | – – – – – – – – – – – – – – – – –
label | e707bd2b-6846-56e4-8901-65c10ded7572 |  | note | CATEGORY: HP*
label | 6140d5b1-7759-5c25-9831-78547f596e73 |  | note | – – – – – – – – – – – – – – – – –
label | 10f07ce5-6da0-5468-a8a2-1a9f591fdd8b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4e5a5ef6-dd72-55f2-a6cb-884b04962aab |  | note | – – – – – – – – – – – – – – – – –
label | 6658bb05-bc58-5b58-9676-1d5547e0ac0c |  | note | VERIFYING DOCUMENTS: This ITP
date | e0215d5f-ca9d-5e44-8b02-9bd58495ee88 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f7363100-7008-54c6-88ff-b815d7ce76e3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1853b711-2735-5e46-8681-cda7b138d838 |  | textbox | Name:
text | dc2407a3-f055-51ef-99a5-2391f9b6d165 |  | textbox | Position:
date | 424dea86-da6b-52cf-ad68-0b323dbfa159 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-153-STR-SSB-Concrete Coating | itp |  |  |  | Yes | ITP-153-STR-SSB-Concrete Coating Rev 0 | 510e5b50-b919-4347-ab2e-441c1105247d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | a2673a8b-fc35-50c9-aafa-ba6458fe44e0 |  | note | Document Title: ITP-153-STR-SSB-Concrete Coatings
label | b223b3d3-4ee9-58dd-a112-dffc5569e651 |  | note | ITP Description: SSB-Concrete Coatings
label | 2346872e-0e0b-54b8-8dbb-214fe0a5f108 |  | note | Discipline (e.g. CIV/STR/RAIL): 153-STR
label | b62b0b25-3068-5914-b2fc-70796cec9dd1 |  | note | Revision Number: 0
label | 4454e4d0-7587-5f11-9fb2-e0d5f2c8426e |  | note | Revision Date: 1/05/2024
label | 9a95467f-c5dc-5207-9a3b-b81cc575c840 |  | note | ITP created by: Mike Freeman
label | 1c94691a-a19c-5502-8e9f-6bfecd6800b6 |  | note | ITP approved for use by: Victor Mira
label | 184094d7-5f57-5141-af0a-58b8f04235e3 |  | note | 1.1 Non Dependent
label | 5941ee97-b769-5279-ba96-a5f0b5dc89da |  | note | Reference: VicRoads Section 685 November 2018
label | 457e5581-c44e-5133-94a8-e8dd2a124716 |  | note | 1.2 Non Dependent
label | 1caa123f-0bc7-5ebf-9711-598ae8ab1d74 |  | note | Reference: VicRoads Section 686 November 2018
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Anti-graffiti System Selection
label | 95509f3c-5aee-5c2f-9f4a-a7756cfe9bcc |  | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (e)
label | a836a56c-9ae1-57d1-9f76-73ad3447137c |  | note | – – – – – – – – – – – – – – – – –
label | 607d977b-8e84-5559-a5a8-756b8e684566 |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | bf53d562-f987-56ae-9715-cbf162bc6751 |  | note | i. be either a film-forming or a penetrant system
label | e1978fe7-c555-5d98-9265-5d7214918269 |  | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | 6f5ccce5-9eb6-5ac2-a9fc-fd979919dfea |  | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | e2afd1be-96dc-52b0-a9e5-84295e7ec681 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | b90c1248-8024-528b-af64-899d7117504e |  | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | 8ffb1d21-d2d4-5fff-960f-b47614def1e5 |  | note | vi. application thicknesses (film-forming):
label | a76ce805-6087-5bc5-9c1c-352a9c18ff5d |  | note | ○ WFT total = 175µm min. OR
label | f4bb2e68-6c4b-5cb1-b704-d95a5a7ee312 |  | note | ○ WTF per coat = 88µm min.
label | 89f5545e-9d7d-5be1-8f17-9cc55b742e64 |  | note | ○ DFT total = 100µm min.
label | 4369a26e-90c7-5889-8cbf-52950befdf40 |  | note | vii. adhesion to substrate (film-forming):
label | 0bd312e5-27cc-5294-9f19-33daa3e18246 |  | note | ○ 0.75MPa min.
label | d4244c0a-c25a-5cfb-b7b4-be2a8071b476 |  | note | viii. application rate (penetrants)
label | 0b7afc0e-a04a-5617-bfde-556c3398f8b7 |  | note | ○ as per the minimum thickness on the manufacturer's TDS
text | 47aa4734-43ee-5703-a284-c09e50f3a225 |  | textbox | Enter: Teambinder Material Approval number
label | 6b7809b4-6c4f-56ca-985e-0957f04be31f |  | note | – – – – – – – – – – – – – – – – –
label | 86839990-ef69-5ab3-916a-0240f826cd56 |  | note | METHOD: Document Review
label | 742aa26f-cbac-540e-a0c8-2e930664ed49 |  | note | – – – – – – – – – – – – – – – – –
label | 781a229e-87b8-5537-a6bc-87d528bc0510 |  | note | FREQUENCY: Once, for each coating system, 14 days prior to application
label | 223a9a3f-3613-5ea5-8f87-db87c80de91e |  | note | – – – – – – – – – – – – – – – – –
label | 0defc65f-19a7-5833-9062-859a2b6b3d4b |  | note | CATEGORY: HP
label | 8744d04e-6893-5013-ab4f-a90693c9e4a0 |  | note | – – – – – – – – – – – – – – – – –
label | 2dd5a0de-3264-5168-95d1-96eba2bec0f5 |  | note | RESPONSIBILITY: Nominated Authority
label | b227393b-03d8-5f00-88ec-d85e84e5e29c |  | note | – – – – – – – – – – – – – – – – –
label | ed3112c5-9727-5273-a547-11037b8cfcd4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f30adebe-651a-5faa-9469-6bde8fbaf8a5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Decorative & Anti-carbonation System Selection
label | 912c743c-052c-5114-844e-0a56337ae8b9 |  | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS, 686.04, 686.05 (a) & (b) Table 686.051
label | 1bb9af8f-d00b-5554-822f-0c53a2256e45 |  | note | – – – – – – – – – – – – – – – – –
label | bbfb9ce4-e5e9-5fe4-b013-d2fba675d242 |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | 18d709d4-eb1b-5c28-b519-c908001526e7 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | 6931f0c3-21b0-545e-bdfe-32d10fefd182 |  | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | ee25c631-e83d-5fe0-b92c-09d1a7583d17 |  | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | 8c18c921-b28f-5f31-8e63-8f198a69b658 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | 587e4df8-789c-59f8-8ed6-9d9e00748101 |  | note | v. be guaranteed to last for 10 years of outdoor exposure
label | f2997a82-4c7c-53f5-87cc-bec886851c6e |  | note | vi. application thicknesses:
label | d8a99468-edab-5fc9-8e24-6c9cf3475fea |  | note | ○ WFT per coat = enough to achieve the total DFT
label | 404ec5a8-5604-5919-b255-de24d19e892e |  | note | ○ DFT total = 150µm min.
label | 41fe288f-9254-5da5-a65c-8f0df1c63559 |  | note | vii. adhesion to substrate:
label | ae3451d2-02db-52a1-aeaa-36c8831de3bf |  | note | ○ 0.75MPa min.
label | ff0e6fd8-0c62-53f9-84ec-790d2250c0ae |  | note | viii. able to bridge cracks up to 0.3mm wide
label | ccf0ae56-114b-5d16-bcf3-064865282089 |  | note | ix. able to be re-coated within 24 hours
label | 8c0da748-2ec6-5e42-a960-4ec87b0a327d |  | note | x. have a minimum pot life of 1 hour
label | 08bc89f1-a260-5920-9379-808279ebc25a |  | note | xi. compatibility to an alkaline surface
label | 6ec249db-05bc-5382-97c2-fb444b52405c |  | note | xii. equivalent air thickness >150m
label | df956bed-4c3a-5a53-83df-42a7fa1f9e4a |  | note | xiii. equivalent concrete thickness >450mm
label | 08a28c0a-5da8-52e4-ac3c-96e546179ae9 |  | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 1897a424-e36b-5cda-8df1-01576c25bb81 |  | note | xv. Water vapour equivalent air layer <4m
label | 84e20a3f-a198-57ec-840e-9e8c53af80c8 |  | note | Enter: Teambinder Material Approval number
label | 17a4d439-8c08-5640-a59f-3fa81a115a7c |  | note | – – – – – – – – – – – – – – – – –
label | d4473971-02d6-5abb-9908-cad7425f1152 |  | note | METHOD: Document Review
label | de75356b-fbd1-5df2-9e3a-f90833e16d62 |  | note | – – – – – – – – – – – – – – – – –
label | 7dc4a61d-453e-58e4-90bb-89d39b8d00fb |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | 66f3c673-08e2-5156-b910-51951e77fc6b |  | note | – – – – – – – – – – – – – – – – –
label | 7dae3b05-69f8-5c4f-9201-a4a349b51f6a |  | note | CATEGORY: HP
label | cdb84924-468b-596f-b550-2ea48a4a37ae |  | note | – – – – – – – – – – – – – – – – –
label | 5cd3d650-7691-5a6e-956b-b0d07c9a88cf |  | note | RESPONSIBILITY: Nominated Authority
label | 2dc50216-3f1c-5330-9061-59cecee5f7e9 |  | note | – – – – – – – – – – – – – – – – –
label | 0e64b1d8-949f-56c4-aa35-68d1d51b7c2e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 13753b8e-7e6a-5e8f-9d9a-724eceffdcd7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Decorative, Anti-carbonation & Anti-graffiti System Selection
label | beec8ade-918a-506b-a330-3399c1661e85 |  | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051
label | 4a469303-9ab6-500d-9dda-f82e1d5f2ca2 |  | note | – – – – – – – – – – – – – – – – –
label | 7681d75c-56a0-50db-8c0e-9b6824672110 |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | 5557fdfa-877a-5a02-9726-c6edc0951bd9 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | 68c4f0f3-7f62-5e1f-9526-ffb2dc9107fa |  | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | 7be5afe6-2dea-5f67-a9ab-7648b290fe4d |  | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | 171b54d2-6709-5f52-a210-11adfaf2ebda |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | 9997528f-21e0-5e1c-ba89-5e7e4f6573ab |  | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | 7a894583-b006-5dd9-b693-9833b4a53b1f |  | note | vi. application thicknesses:
label | 01efcaa7-1b9b-5fe6-850c-983cf804b1c3 |  | note | ○ WFT per coat = enough to achieve the total DFT
label | 3e2ae81b-8b26-58e2-a070-7fb2e1382460 |  | note | ○ DFT total = 150µm min.
label | 747eb9b9-8831-5425-a23e-86d36d0e608c |  | note | vii. adhesion to substrate:
label | 87c95401-5e65-5016-b207-d4a2772145b6 |  | note | ○ 0.75MPa min.
label | 754a76fe-3da8-54cd-a6df-7089a0db049f |  | note | viii. able to bridge cracks up to 0.3mm wide
label | d7bebc9b-36af-5048-b84e-ea0ca358d082 |  | note | ix. able to be re-coated within 24 hours
label | 58e36c0f-b30d-5542-9793-45f7867e4c5c |  | note | x. have a minimum pot life of 1 hour
label | 5099b4bf-4025-581d-b6af-d85a3848219c |  | note | xi. compatibility to an alkaline surface
label | 3040170e-16b4-5add-9ee4-32d8fb4df5f5 |  | note | xii. equivalent air thickness >150m
label | 4fb2e23a-4ac4-5f74-ab6b-6b99c83c9152 |  | note | xiii. equivalent concrete thickness >450mm
label | 64d0c09b-1843-55c2-963b-a66cdf14f49b |  | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 78d4cffa-59af-506c-9d2d-b8145d523750 |  | note | xv. Water vapour equivalent air layer <4m
text | b122acef-9979-5604-aab8-cbf07c360b10 |  | textbox | Enter: Teambinder Material Approval number
label | 4a1769ac-ff80-5f13-a0ad-339ded1954a4 |  | note | – – – – – – – – – – – – – – – – –
label | 6556d936-a5ab-5c39-9e99-5743917d270a |  | note | METHOD: Document Review
label | 98e44cbf-cc6d-5391-9996-d0cce364b5f0 |  | note | – – – – – – – – – – – – – – – – –
label | d7b7fef8-f22e-5405-b479-9956d0ae0421 |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | 1ce65ec3-542a-51e3-9317-2945ab0c1f93 |  | note | – – – – – – – – – – – – – – – – –
label | 4be87227-6b3a-5de3-beea-668d7f46feac |  | note | CATEGORY: HP
label | da070b61-e1b6-5dac-b79a-ca51a124f512 |  | note | – – – – – – – – – – – – – – – – –
label | b589efd5-8781-5085-abcd-226558ea9fa0 |  | note | RESPONSIBILITY: Nominated Authority
label | b327907a-f14d-57b0-ad5a-680517e81145 |  | note | – – – – – – – – – – – – – – – – –
label | dc64b4dd-65fa-542a-83f1-7d6382efe410 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 138e9fba-4588-558e-8316-2f4889e9b5f7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Atmospheric & Splash Zone (Dual Protective) System Selection
label | 61f637f2-5ce3-5b87-8bdd-f5f9dbd00d8a |  | note | REFERENCE: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051, 686.05 (c) (i) & (iii)
label | 7a96bb6d-c822-515d-ae1b-c139e6226720 |  | note | – – – – – – – – – – – – – – – – –
label | 1f1a97b7-4c67-5da2-a495-f6cc8185fd8b |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | 6cc71211-228a-58f7-859c-608a148d90ea |  | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
label | faa74049-20a8-5099-a819-2aa1a216a1d0 |  | note | ii. all coats to be compatible with each other
label | 60cad2b9-8a7f-53c8-8557-eb275915d822 |  | note | Penetrants:
label | 2d6803d4-fbce-5d31-b5e2-e177ee553cc3 |  | note | iii. active ingredients:
label | 5802c75d-a6c6-56fe-8470-0886f2953915 |  | note | ○ Silane = at least 95%
label | f718d1b2-7d2e-5687-857d-df5180c4a069 |  | note | ○ Solid silane & silane cream = at least 80%
label | b02bc645-c75c-534b-90cf-05118755fb8b |  | note | ○ Silane-siloxane & siloxane = not specified
label | b7be8725-90eb-5f57-aafe-17b6e9e3dc5e |  | note | iv. application rates:
label | 29a60e97-9f72-5e62-99e4-6acbde8e302f |  | note | ○ Silane = 2 applications of 0.3L/m² min.
label | 0a225c0a-ac7e-5409-ace6-3e3512eee0a1 |  | note | ○ Solid silane & silane cream = 1 application of 0.4L/m² min.
label | d76b9097-4f99-5e90-bb23-b8cbd9e5a94f |  | note | ○ Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
label | 61cf4a5c-f2f3-52d8-bcca-745439b0c186 |  | note | Film-forming coat:
label | 4077ae14-78cc-5cb0-8449-0eb1677fcca9 |  | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
label | b7f637dd-919f-5c21-920e-a88f3db5841f |  | note | vi. to be water or acrylic based, solvent-free
label | a5c545a0-a52a-516b-85b0-a38ffbddf233 |  | note | vii. to be non-yellowing, colour-fast and not subject to fading
label | e430ab2e-31b3-5954-a1a2-f914b2305283 |  | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | 6f4eae1f-e199-58c3-ac9b-3a3110b32ed0 |  | note | ix. application thicknesses:
label | ba31683c-14c6-5774-9495-040c7cc3bce0 |  | note | ○ WFT per coat = enough to achieve the total DFT
label | a47ca5db-1ba7-5b04-bba7-4089fe1c5d07 |  | note | ○ DFT total = 200µm min.
label | 0f9210d1-3b14-5a12-a2dd-25db06a7b222 |  | note | x. adhesion to substrate:
label | 6b501444-3bec-5295-8380-13a2a17499e2 |  | note | ○ 0.75MPa min.
label | df7567b4-acb1-5281-986b-fc75ed503de2 |  | note | xi. able to bridge cracks up to 0.3mm wide
label | 3e8ba69d-f136-5536-a989-10bb9b29c75e |  | note | xii. able to be re-coated within 24 hours
label | d8d0971f-9cd5-5c47-99e5-37d7949df9f2 |  | note | xiii. have a minimum pot life of 1 hour
label | c6ac622b-b203-59fc-b560-b69435f50530 |  | note | xiv. compatibility to an alkaline surface
label | 9cab69e9-9f64-5a1e-8123-6604687fb87d |  | note | xv. equivalent air thickness >150m
label | a4bc5bc7-0e42-54dd-a6b1-10aaa8b2d41f |  | note | xvi. equivalent concrete thickness >450mm
label | 7147e4fe-fcf6-5c92-9e6e-b2d86791a327 |  | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 0d9d516e-5162-5819-b89c-c21411daf350 |  | note | xviii. Water vapour equivalent air layer <4m
label | a5ddb5c6-f038-5e34-8f60-c2fffd2a1aae |  | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
label | 75930776-e960-504c-99f2-7a775ebb56b4 |  | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
text | 04dbed72-1558-5d5e-970b-f9bbd6cea303 |  | textbox | Enter: Teambinder Material Approval number
label | 13d8a373-3b82-5e86-b256-ac200be8babf |  | note | – – – – – – – – – – – – – – – – –
label | ee891446-75fb-5d0c-bfb5-8a6f6f0b112d |  | note | METHOD: Document Review
label | 74bbee15-9b69-58a3-868b-83348bb079e6 |  | note | – – – – – – – – – – – – – – – – –
label | 040c49b8-5aa1-5862-bc33-2e17ce599cef |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | be330a99-f53a-5aa3-90cc-8c0d7b47c43f |  | note | – – – – – – – – – – – – – – – – –
label | 5fbfac16-fee6-5b0e-9b49-665802d80f70 |  | note | CATEGORY: HP
label | 8d1b5d60-6b6b-5adc-a153-b5afc3e0246d |  | note | – – – – – – – – – – – – – – – – –
label | e1ae9fb2-39ec-59b6-b7c5-1f39f3275c26 |  | note | RESPONSIBILITY: Nominated Authority
label | e76b83af-c811-5678-b2ea-b18e8bdaea67 |  | note | – – – – – – – – – – – – – – – – –
label | 0b7a12ab-804b-5798-b04c-a5de29fbfcd6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 8ef3e856-501d-53ab-befc-bcdfe791ad85 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Procedures
checkpoint-status |  |  | checkpoint | 3.1 Work Procedures
label | ba12f18e-9c6b-5944-8594-376b118fe3dd |  | note | REFERENCE: 685.05, 686.04
label | 28db0356-8191-5dc1-8d2a-ed500b7a9c3c |  | note | – – – – – – – – – – – – – – – – –
label | 29bb2b76-2739-5261-bdd0-5172f7165b74 |  | note | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
text | 9ed6fc4f-8900-5c56-9744-6c98411249b2 |  | textbox | Enter: Teambinder Hold Point number
label | 15cf687a-e053-5d14-bc85-95c66db0bf32 |  | note | – – – – – – – – – – – – – – – – –
label | 8c0fcd63-5534-5760-9b38-0f7fe4c95877 |  | note | METHOD: Document Review
label | 5e65436f-9b90-5d01-8f90-e00c20792a57 |  | note | – – – – – – – – – – – – – – – – –
label | 5b04c543-0883-50a5-ab5e-efcd22e665dc |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | ea427dff-0cce-5e58-927b-16fa664249ef |  | note | – – – – – – – – – – – – – – – – –
label | d0f7e176-5d5c-5799-b2b1-35fc0f5dbdb6 |  | note | CATEGORY: HP
label | 6d430ad6-ef99-542b-b77b-63c666dda2c3 |  | note | – – – – – – – – – – – – – – – – –
label | 2f761957-e1e9-5e86-9b3d-d8d9cf6d1539 |  | note | RESPONSIBILITY: Nominated Authority
label | 33dfa5ce-2e73-5802-a4d8-0a392ab90262 |  | note | – – – – – – – – – – – – – – – – –
label | 98704389-25b7-594c-949b-0f1056bc2b9a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | cd25c0d5-d5fe-52be-9739-8aa3ce48f750 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Coating Personnel & Equipment
label | dd0f91fc-117f-568b-804b-e575210475aa |  | note | REFERENCE: Coating System TDS, Surface Cleaner TDS 685.16, 686.18
label | 7610010f-92df-5251-8f30-207366d68852 |  | note | – – – – – – – – – – – – – – – – –
label | 1c904d5f-db27-5ba5-a93d-466ef38462f6 |  | note | ACCEPTANCE CRITERIA: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
label | d6dac53d-1c55-5d7e-8943-5bfc51b9f337 |  | note | ○ Application personnel require 2 years minimum experience.
label | 2571debd-19a4-5a3c-970c-a163d58013c4 |  | note | ○ The supervisor shall remain present at all times.
label | d186f641-c915-55ca-b007-1aacea934b77 |  | note | ○ Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | e4781095-8ff2-5cf4-8886-a45b58e4777b |  | note | – – – – – – – – – – – – – – – – –
label | fa69540a-7fe3-5c19-a0d4-98b72fa004c5 |  | note | METHOD: Document Review
label | 4995748a-1754-5f97-bb92-bac26ec140a0 |  | note | – – – – – – – – – – – – – – – – –
label | 8104c055-85bd-5a91-838c-8e6946deedea |  | note | FREQUENCY: Once, prior to application.
label | 2c69c8a1-5a42-5e9b-ae8f-86044b4d897a |  | note | – – – – – – – – – – – – – – – – –
label | 4df82aad-98d1-5473-bf5b-0cb8cbc49fba |  | note | CATEGORY: IP
label | 0ebda2e1-d538-5176-8472-60a47625ae77 |  | note | – – – – – – – – – – – – – – – – –
label | 68708fe8-1174-516b-a6f3-b955ea54fc80 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c0143734-079c-5bd5-92ea-adf1868a2591 |  | note | – – – – – – – – – – – – – – – – –
label | 27d9918d-1d0a-5517-8bbd-9fbb3537527a |  | note | VERIFYING DOCUMENTS: This ITP
date | 1cde5c3f-ad78-536f-b31c-d3e3f140d985 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Protection of Adjacent Works & Property
label | 5d9fff36-d088-588b-b8fe-2f4e681991e8 |  | note | REFERENCE: 685.17, 686.10
label | 3dc8d845-c789-5046-9d18-873f5ab7e75f |  | note | – – – – – – – – – – – – – – – – –
label | d9921196-f249-5733-9624-f733e12543c5 |  | note | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
label | caaff5e4-e7f7-5e42-baa9-03a2f349cb4d |  | note | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
label | 9130509b-ba3f-50b3-9034-e12e55c5d840 |  | note | ○ Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | 35d2be67-512b-5ea5-99f2-6f96778e6cf4 |  | note | – – – – – – – – – – – – – – – – –
label | 9e69c358-a12c-55bb-85b3-9c5433e8c74d |  | note | METHOD: Visual, Document Review
label | df10e76e-c90e-5538-b4d6-c11f685088f8 |  | note | – – – – – – – – – – – – – – – – –
label | b3ad4109-6277-5019-b7ac-230d57d60867 |  | note | FREQUENCY: Where applicable, 2 days prior to application.
label | 3a33f069-b126-5c95-832e-aec724b8193e |  | note | – – – – – – – – – – – – – – – – –
label | ca55f1dd-4622-5703-9ac4-b2f63262bff0 |  | note | CATEGORY: HP
label | 22874418-4898-5fa4-b147-473bd3b25597 |  | note | – – – – – – – – – – – – – – – – –
label | 10904c58-5a1d-5f57-9304-23ea23517869 |  | note | RESPONSIBILITY: Nominated Authority
label | 29ac32a1-72eb-5bed-b2d8-40b80ba24539 |  | note | – – – – – – – – – – – – – – – – –
label | 93c64c37-5508-5aef-8dc1-ef30e4799516 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | d015f59c-d383-5ff6-96e1-0c7716eedeaf |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Minimum Concrete Curing Period
label | 799709de-9ea3-5fa8-be1e-10f9a5197239 |  | note | REFERENCE: 685.08, 686.16
label | 172b6a33-8fe6-54c8-be55-c231ce52fe0d |  | note | – – – – – – – – – – – – – – – – –
label | 51cafa55-c6d8-5a63-8c9c-c0745e39be1e |  | note | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
label | a8abf057-db39-5872-a9bb-8f0e7e002c5c |  | note | ○ Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
label | a9cd211e-5b97-5378-ab7b-623094a59005 |  | note | ○ Accelerated cured concrete = 14 days
label | 4eac582d-776d-5b4d-8661-7f3ffd9b7d17 |  | note | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | edbc8d22-460c-54a5-9dc5-3a11b7fa82e5 |  | note | – – – – – – – – – – – – – – – – –
label | e2f18f6b-1bc2-51e3-98c7-356622a605ca |  | note | METHOD: Visual, Document Review
label | 076313ff-b237-5292-890e-a516a5c0d6d8 |  | note | – – – – – – – – – – – – – – – – –
label | d9760de1-6fc4-515a-b1d4-24210205165a |  | note | FREQUENCY: Once, prior to application.
label | eaa7dde1-3482-5e99-9bae-202499fb71fb |  | note | – – – – – – – – – – – – – – – – –
label | 1609550c-d29c-5334-a829-84edffef1db0 |  | note | CATEGORY: IP
label | 6cd8c2e9-935c-5ace-9d39-69c4ab0e53fa |  | note | – – – – – – – – – – – – – – – – –
label | b2744ab8-58a1-56b8-ade3-5f66dc39c1fe |  | note | RESPONSIBILITY: SE/PE/SPE
label | 80126404-7341-5e3d-89c9-27409f87e192 |  | note | – – – – – – – – – – – – – – – – –
label | 3d926126-2c11-5f49-aebf-243bc4f96e99 |  | note | VERIFYING DOCUMENTS: This ITP
date | f8f5f392-18c9-55a3-b39a-b42dc0430777 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Trial Application (or Past Performance) Inspection
label | 001678f9-cb0f-5fdf-9efc-e4e423bd9ff1 |  | note | REFERENCE: 685.11, 686.13
label | 6f8f3388-7806-5fce-bb1d-b36353418e21 |  | note | – – – – – – – – – – – – – – – – –
label | 0a9c9211-2c4c-57f2-a044-56e7ddf8daee |  | note | ACCEPTANCE CRITERIA: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
label | 0a59bd13-b0fb-5a27-b085-e5d8c7c0c891 |  | note | ○ Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | 80775703-18e1-5c13-b713-61622ded5d27 |  | note | Attach: Inspection Photographs OR
text | da2b775a-312b-5d4f-8fa2-42acf6d79699 |  | textbox | Enter: Teambinder Hold Point number
label | bfce6e81-10a2-5383-8623-076c23022aa2 |  | note | – – – – – – – – – – – – – – – – –
label | 53e9fbfb-7640-5223-ada0-fcb3ce7c96ea |  | note | METHOD: Document Review
label | 509078a8-02e9-55d2-ac46-8866bd0c598b |  | note | – – – – – – – – – – – – – – – – –
label | 68b79f99-05b6-553b-a4fb-63892a26660a |  | note | FREQUENCY: Once, for each coating system, 7 days prior to full coating application
label | 2ed03727-8277-5c51-bddf-14ae8dc1f0f3 |  | note | – – – – – – – – – – – – – – – – –
label | 83bcf7df-222a-576d-bfb2-6f42ab5bff48 |  | note | CATEGORY: HP
label | 1bfd4477-da4d-5b48-beeb-e995b3f5cb3f |  | note | – – – – – – – – – – – – – – – – –
label | 4aa58030-d92d-5625-aad7-151e7633bea4 |  | note | RESPONSIBILITY: Nominated Authority
label | 39e6ba2b-c9fa-59b7-acd3-3e8137ba58e8 |  | note | – – – – – – – – – – – – – – – – –
label | ca598a9a-911c-5e95-8ae2-bb521e62af82 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | bef1abfc-5b7c-5e0e-b794-7d6648d97718 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Material Records
label | 78099367-a979-548b-b658-b6668e81a82d |  | note | REFERENCE: Coating System TDS, Surface Cleaner TDS 685.10, 685.12
label | 985c31f9-5922-5823-9d81-aa1857247138 |  | note | – – – – – – – – – – – – – – – – –
label | f3644dc4-bfec-5a85-a48f-f8394aa63036 |  | note | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
label | 872b7b90-cf64-5ccc-9008-719acfc9c7f9 |  | note | – the manufacturer's name & address
label | cf75c8e1-405c-59d8-ba54-fc6bb035231a |  | note | – product reference
label | 050fcfca-1701-5fd1-8964-69ca8a7950cf |  | note | – batch number
label | 921fd8de-01c1-5830-8fd5-f3aabe22405f |  | note | – quantity manufactured in the batch
label | ca940e9c-04ca-5b38-b74f-ddb7888c70c6 |  | note | – date of manufacture
label | e51eecc4-7385-50c5-87eb-9a04dc410716 |  | note | ○ Product beyond the manufacturer's shelf life shall not be used.
label | a490331e-36ea-51a2-bf12-45508552cce1 |  | note | ○ Each product shall be traced to final location.
label | 05133659-9e8b-5600-9c58-5f3af6e575f0 |  | note | – – – – – – – – – – – – – – – – –
label | 195db92f-7c8e-5baf-aa38-0b1f0849a4e2 |  | note | METHOD: Visual
label | 5b5bae28-f905-5b0d-bade-8dd19122a432 |  | note | – – – – – – – – – – – – – – – – –
label | e51120e5-2d7a-5f2f-9061-0329d99d74b6 |  | note | FREQUENCY: Prior to application
label | 3270c516-2cc5-568b-9e62-a513bc4da97e |  | note | – – – – – – – – – – – – – – – – –
label | 63141df1-a95f-50fd-9e77-20a800db3721 |  | note | CATEGORY: IP
label | 8bf914ee-7b9c-52f1-825e-8bedb15bf87c |  | note | – – – – – – – – – – – – – – – – –
label | 3feb6a5c-eacd-5c50-9db4-343b0e975cf3 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f0a0ac37-9a42-594b-9c5d-6a819292cad9 |  | note | – – – – – – – – – – – – – – – – –
label | 638a4927-3ca2-5a03-a7ee-9e93521d8475 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4c7289e6-bec4-5c94-9419-b26ca822a583 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Weather Conditions
label | 2a1923c8-7810-5f04-b940-a51e0eb9a37c |  | note | REFERENCE: Coating System TDS, Surface Cleaner TDS 685.09, 685.12 (a), 686.11, 686.14 (a) (iii)
label | 22a98255-9f10-59d2-a067-d591a7e6bef3 |  | note | – – – – – – – – – – – – – – – – –
label | 4d0631dd-a6ea-5443-bbf3-c63b45785256 |  | note | ACCEPTANCE CRITERIA: Coating systems shall not be applied under any of the following conditions:
label | 58a65a71-0736-5b53-a2af-331ea2062676 |  | note | i. windy conditions where spray/splatter may be generated
label | 80d19ecc-dd1e-5244-b383-5b906c423845 |  | note | ii. when wind-borne debris is likely to contaminate the uncured surface
label | 0e5abe5b-04b8-534f-864c-b54faffb6b73 |  | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | e7485289-9ec7-5953-8054-ebadac8ede47 |  | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | a9f5f853-5cbb-552f-9210-d30d8478938c |  | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | d8cc858e-2d1b-5aa3-a98c-0d221888e874 |  | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | 585f7cfd-abbf-5744-8c07-841f9e96b4f0 |  | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | 8b18a431-0ca1-5681-9de6-2d33898f427f |  | note | ○ Weather conditions are to be recorded.
label | aa04a8d4-9e8e-5cb9-a779-aaa98175b745 |  | note | – – – – – – – – – – – – – – – – –
label | 94817c90-eb17-53da-81e2-3043416249ae |  | note | METHOD: Visual, Measure
label | c8547c70-6637-534b-9ad0-867a54f0e2c2 |  | note | – – – – – – – – – – – – – – – – –
label | 5ccccb0d-1c92-5874-8365-5b159025eb4f |  | note | FREQUENCY: Prior to application and every 4 hours per shift
label | 9d031797-8636-5970-85c4-01c0dd1d4426 |  | note | – – – – – – – – – – – – – – – – –
label | 7c0f703b-c859-5f27-b56e-e7394bf699d8 |  | note | CATEGORY: IP
label | 2309adb6-62a3-55ec-84b7-0f608dd426d6 |  | note | – – – – – – – – – – – – – – – – –
label | 7a073671-46b3-5967-ad2d-0299c697174c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 21d58216-3844-54f0-97a6-dad40e0df237 |  | note | – – – – – – – – – – – – – – – – –
label | 6e811cdf-0bcd-5874-81bf-cf67e70eb70e |  | note | VERIFYING DOCUMENTS: This ITP
date | 5383d99f-c2dc-5d0f-85f3-62f23dde91a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Surface Preparation
label | 6cbd7899-5281-5c89-ac8e-39d5bddccf73 |  | note | REFERENCE: Surface Cleaner TDS, Coating System TDS 685.05, 686.06
label | bf4513ae-824e-5782-a6e3-1dc753644bd5 |  | note | – – – – – – – – – – – – – – – – –
label | af85e210-5a2b-5e73-822a-9c47c80d8b8b |  | note | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
label | 8f81cb45-52ca-55ee-9079-afaf300ef956 |  | note | ○ The surface shall then be flushed with water.
label | 88ee3d6a-1caf-54fc-a72e-0e7e467122f4 |  | note | ○ Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | 2c077638-ada8-5bcb-85e6-7527d503eeee |  | note | – – – – – – – – – – – – – – – – –
label | 61ebd095-cf78-53b2-8006-cfd316ab2377 |  | note | METHOD: Visual
label | a4db9ea5-2000-5a8e-8bc0-47be57f9611e |  | note | – – – – – – – – – – – – – – – – –
label | 38dcf8f4-b2d2-5c8d-a223-001c2560bbbd |  | note | FREQUENCY: Once, prior to application.
label | 334a4c46-bbfb-5934-872d-db812acbe71a |  | note | – – – – – – – – – – – – – – – – –
label | ca107e04-8df1-592c-a2fe-2c921911b8b8 |  | note | CATEGORY: IP
label | 17dade0e-032f-552e-88d6-17e4794c2601 |  | note | – – – – – – – – – – – – – – – – –
label | 3bc2b417-17e7-55a3-9fc0-6686be758488 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 600627e2-77f4-5ebc-946b-88383f05b5dc |  | note | – – – – – – – – – – – – – – – – –
label | e4cb1dbb-6b17-5ffa-b9c7-05c8187e7ed5 |  | note | VERIFYING DOCUMENTS: This ITP
date | c008557f-cb35-5eac-93e0-3bfd7b4c29f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Surface Moisture Testing
label | 91ba64d2-d71a-512f-bac1-78a07671a98a |  | note | REFERENCE: 685.12 (a), 686.14 (a) (iii)
label | 125f9b05-d706-554e-829a-74b525444884 |  | note | – – – – – – – – – – – – – – – – –
label | 5d6b5467-43f7-59e9-bcec-e600e598559f |  | note | ACCEPTANCE CRITERIA: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
label | d18420bd-9ff8-5b5e-a75c-7bec7c983529 |  | note | ○ Surface moisture conditions are to be recorded.
label | 00577217-d922-55ea-990f-5f4a9bf61a90 |  | note | – – – – – – – – – – – – – – – – –
label | 9c47e49d-d5a9-5c5e-a8bf-359cde8066cf |  | note | METHOD: Test
label | 4018bb4b-d7ff-512e-b5d9-9c109316e65e |  | note | – – – – – – – – – – – – – – – – –
label | 89f5eda1-3e3e-502d-a151-50ccd1fbdb15 |  | note | FREQUENCY: Immediately prior to application, 1 no. test every 50m²
label | 3d0286dc-b9f2-573b-b925-448edd574aba |  | note | – – – – – – – – – – – – – – – – –
label | 3b1c02e0-278c-511c-a3a8-6cc91421d28a |  | note | CATEGORY: IP
label | 90d46e62-626e-51ee-9642-744f3a26121b |  | note | – – – – – – – – – – – – – – – – –
label | 9191f35c-c882-56a5-836a-61dc640b9f84 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4242447e-e24a-5c96-9880-921959cd6e9e |  | note | – – – – – – – – – – – – – – – – –
label | 4af4552a-aec5-589f-aec5-978935637643 |  | note | VERIFYING DOCUMENTS: This ITP
date | d99d1241-2728-57bc-be3a-8e5fd444a762 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Method of Application
label | 0b1caafd-c127-53fa-b4ee-5ecf51d47d45 |  | note | REFERENCE: Coating System TDS 685.07, 686.07, 686.09
label | e7bfa40e-b04f-549c-8de9-1ba0c7275f73 |  | note | – – – – – – – – – – – – – – – – –
label | 5b289626-d096-52a2-9c26-cd434d398c52 |  | note | ACCEPTANCE CRITERIA: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
label | 6e95b0b9-553a-591c-96c2-e2fdb85b79fe |  | note | ○ Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
label | 3d78037b-70e3-5ccb-8f00-f3f207b75f1b |  | note | ○ For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
label | 55070f18-9be8-5ce7-8bd4-b3971c3f8713 |  | note | ○ Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | 041e2396-0dac-5a6a-945a-40c696cb0bde |  | note | Attach: Coating Application Record
label | 7637b6f9-95a4-5c5c-80b3-df373d242f86 |  | note | – – – – – – – – – – – – – – – – –
label | 1a95fe37-7b4f-511c-9af5-4eb1d6be9c4b |  | note | METHOD: Visual, Measure
label | 848b731a-34db-574f-9b1a-42897abf081f |  | note | – – – – – – – – – – – – – – – – –
label | e70b593c-c814-542d-9d4b-f189f56898fb |  | note | FREQUENCY: Each coat
label | af4bc6a2-3247-57da-b4a3-4b7e17855b2b |  | note | – – – – – – – – – – – – – – – – –
label | 88387a0d-7238-51a9-a616-25e2d8ed32d5 |  | note | CATEGORY: IP
label | b94168fd-e4a7-554e-8899-e7881117be89 |  | note | – – – – – – – – – – – – – – – – –
label | 11095350-35ab-5ac2-84a5-0797066c2d10 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b4198441-d039-55f0-99d3-cbea93eebb6d |  | note | – – – – – – – – – – – – – – – – –
label | 0bec1f1e-a88b-5a53-b1b2-e1f7b45ffc76 |  | note | VERIFYING DOCUMENTS: This ITP
date | 62372a7e-3def-5696-9b2e-8cb540500d64 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Wet Film Thickness (WFT) Testing
label | e9219d4c-d6ab-564d-ac48-1a469b2cb44d |  | note | REFERENCE: Coating System TDS 685.12 (b) (ii), 686.14 (b) (ii)
label | e7e2164c-137f-5b27-af0f-af8e1e64d45e |  | note | – – – – – – – – – – – – – – – – –
label | f53f9826-a018-55d3-9371-13c2aa97a554 |  | note | ACCEPTANCE CRITERIA: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | d4062a9c-e029-54e3-bd9e-04d9e480fd2e |  | note | Attach: WFT Test Results
label | 79c7db84-af3e-53b4-889b-61a916fb8cd9 |  | note | – – – – – – – – – – – – – – – – –
label | 83cd62bd-2daf-5f1a-ac64-ce0515e571d6 |  | note | METHOD: Test
label | 9888185c-f8a1-5f60-94c8-47cc73f527b9 |  | note | – – – – – – – – – – – – – – – – –
label | 7c622d23-0263-548e-9a55-0b8d7de2bd92 |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 500e57e1-c9ea-5992-a484-57750f45b2a1 |  | note | – – – – – – – – – – – – – – – – –
label | 3847d14f-cbee-5d49-bbb1-ee12c122de68 |  | note | CATEGORY: IP
label | 4805faf3-c422-5e74-a4bf-13739e7f787b |  | note | – – – – – – – – – – – – – – – – –
label | 8032bd4c-e2ba-525a-8eb5-c0b48b19a2d7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 014f0be3-c83b-5c61-b916-406ba5d741b1 |  | note | – – – – – – – – – – – – – – – – –
label | 8be8a128-8d4d-5f06-bca2-591d837d5d24 |  | note | VERIFYING DOCUMENTS: This ITP
date | 919e3fe4-8596-5b44-b28d-5645da0110ff |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection & Defect Identification
label | 675e3620-54bc-5363-b7ca-77b31707fd04 |  | note | REFERENCE: 685.07, 685.13 (d), 686.07, 686.15
label | 39cbbeb8-c955-5e71-8746-9a179b2c5586 |  | note | – – – – – – – – – – – – – – – – –
label | fb2e2d2a-cc3e-51a2-b8ef-6f37b802ddac |  | note | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
label | 8ba6eb56-84b3-5ca6-8f5e-c73317bb7bfb |  | note | ○ Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | 3c990c03-a6fb-55f8-9848-ca693ee32ce8 |  | note | – – – – – – – – – – – – – – – – –
label | f4935d89-9afe-505b-9b5b-d70be6afa1a4 |  | note | METHOD: Visual
label | 384aa30e-aab1-5b6b-bdab-7cc5a1d09a0a |  | note | – – – – – – – – – – – – – – – – –
label | 4b06f16b-7b98-5292-af92-e8ef33fc4347 |  | note | FREQUENCY: After each coat
label | f829aa23-02d2-5b37-b1d9-06ff877459c9 |  | note | – – – – – – – – – – – – – – – – –
label | 8371dff6-7d8f-594f-9301-fbdec7a539c7 |  | note | CATEGORY: IP
label | f0e6b42a-d2e0-56cb-8f64-77993e5d71af |  | note | – – – – – – – – – – – – – – – – –
label | 6854a716-20e0-5067-8c79-b22bff694319 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 051d84b6-7e8b-59f7-a1e6-0986cff7cbed |  | note | – – – – – – – – – – – – – – – – –
label | a462e1df-7b3c-506c-a979-20103fbb4ee4 |  | note | VERIFYING DOCUMENTS: This ITP
date | 79be88bf-2b92-59cf-8af2-863c8124f554 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Drying and Curing
label | 8fe20414-e7a8-5bff-a79e-85fae8d403db |  | note | REFERENCE: Coating System TDS 685.17, 686.10
label | dca1bacd-7fb9-5ba1-a47b-d38b79a67672 |  | note | – – – – – – – – – – – – – – – – –
label | 64892708-e9d5-54b3-bb54-08e3d8b360da |  | note | ACCEPTANCE CRITERIA: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | 0427fb8a-9b15-5302-803e-bcbb0a8e98cb |  | note | – – – – – – – – – – – – – – – – –
label | 9ce92096-43c4-5c79-9083-69462a264f14 |  | note | METHOD: Visual
label | 2ee37090-2f8a-592c-9127-d9f17972af73 |  | note | – – – – – – – – – – – – – – – – –
label | 4db18fc7-ebc9-5f3b-aa92-8ae897e4dcd2 |  | note | FREQUENCY: After each coat
label | c7c0102e-6a65-59e4-ab8f-8537a99d092d |  | note | – – – – – – – – – – – – – – – – –
label | e104d57a-7a49-5f64-ba3e-e1274c487826 |  | note | CATEGORY: IP
label | 2ad4fc6a-8db8-5112-85c5-c26b21e3942d |  | note | – – – – – – – – – – – – – – – – –
label | 4947cf6a-63df-58dc-a656-c8ad32463be1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 65c8ca02-efeb-5a0e-a860-efb873989773 |  | note | – – – – – – – – – – – – – – – – –
label | 4192b1bd-3571-5523-bf57-e60e795c9d09 |  | note | VERIFYING DOCUMENTS: This ITP
date | df1cffe6-9c41-5d91-a5db-5ae8cee34577 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Clean-up & Waste Disposal
label | d4e2fee5-0a18-592c-8f51-951b2249fc58 |  | note | REFERENCE: 685.09 (c), 686.10
label | e58be2bc-9ec8-5dd6-9b5e-478feb7746b1 |  | note | – – – – – – – – – – – – – – – – –
label | 955009be-4c74-578c-80da-c2aa8fd2f0f9 |  | note | ACCEPTANCE CRITERIA: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
label | ed32fdbb-accb-56b3-ac7e-8ecced2e9ff5 |  | note | ○ All rubbish and remaining coating products shall be removed from site.
label | eff8f009-7381-5c6c-8a28-c182787ef6cb |  | note | – – – – – – – – – – – – – – – – –
label | 2b9d98b5-0a7d-5a1a-9f30-89539121025c |  | note | METHOD: Visual
label | 15cd90e8-e684-5f69-bd10-d20e897324db |  | note | – – – – – – – – – – – – – – – – –
label | 798da41a-5ed9-5781-a687-b282c37090ad |  | note | FREQUENCY: At completion of Works
label | 1c256058-1ce0-51fa-ae59-2a8d71137885 |  | note | – – – – – – – – – – – – – – – – –
label | ca97714f-06b0-5910-b921-7c9e1d5b0097 |  | note | CATEGORY: IP
label | 3f7a8080-0127-54f7-95fc-9d5a95288e51 |  | note | – – – – – – – – – – – – – – – – –
label | 006a7949-a572-5518-9a31-3ca2e9cfecf0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 766ff7e1-e2e4-5b2c-8617-8f0300e36b78 |  | note | – – – – – – – – – – – – – – – – –
label | 406b39c3-2adc-5cd9-8c49-6506cb056a28 |  | note | VERIFYING DOCUMENTS: This ITP
date | bdbe9527-49a2-56e9-9fbf-3a52825d444d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Dry Film Thickness (DFT) Testing
label | 0690805d-5cdf-56f3-9c7f-000bdd5360ce |  | note | REFERENCE: 685.12 (b) (iii), 686.14 (b) (iii)
label | 44df36b8-cffe-538d-a503-29bc8c53e9b2 |  | note | – – – – – – – – – – – – – – – – –
label | e96e7952-e236-50e2-aa1f-6b6115534b88 |  | note | ACCEPTANCE CRITERIA: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
label | a20d5caa-307f-5e5f-8ec0-53945dba8c83 |  | note | i. Anti-graffiti system = 100µm
label | 630b4510-24cb-5d5d-ad3f-6fa0d1efb978 |  | note | Ii. Decorative & anti-carbonation = 150µm
label | 1f43f235-c83c-5df7-8032-b5447a46b556 |  | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
label | 35423a2c-23f4-5f33-9b68-7d0055d48fd5 |  | note | iv. Atmospheric & splash zone (dual protective) = 200µm
label | 065d8faa-0bc8-5435-a4b6-507b559c3824 |  | note | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
label | 9d570c1e-ea63-5b1d-abb3-7159ea67f5fe |  | note | Attach: DFT Test Results
label | 3c9e7d41-0d3e-5970-a535-02d6884f1ae7 |  | note | – – – – – – – – – – – – – – – – –
label | 7470c1eb-d363-5746-b6ad-0f8526300284 |  | note | METHOD: Test
label | f8ebf29d-7918-5cc3-a8d7-d48293da2055 |  | note | – – – – – – – – – – – – – – – – –
label | c331c14c-e564-554f-b853-0a744fe28a3e |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 87d51e30-3c93-5988-ba9d-3899c4221c9e |  | note | – – – – – – – – – – – – – – – – –
label | 9eefe6b3-c184-50c0-99dd-cb6f59fb1d31 |  | note | CATEGORY: IP
label | d589d285-252c-579b-825b-d7a11142923d |  | note | – – – – – – – – – – – – – – – – –
label | 268f39b0-50d4-5e47-8104-775458379169 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1df76338-08cc-5ca8-a76e-5cea192c77e9 |  | note | – – – – – – – – – – – – – – – – –
label | a90973ac-a0d7-5b52-b534-9dafe274e8af |  | note | VERIFYING DOCUMENTS: This ITP
date | 71d6ffbe-baa8-57f3-a220-8cd94ad5463a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Adhesion Bond Strength Testing
label | 882d73a9-2e78-5409-8228-47dab9a84eb9 |  | note | REFERENCE: 685.12 (b) (i), 686.14 (b) (i)
label | 22eb6114-eb00-5ed9-a05e-6cf5844f7446 |  | note | – – – – – – – – – – – – – – – – –
label | 79fd3311-8b1c-5ce8-93d8-262219abcc6f |  | note | ACCEPTANCE CRITERIA: A minimum of 14 days after application, the bond-strengths between:
label | d00aac2b-c504-5582-8f70-cd592ac9bfd7 |  | note | i. the coating system to the substrate, and
label | 11a84be9-d898-5c7c-ace4-32a2a6bfdaa1 |  | note | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
label | 2363b8d9-2229-59fd-9833-8e9f7467befb |  | note | ○ The subsequent results shall be greater than 0.75kPa.
label | c7bc1759-21a9-55e7-a7c1-45ce6a2a8e3b |  | note | Attach: Adhesive Bond Strength Testing Results
label | 6009e094-9dc2-52f9-9f52-e3ac327097c4 |  | note | – – – – – – – – – – – – – – – – –
label | e624640a-2220-51a4-b1fe-622f36c6cb52 |  | note | METHOD: Test
label | 24d5e507-9754-59b6-9b55-1d6ad9ea8959 |  | note | – – – – – – – – – – – – – – – – –
label | f10e8d2b-4a12-5ad3-98ec-1b9728bf7379 |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 173a046c-c50c-5040-8be7-40e51c7a3629 |  | note | – – – – – – – – – – – – – – – – –
label | a83ec978-d43e-571e-b10f-11340c1a6ca0 |  | note | CATEGORY: IP
label | 49fcbc38-6565-53c5-b721-7ebfb47b69aa |  | note | – – – – – – – – – – – – – – – – –
label | 5db85fc3-d91c-547f-8e44-bf944f26094e |  | note | RESPONSIBILITY: SE/PE/SPE
label | b03febcd-c5f2-5008-b5bb-a4312d9ff5a0 |  | note | – – – – – – – – – – – – – – – – –
label | cf20a851-0b9d-50a0-a8e6-66af0aff6e8e |  | note | VERIFYING DOCUMENTS: This ITP
date | 2a990c94-75bc-5402-9231-1a1adcf12b8e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Penetration Depth Testing
label | 86cf5c51-3272-562f-9a94-2cc68c03b93a |  | note | REFERENCE: 685.12 (b) (v), 686.14 (b) (v)
label | 4428e3d0-6d11-5f91-a403-e4ade7553c7b |  | note | – – – – – – – – – – – – – – – – –
label | 840f56dd-82d3-5296-a573-992d336994e3 |  | note | ACCEPTANCE CRITERIA: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
label | 725ce903-2840-551a-8895-5655de1562e8 |  | note | The subsequent results shall be:
label | e40eccc3-66ef-5c95-9f2c-2ffc25a73442 |  | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
label | 647408d7-9d0e-59c2-af85-12fa91484f6f |  | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
label | a26e6d60-b588-52b0-8a65-9a0f775f13b3 |  | note | iii. Silane-Siloxane or Siloxane = 3mm min.
label | ec768c48-5e70-5f9c-9f7f-0d364894825b |  | note | Attach: Penetration Depth Testing Results
label | 3770d364-11fe-5ff2-bb8b-6f1a507b27cc |  | note | – – – – – – – – – – – – – – – – –
label | dc952c5f-0e35-5fab-ba43-f0ad4c18900d |  | note | METHOD: Test
label | 52c1faf3-5b38-5e5e-a8b9-71f30280357c |  | note | – – – – – – – – – – – – – – – – –
label | 2469bca5-2775-5efb-860c-dbd37faa8f22 |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 3bca78fa-f0d5-500d-a1b2-006d2a3b7a2d |  | note | – – – – – – – – – – – – – – – – –
label | 9d515094-0556-5fbd-912f-2829a7c66d69 |  | note | CATEGORY: IP
label | 6c2f8796-6f2a-53cd-8149-a1975d0fda77 |  | note | – – – – – – – – – – – – – – – – –
label | 2a74e772-412d-5e75-8d33-1dbdc5870baf |  | note | RESPONSIBILITY: SE/PE/SPE
label | d017b552-7300-59d0-aa3e-03aca3974e33 |  | note | – – – – – – – – – – – – – – – – –
label | 5badd70e-599b-5509-ae19-6ea81fd51ceb |  | note | VERIFYING DOCUMENTS: This ITP
date | 5bb01391-1526-5f13-8621-20ededb21a0f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Non-conforming Coatings
label | 351bf315-014d-5007-81ea-923d499addd2 |  | note | REFERENCE: 685.14, 686.17
label | 071b3c72-3350-51ab-abca-66d1ee7b3d67 |  | note | – – – – – – – – – – – – – – – – –
label | 321e963c-33f0-5f23-8c0a-29194a26b579 |  | note | ACCEPTANCE CRITERIA: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
label | 46d3490f-326b-5ce3-ba09-4d35dac8c81a |  | note | ○ Such Work may include removal of the coating, surface preparation and re-application.
label | a4c5658f-3417-5c88-8314-96ddf18b4ad8 |  | note | ○ Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | c471096d-b123-5ed6-8c8a-41fa5d55ccf4 |  | note | – – – – – – – – – – – – – – – – –
label | 0636603b-fe43-56aa-8618-78656c2eac55 |  | note | METHOD: Visual
label | 061a5e93-101c-57eb-b18c-6a36e4308826 |  | note | – – – – – – – – – – – – – – – – –
label | 2c93f8b1-5363-56b0-8b29-7ae53f0586e5 |  | note | FREQUENCY: Where required
label | 3305c8e2-e91f-52f7-9656-6fae76b23f95 |  | note | – – – – – – – – – – – – – – – – –
label | 52b18e28-f0e7-5953-a7d4-60fcb5e5b509 |  | note | CATEGORY: IP
label | a1c29f46-f1ad-51b9-b152-a6964af47b85 |  | note | – – – – – – – – – – – – – – – – –
label | 29a7c464-a02d-5d19-a221-c0c693f95a74 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 90f3f27a-9a88-542c-b60b-746c5c7875b0 |  | note | – – – – – – – – – – – – – – – – –
label | d2b034f5-9180-52b1-84a0-a7eea1f758ad |  | note | VERIFYING DOCUMENTS: This ITP
date | 5a6aedfc-514f-53cf-9d0a-331d51fa415a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Coating Application Guarantee
label | d238859b-edd5-59ca-8972-0810726d85d0 |  | note | REFERENCE: 685.06 (b), 686.05 (a)
label | 7293d45e-d449-5292-b3b7-283508920f87 |  | note | – – – – – – – – – – – – – – – – –
label | 13098313-8ff2-58ee-b2c3-3f82ac7c0a7a |  | note | ACCEPTANCE CRITERIA: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | 94a72e2f-c4ef-582d-b1f2-d379513ccc7b |  | note | Attach: Coating Application Guarantee
label | 6c18685d-b16b-59c2-80b7-b047b24c20d7 |  | note | – – – – – – – – – – – – – – – – –
label | 83beabff-2e44-59b0-b797-3aac436843f8 |  | note | METHOD: Document Review
label | 82791c0f-b0e2-5682-a965-802509dce493 |  | note | – – – – – – – – – – – – – – – – –
label | 9d0086a3-feda-5a22-b5be-177a26b52893 |  | note | FREQUENCY: At completion of Works
label | cb96e163-9eba-5b54-8d51-f569b1b22ede |  | note | – – – – – – – – – – – – – – – – –
label | 8b685bc4-ce4e-54c8-9db3-beee9b29c872 |  | note | CATEGORY: SP
label | 9d0ecf68-3e29-51cc-99c4-1b239a7f0898 |  | note | – – – – – – – – – – – – – – – – –
label | 899b1067-12d5-5a82-8917-823689cd970b |  | note | RESPONSIBILITY: SE/PE/SPE
label | d30f2a63-eba4-5610-883e-6e00789d006e |  | note | – – – – – – – – – – – – – – – – –
label | 9de736ec-af6f-5e06-9710-b627eb034b60 |  | note | VERIFYING DOCUMENTS: This ITP
date | 64a94867-fbf2-5945-9a86-36e5a2a32fbb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Repair to Damaged Coating
label | 10bfa162-7827-50d5-96f1-5aba26d392ad |  | note | REFERENCE: 686.17
label | 16a58475-f6b2-54ba-bcc8-5f8447adb535 |  | note | – – – – – – – – – – – – – – – – –
label | 89f5f481-a9ab-5f37-a290-a7c83f6c277a |  | note | ACCEPTANCE CRITERIA: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | 626a97d8-7173-5be8-b50a-f3678d9c8683 |  | note | – – – – – – – – – – – – – – – – –
label | 78353e69-4eb4-574a-accf-740ec29c25e1 |  | note | METHOD: Visual
label | 1acd6a17-68d3-5d54-9ac7-28e72a438820 |  | note | – – – – – – – – – – – – – – – – –
label | 9830da38-b7bf-558e-992a-702f664d1148 |  | note | FREQUENCY: Where required
label | 3cd3e939-9b3c-5f94-bc53-db13acd70566 |  | note | – – – – – – – – – – – – – – – – –
label | 6285c43f-ea55-5c76-8217-f88c6fef3348 |  | note | CATEGORY: IP
label | 1b3238ec-a033-551d-b514-41e63016388d |  | note | – – – – – – – – – – – – – – – – –
label | 7da553e3-497b-5255-90f7-f8526910a41f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2544481b-bcb5-561e-803e-e4fd3fd11c5b |  | note | – – – – – – – – – – – – – – – – –
label | fd5f59b5-5b99-5072-a8e5-238590d0e4fc |  | note | VERIFYING DOCUMENTS: This ITP
date | af8d7e63-454d-534d-a2a5-7fbc9d6304f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 Non-conformance Report (NCR) Closure
label | 705a32a3-cddc-5643-8081-5fab7e701903 |  | note | REFERENCE: MRPA Quality Management Plan
label | f6c8a820-7eaf-57ac-bfcb-c51fcd28744d |  | note | – – – – – – – – – – – – – – – – –
label | aeaee244-b1d3-5cdb-80d9-b67514307648 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | d979d0db-e4e5-5822-a238-4a99caf433c3 |  | note | – – – – – – – – – – – – – – – – –
label | 708475be-f0d3-53d0-b6a0-abf3e1d79147 |  | note | METHOD: Document Review
label | 3a82507f-4372-5e60-9e72-388d4f5b53dc |  | note | – – – – – – – – – – – – – – – – –
label | 2762d346-04d5-53d0-bfc0-9e7c7e8c339e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e49620f2-12bf-5cba-89bc-0ce211d59e0f |  | note | – – – – – – – – – – – – – – – – –
label | b5806e8f-8f0a-5d21-8e0a-508401fde1c3 |  | note | CATEGORY: HP*
label | 8fad31ab-36bc-50e8-b9c1-782ebcc6e6b3 |  | note | – – – – – – – – – – – – – – – – –
label | de507a4f-b4bd-59aa-bace-8e85db0cd070 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a11f605f-c53b-564c-9fd7-589ba33ccbb4 |  | note | – – – – – – – – – – – – – – – – –
label | c41d41c8-917a-5d1e-a3e2-7bc77d2b9fb7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 109e2b71-4dd8-5b89-8507-740d851243b1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 58d6aabe-6c8a-5e63-8cab-07742ef73211 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d8117cf0-8552-52aa-909c-0bd52959a01b |  | textbox | Name:
text | 5ac02c4d-1b10-567a-a3d6-90f17d1a3615 |  | textbox | Position:
date | 2681182d-eef2-5581-a43d-2acae8110959 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-133-STR-SSB-Structural Concrete | itp |  |  |  | Yes | ITP-133-STR-SSB-Structural Concrete Rev 0 | 53a7eae4-2a8c-4e47-bca6-04c89f1b7c4d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 3617ce0a-f7b3-548e-8268-b2c8b7a12626 |  | note | Document Title: ITP-133-STR-CAMMS-Structural Concrete
label | 3a9e34e3-8dbb-53a2-9325-ddfe7e19db5a |  | note | ITP Description: Structural Concrete
label | e57a94a5-387f-5323-8c06-9075e089671c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 21305406-3d32-5171-bb75-5ecf55dfb77c |  | note | Discipline (e.g. CIV/STR/RAIL): 133-STR-CAMMS
label | da9b291f-1e57-5bce-97ec-440adb54db81 |  | note | Revision Number: 0
label | 6541a096-20d6-55c8-bf2e-c937ed307ac9 |  | note | Revision Date: 8/02/2024
label | f3e46dab-1dad-5348-8dda-6bbb20c36c3f |  | note | ITP created by: Iyasu Enoro
label | 34ae75b3-5b99-5162-ada1-b011f8b323b8 |  | note | ITP approved for use by: Victor Mira
label | cbbf10d1-294e-5d02-ae18-566f17f883cb |  | note | 1.1 Non Dependent
label | caa04885-52ff-57b8-8198-115309927cd2 |  | note | Reference: VicRoads Section 602 October 2007
label | c404ecaf-fea3-5156-97fc-d569fa45f539 |  | note | 1.2 Non Dependent
label | aaea576b-3ccf-577a-9a0c-ee5e9b8d3404 |  | note | Reference: VicRoads Section 610 February 2020
label | f9afbce4-e9ff-5544-8862-141fb4371ca4 |  | note | 1.3 Non Dependent
label | 6c643811-3dbe-59bd-8281-4fd0d7b6fc93 |  | note | Reference: VicRoads Section 611 November 2018
label | 22e7d66c-f7f1-5514-b510-22b577e8bb12 |  | note | 1.4 Non Dependent
label | f68009ad-c4d7-551c-aa00-c869d96ecd34 |  | note | Reference: VicRoads Section 614 June 2017
label | 6475064a-77f8-52ca-83bc-657794622eee |  | note | 1.5 Non Dependent
label | ba9694f2-e8f2-592f-8322-0fef609da647 |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 18a6b5d4-f202-59a7-9b93-bd2401e979ec |  | note | REFERENCE: 610.07 Table 610.071 IFC Drawings
label | 62bfa5d0-b4fb-57ab-af0f-ace58a311b0e |  | note | – – – – – – – – – – – – – – – – –
label | 18cd4c66-cba9-5c3c-ba3c-9e9cf11fc54b |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 4fff605f-632c-55d9-89b2-98745acf1298 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | e84e266e-085d-5555-8e74-6148e8a69a63 |  | textbox | Enter: Teambinder Material Approval number
label | 33249643-ba3d-5e7e-95c4-5ce1ab247bca |  | note | – – – – – – – – – – – – – – – – –
label | 36f47d36-83a7-55e3-a119-14a2da4f0245 |  | note | METHOD: Document Review
label | 18c44e6d-8d06-5ebb-a81d-4ab717fce144 |  | note | – – – – – – – – – – – – – – – – –
label | f837704f-4b6a-5265-ae0f-01717f7d93c3 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | b7dc8daa-d314-56b1-940a-bab3133efb73 |  | note | – – – – – – – – – – – – – – – – –
label | d317990c-8347-5a4d-ae35-2f0b7cefc721 |  | note | CATEGORY: HP
label | 26423c1c-0c22-56fe-a0ad-54738d15822c |  | note | – – – – – – – – – – – – – – – – –
label | 670fac2f-197f-5f0f-8640-3308c00616b0 |  | note | RESPONSIBILITY: Nominated Authority
label | 83e9b1c5-7f7e-56ec-a2dd-50796beb342b |  | note | – – – – – – – – – – – – – – – – –
label | c2fc748c-794a-50c0-bb30-c551fc7db14a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 4f70eee1-a005-5422-b6b3-d37e3aaef5ea |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 56434563-8375-5880-be11-626ca2b66a65 |  | note | REFERENCE: 611.05 (a)
label | fe664fd3-ffaa-54fd-9737-6a660a40d242 |  | note | – – – – – – – – – – – – – – – – –
label | bae02d4f-d4cc-5d86-a538-46896ba32da3 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 4b2160f7-7602-542f-ba21-bf17bb9b1aa9 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 25409886-af99-5923-83b4-57cd03ceee67 |  | textbox | Enter: Teambinder Material Approval number
label | 03515f44-0008-5818-95bc-b2ad2147aa16 |  | note | – – – – – – – – – – – – – – – – –
label | b6de3505-d03d-5f80-88f4-6807489df3c8 |  | note | METHOD: Document Review
label | 1d17dc86-07a3-5fdb-9de1-f880ff05cba9 |  | note | – – – – – – – – – – – – – – – – –
label | ee942b53-3b2f-5573-aba3-4ea50efe7b8f |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | b2174777-2fd7-5257-aca0-fcb41b52b2c5 |  | note | – – – – – – – – – – – – – – – – –
label | 6c28f9fa-f000-5acf-979f-898b83134d78 |  | note | CATEGORY: HP
label | 27063d47-bae6-57d7-ac60-afc7468c50b6 |  | note | – – – – – – – – – – – – – – – – –
label | e3e8c2a6-6362-5028-96ae-c2c9803c1967 |  | note | RESPONSIBILITY: Nominated Authority
label | ce6ada9f-e64f-5135-800b-8bd0094a3d5f |  | note | – – – – – – – – – – – – – – – – –
label | f870dd2e-5a7d-5226-ac3b-b0a61f2d837f |  | note | VERIFYING DOCUMENTS: This ITP
date | 6b5dcaeb-a04c-587e-a3f1-5945d9334614 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 4a26950b-7f51-55ee-9ac0-fbc967c4c3d4 |  | note | REFERENCE: 610.26 (a)
label | 80848350-222b-5c87-a84e-d4be3e3a5214 |  | note | – – – – – – – – – – – – – – – – –
label | c14bf559-38b4-558a-b267-28037fb84306 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 249d0f72-5cef-5e21-8b98-109c2af9c6c9 |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | cca9a073-11c4-5cea-bf21-4ce8478a32b2 |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | aec07bb9-9c4a-5205-ad1e-24031b788d13 |  | textbox | Enter: Teambinder Material Approval number
label | c9a25040-a198-5bc4-a9dd-24cdc8a44d47 |  | note | – – – – – – – – – – – – – – – – –
label | 9f05de0a-e943-5d5a-866f-98afc8c4d3b8 |  | note | METHOD: Document Review
label | 388d8abf-594c-597d-9659-0f7328a21eb8 |  | note | – – – – – – – – – – – – – – – – –
label | 4a9652a1-e4ba-56a7-977f-28a1ea9855b5 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 597c113e-6d72-5e6e-88fe-94a789a28681 |  | note | – – – – – – – – – – – – – – – – –
label | a23ef16f-88bd-5b57-be57-cdd94807d374 |  | note | CATEGORY: HP
label | 9611cb89-6c71-5d26-bd16-17a06663f6be |  | note | – – – – – – – – – – – – – – – – –
label | ac7ef350-50bf-50ab-b279-2f222b53b660 |  | note | RESPONSIBILITY: Nominated Authority
label | 689c2d60-c790-5e10-8690-1f625ca96b66 |  | note | – – – – – – – – – – – – – – – – –
label | a48d0209-c754-5b2f-b13f-7b03cd892d09 |  | note | VERIFYING DOCUMENTS: This ITP
date | d9b7fd26-b7f6-5af5-882b-834a46912137 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 7dd7d90a-9b17-5b1f-a3ba-ac0d276c72f1 |  | note | REFERENCE: 610.17 (f)
label | da3a5733-827b-5872-9df6-2dc994dc7807 |  | note | – – – – – – – – – – – – – – – – –
label | f075f242-bbae-5703-a86b-f6db6e33c0e0 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | efeeabae-51cc-5aa9-bdf0-ca46d6ee1144 |  | textbox | Enter: Teambinder Material Approval number
label | 206abcd7-addf-545f-bdd4-5cb7e9446539 |  | note | – – – – – – – – – – – – – – – – –
label | bb292ffa-0aaa-5aea-b104-a34401df9c3b |  | note | METHOD: Document Review
label | 8567f9c3-143a-5fc5-9515-9a2d8e02de2b |  | note | – – – – – – – – – – – – – – – – –
label | c42c865d-d24f-5139-bedc-dc7c3a930c7d |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 70893350-a83e-552d-872a-62b92cd72e32 |  | note | – – – – – – – – – – – – – – – – –
label | b71ba94b-dee2-50f1-b3f9-f3cab86a0f83 |  | note | CATEGORY: HP
label | a05703a8-93c5-5eaf-8f29-6007303cd65a |  | note | – – – – – – – – – – – – – – – – –
label | 2b9d23ed-aee7-52ab-92fd-f1ccadc5ee3d |  | note | RESPONSIBILITY: Nominated Authority
label | 8a2151de-1c2d-5579-aaf6-cd474deed4fb |  | note | – – – – – – – – – – – – – – – – –
label | c4282269-8134-5bf8-9406-ef83ef2d322e |  | note | VERIFYING DOCUMENTS: This ITP
date | 5638e6b5-011f-5a6d-b342-8b0de656b6d7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 7ebbd610-2ba9-54e4-ad2b-6031fd81d732 |  | note | REFERENCE: 610.23 (d)
label | 7fdeb5d2-ed98-5b0c-892f-5db27798ac55 |  | note | – – – – – – – – – – – – – – – – –
label | e8b8c564-3c9f-5aea-a635-74eb464975ad |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 2f61cc7c-3c40-5401-aca2-c086bf3f636e |  | textbox | Enter: Teambinder Material Approval number
label | cc42a900-2dc1-52d6-8568-0b5d6530f1b4 |  | note | – – – – – – – – – – – – – – – – –
label | f53851ed-87c9-5e0c-a2c0-f726b0a0d199 |  | note | METHOD: Document Review
label | 19b35606-363e-56a1-a20d-2fe788bc8560 |  | note | – – – – – – – – – – – – – – – – –
label | 988cdcb7-d376-53ce-8d4a-6c8fcb303778 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | f1c64ebd-8762-542a-8b12-ff6df004e791 |  | note | – – – – – – – – – – – – – – – – –
label | 12ed6048-86fc-5f90-a229-1c89f8c9f791 |  | note | CATEGORY: HP
label | 20d77c8e-7dbc-5f49-93fd-c5d7534c4e76 |  | note | – – – – – – – – – – – – – – – – –
label | cc321b92-84d1-5e79-b481-6e764203b93f |  | note | RESPONSIBILITY: Nominated Authority
label | f80a3973-c594-53ad-969f-73681e2a667a |  | note | – – – – – – – – – – – – – – – – –
label | 0d0269c1-4b0e-5765-b64c-5bee0868497c |  | note | VERIFYING DOCUMENTS: This ITP
date | 53b18ec2-3293-504b-90db-50f4df50d3c5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 632b1ea6-4b6d-5bd9-9001-8cc59655c607 |  | note | REFERENCE: 610.18 (a) (i)
label | 581d4b87-2223-51d8-a301-c50316e01e4f |  | note | – – – – – – – – – – – – – – – – –
label | 00658e84-b8ff-53d2-a458-21441a35bc26 |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | e483756b-2e29-525a-be7f-7b2bd3f1dec3 |  | textbox | Enter: Teambinder Approval number
label | 577b0e00-075a-51e2-a45e-200ff94bf559 |  | note | – – – – – – – – – – – – – – – – –
label | f03601c0-975b-5f4c-8c96-38c04074b90b |  | note | METHOD: Document Review
label | 5b5513ea-fa52-5823-8696-443d381fbc41 |  | note | – – – – – – – – – – – – – – – – –
label | 6e7ff9a9-37aa-53e2-af37-595e61bc2a53 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 98fadfc4-5ff7-5816-88dd-880f0f087da7 |  | note | – – – – – – – – – – – – – – – – –
label | d8155cb9-46c9-5e36-a287-8b0d4900d330 |  | note | CATEGORY: HP
label | 56adf78f-f85b-53d9-9f09-a1ec83c4116a |  | note | – – – – – – – – – – – – – – – – –
label | e3ae0ff3-0bf7-58c8-ba7a-cf4e3361e59d |  | note | RESPONSIBILITY: Nominated Authority
label | 5a906e92-0cf2-5ac9-8f6f-9308517d5b02 |  | note | – – – – – – – – – – – – – – – – –
label | 350a82d0-9a5e-5872-8b00-ce3085f24611 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5c533eb8-1bc7-5284-b9e1-3013d87006d4 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | e0e8c368-1dfd-5501-b7eb-365fb406538a |  | note | REFERENCE: 610.18 (a) (v)
label | 99cb1c07-458b-5e3e-8980-417f243947f4 |  | note | – – – – – – – – – – – – – – – – –
label | 6305c4f4-a305-58c6-a851-087fc1635775 |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 3066dad7-8ee5-587b-b5e2-f249525fc2fd |  | textbox | Enter: Teambinder Approval number
label | 53b8d1f4-7119-56cb-9419-068dca622ae0 |  | note | – – – – – – – – – – – – – – – – –
label | 7f9a64fa-1f8c-5c30-be03-f3ceca059b00 |  | note | METHOD: Document Review
label | a7abd993-fca5-57a7-8a62-1f3ebddda095 |  | note | – – – – – – – – – – – – – – – – –
label | 7318a5ff-6de5-52e4-9f1b-6c147d92a27a |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 079d03a2-7d5a-582e-9292-12d716da7ade |  | note | – – – – – – – – – – – – – – – – –
label | 625926a9-2a95-5bfa-ac11-6d425064ba79 |  | note | CATEGORY: HP
label | 299058bc-c255-5892-99e0-18da4ff3fe84 |  | note | – – – – – – – – – – – – – – – – –
label | b6683516-9e7a-5a23-ae3b-96e2eee7df33 |  | note | RESPONSIBILITY: Nominated Authority
label | 64332483-3c49-58ea-a00f-47b6cdbb294d |  | note | – – – – – – – – – – – – – – – – –
label | f3958f59-9f1a-5eb6-823d-d7f4e292cd33 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | ceaf9442-a3e5-58e6-a73a-4e1e6cce028b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | 9287d04c-3352-5613-ac58-52fdd4a40442 |  | note | REFERENCE: 610.18 (a) (iv)
label | 4f52013d-746b-57f9-bab9-9b02b709f381 |  | note | – – – – – – – – – – – – – – – – –
label | 4451dae8-501c-501e-bec7-67ee3ac9c6b7 |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | b38a0729-6931-5318-a471-c01addcc15a1 |  | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
text | c4662b56-d5a2-5b64-b811-6bae353fb69f |  | textbox | Enter: Teambinder Approval number
label | 4267c090-ff78-560a-8a30-7e24e87808f1 |  | note | – – – – – – – – – – – – – – – – –
label | e4c116d6-54a3-5251-8281-c34c53d56567 |  | note | METHOD: Document Review
label | 2866f510-ee4b-57d1-927f-58c6f17d853b |  | note | – – – – – – – – – – – – – – – – –
label | 77cd39b7-4e6b-50c0-b3ce-ea6af8c03f89 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | d1754fea-abf6-5d4f-b079-f88eb0d353d7 |  | note | – – – – – – – – – – – – – – – – –
label | fb6ea59b-38c1-5c21-afc7-83d0075a429a |  | note | CATEGORY: HP
label | 1adbd660-d30a-5973-9d66-bf1275bcc90a |  | note | – – – – – – – – – – – – – – – – –
label | 9c2e07d1-7f63-5e0c-9b91-bceaae02df6d |  | note | RESPONSIBILITY: Nominated Authority
label | 949fb72c-920f-510e-b655-0579dfa39ac5 |  | note | – – – – – – – – – – – – – – – – –
label | dd75bc65-5595-5f95-b570-661416eadaeb |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | c5e57bdb-3dc4-5196-9c73-135f39e4d61f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 10b5da00-4e8e-575c-8a6c-23f41dd956b5 |  | note | REFERENCE: 610.17 (a)
label | 6d0db8c0-cfd5-5caa-bb15-0a3972ad7887 |  | note | – – – – – – – – – – – – – – – – –
label | 1f9aeeef-e1f7-573e-a312-ccf118a64760 |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 4cda3a38-9881-568c-be08-107ff7dd15a3 |  | textbox | Enter: Teambinder Approval number
label | de8e08ce-dd34-502b-8bfc-81fb7f514aac |  | note | – – – – – – – – – – – – – – – – –
label | b896b046-77d4-5d0b-8a15-9c905d70965a |  | note | METHOD: Document Review
label | aa3ac717-6307-5e15-8924-ef09983233b4 |  | note | – – – – – – – – – – – – – – – – –
label | af1fb91a-3800-55b3-9729-a5974a9a4d6c |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | 481b81cf-375c-517f-8008-ea056952cc0e |  | note | – – – – – – – – – – – – – – – – –
label | 02d26eb7-0261-5efa-a2af-3b33dc413fc6 |  | note | CATEGORY: HP
label | b36c6baa-fe48-56cf-a3d8-6ed5583d6e08 |  | note | – – – – – – – – – – – – – – – – –
label | bf4ba29d-8325-5ebb-aaaa-a8a297a3a92b |  | note | RESPONSIBILITY: Nominated Authority
label | 47d84d77-716a-5f7b-968a-c5c325ef9ed1 |  | note | – – – – – – – – – – – – – – – – –
label | 1650d610-b4ca-5fe8-a312-2e1754ea565a |  | note | VERIFYING DOCUMENTS: This ITP
date | dda03089-e720-5f52-98c7-e87bf23cda3f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | 546e9e59-02fa-55cd-91cd-477824926d2e |  | note | REFERENCE: 610.23 (a)
label | 198f6ed1-da4b-5957-bf8d-03e3b95d7f4c |  | note | – – – – – – – – – – – – – – – – –
label | 0596029f-a124-5219-8a2d-4f6074edd3ef |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 3dc8f208-44ac-5595-92c9-f0829e904593 |  | textbox | Enter: Teambinder Approval number
label | 534664d8-d75d-5437-98f3-a3f4085e1a90 |  | note | – – – – – – – – – – – – – – – – –
label | df0b402f-18e7-508c-be9a-4e18c662b2c7 |  | note | METHOD: Document Review
label | 4b147056-bd05-5b46-bcbd-7bf2d22fac04 |  | note | – – – – – – – – – – – – – – – – –
label | 678b2c66-d2c0-513c-9d11-83858364cab1 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 52697f01-cd25-5358-bb43-d5ecd93ba1b5 |  | note | – – – – – – – – – – – – – – – – –
label | 2b35d2ea-0181-5fc7-a2f9-1f1848139520 |  | note | CATEGORY: HP
label | 8a05c230-bc12-562a-a403-1ea50c55603c |  | note | – – – – – – – – – – – – – – – – –
label | 867d90ff-4f6d-5a19-9aa9-c1eaee726d60 |  | note | RESPONSIBILITY: Nominated Authority
label | 898d6818-8988-5f36-95c9-1bc5782f9348 |  | note | – – – – – – – – – – – – – – – – –
label | 92511afa-ac67-505f-8a33-28b4be0b5e8e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | af807591-5069-5d67-9608-ec293a4e5377 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Concrete Drilling Procedure
label | 67386919-07a2-5f15-9ebf-92ca0dcc1b33 |  | note | REFERENCE: 610.46
label | 72488c75-927e-520f-a3b5-c2b3f1024547 |  | note | – – – – – – – – – – – – – – – – –
label | 305632b4-2c1f-52d2-876b-25e3b87ecc04 |  | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | 853b364c-6e51-544b-8a11-ab618d9af539 |  | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | 7df266b1-6a66-555e-9f19-365237208a20 |  | textbox | Enter: Teambinder Approval number
label | 6c833848-5240-5000-813b-49bd528915c1 |  | note | – – – – – – – – – – – – – – – – –
label | 75694289-ab85-5d9b-a3f6-b4b7080dcbc3 |  | note | METHOD: Document Review
label | 96cf7811-86e0-5fed-a5f8-7bf23f159b33 |  | note | – – – – – – – – – – – – – – – – –
label | edc1d3a4-8bde-554e-95ca-e7c3777c04a6 |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | 9b4271b0-3ef1-50a8-83f8-fa2f169527ae |  | note | – – – – – – – – – – – – – – – – –
label | d2d3beca-c920-5e90-acdc-e7f0a24f0faa |  | note | CATEGORY: HP
label | 3c9d4a76-4150-502c-bfd4-f0f13300917d |  | note | – – – – – – – – – – – – – – – – –
label | 42e5390e-b9c4-5da7-ac06-accf59d2d5d3 |  | note | RESPONSIBILITY: Nominated Authority
label | 54a2f26e-93e3-504d-ba17-acfb6b18caf0 |  | note | – – – – – – – – – – – – – – – – –
label | 9739e546-1709-5279-8241-097dd370c257 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5761771b-21ff-5160-bc33-15e0156c8a8a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Temprature difference measuring-Calibration
label | 9b297b0b-c582-5415-82e3-e10c9813bee8 |  | note | REFERENCE: MRPA Quality Management Plan
label | f025bd66-4874-5c50-8e2f-0e6f24ff840e |  | note | – – – – – – – – – – – – – – – – –
label | fe6a24f5-2641-5b85-a335-38c63455b658 |  | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
label | 7c143489-250f-5197-bfde-498c7331e32d |  | note | Attach: Calibration certificate
label | cfc83ea9-7c39-5ef4-ac53-996e21de05f8 |  | note | – – – – – – – – – – – – – – – – –
label | 10f3e4b7-820f-5a47-995c-3e30d117b736 |  | note | METHOD: Document review
label | 63ed4198-c191-572d-950f-a8165b9a7b1d |  | note | – – – – – – – – – – – – – – – – –
label | 6b08356c-852d-53ef-bf8b-adb48d1e9730 |  | note | FREQUENCY: Where applicable
label | 3c62b04f-6c34-52f8-87c3-39d934c76e32 |  | note | – – – – – – – – – – – – – – – – –
label | a084602f-cd23-5425-b603-b32359c93b8a |  | note | CATEGORY: HP*
label | 8ded140a-4f6d-5b6d-8d6a-27d995243cc6 |  | note | – – – – – – – – – – – – – – – – –
label | 7d6a61ab-36b9-5313-8eff-51caa8dc7c3d |  | note | RESPONSIBILITY: PE
label | f523ce56-ec9e-56f4-b853-d1fc417e2b1b |  | note | – – – – – – – – – – – – – – – – –
label | 1669e1a3-963e-53de-bcc7-8c69b758469f |  | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
date | fc74f4e5-eab2-5dc6-8045-a8e4ef4f663c |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 228571e7-4d30-5326-a5ed-991bec3aac95 |  | note | REFERENCE: MRPA Quality Management Plan
label | c881977d-4c16-5ef0-b570-14e957a0d2a4 |  | note | – – – – – – – – – – – – – – – – –
label | a506ed15-cd97-513e-807a-8fcf0749ca2f |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 60d8c406-1961-54b2-9b1a-c22934e3dc0a |  | note | – – – – – – – – – – – – – – – – –
label | d100728d-b7ed-51f5-bbfc-fffcaa54d75b |  | note | METHOD: Document Review
label | d19f064e-9774-5c54-8bf7-74fe92b5be99 |  | note | – – – – – – – – – – – – – – – – –
label | 4fc953d4-749a-5623-9e2f-c518d550a7bd |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 38f9e019-f5c2-5e25-8ad6-cd4e4759e189 |  | note | – – – – – – – – – – – – – – – – –
label | fd694c3a-b938-51f0-8d39-8b2d0e5936b7 |  | note | CATEGORY: HP*
label | ff98d5d5-fa20-58ac-b98e-da042b6a90ef |  | note | – – – – – – – – – – – – – – – – –
label | 89357b38-31db-5bbe-af46-00c11425ba3a |  | note | RESPONSIBILITY: All
label | d6a8b424-a7cd-5694-b81e-a87ff7439035 |  | note | – – – – – – – – – – – – – – – – –
label | 8300f86b-b554-5545-8c4c-d2bf6b828f6f |  | note | VERIFYING DOCUMENTS: This ITP
date | 304e09c0-2066-5345-a1b7-7e8fc3e5715d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | cf018bb8-4ba3-5631-9f34-9f73c92fb28a |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472
label | 81b8a8ba-f731-5c6b-b67b-608d991e3f6a |  | note | – – – – – – – – – – – – – – – – –
label | 830b30f4-caf5-5dca-af75-7b2dfeb9439e |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | 0e8d2852-69e7-532b-8d63-b7f5bf3785f8 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | c1751ce6-4359-574f-bf4a-6e8305a51877 |  | note | – – – – – – – – – – – – – – – – –
label | ca58b5d1-2373-5eae-9d83-55838382be22 |  | note | METHOD: Measure, Visual
label | 0f159bd1-3054-5b1a-92b1-7072fc49251b |  | note | – – – – – – – – – – – – – – – – –
label | 76666acf-2f23-5e0c-882a-473eea96efc3 |  | note | FREQUENCY: Each element
label | a3c96e9e-a98c-51a2-830e-4fe8c66dca2a |  | note | – – – – – – – – – – – – – – – – –
label | 8b173766-4e2c-56e6-8721-4fa7b66e32b8 |  | note | CATEGORY: IP
label | 4175ea55-b8e1-5f59-8116-956042bca06e |  | note | – – – – – – – – – – – – – – – – –
label | cfad84e4-60d1-5ed4-9a71-f1111b8ef336 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 59ba58cf-e7b5-54bc-89c5-329c1e9a7afb |  | note | – – – – – – – – – – – – – – – – –
label | d16a0ffa-657a-543c-8e21-32b1c861905f |  | note | VERIFYING DOCUMENTS: This ITP
date | 43c6b838-cf1b-5bb2-8838-5e94ebaa9440 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation support
label | 689f3bfc-8a53-571c-b12e-d9221b15ae02 |  | note | REFERENCE: 602.02
label | 8e09e336-74e3-594a-a1f0-14f7c5126baf |  | note | – – – – – – – – – – – – – – – – –
label | 61fcfc2c-1123-5978-854d-ba428a711df6 |  | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | c2909fb8-5aed-5de6-bdaa-e681c04bebda |  | textbox | Enter: Teambinder Approval number
label | 39b049e9-ce37-50a4-a1b2-570f9d1b9b51 |  | note | – – – – – – – – – – – – – – – – –
label | a0f8e2ae-a721-5343-8443-14102c217c6e |  | note | METHOD: Document Review
label | 0739cb79-e528-5418-8d8e-f376dafb719d |  | note | – – – – – – – – – – – – – – – – –
label | 061d0535-60f5-5060-90a4-10637fe498a5 |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | 9c9d61fd-6f22-5d4f-9f6a-bc56b8494cb4 |  | note | – – – – – – – – – – – – – – – – –
label | e8c43c1d-a8e9-5b72-8fc2-30fac6e31d80 |  | note | CATEGORY: WP
label | 44457bfa-8143-5ced-b370-67f490550242 |  | note | – – – – – – – – – – – – – – – – –
label | 0a563983-b321-564e-9e62-51438c6ab8ad |  | note | RESPONSIBILITY: SE/PE/SPE
label | ba7591c4-dc57-5b2e-a65f-faf97fdb32cd |  | note | – – – – – – – – – – – – – – – – –
label | b8f3e8d2-c254-51fc-a578-4e00f53be441 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 44d38e9b-4fc0-599a-8c5f-197c86fb9102 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation Inspection
label | 1ed51713-eb62-5ba5-a536-7cc321f51df7 |  | note | REFERENCE: 602.03
label | 1eb899c6-6183-555c-98b6-44156f1fdd2f |  | note | – – – – – – – – – – – – – – – – –
label | b7c38f01-c8dd-56d5-98e9-018e7a4ff1bf |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | b957ff58-d5a0-53c0-bc85-41e246023971 |  | note | – – – – – – – – – – – – – – – – –
label | bac2468b-8345-56f4-a5ee-63ba2ff42440 |  | note | METHOD: Visual
label | 94074fb5-3931-5467-a349-a4ac29b8e4f3 |  | note | – – – – – – – – – – – – – – – – –
label | 5ead8f14-4e80-54c2-afa9-de56c42a5a0a |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | f5fa7215-872e-57f3-9a8b-a94fbfe25e8f |  | note | – – – – – – – – – – – – – – – – –
label | 4f2e9b2d-cfe1-57ad-9cc2-ae47669fcc5f |  | note | CATEGORY: HP
label | 706cdd4d-ed54-5162-8d8f-8d8939a867d0 |  | note | – – – – – – – – – – – – – – – – –
label | a8dc1f60-c3dd-585f-9870-98aa98cacddc |  | note | RESPONSIBILITY: Nominated Authority
label | 910688e0-3d09-550f-ad64-93f6a0020257 |  | note | – – – – – – – – – – – – – – – – –
label | ff54eb6c-c4a7-538a-a498-c5c5bd241aee |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | afda0287-0c09-5a8c-adce-246f9e75d6aa |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | a57b2d38-5ae2-5464-8e25-dbcd378fad65 |  | note | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
label | c5ee9cab-5e54-5057-a6b1-ab3c6bac2b81 |  | note | – – – – – – – – – – – – – – – – –
label | 96fb0d0d-b588-539a-b9d9-67eac97fcce8 |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 1610eb5a-46ba-54d0-a98d-157c14eb78bb |  | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | d33f2b89-4745-59d4-b791-9222a801a025 |  | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 27b2d3cb-d8ef-5b8f-8371-74a3f2905898 |  | note | – – – – – – – – – – – – – – – – –
label | 8eda1a80-6005-5759-813a-095eb073ee2a |  | note | METHOD: Document Review, Visual, Measure
label | 0347a7d2-b205-5835-b1e7-6ae2b1eecce5 |  | note | – – – – – – – – – – – – – – – – –
label | fdf6a2b1-19bf-59e5-a3b6-efdc8b71faea |  | note | FREQUENCY: Each type of element
label | cd366b12-1f3a-515a-9cc1-9a1bc069549e |  | note | – – – – – – – – – – – – – – – – –
label | e4ee535e-acd7-5d10-b145-442e088c663c |  | note | CATEGORY: IP
label | 89e72805-238f-5f48-8638-8edc188e085f |  | note | – – – – – – – – – – – – – – – – –
label | e56303c6-8da9-5029-bf4c-edb9fad2fa5b |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | 1d46ec74-521d-5640-af62-0364bd6f18f7 |  | note | – – – – – – – – – – – – – – – – –
label | 92736f37-2658-5178-9dd1-8252e1a8174a |  | note | VERIFYING DOCUMENTS: This ITP
date | d30061ac-ea7a-5381-88f3-ae58ef1429a3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | 215c9e07-a296-5dca-ad71-767b52d8841e |  | note | REFERENCE: 614.08
label | d0132289-3916-583a-a73b-8f9f73a30795 |  | note | – – – – – – – – – – – – – – – – –
label | 68991295-a3ff-5cd8-a5c9-b35a3c6bfce4 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 0d238679-32da-5218-b12d-82d24731a0d5 |  | note | ○ Walls with heights greater than 2.0 metres
label | 0c779dab-969a-5538-8ef6-553968107703 |  | note | ○ Any member for which self-compacting concrete is proposed.
label | 37211f32-f44f-530e-9edb-81320976fb2a |  | note | Attach: Attachment A
label | 73b0a59a-fb1b-5a39-8c66-180a91567f85 |  | note | Attach: Attachment B
label | 5c17a99c-7513-5d2e-b27c-9281969ae017 |  | note | – – – – – – – – – – – – – – – – –
label | 4f02a41c-05c9-563e-8780-708071101a20 |  | note | METHOD: Document Review, Visual, Measure
label | 95ea7c81-49a3-521f-8bf1-1fa5cf357e02 |  | note | – – – – – – – – – – – – – – – – –
label | b26da431-7431-5aff-9f39-0db0c3db5540 |  | note | FREQUENCY: Each element (where greater than 2m)
label | 40c7990c-0f99-5a91-8887-993693cb58f1 |  | note | – – – – – – – – – – – – – – – – –
label | 6ef8346d-e65c-54c2-9879-059a4f267269 |  | note | CATEGORY: HP
label | 0bfe2fa1-6df5-5bbe-b3c9-12199c0864d6 |  | note | – – – – – – – – – – – – – – – – –
label | 273dc534-1602-5e56-9671-37fb50ecde3e |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 8d89316e-bbbe-5cfe-bed8-5a6fab6502e4 |  | note | – – – – – – – – – – – – – – – – –
label | 504fddf0-474b-5b99-83ac-51d04db21377 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 9cc4df0c-3b75-569b-add6-28aec85bbd0b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 9c759842-9472-5b95-a144-fd6e1bfbeee9 |  | note | REFERENCE: 614.08
label | e36b068c-51db-587e-813d-a9085c2d1ff7 |  | note | – – – – – – – – – – – – – – – – –
label | 03ffd202-bf2f-595d-8316-dafb9e4bdfd7 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 0ef118df-a768-55ff-b745-ce9414c3cd98 |  | note | ○ Walls with heights less than 2.0 metres
label | b9c33267-4134-537c-b8c3-da161349e655 |  | note | Attach: Attachment C
label | 4579743e-d3f2-5a58-a232-258a640f2623 |  | note | – – – – – – – – – – – – – – – – –
label | 9083da68-567f-556e-b494-0187c5ecc1f4 |  | note | METHOD: Document Review, Visual, Measure
label | 696788ea-2a1a-51b5-acbf-d1ab10841d5d |  | note | – – – – – – – – – – – – – – – – –
label | 2d4c3d61-a5d4-5160-afbe-32bd9ae0a216 |  | note | FREQUENCY: Each element (where 2m or less)
label | 9eacd631-780f-5e72-939a-89a60024ccb4 |  | note | – – – – – – – – – – – – – – – – –
label | fbb247d3-e798-5074-9b3c-06e7054ca745 |  | note | CATEGORY: HP
label | 98122fff-c85d-5f7a-a3ec-ad22926f000e |  | note | – – – – – – – – – – – – – – – – –
label | 0abbb8dd-3b51-50d7-87d9-0706d8920e7e |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | cc90f28e-782d-5809-82ef-dda5a7d3d658 |  | note | – – – – – – – – – – – – – – – – –
label | cf166c61-505e-56ab-999b-76c4af6c1604 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | fbfd1fbe-9f46-5dc4-9dc0-b896d5e5cf03 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | e87b4ea7-0b65-57cb-aca5-5e7c3551bfdb |  | note | REFERENCE: 610.47 (a) Table 610.472
label | a83465a6-eb88-5869-b566-1ffbae4ffd32 |  | note | – – – – – – – – – – – – – – – – –
label | dede3c59-ad57-505c-946b-abea844a99bf |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | 7fda2bbb-2b2d-572e-987d-e14256e3f045 |  | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | 8533e936-046f-5ad1-81ac-4037ed072072 |  | note | – – – – – – – – – – – – – – – – –
label | cd5022a1-e205-5e0f-b52e-226cd798a079 |  | note | METHOD: Measure, Visual
label | 86823f8a-c2ba-5795-9097-da0675e11ada |  | note | – – – – – – – – – – – – – – – – –
label | f8900018-bbab-5228-aaf4-97ef4663d4a7 |  | note | FREQUENCY: Each element
label | 72ad85fc-6f73-572b-8045-760f29221254 |  | note | – – – – – – – – – – – – – – – – –
label | 0e9d13eb-fc32-5fc0-9cb6-da9033ae2a0b |  | note | CATEGORY: HP*
label | 0ea95999-5849-5efa-ad25-47d43a96d429 |  | note | – – – – – – – – – – – – – – – – –
label | 1dd0482d-b79b-5b6a-9a93-a5f08dff073a |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | dc227623-914c-57fa-a142-c3a4575efb78 |  | note | – – – – – – – – – – – – – – – – –
label | dab56508-d392-52dd-8911-88c6d51666a1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6dda4d50-7908-575a-a6c9-b0690e78365e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | a09b1cc3-64cb-54b8-b73f-a39af69ecd8d |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | 8cea1052-44c6-594e-9203-85045db837a2 |  | note | – – – – – – – – – – – – – – – – –
label | c2c464e3-10cd-595b-897a-aa223bb3f295 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 9108de18-0600-5033-867c-7b96f77e5ab7 |  | note | ○ Projecting reinforcement is the correct length and location.
label | 7fc6681e-278e-547a-ab0d-f0f562536cf0 |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | f6922d07-bb6d-5bb7-948f-1031f7567732 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 813bfc61-b1d5-5a81-9f2c-ebff0d8efc1e |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 392bbff2-7179-5a28-9de5-16e6aca2cc0c |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | 9145bd8b-11d1-5c7d-86c3-b802e75fa627 |  | note | – – – – – – – – – – – – – – – – –
label | 99920efe-34fe-5a70-9f80-7e6f275eac24 |  | note | METHOD: Measure, Visual
label | 93c2bfe1-fb41-5941-88d4-e4a287975a90 |  | note | – – – – – – – – – – – – – – – – –
label | a8d2a962-da30-5734-89b8-235500c9dcd8 |  | note | FREQUENCY: Each element
label | 313db5c7-a176-5a93-8e6f-f60d1bd055a4 |  | note | – – – – – – – – – – – – – – – – –
label | 3b9894af-802c-5d31-8b7e-592b5373b8bd |  | note | CATEGORY: IP
label | b00c6c99-6c1c-5d1f-a012-fbbf9f4b6708 |  | note | – – – – – – – – – – – – – – – – –
label | 0b4066b7-83d2-526f-a38a-e1fce6ed07ea |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 914ba1c7-ef3b-5504-aa5e-3609752661fd |  | note | – – – – – – – – – – – – – – – – –
label | 6c77a0c3-2413-5450-9113-7ea9a2b88a6b |  | note | VERIFYING DOCUMENTS: This ITP
date | c49bece4-26cc-5b5c-985c-9f0b58f57f46 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | 8df2b242-8fc3-570b-b1a4-e38e867acad0 |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 03cd870e-2b7b-5612-b077-d28158ea9137 |  | note | – – – – – – – – – – – – – – – – –
label | 0b84fbe5-b4d1-5930-9893-d15ab9a0e072 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 90533280-b6b3-506a-9820-69fc9fd56f4a |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | b7692507-6f21-5f9c-8a9e-8266474edf88 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 06d2a469-f9a0-592c-95e1-f237a70aad65 |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 347bc44f-20c6-5731-9510-df086284df2a |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 772d724f-3697-5b08-bb28-88a6b4c69a3f |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 72eec155-1f05-58df-a473-f27cadb322be |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 746259a7-a29c-57ac-acb6-b8504f97797a |  | note | iii. Ducts and conduit location = ±12mm
label | 598f33db-74dd-508e-93d4-014ae4715351 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 91d6c0ce-0db4-5b95-bae2-7723ead97342 |  | note | – – – – – – – – – – – – – – – – –
label | 91816efc-f114-524e-9313-94c095139e02 |  | note | METHOD: Measure, Visual
label | 1d73c8ec-a285-5fb8-9c70-57643da1c866 |  | note | – – – – – – – – – – – – – – – – –
label | 6279254a-e09b-5aca-99bb-b5db04df5d68 |  | note | FREQUENCY: Where applicable, each element
label | 8d722559-f0e2-544d-9686-904a8f7d6519 |  | note | – – – – – – – – – – – – – – – – –
label | 8139bc4f-6fcb-56c2-a7d2-f72365eb6c3e |  | note | CATEGORY: IP
label | 5238d028-3107-57b1-b3d7-fa23225cf2ef |  | note | – – – – – – – – – – – – – – – – –
label | 830275db-1764-52a1-88c2-a5a40c4df49e |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 584063ec-8f0c-527d-b956-ab4dfcfe7f04 |  | note | – – – – – – – – – – – – – – – – –
label | f9f4e426-3f21-5533-96d2-88a241cb9dc9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 28e7de03-3543-5445-abf0-7dd6b93e763a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Thermal Differential Monitoring
label | bc980bab-bb34-5d7c-9fa2-2e55ebe5cf61 |  | note | REFERENCE: 610.22
label | d799b5eb-7876-5e06-9eb1-15fd79afa661 |  | note | – – – – – – – – – – – – – – – – –
label | 1fab0fca-0d31-5c9d-aadf-ed765303786a |  | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
label | fba7680a-e562-5ea8-b98f-5fcc07b258a1 |  | note | Only applicable if the element has:
label | a4b22af4-edb5-5231-81fd-77193d2a557f |  | note | i. the smallest sectional dimension exceeding 500mm
label | 05d6a62e-4c1b-5030-a4cb-df471b0cdc2e |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 79d369df-892a-5a60-aa93-eb20351d08ad |  | note | – – – – – – – – – – – – – – – – –
label | e585f825-3112-5d08-a3b9-ef1f2582823e |  | note | METHOD: Measure
label | ee83ad63-86e5-5633-a4bf-d61e6cb28bef |  | note | – – – – – – – – – – – – – – – – –
label | 1bd549e1-fc34-5650-bc5a-017f027f63d9 |  | note | FREQUENCY: Where applicable, each element
label | 1c78aae9-0075-556b-a264-1c1691cacfc6 |  | note | – – – – – – – – – – – – – – – – –
label | 6527ba10-bf54-5aff-8851-9bf600273ab3 |  | note | CATEGORY: IP
label | 02675efc-3776-5972-9c88-6e457a96fd43 |  | note | – – – – – – – – – – – – – – – – –
label | 6114411c-e461-5e9b-9e56-a1018d95aee5 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 9af98789-9a92-5729-8877-264426a9e6e7 |  | note | – – – – – – – – – – – – – – – – –
label | 58c6ac30-59da-5b45-b42e-26cdc29e0e6e |  | note | VERIFYING DOCUMENTS: This ITP
date | 5003147e-96bf-5824-951c-b76b660452c0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-pour Inspection
label | bde86661-946b-520e-bec8-b0678ee7e2fe |  | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
label | 4ac5b7d4-a30e-5ced-81a7-26d31bb852ed |  | note | – – – – – – – – – – – – – – – – –
label | 214f435b-593b-559f-8527-56e853dc13b9 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 2bff291d-36ae-5b15-8169-9f52a63646f8 |  | note | ○ All foreign material has been completely removed from the forms.
label | 0aeaca2e-b933-50fb-b741-5a938e78657e |  | note | ATTACH: Pre-Pour Checklist
label | db7389bf-050a-5abf-a70b-a312cff93fa8 |  | note | – – – – – – – – – – – – – – – – –
label | 2a2f9164-b89a-5f15-85f9-78387024456b |  | note | METHOD: Measure, Visual
label | 8ba75a98-bb99-5795-adaa-9476ba672582 |  | note | – – – – – – – – – – – – – – – – –
label | 06372b2a-f161-5732-89c5-f49ac07a93bd |  | note | FREQUENCY: Each element
label | f6f2f1ea-91be-5f3c-bc68-1587db2ca501 |  | note | – – – – – – – – – – – – – – – – –
label | fecd5b27-5aa1-52b3-a281-3d887ca6ad86 |  | note | CATEGORY: HP
label | ba91e922-1f52-5a72-8fc3-a5fbde41d346 |  | note | – – – – – – – – – – – – – – – – –
label | c4980ec2-2572-5b93-8541-6af651dbf161 |  | note | RESPONSIBILITY: Nominated Authority
label | 3f785c8f-6e45-5c1e-aa92-5a6699801338 |  | note | – – – – – – – – – – – – – – – – –
label | 336dddb1-0a5e-5df9-ae96-47c92fc3da90 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
date | e35c991f-9f14-532c-aa7a-858846439de0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions & Evaporation Limits
label | 7920f989-2d7b-5294-be4d-a06bb258ec65 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e), Table 610.171
label | 49c76626-d41c-5e4c-8a9c-193ef80cc5fd |  | note | – – – – – – – – – – – – – – – – –
label | f2a9acb1-8fea-5587-a2c1-5d22a300205e |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 80975b1a-4fef-5ef0-b3c7-d21c65e1dac2 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | b3d30f41-b292-512b-8132-0ce9d9ecf9ab |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 29a1648a-67eb-5844-ac36-b93e95216297 |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 3c45bba4-d041-5a4f-903f-6ecb5e8761d7 |  | note | Record: Required information on the Concrete Pour Record.
label | a5234362-0315-5568-9b48-bf6adbcb1295 |  | note | – – – – – – – – – – – – – – – – –
label | 50230019-d8c5-5730-be4e-929d11b0ab52 |  | note | METHOD: Measure, Visual
label | 603522b8-c1f0-506f-b601-90a462d9264f |  | note | – – – – – – – – – – – – – – – – –
label | 0c9329d0-253f-538a-b521-0bf612ce1449 |  | note | FREQUENCY: Each element
label | 4ca38b86-66fe-50ab-be91-fcb264120d79 |  | note | – – – – – – – – – – – – – – – – –
label | 99a0f9eb-1411-53b2-8a84-d6ed72b252fe |  | note | CATEGORY: IP
label | 7f9ee751-c075-59c3-b86a-ee6658dd52af |  | note | – – – – – – – – – – – – – – – – –
label | 3d7cb455-558d-52ce-a2e4-f5e98fa7adde |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e26e0eb4-2849-5fba-8c89-9c2652463fed |  | note | – – – – – – – – – – – – – – – – –
label | 9a641759-e523-521a-a814-17477ebc5b41 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 633ade92-d8ff-59ea-966a-0634cf4b41c4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Sampling Frequency
label | 9a064030-3731-5fee-b8c9-fa3d6077d795 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | 5eb887ba-80eb-523d-8186-580b48b14cc0 |  | note | – – – – – – – – – – – – – – – – –
label | 3bb69ff5-2ddd-564f-8bc2-3a5ac471012e |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 8b7680dd-8fee-5139-b17f-1dce74e56008 |  | note | 0m³ to 10m³ = 1 sample
label | e95bf7f7-f977-51ef-9d16-205cc507d4f9 |  | note | 10m³ to 25m³ = 2 samples
label | e4b886f9-e964-5f14-82cd-8606894305ee |  | note | 25m³ to 50m³ = 3 samples
label | 963e1a42-51fe-58a4-81f7-a5b624024e58 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 6a8a3b97-a9a5-5cdb-9bfe-8769e02cffb4 |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 918095b6-65c6-5a4a-bcbc-acefc3c6e815 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | a7387b7d-01e6-5147-892b-5a4dc6499f5b |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ea579f29-7904-5db6-beb8-5063633a587c |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 0ffa58bf-2b61-58e8-bdd2-5d70c8d2bff7 |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 51054f46-295e-560e-9043-a56bf1a4962f |  | note | Record: Required information on the Concrete Pour Record.
label | 3b0e091c-cdd3-5c15-a936-89564486a1cf |  | note | – – – – – – – – – – – – – – – – –
label | dc810b55-079e-5982-8ca0-75ce12b6b415 |  | note | METHOD: Test
label | f25ab48a-f75d-5836-bd13-1b6c9874ccc2 |  | note | – – – – – – – – – – – – – – – – –
label | 80973312-08a1-574a-bfec-353c15970f24 |  | note | FREQUENCY: Each element
label | 32a2c2e8-dab0-5dfe-8939-4543f5654d5a |  | note | – – – – – – – – – – – – – – – – –
label | 8ed8d1a1-bfb8-52c3-930b-92bc8e64a0e6 |  | note | CATEGORY: IP
label | dbc86553-45a4-5ac8-9d4f-c8c81ae7c74b |  | note | – – – – – – – – – – – – – – – – –
label | 086ba968-2264-53cd-abcc-c5e7927c9d5a |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 126b94af-d740-5b2c-8852-2e78ff2ee50d |  | note | – – – – – – – – – – – – – – – – –
label | 2d00f970-6b44-5817-85ef-01194eb5ab2e |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 597b6036-63c9-52fe-8576-399e3b179f64 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Slump
label | 4bcfc3cc-fbb1-5cfd-b1d4-7a8836a6781b |  | note | REFERENCE: 610.16 (c)
label | b3c2af49-690f-57c0-ad3f-33dbd757410d |  | note | – – – – – – – – – – – – – – – – –
label | de36be57-7a74-5451-8c8f-9f0873db63b4 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | 24e959b8-057f-500f-87b8-8e3a60b03ac3 |  | note | <60mm = ±10mm
label | 3856595a-4a92-53a0-b41d-6c419d0b6de4 |  | note | ≥60mm to ≤80mm = ±15mm
label | e18b45d3-86c8-5d82-bfcd-c01eae75b84c |  | note | >80mm to ≤110mm = ±20mm
label | c1bec4a2-0f0b-5fb3-883f-8000dbef7067 |  | note | >110mm to ≤150mm = ±30mm
label | 2e6cbfe1-5f08-58ed-b9fb-e087ce3e57e3 |  | note | >150mm = ±40mm
label | 15ca0e1a-a943-5367-9959-4fa464520e8f |  | note | Record: Required information on the Concrete Pour Record.
label | 39ceed1e-7b46-5f9e-b101-f2919d072489 |  | note | – – – – – – – – – – – – – – – – –
label | 49cdf2ec-df38-5d0b-9932-afb41db1ffd2 |  | note | METHOD: Test
label | 5c9e4f04-e608-5d82-9e97-258ccff61267 |  | note | – – – – – – – – – – – – – – – – –
label | 6c7a3357-acbe-5498-b6f8-d1dd2da2db8e |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | 45cafdb9-3324-58e3-a817-a2cabdfc3d44 |  | note | – – – – – – – – – – – – – – – – –
label | 39680b01-1f57-5129-8a8a-74b376f586e9 |  | note | CATEGORY: IP
label | 33da3bb4-d74e-5a00-8e5e-2aa85174a604 |  | note | – – – – – – – – – – – – – – – – –
label | a4fa7531-5efb-5dac-b166-15f8d77b3b2b |  | note | RESPONSIBILITY: Concrete Tester
label | 1e17d127-1005-5e2b-924f-1dcb3e3eb666 |  | note | – – – – – – – – – – – – – – – – –
label | c0afbaf7-fe9d-5206-a113-44f41fa55429 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | c0e6ea34-fc58-5ecf-8f02-aaefe645c192 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
label | 2f2fe718-39a7-5291-8241-5dc0d6110c94 |  | note | REFERENCE: 610.13 (b)
label | 49de7e84-e82e-5a79-9746-e4870db782ff |  | note | – – – – – – – – – – – – – – – – –
label | d222781b-7254-587e-92c9-cba63ac57664 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | e809f61f-e532-5256-b310-ec1f8f28c15d |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 1f92e563-b520-590d-bb3d-8ab958b2f1de |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | d31b5d0f-7781-5314-96ca-532db4644898 |  | note | Record: Required information on the Concrete Pour Record.
label | 8d6a044a-82be-5f45-9e39-5428235e93b4 |  | note | – – – – – – – – – – – – – – – – –
label | cbb72424-06ab-5fd4-8b85-be8aa40619c6 |  | note | METHOD: Test
label | 6743909d-2918-5a4e-b9bd-24b196e47038 |  | note | – – – – – – – – – – – – – – – – –
label | ab5e6826-59ac-56a1-997b-de5e5d766415 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 537c0584-620f-5961-ad34-c9842f1b8107 |  | note | – – – – – – – – – – – – – – – – –
label | c5dcf787-b2cb-5552-8686-d475cf3da287 |  | note | CATEGORY: IP
label | 7b41219f-ba41-5a3e-8550-61c6882f9733 |  | note | – – – – – – – – – – – – – – – – –
label | 22634bcd-1373-5249-9339-654526d0ca28 |  | note | RESPONSIBILITY: Concrete Tester
label | caad3818-c17d-51f7-a24d-122896f5e6e2 |  | note | – – – – – – – – – – – – – – – – –
label | 71667c95-7389-59ce-9a30-dce8ba78ff9f |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 4772a52c-4d54-58de-ac5d-2f52c006a28c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
label | d4b9bc5e-0bde-5480-ab2e-9be3c53c4223 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 98d942fc-20f0-5ce7-b69d-7603c739c791 |  | note | – – – – – – – – – – – – – – – – –
label | ebab7169-f431-57d6-b53d-0fb8857bb77c |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | ae703c67-b831-5401-b865-dcc7ac8b0bd4 |  | note | Record: Required information on the Concrete Pour Record.
label | 22c8067c-e4a5-5abf-bbc4-865825c91acd |  | note | – – – – – – – – – – – – – – – – –
label | c2ce0cdf-92a8-5e8a-8721-3a2b6cc25db4 |  | note | METHOD: Test
label | e59a7651-e9ab-5c91-95c4-30b655391a7b |  | note | – – – – – – – – – – – – – – – – –
label | dade0410-b1cb-5145-ac87-bc5a4ffb4e8c |  | note | FREQUENCY: Each sample
label | fb44e19f-08e5-581b-8064-d31878b56955 |  | note | – – – – – – – – – – – – – – – – –
label | ae9826b3-3361-5138-91d6-52d4eec43394 |  | note | CATEGORY: IP
label | 4fcacd16-b92b-50c3-a2b6-b86cff6e08c0 |  | note | – – – – – – – – – – – – – – – – –
label | 90257ba4-f367-5ced-bf93-98286186cb29 |  | note | RESPONSIBILITY: Concrete Tester
label | 4c352764-d170-54db-ba64-7548a26e111a |  | note | – – – – – – – – – – – – – – – – –
label | 067104b7-0ebe-5801-8727-1ff71581a087 |  | note | VERIFYING DOCUMENTS: This ITP
date | 29cb598b-d72c-5ef0-b173-b5f176fd031d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Supply & Discharge Rates
label | da4b4c10-a375-5847-9538-ecb4dc3c22ad |  | note | REFERENCE: 610.13 (a) & (f)
label | cd563335-88a8-5fab-866e-b477a06061d2 |  | note | – – – – – – – – – – – – – – – – –
label | d2913d7d-56a3-5ca8-b0a6-9ba590da0c95 |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 5026b67a-176c-5b40-8f42-3ac7ace02a28 |  | note | ○ No water is to be added once discharge commences.
label | 42a7c318-c779-5af3-a73e-b798d2e89b20 |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | 2a1866d7-5d36-5300-8e06-e89914427f89 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | 39306197-737d-5931-9d0c-8137463b80d0 |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 9f8b72fd-b24f-52d5-9b0b-6f02e313efd8 |  | note | Record: Required information on the Concrete Pour Record.
label | 23819e85-121a-50a3-b41f-e860c5b240c3 |  | note | – – – – – – – – – – – – – – – – –
label | d107245a-27f9-571a-95c2-690da89c9e5e |  | note | METHOD: Measure, Visual
label | 4454edce-8b8d-58b8-b850-187b98caa507 |  | note | – – – – – – – – – – – – – – – – –
label | a4ea42ab-1211-5824-9d78-647b3787b882 |  | note | FREQUENCY: Each load
label | ac27f5d0-d750-5c78-a9c0-39f861e21eb3 |  | note | – – – – – – – – – – – – – – – – –
label | 72925e05-f645-5a56-b8b4-9fbb763c9fcb |  | note | CATEGORY: IP
label | dff42072-64df-59b7-8f60-83666816f291 |  | note | – – – – – – – – – – – – – – – – –
label | 3e3a461a-1298-5e2f-bbdd-0dad16101d71 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 76dd45c8-5493-5117-938d-6cdfce7e80a0 |  | note | – – – – – – – – – – – – – – – – –
label | ecd17b52-b51e-55ff-b330-480179fc402d |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 382e3765-6f70-5324-a882-8ce4c666af34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Placement & Compaction
label | 1fb6c7fb-c7e7-560b-9796-07f81d22afef |  | note | REFERENCE: Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | 8540691b-dfa6-567c-a915-08a0964ea8f1 |  | note | – – – – – – – – – – – – – – – – –
label | 9f034357-2a54-56d9-af55-ecf6fca45659 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 4e8094c4-1048-5aef-9ca5-365f54e36c7a |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 4a8b5426-22f2-53ef-985b-530c092f8d92 |  | note | ○ Concrete is not dropped freely from a height exceeding 2m.
label | 8e215548-380b-54cf-a83b-eccc368b2b8a |  | note | ○ Concrete is not moved horizontally by use of vibrators.
label | 83df6988-1669-5861-9183-35543535187b |  | note | ○ Adequate compaction is ensured
label | e9390c75-30d4-5b18-87d1-ef013063de33 |  | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 7ecbd09b-e8f5-5c3e-bb45-7e614cb4aa3b |  | note | ○ Concrete layers are not more than 350mm
label | 16e7284f-3e8b-51b3-b906-876ef4325c99 |  | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 63b8361b-4bc7-5a67-9bfb-3ec1b8fcb989 |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | cb6d9eff-b23e-51bf-87bd-0f88a8795c1e |  | note | Record: Required information on the Concrete Pour Record.
label | 37927f53-769a-56aa-bbc3-fc85a5a4f98c |  | note | Attach: Concrete Pour Record
label | a4e24a02-a8d8-5811-9eff-588ec7d4b8c8 |  | note | Attach: Concrete Dockets
label | 35467c78-3a0a-5c17-ade7-2739a391f4b4 |  | note | – – – – – – – – – – – – – – – – –
label | be8f91e6-2e9e-556f-abcc-219283149371 |  | note | METHOD: Visual
label | cc8619fe-3e35-5287-8d95-58c9a7e87468 |  | note | – – – – – – – – – – – – – – – – –
label | 1a1522fe-722f-5fcb-9ab2-d527e470c5c0 |  | note | FREQUENCY: Each load
label | 98cda946-673e-522f-b4a7-56f0a3de8949 |  | note | – – – – – – – – – – – – – – – – –
label | 0b85d246-c438-5108-9057-073af405d9cc |  | note | CATEGORY: SP
label | 85122871-436b-5f03-a254-1132609a2607 |  | note | – – – – – – – – – – – – – – – – –
label | d01d47b6-bdbe-5d89-a454-5361bb862a77 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 66a855a3-6e50-56fb-8501-d8c0684d5276 |  | note | – – – – – – – – – – – – – – – – –
label | 8fabdeb5-6e57-5ce3-9700-bb1fb9c306cb |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | 42fd6c48-be2c-593f-83b0-986b9b54b51a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Surface Finishes
label | bed066cb-2f35-5289-9820-e74a858252b0 |  | note | REFERENCE: IFC Drawings 610.31, 610.20
label | 4f91c1f1-28b0-5f62-a264-6f6f88b8cef4 |  | note | – – – – – – – – – – – – – – – – –
label | 160d3633-13a2-5107-a175-e10fac458f64 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | fcac7b32-0b44-5fdf-9637-85effb285096 |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | a811ad9e-3e46-5e9b-8d76-ebbb7e1a6f6b |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | e999c9dc-66b2-52a6-a5ef-b3d4e935f235 |  | note | – – – – – – – – – – – – – – – – –
label | 40b4ef40-2eab-57c1-898d-15c6a5865bc7 |  | note | METHOD: Visual
label | 7cb1c30e-d73d-5179-8ad8-a7054baa8b40 |  | note | – – – – – – – – – – – – – – – – –
label | 040b84fa-aac7-5f57-a5cf-54dfc7d70926 |  | note | FREQUENCY: Each element
label | c565ca54-ca08-5717-926e-8db2e95057ae |  | note | – – – – – – – – – – – – – – – – –
label | 8ecee906-950b-52d3-8dc3-dd1a02de67cc |  | note | CATEGORY: IP
label | d8abaef7-a8bf-5cd4-80c2-5f70603f46e6 |  | note | – – – – – – – – – – – – – – – – –
label | eea45dbe-16ee-5822-88bb-a5c26251a3ba |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5f1f8ee9-5e64-59a3-a50d-e4bc1fa911c0 |  | note | – – – – – – – – – – – – – – – – –
label | 4ba62632-dc0b-5ac5-aacd-803aa5655845 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6645dbaa-1e2a-5b35-bd8b-a972b2f707ce |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Curing-Top Surface
label | fdd31c9e-1e72-5ae3-bd75-4c479ee3d78a |  | note | REFERENCE: IFC Drawings
label | 315c65be-7c15-5c2e-b623-740835ed3f87 |  | note | – – – – – – – – – – – – – – – – –
label | 6f78163c-8d47-53a0-a425-9fcf9af372ef |  | note | ACCEPTANCE CRITERIA: Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | c01c50a4-2e67-5d22-855b-12b53c7e2c9f |  | note | – – – – – – – – – – – – – – – – –
label | 11567f60-82f4-5059-9ba7-5659750f0155 |  | note | METHOD: Visual
label | 8ca66b26-8ac3-50b1-a0bf-80e49124bfae |  | note | – – – – – – – – – – – – – – – – –
label | fc4fbc01-2bbf-5c2f-88cc-71755bfdef7c |  | note | FREQUENCY: Each element
label | 663f7fa1-b259-5e7f-b10d-f28a90b03be5 |  | note | – – – – – – – – – – – – – – – – –
label | bf691c43-3cbc-5179-bfd1-8ef3ab8f4dc2 |  | note | CATEGORY: IP
label | 8f119521-9756-52f4-9bd5-71cab59e3eff |  | note | – – – – – – – – – – – – – – – – –
label | a7c8716a-69bd-5aa9-8326-9e43c3a239eb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | c40b39bf-806a-5e86-90c4-0fccaedb92db |  | note | – – – – – – – – – – – – – – – – –
label | c3cfb61c-90b6-5e9b-a04e-293876b87d4b |  | note | VERIFYING DOCUMENTS: This ITP
date | 34ea78b5-129d-5cce-bca5-d7c03c3d842c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Curing after formwork removal
label | 7cbedca8-1bb6-5b3b-929c-1fd6f1ddcc01 |  | note | REFERENCE: IFC Drawings
label | 20ea7db7-7c75-554d-a9d5-5aba57ac0a54 |  | note | – – – – – – – – – – – – – – – – –
label | b2afd64d-034c-51ed-b252-be447a4875de |  | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 0bd70ae5-0d47-5599-b2d2-8e5476e12681 |  | note | – – – – – – – – – – – – – – – – –
label | 9e6571f8-da9e-592a-b838-58c45e237a9d |  | note | METHOD: Visual
label | d2557abe-9384-5fb6-bc88-9a617abceae5 |  | note | – – – – – – – – – – – – – – – – –
label | 788e94b6-87f2-5ded-9ab6-7740fcf1a4cc |  | note | FREQUENCY: Each element
label | b236041b-3dc6-5986-8941-61aa1d0d29dc |  | note | – – – – – – – – – – – – – – – – –
label | 43526095-5a75-5d48-8564-d708ca69e97a |  | note | CATEGORY: IP
label | 155a3ce6-54b3-5b59-8940-b81a4a2dce74 |  | note | – – – – – – – – – – – – – – – – –
label | 56cdf59b-7fa8-50df-98c0-ccbc36ceceac |  | note | RESPONSIBILITY: SE
label | 4dac2884-82b9-531f-b6de-0c3e07501a4c |  | note | – – – – – – – – – – – – – – – – –
label | d082127a-fc89-5595-849d-0540adc833e7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0554b793-00a8-5b12-bdec-6183c74cfeb7 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | 579366d6-4414-5b5a-82a0-d2c5dfebdb78 |  | note | REFERENCE: 610.22
label | c2e911a3-2253-517c-a1ca-6827390290b7 |  | note | – – – – – – – – – – – – – – – – –
label | 65ea8926-df1e-5032-9c36-593abf68b703 |  | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 42fc1e94-16c5-5df1-8dda-a682ab88f819 |  | note | Only applicable if the element has:
label | c8376195-47af-56f7-9f8f-5de7d36e2f9c |  | note | i. the smallest sectional dimension exceeding 500mm
label | fda78224-8dbf-5464-a1e6-83dcf2fe962d |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | 1b87d277-1538-53c6-8261-1c107e2e5c6b |  | note | Attach: Thermal Monitoring Report
label | 7d5283f7-e590-557d-8d2b-0e0c3e679b8f |  | note | – – – – – – – – – – – – – – – – –
label | 608bec93-1c31-50ff-ab81-a918c484fd6a |  | note | METHOD: Document Review
label | 2ba01d93-7910-5c74-8aad-61241642dcbd |  | note | – – – – – – – – – – – – – – – – –
label | 6ac67a55-0703-5f0f-9eb3-ae66f3d4bfb3 |  | note | FREQUENCY: Where applicable, each element
label | 66483603-5122-5612-b810-0aaff2f92e60 |  | note | – – – – – – – – – – – – – – – – –
label | 5765b621-90fa-5f9e-9428-d54bfbeb12ce |  | note | CATEGORY: IP
label | 114b8bfc-8a0d-588a-9711-2e8b95222e2f |  | note | – – – – – – – – – – – – – – – – –
label | fd5a3a7d-765f-510d-a9cc-466872ccfcd2 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 198ab2a9-dfbe-5c97-92bb-eca7725d9b52 |  | note | – – – – – – – – – – – – – – – – –
label | 81201e9b-69a6-51d8-aed6-27b02019438d |  | note | VERIFYING DOCUMENTS: This ITP
date | 61a21e79-5347-529e-8f86-d03b7be08570 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
label | 1b5d9373-d2b6-5001-9109-4cfe1935339d |  | note | REFERENCE: IFC Drawings
label | f0e892f9-0a02-5e02-9465-618f4caf91d8 |  | note | – – – – – – – – – – – – – – – – –
label | 573676b6-19ec-5e1b-b7cf-4f7576a3f201 |  | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | a2e8e413-c3d7-5f9b-9d88-cd21c9ec973b |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 94f35d4a-dca9-5e3e-bb46-3b8fd9743cb1 |  | note | – – – – – – – – – – – – – – – – –
label | 4e48f9ea-dda0-5cd0-81aa-61a29ab3e680 |  | note | METHOD: Document Review
label | e7ee6cf5-0fe3-51a3-9f8f-602b0a1ea705 |  | note | – – – – – – – – – – – – – – – – –
label | 42612da0-dcf5-5822-9177-f90a9e6f1638 |  | note | FREQUENCY: Where applicable, each element
label | 57d5f02f-699e-5da9-9764-ca13b2c2c410 |  | note | – – – – – – – – – – – – – – – – –
label | 813f9e45-0b8d-5e9e-bb34-91761ec22976 |  | note | CATEGORY: IP
label | 180cba94-41ae-5bfc-a782-2209108a3018 |  | note | – – – – – – – – – – – – – – – – –
label | 45a1dbcd-a8f1-59e6-9216-2fbe25b5a9d5 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 58bd2e0f-8166-533b-95ea-cd7fc8975917 |  | note | – – – – – – – – – – – – – – – – –
label | 33892ad7-4e1a-52b4-adf1-16cf4e524d79 |  | note | VERIFYING DOCUMENTS: This ITP
date | 332f89a5-d1ca-5d3c-8fb8-7e1c92273339 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection - Cracks
label | aca7bf82-2bf0-55fe-9fd3-268d6b45d7da |  | note | REFERENCE: 610.24
label | e0bd379c-da1c-526f-ab27-33c122b8c395 |  | note | – – – – – – – – – – – – – – – – –
label | 67a4ca32-f4cf-56ac-b8f9-955134de30c1 |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
label | 6f130200-222a-5f80-9e7f-11567ae00759 |  | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | c90bfdf1-798d-5b43-b6d2-186c6e46a36a |  | note | – – – – – – – – – – – – – – – – –
label | 41491c7b-3e19-559a-8e1e-73b692cb5e6a |  | note | METHOD: Visual, Measure
label | 26fa7b65-6071-5b19-b724-d88a1ab2ef27 |  | note | – – – – – – – – – – – – – – – – –
label | 69dc9c09-0436-5eda-8e38-798153f4ce1e |  | note | FREQUENCY: Each element
label | 62064e0b-ee87-5162-adbe-707becca640f |  | note | – – – – – – – – – – – – – – – – –
label | 8d663a75-a7bd-5808-843f-5fed0cae9462 |  | note | CATEGORY: IP
label | f29a126e-6f71-5274-a38c-7fc2fb355789 |  | note | – – – – – – – – – – – – – – – – –
label | acbda6f2-8fd1-5e7c-bc33-4461aea712cb |  | note | RESPONSIBILITY: SE/PE/SPE
label | 40842fd7-5ce2-5f34-9a10-762abc1d4624 |  | note | – – – – – – – – – – – – – – – – –
label | f5bb5547-d3f4-5a92-a052-73cca61d0250 |  | note | VERIFYING DOCUMENTS: This ITP
date | 92c45535-6197-57ba-b39c-28a1091edc05 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Surface Finish
label | d1f1ad70-4fab-58c8-aaa3-e2498c2b56e7 |  | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
label | add94181-8354-5386-ad0c-874c8f3563ab |  | note | – – – – – – – – – – – – – – – – –
label | 49442c57-e408-5818-805d-46e98b1e172d |  | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
label | dc15321a-4d3d-5b5d-88e0-8ada2b70223a |  | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | e858c277-9d19-5bf1-8c5f-270730c46a99 |  | note | – – – – – – – – – – – – – – – – –
label | 526a3c7d-1ec5-50f8-bb07-9ad590968634 |  | note | METHOD: Visual
label | cdd5304b-a7aa-5a0e-91f3-5e1ed118a816 |  | note | – – – – – – – – – – – – – – – – –
label | 540df31a-1ea1-508f-be4e-c8946a4711ce |  | note | FREQUENCY: Each element
label | 53110a7b-fac0-5e62-a330-64b694a77a9a |  | note | – – – – – – – – – – – – – – – – –
label | 56ffbb2c-f631-5cd1-a1af-1fec9469a516 |  | note | CATEGORY: IP
label | ce6ade44-4b23-52dd-84c2-74baa1bc39b8 |  | note | – – – – – – – – – – – – – – – – –
label | a7981130-5748-5cc7-8cf5-179e857de15c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3c9d4772-764a-5ef3-9676-4d48f88c29f8 |  | note | – – – – – – – – – – – – – – – – –
label | a5c35094-af8e-56e9-85a8-e680412d6e49 |  | note | VERIFYING DOCUMENTS: This ITP
date | 926bdd38-c625-5829-be3a-31aea83249d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Measurement of Concrete Cover
label | 18b98800-7ef9-5bed-a870-9c4060d5a746 |  | note | REFERENCE: 610.34
label | 89c9b5c1-77fb-52ce-80d6-7d14dc2c7f76 |  | note | – – – – – – – – – – – – – – – – –
label | fd1737b6-02ad-51d7-a726-9f419d16d1ec |  | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 06b67d18-02ec-5030-aa14-7c26a13eef60 |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | 29f2f737-0523-5fa7-b221-b631d14377b4 |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 41430883-1608-5d61-ac0a-9aed432951a4 |  | note | Attach: Covermeter Check Record
label | 68e1326c-fb74-5ee5-8150-586ea9c3175d |  | note | – – – – – – – – – – – – – – – – –
label | 6d05061a-b5d0-5238-b230-617a0bbe67c2 |  | note | METHOD: Measure
label | cc1088da-7321-5bfb-884e-e22b7f7a4297 |  | note | – – – – – – – – – – – – – – – – –
label | 0dfe733c-73b3-524b-9382-35aaf6a35103 |  | note | FREQUENCY: Each element
label | 02dc3136-7e58-535f-9428-fc8a640ad3eb |  | note | – – – – – – – – – – – – – – – – –
label | 1f4e7747-ec97-5915-acba-aa3c4f1fcfaf |  | note | CATEGORY: IP
label | 413732a1-863f-5d4b-8ca7-2a17ff510e1b |  | note | – – – – – – – – – – – – – – – – –
label | ceb591b0-1664-5549-838f-23bdb90cfaca |  | note | RESPONSIBILITY: SE/PE/SPE
label | ece82cab-b644-51e4-b688-1a040cd588d8 |  | note | – – – – – – – – – – – – – – – – –
label | 290a9a40-5795-556e-8b14-749a94931825 |  | note | VERIFYING DOCUMENTS: This ITP
date | 27bbe8bc-99be-5e3d-8e3e-dead541862e6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | f288463a-50c4-57f0-a106-c27f73e623f1 |  | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | dc0de755-424e-5054-9b62-92ff69b1cd62 |  | note | – – – – – – – – – – – – – – – – –
label | 89ea1698-b524-5e33-bedf-4d97dd1c3338 |  | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
label | 2d31ab0d-4cd8-59e3-ba70-460ce189661d |  | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | 5ef7c433-3efa-561d-9c03-9335d1f403df |  | note | Attach: Concrete Test Results or Maturity Test Results
label | d6ff6b92-beed-54d6-9b9e-db127c582f1e |  | note | – – – – – – – – – – – – – – – – –
label | 74edb0b9-1426-5bc2-afe1-a2212ea68e20 |  | note | METHOD: Document Review
label | ccf34cc3-fe99-5c59-8748-04e240a14d31 |  | note | – – – – – – – – – – – – – – – – –
label | 951113bc-7a8c-5aa8-86b3-840e45517ea0 |  | note | FREQUENCY: Where applicable, each substructure element
label | 24cfe2d6-2612-5d8a-9fb4-64f64bd20a75 |  | note | – – – – – – – – – – – – – – – – –
label | d20a2470-1397-5703-b511-f8b8dea747c5 |  | note | CATEGORY: SP
label | 8dd9954c-8496-53e5-b053-f514f2fc62ea |  | note | – – – – – – – – – – – – – – – – –
label | 140c24ed-0759-59b7-950a-99104160e434 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5ce03f86-086f-553a-a683-661fee1ac1f5 |  | note | – – – – – – – – – – – – – – – – –
label | 36dde0e8-bd37-5702-a08e-2bf08e780db6 |  | note | VERIFYING DOCUMENTS: This ITP
date | ed785a37-1a61-582c-ae57-499e9d919527 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | 3c66a637-ca6f-543a-a453-24b42b936dab |  | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
label | cfdd8ec1-9e78-5934-bd01-b7fc523deedc |  | note | – – – – – – – – – – – – – – – – –
label | 6b05e89f-3128-5510-9253-ba9549c42dd9 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 2b6e3228-f8f0-5655-aa94-7dcf5eed2ee2 |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | b669fc09-2c20-5ac4-939d-5c9567a0313a |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | b841d884-b01e-582a-8f3a-9b00fb932f4f |  | note | Attach: Compressive Strength Test Results
label | 2b656301-89ad-588c-bd83-73d84a470bab |  | note | – – – – – – – – – – – – – – – – –
label | 77a0df4e-db05-516e-9377-552a8f27edc3 |  | note | METHOD: Document Review
label | 04d36855-d182-50a2-8a6b-f001d1572aaf |  | note | – – – – – – – – – – – – – – – – –
label | 2cee84a3-111c-5b87-af20-ba49b55ac74f |  | note | FREQUENCY: Each cylinder
label | a6c00103-0b69-58ff-bc83-0f58dcd16c81 |  | note | – – – – – – – – – – – – – – – – –
label | cb1b40cf-91d6-5ccf-86af-29e5e10a5467 |  | note | CATEGORY: IP
label | 7a997df6-d7b2-5bbc-a589-186f34beecce |  | note | – – – – – – – – – – – – – – – – –
label | 4d0ed923-be47-597c-b6e9-6e68d03b931f |  | note | RESPONSIBILITY: SE/PE/SPE
label | d4ed377a-3062-5543-8c3c-84ba4a8b8da9 |  | note | – – – – – – – – – – – – – – – – –
label | 812c2898-e0be-59c9-99fb-92a36a29b137 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2415e92a-3d29-5d1c-b810-43baa6eb09a5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | a9d01638-da74-516a-bfab-6a9053f78b7b |  | note | REFERENCE: IFC Drawings 610.47 Table 610.472
label | 51c56989-d65c-5519-a79d-9722766ed9e0 |  | note | – – – – – – – – – – – – – – – – –
label | 0b28a700-5c7e-5034-a7af-9e15ad8eec62 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | 6311e58c-0068-57b2-a4c5-64646f90d3df |  | note | Attach: Survey As-builts / Survey Report
label | 812e1e18-74b0-56a4-9ef0-165b329b0256 |  | note | – – – – – – – – – – – – – – – – –
label | f8cd379f-cec7-56c6-9343-96a6ef7629c1 |  | note | METHOD: Document Review
label | 82cbd0e6-2920-5997-908d-99e6d7d15d08 |  | note | – – – – – – – – – – – – – – – – –
label | 933f0525-cd73-530a-9e7c-c6aa4c9c440f |  | note | FREQUENCY: Each element
label | 41d9f47b-8a46-56ce-b8ad-532797720a86 |  | note | – – – – – – – – – – – – – – – – –
label | a5673ee7-7c55-5b04-8b92-e2c77b7b9d18 |  | note | CATEGORY: IP
label | caf3f08b-d3ee-55a5-8ba6-e1fc40168c7b |  | note | – – – – – – – – – – – – – – – – –
label | 378c2d07-994d-5fa1-9b0c-cb709734f58e |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e970f705-c0ab-510d-bea0-0b7226c9298c |  | note | – – – – – – – – – – – – – – – – –
label | 85269567-1539-5656-880c-09fd1453f10b |  | note | VERIFYING DOCUMENTS: This ITP
date | a5cd4ab5-c59f-5bb7-bdb3-b74f222024a6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | 35a9acee-e673-56d2-8df7-d493524fa737 |  | note | REFERENCE: MRPA Quality Management Plan
label | 12968ef5-2816-5e03-bd7b-1e07b8504f92 |  | note | – – – – – – – – – – – – – – – – –
label | 718c1863-8a68-5190-bb1f-3a89c78ebbde |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | f1cc183c-81bd-5643-a475-16263aa8c73a |  | note | – – – – – – – – – – – – – – – – –
label | 3e8b4abf-aafd-5519-ade8-f5f6131dffdc |  | note | METHOD: Document Review
label | 6d17ed25-0025-5fa3-b25d-4f48258f60ec |  | note | – – – – – – – – – – – – – – – – –
label | 7b7dcb5a-8b3f-5fa9-9b8e-e75c97271ee4 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0b795d04-e987-5f91-9eb5-d7f3af4a4620 |  | note | – – – – – – – – – – – – – – – – –
label | cc8f2fe3-05b1-5b3f-99a8-dfb4ed5853a6 |  | note | CATEGORY: HP*
label | e6545563-4107-5c98-be0a-90e76be47800 |  | note | – – – – – – – – – – – – – – – – –
label | 415d0751-6218-58ef-821c-557889d6a088 |  | note | RESPONSIBILITY: HP*
label | 2beab900-e426-5aee-9e0c-d4b8fad9b798 |  | note | – – – – – – – – – – – – – – – – –
label | 3ffd7575-aaa5-5779-a800-348675b5d246 |  | note | VERIFYING DOCUMENTS: This ITP
date | 99f38a1e-54c3-58b2-8138-fc46479a907c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6e236b4e-1376-5d8a-9690-826ed856261e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a98216f1-1908-53f8-a5f7-da87f4cdf822 |  | textbox | Name:
text | 6c446545-d914-5a4f-9d09-a0269d911ef7 |  | textbox | Position:
date | 6622ee09-73fa-5930-9007-53767782cdd0 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-089-STR-SSB-Precast Driven Pile Installation | itp |  |  |  | Yes | ITP-089-STR-SSB-Precast Driven Pile Installation Rev 0 | 682b3e93-b886-4b68-9da0-d8c2de32b70b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 0c2b3e02-7cbe-5b14-a108-a38aa5c867a3 |  | note | Document Title: ITP-065-CIV-Camms-Landscaping-Ground Preparation
label | d3251015-c2a1-5698-8d12-a52a5b4b3c49 |  | note | ITP Description: Landscaping - Ground Preparation (Subcontractor)
label | 932b4185-c915-5271-ace3-6a6abfd3d7f0 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | b3a0db35-c807-5343-b5db-95e33830c97e |  | note | Revision Number: 0
label | 07440d0b-92d1-5fda-9c48-94cdf361010b |  | note | ITP created by: Victor Mira
label | 7738fa20-f9c6-5ff7-b387-a27471ab8477 |  | note | ITP approved for use by: Victor Mira
label | 3c4715ae-7ff0-5b7d-99aa-475be42ad983 |  | note | 1.1 Non Dependent
label | 6f13767b-3842-5bd2-a666-d9ef70b22dc3 |  | note | Reference: AS 2159-2019
label | 28cdc70b-8658-5ac2-9599-df8db7be83e2 |  | note | 1.2 Non Dependent
label | 3167bcbe-e39c-563f-96fd-3cea2449e6b5 |  | note | Reference: Vicroads Section 605 June 2018
label | a1a3c698-4d55-5452-810f-c3b62049cfdb |  | note | 1.3 Non Dependent
label | 70403535-9983-5c43-8434-7054ac0cf7a7 |  | note | Reference: VicRoads BTN 023
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Precast element
label | 09ab5e77-afab-506b-aab1-398908605461 |  | note | REFERENCE: IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (March/June 2019)
label | 505fcc85-abe3-520d-a5bf-15aaf0f16e93 |  | note | – – – – – – – – – – – – – – – – –
label | 890e68a6-8cdc-5105-9d54-6cc69f55c82b |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the Quality Assurance documentation for each element, typically this consists of:
label | 4f10705a-88ea-5efb-b14d-fd21e5041435 |  | note | i. Certificate of Compliance / Birth Certificate
label | 8cf1524e-000e-51bf-b3a7-15ce93643097 |  | note | ii. Compressive strength test results
label | c019d744-283f-5b93-b4c0-605877f3084a |  | note | iii. Precast Lifting Design
label | 0361dfe1-a9cd-5eeb-910b-5edd0f321bd0 |  | note | iv. Pre-pour check sheet / ITP
label | f9ef298a-2612-50d3-8244-d4919e2ab36b |  | note | v. Post-pour check sheet / ITP
label | d5e6543e-8f09-5f1f-9c90-ee289d3d8e45 |  | note | vi. Covermeter check record
label | 265fb25e-70c9-5e5d-8942-8742f9af3c43 |  | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast as per VR 610
label | 84534942-49ed-58d2-8c8e-a04555116ff7 |  | note | Minimum age before driving:
label | 9424bb9f-b7b3-5a3b-a25b-eb7ed47f7daa |  | note | ○ Steam cured 7 days after the date of casting
label | 6406287a-97aa-54cc-9a0b-e6458c7764d4 |  | note | ○ Moist cured 14 days after the date of casting
label | 0d155a25-f92a-57d7-b607-8145be5cf439 |  | note | ○ provided that in all cases the specified concrete strength has been achieved.
label | 67ea357e-1034-52e2-a073-e0cfd8eef7d2 |  | note | ATTACH BIRTH CERTIFICATE
label | bc948092-dbf7-5f32-ba10-30c8e46caf29 |  | note | – – – – – – – – – – – – – – – – –
label | 0e568f6b-cca5-5955-bbdf-b2e8b0983702 |  | note | METHOD: Document Review
label | 9549056e-a489-50ca-acb6-ddecbfaed3b9 |  | note | – – – – – – – – – – – – – – – – –
label | a3df08c0-77b1-577d-b2db-2bb6001d8eec |  | note | FREQUENCY: Each element
label | b91a5765-bff3-5d63-b9e7-d143c10f9667 |  | note | – – – – – – – – – – – – – – – – –
label | 4a980461-3db2-56fe-a544-e2a761444d8d |  | note | CATEGORY: HP
label | 9a7d472d-88cd-586f-98ce-4d7e8647be08 |  | note | – – – – – – – – – – – – – – – – –
label | f15cf415-dac7-5ed8-b51d-d23f7687a30d |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 01661989-3576-5e6d-b678-1c61f75ddf66 |  | note | – – – – – – – – – – – – – – – – –
label | 46cc7c72-0bab-5dde-96fc-6b31f787af78 |  | note | VERIFYING DOCUMENTS: This ITP, Birth Certificate
date | 20cf5673-d654-5f05-86cf-604c6cf5257f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Precast piles
label | 9d6d8f2c-6f14-583e-a9a0-6887bd2381a3 |  | note | REFERENCE: VR 605.01
label | 2057ca60-ebc0-50f4-ae77-2fb0f7008bf0 |  | note | – – – – – – – – – – – – – – – – –
label | d3aa1072-a3f6-5a78-bd0a-c2ef24caff4f |  | note | ACCEPTANCE CRITERIA: Care must be taken to ensure that piles are not damaged during transport, handling and driving.
label | 215f0a9f-5755-52b6-b91a-60f7982dba81 |  | note | ○ Piles shall be inspected for their length and cross section prior installtion.
label | d1039ea5-2e2d-5d55-8894-a92d9fb44abd |  | note | ○ Piles shall be inspected for any defects.
label | 51368c07-52c5-5e7d-8cf5-a8e33e090eaf |  | note | – – – – – – – – – – – – – – – – –
label | 9551e091-050d-524f-a584-87d22c4bb5af |  | note | METHOD: Visual
label | 84590600-8e1c-54ec-93f6-3fe3493cc7e6 |  | note | – – – – – – – – – – – – – – – – –
label | 91f05441-3f3f-50f3-a73d-51eaad41b9df |  | note | FREQUENCY: Each pile
label | 9c61030a-34c1-5c94-a3ad-0570af6bcc87 |  | note | – – – – – – – – – – – – – – – – –
label | af428225-771d-5682-a90d-67b9fccb7b2b |  | note | CATEGORY: HP*
label | e91ad308-6478-5b1d-b1fe-62ceab3dcd6b |  | note | – – – – – – – – – – – – – – – – –
label | 1c85a97f-c8a4-5e75-9f2f-3ddbe807884a |  | note | RESPONSIBILITY: SE/PE
label | 8e958899-5442-5cf4-862d-93fe4ba485e6 |  | note | – – – – – – – – – – – – – – – – –
label | 126dbb1d-1045-53bf-b942-a77e8dbfa959 |  | note | VERIFYING DOCUMENTS: This ITP
date | 46f1212e-6cf9-5a36-a9ac-b3b0776e7740 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Driving System
label | 5206ee4e-7fd6-540e-b3f4-c713a1cd219b |  | note | REFERENCE: VR 605.02
label | 37cc1932-3b0d-5bfa-a736-a0534ba1a437 |  | note | – – – – – – – – – – – – – – – – –
label | b806e463-1d20-5b68-820d-7f583f190702 |  | note | ACCEPTANCE CRITERIA: If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m.
label | 3014f124-821c-55e0-9e96-04d157850703 |  | note | ○ The Contractor shall provide details of the driving system including the make, model and rated energy of the hammer, the mass of the helmet, and the proposed cap-block and cushion materials.
label | 5e4c9f0a-49a2-53b2-a2fb-95f961b4ac8d |  | note | ○ These details, including calculations which demonstrate that the proposed driving system has sufficient energy to achieve the specified pile test load, shall be submitted to the Superintendent for review not less than 14 days prior to the commencement of pile driving.
label | ca1d5497-6ce9-542b-8da4-ee3777423503 |  | note | ○ If a drop-hammer is used, the height of fall of the hammer shall not exceed 2 m.
text | d1de81d8-24cf-5d53-92a7-b0f5fcca5845 |  | textbox | Enter: Teambinder Approval number
label | 10b9d996-d6cf-502c-8d1e-9bcf4fef912e |  | note | – – – – – – – – – – – – – – – – –
label | fe914f00-05a2-51d6-94aa-66755244ef1c |  | note | METHOD: Document review
label | 61c4b6cc-570c-559e-a030-194d0e2a578b |  | note | – – – – – – – – – – – – – – – – –
label | 532d8344-e2c6-57e1-a181-3fa6b87c1e2d |  | note | FREQUENCY: Prior driving
label | 656b7631-e58f-5659-bd05-3ac1f68ea623 |  | note | – – – – – – – – – – – – – – – – –
label | c6aa5f21-c574-5335-8c42-51e1515a5323 |  | note | CATEGORY: HP
label | 1a4d97f0-1512-57a8-93e5-b16bc13df2d8 |  | note | – – – – – – – – – – – – – – – – –
label | 765cdb6e-d1f3-5bf2-a01a-03979f9e9527 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | c6a0b5e5-20c4-50da-9229-93944eaac8d8 |  | note | – – – – – – – – – – – – – – – – –
label | 232cac7a-e3f1-5fe6-a1cc-5c95a82769d9 |  | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | da21c924-4203-5dfd-bca8-4b9a55252567 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Monitoring
label | c9b1889f-718e-5b54-82b1-97f9420afba5 |  | note | REFERENCE: 605.04
label | ba8decb3-821a-5116-b7ef-25dec41a4ddb |  | note | – – – – – – – – – – – – – – – – –
label | f68db9b8-13a8-5ce9-82b1-4367bb6f27fb |  | note | ACCEPTANCE CRITERIA: Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile. Where set measurements cannot be undertaken due to OH&S issues, the Contractor shall provide alternative methods to the Superintendent for review at least 7 days prior to pile driving.
text | d69cada0-3f51-5405-b649-2ddc7969405d |  | textbox | Enter: Teambinder Approval number: [free text box]
label | c00fc7cb-8f4b-5e8e-a646-ec3f6611a906 |  | note | – – – – – – – – – – – – – – – – –
label | ee127315-de8a-524a-8b01-2ee00a04609b |  | note | METHOD: Document review
label | 1eb68c12-d17d-5c6d-a1c8-1c9478df7df5 |  | note | – – – – – – – – – – – – – – – – –
label | 435cff8c-7059-5eda-acb9-ca34d6cc3b7c |  | note | CATEGORY: HP
label | 05ad8426-5994-57a3-b562-ec1cee113e75 |  | note | – – – – – – – – – – – – – – – – –
label | f140d849-66ba-5d0d-8b27-213cabc2f4b1 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | f6c6eb91-e49f-5bd3-92c3-a7207b29cc41 |  | note | – – – – – – – – – – – – – – – – –
label | 97e20d71-5c5f-5272-8cd6-d3303af333b5 |  | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | 1c5d04fd-5ab6-5700-ae01-1c12902147b8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Pile testing-Prequalified consultant
label | c453e7d4-cb91-5da4-a5f7-03ec6e4e698b |  | note | REFERENCE: 605.07 (b)
label | f91e85ab-66b7-59a1-a79a-5c89153ae478 |  | note | – – – – – – – – – – – – – – – – –
label | f79cbaee-7b40-507d-855b-7e3dec48fb75 |  | note | ACCEPTANCE CRITERIA: All high strain dynamic testing shall be undertaken by a prequalified consultant and approved by the Superintendent. The consultant shall be independent of the piling contractor and advised to the Superintendent at least 2 weeks prior to testing.
label | 4ccf53d6-6fd1-5c4c-a4c8-8003489522b9 |  | note | ○ The test procedure and test reports shall conform to the requirements of AS 2159.
text | 78c677fb-841a-5629-b4f8-79472604c754 |  | textbox | Enter: Teambinder Approval number: [free text box]
label | 6fdfab24-c857-5977-9de3-9b68a20fac48 |  | note | – – – – – – – – – – – – – – – – –
label | 32a632d9-380f-51ac-bec8-84482924be23 |  | note | METHOD: Document review
label | f96e6e15-8deb-5627-bee3-d84468bde504 |  | note | – – – – – – – – – – – – – – – – –
label | f0f41752-c09a-55b7-b027-a90e8e1372b3 |  | note | FREQUENCY: Each test
label | b3dec4c0-1ab6-56c8-a47d-c8a87ea7916a |  | note | – – – – – – – – – – – – – – – – –
label | ca41fea6-e272-5e87-948b-14bc47d46a82 |  | note | CATEGORY: HP
label | d735164a-ba41-567c-bec3-925be280e382 |  | note | – – – – – – – – – – – – – – – – –
label | 50fd5404-6b3e-5f83-821f-1efc0f38e4d1 |  | note | RESPONSIBILITY: PE/Nominated Authority
label | e80b1635-cae9-5a7f-a5f0-2078b57e1872 |  | note | – – – – – – – – – – – – – – – – –
label | f0322555-3efa-5625-863a-1a9e34295f99 |  | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | 3484f509-64db-586d-baa7-988566899c09 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Pile-Approval for using HILEY Formula
label | 5812bb45-569e-50a6-8b5d-15993c22b155 |  | note | REFERENCE: 605.04, 605.05 (a) BTN 023
label | 8952e1f1-413e-5b36-97c4-169b1cb3279a |  | note | – – – – – – – – – – – – – – – – –
label | a6158753-2950-5ef7-b7a2-1d22d996e595 |  | note | ACCEPTANCE CRITERIA: Pile testing using the Hiley Formula may only be used for bridges of low significance and where high strain dynamic pile testing is not practical. Advice should be sought from Technical Consulting Geotechnical Services if pile testing using the Hiley Formula is to be adopted.
label | 08c6505b-40ea-5f44-b124-74a1f5041a77 |  | note | ○ The dispensation conditions for Pile Driving Analyser (PDA) for predominantly laterally loaded piles may be applied to embedded retaining walls or other structures, subject to compliance with the criteria listed in Table 1 of BTN 023. Where any of the conditions cannot be fulfilled, relevant structural and geotechnical reports must be provided to the DTP Chief Engineer – Roads for review and approval.
text | b1d4bb53-f250-5442-8722-2fe7f4d174c8 |  | textbox | Enter: Teambinder Approval number: [free text box]
label | c27cf50b-7397-51ac-a49c-f7974354b195 |  | note | – – – – – – – – – – – – – – – – –
label | f1f8e3b4-aa02-5b41-9664-ce5779c37cf1 |  | note | METHOD: Document review
label | c031e6bd-0a03-5ac9-8be0-c69e909304ce |  | note | – – – – – – – – – – – – – – – – –
label | 4c5f2b3f-d8b5-5b97-8272-9facc43936ae |  | note | FREQUENCY: When Applicable
label | 10458fd3-a1a4-535f-92b2-8e75a1203c63 |  | note | – – – – – – – – – – – – – – – – –
label | 1b0575a8-a0f5-54bc-8c80-050baae506a4 |  | note | CATEGORY: HP
label | 9cbad073-1f28-56dd-b8d7-3b8333de65f0 |  | note | – – – – – – – – – – – – – – – – –
label | 5ece008f-58c9-53f8-8d99-3580f3e6deba |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 3409a7fa-241a-599b-878f-70e86fb0b79b |  | note | – – – – – – – – – – – – – – – – –
label | 54de208c-1231-53c5-b7d4-679b722153d9 |  | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | 7200c0a2-5ee7-5c55-9375-9909d3154554 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 3c6d90ea-0f7e-5950-b5bb-bacd9dc23c4b |  | note | REFERENCE: MRPA Quality Management Plan
label | 8d59f9c9-f77c-5baf-a4c2-9fca3c7cf07e |  | note | – – – – – – – – – – – – – – – – –
label | 833b52a8-5d35-5fb8-a077-f42932aa08c6 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 4c983e5b-ad46-5cf2-be08-986f239cb8e8 |  | note | – – – – – – – – – – – – – – – – –
label | 7eb613e0-a02e-57be-a0cb-48bf830d497e |  | note | METHOD: Document Review
label | be1b2329-2699-5bb9-bf28-daa334552778 |  | note | – – – – – – – – – – – – – – – – –
label | a54751e4-3978-5122-97f8-854776ab812f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 08c08988-ea12-50c9-8e66-6ebcb28e3bd3 |  | note | – – – – – – – – – – – – – – – – –
label | d53fcd58-a022-5e9e-9b7b-f6a05273829e |  | note | CATEGORY: HP*
label | c1403943-422f-56fc-a935-fd45b39928cd |  | note | – – – – – – – – – – – – – – – – –
label | 1d47f1a8-881f-57cc-91fa-134063be2518 |  | note | RESPONSIBILITY: SE/PE
label | e50a504c-7df4-554a-85aa-51cc64eb6849 |  | note | – – – – – – – – – – – – – – – – –
label | 12183888-60b9-5f12-95d4-efa41e1e46ab |  | note | VERIFYING DOCUMENTS: This ITP
date | 1ba4f86a-c0c2-5952-abd9-f11b136abce8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pile-Ultimate Capacity- Wave Equation-First pile in the group
label | 18ca8b1d-9efd-5bff-b97b-2f1564065e8d |  | note | REFERENCE: 605.05 (b)
label | 8df7941d-63fb-5031-981b-9a48a7fe66fc |  | note | – – – – – – – – – – – – – – – – –
label | 67900ff3-a583-5cb6-b309-4b14f0cbc687 |  | note | ACCEPTANCE CRITERIA: The initial pile in each pile group shall be monitored with Dynamic Testing Equipment DURING DRIVING.
label | 39b63eed-9ada-5ab2-a142-8f75c62369d1 |  | note | ○ The records shall be subjected to closed form dynamic solution and wave equation analysis.
label | b41f149c-2246-587e-868c-cdcd3602ce18 |  | note | ○ Pile stresses during driving shall not exceed 0.8x fc) compression and 1.1x SQR(fc) tension for concrete piles, where fc is the concrete strength.
label | a07df8d4-1793-5207-900e-5d3e86ac8217 |  | note | ○ The measured stresses in the pile induced during pile driving and ultimate pile capacity calculations shall be submitted to the Superintendent for eview prior to driving further piles.
text | 674c6934-eab8-539f-a1ba-5dfac4e33aa7 |  | textbox | Initial pile in the group:
label | ef2d63c3-3c3b-5058-b5b5-e74303fc9b5c |  | note | – – – – – – – – – – – – – – – – –
label | 5090cced-fac1-59a8-bcb9-86594509c844 |  | note | METHOD: Document Review
label | e1844051-844c-5dc6-83aa-95304517e832 |  | note | – – – – – – – – – – – – – – – – –
label | 3a385656-fe0f-57cb-873b-2eee0246e028 |  | note | FREQUENCY: One for Each Pile Group (First pile in each group)
label | 6769badc-9713-5e40-80a7-03bcdbade0cc |  | note | – – – – – – – – – – – – – – – – –
label | 315f747f-e5c8-5bd5-a378-76987c740432 |  | note | CATEGORY: HP
label | 31d4042e-0493-5ef7-8491-598dc5e99b43 |  | note | – – – – – – – – – – – – – – – – –
label | eb4ce9e5-371a-5f2f-b3e4-366ab007386c |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 009ab34a-ddf8-5b7f-9bf3-6a05f2914ef4 |  | note | – – – – – – – – – – – – – – – – –
label | aab002a7-8c3c-5a75-942d-415fb536474b |  | note | VERIFYING DOCUMENTS: This ITP, ConQA Hold Point Release
date | a87ccc67-e7d0-5949-87c1-1c03c4201851 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Survey Set out
label | 340650ee-aeb0-5b61-9c9b-c530bcedfbc5 |  | note | REFERENCE: VR 605.04 (c)
label | 63ec29e5-c672-5bf8-adb4-d29565fe2edb |  | note | – – – – – – – – – – – – – – – – –
label | e0c37af4-3eea-5bf8-b261-da96355aaa50 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements within the tolerances:
label | 660319cf-259d-56e7-8003-6843e9b26c70 |  | note | ○ pile head centre, ± 50 mm of the specified position.
label | e0a673fe-6e62-50eb-b30e-2fb24b7cdafb |  | note | – – – – – – – – – – – – – – – – –
label | e03567fb-7f22-57b2-80fe-be917bc74bcd |  | note | METHOD: Survey
label | 90a02cd0-fcd5-5817-87a9-d74afa41741f |  | note | – – – – – – – – – – – – – – – – –
label | d4346beb-68d0-59dd-86ca-f55200714816 |  | note | FREQUENCY: Each pile prior driving
label | 095dd307-2932-5724-9dfc-4e4ebbf8d956 |  | note | – – – – – – – – – – – – – – – – –
label | ef665d67-7e1d-56f6-835a-8d548090ae13 |  | note | CATEGORY: IP
label | 8015ed48-bd30-5360-8b2b-12728f779082 |  | note | – – – – – – – – – – – – – – – – –
label | 8d961cb4-82c7-5b2e-bcc5-3d3b4d060269 |  | note | RESPONSIBILITY: SE/Surveyor
label | f0be51d0-e6da-5613-94f5-e288b2add67d |  | note | – – – – – – – – – – – – – – – – –
label | ff98e03b-1cf6-53f4-a07c-252c8e627709 |  | note | VERIFYING DOCUMENTS: This ITP
date | f5905de7-52f7-5407-91ee-1406de820462 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Driving-Pile protection
label | ec2a0a03-f058-5b81-bf46-196e730f0dcb |  | note | REFERENCE: 605.04
label | cbfa00f6-021f-5aba-8b3c-6356a182644a |  | note | – – – – – – – – – – – – – – – – –
label | 818f8b22-f341-5b8c-b690-69786d3b9266 |  | note | ACCEPTANCE CRITERIA: During driving, the tops of the piles shall be held and guided by a suitable helmet and protected by a cushioning material, to avoid damage to the pile.
label | 506a1440-d964-5508-86cc-41aa2d88c000 |  | note | ○ Piles shall be guided into the specified position and shall not be bent or sprung into place during or after driving.
label | 34dd9cf6-b0bc-5567-ba76-2f2146852464 |  | note | – – – – – – – – – – – – – – – – –
label | a5a706ec-4d8e-5577-95ab-8e4773b29808 |  | note | METHOD: Visual
label | 79b21d80-4f41-5a27-a8ea-a18a02f47961 |  | note | – – – – – – – – – – – – – – – – –
label | d4916286-22ed-5ae5-82c5-28e8dd92ed35 |  | note | FREQUENCY: Each element
label | 61f891de-7030-57e3-8688-6fda7cadb025 |  | note | – – – – – – – – – – – – – – – – –
label | 6185e5bd-7e33-5617-8bca-662594f56e86 |  | note | CATEGORY: IP
label | 9784b812-4e3c-5043-8bc2-a3ee6e86df16 |  | note | – – – – – – – – – – – – – – – – –
label | ee81bd6e-6e5f-5255-808e-d9c4d0f73ac5 |  | note | RESPONSIBILITY: SE
label | 6585705c-9080-5a1d-9f91-b8612039ed0a |  | note | – – – – – – – – – – – – – – – – –
label | b6d9aea9-d5f7-5eb0-ac51-00b844c3983b |  | note | VERIFYING DOCUMENTS: This ITP
date | 96b1dcd5-0e01-5561-a554-217466028609 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pile alignment and Straightness
label | f62f6a3a-064d-5953-997b-27596797f0cd |  | note | REFERENCE: 605.04
label | a5944d4e-df04-5f4c-90c4-4345a653fe2b |  | note | – – – – – – – – – – – – – – – – –
label | d393395c-9daf-5540-9997-a1f6824bbaba |  | note | ACCEPTANCE CRITERIA: The Contractor shall ensure that piles achieve the specified accuracy of level and position. The following tolerances shall apply to piles after driving:
label | 0eef5acd-be1f-5396-b3f0-24ff2970a14a |  | note | ○ pile alignment: deviation from the vertical or the specified rake shall not exceed 20 mm per metre length of pile
label | 0890b579-0c87-5c11-b287-18bca821ea21 |  | note | ○ pile straightness: deviation from vertical shall not exceed 5 mm per metre length of pile
label | 8e9b0e33-0c5f-5365-85a1-608cfbc73208 |  | note | – – – – – – – – – – – – – – – – –
label | f89fcf3e-1a78-5b6d-a2e7-fc7a4d0e56d3 |  | note | METHOD: Visual, Measure
label | 1e5a660b-fbae-5d31-a206-7ce0bb34dbe7 |  | note | – – – – – – – – – – – – – – – – –
label | 2bf87edf-b023-5dc3-b78d-9fa8ee556ba6 |  | note | FREQUENCY: Each element
label | da8c138c-c0e6-560e-9ada-ae54c9c4491e |  | note | – – – – – – – – – – – – – – – – –
label | 273c8f84-cad2-5dd4-b10e-3eced69bbd62 |  | note | CATEGORY: IP
label | 419e268c-c2ed-5440-b600-587c31a8ae06 |  | note | – – – – – – – – – – – – – – – – –
label | fa924227-755a-52c1-84fa-7d45acb07850 |  | note | RESPONSIBILITY: SE
label | 53c0e7cf-8ed5-5a45-b5fb-d827099d8f88 |  | note | – – – – – – – – – – – – – – – – –
label | 997534cf-52d5-58e9-94d0-d610ddd22535 |  | note | VERIFYING DOCUMENTS: This ITP
date | 65c44005-cd59-5aac-a84e-15c501d16597 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pile driving-Monitoring
label | 99a78319-a4df-59fb-976a-404f205aa740 |  | note | REFERENCE: 605.04
label | 5733b7b1-01be-5a93-9ffc-089dd2fc9951 |  | note | – – – – – – – – – – – – – – – – –
label | 94ca554d-1289-5f86-a7ec-62e474c11f03 |  | note | ACCEPTANCE CRITERIA: Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile.
label | 6b9b0266-9932-52f5-99ad-36d3f1e67050 |  | note | – – – – – – – – – – – – – – – – –
label | 2d456c58-daaa-52de-b604-1adbb0bcb0d2 |  | note | METHOD: Visual
label | edc958d0-ccd3-5e47-8654-68846bdc637e |  | note | – – – – – – – – – – – – – – – – –
label | 0c326300-1dea-5a40-85e5-a9645a1601c4 |  | note | FREQUENCY: Each element
label | e1d25a8a-0af1-5c02-b96d-72d52f97f1c4 |  | note | – – – – – – – – – – – – – – – – –
label | 2f0fd7a8-2469-5ee9-ab59-54b021a2e1ff |  | note | CATEGORY: IP
label | 0b0cc8e4-c42d-598d-aaa8-cd42ac39eb3b |  | note | – – – – – – – – – – – – – – – – –
label | 40a99e89-9705-50e1-9d72-f28c239b2acf |  | note | RESPONSIBILITY: SE
label | ee8d41aa-15ce-5f55-9883-2a212315ff9a |  | note | – – – – – – – – – – – – – – – – –
label | b612c1fc-380b-5832-b502-02a5517b72e8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 1515e8c4-20b9-5c26-a81c-1b1769301e58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pile Driving operation
label | 701557cd-64cd-54a4-aa94-0a3c8ddc1104 |  | note | REFERENCE: 605.04
label | 03930afb-cb43-56e3-a5dc-cddcdb174d90 |  | note | – – – – – – – – – – – – – – – – –
label | 51e6c808-79ba-51ed-886c-a7e32b187034 |  | note | ACCEPTANCE CRITERIA: Each pile shall be driven in a continuous operation and not left partly driven.
label | 0aaac1a3-7bd1-54e8-848d-aa68cf441f60 |  | note | – – – – – – – – – – – – – – – – –
label | 78f13e20-6b9b-59d1-807e-8a1aa1e07676 |  | note | METHOD: Visual
label | 48bf8014-dcd6-53c9-8f86-30004bed6f77 |  | note | – – – – – – – – – – – – – – – – –
label | 5d0d3c0f-25d2-5bf7-8b18-782978d523ff |  | note | FREQUENCY: Each element
label | f8786ee1-5fa2-51c0-a843-ff6bef38d5c8 |  | note | – – – – – – – – – – – – – – – – –
label | 74dae29e-cfe7-5696-932c-94913bb2b401 |  | note | CATEGORY: IP
label | 5702b6a6-fa18-5fea-b289-1b5e4a73cb40 |  | note | – – – – – – – – – – – – – – – – –
label | aa156107-3722-5e0b-80f1-c1c11d42c0ae |  | note | RESPONSIBILITY: SE
label | 8dc1f5c7-1a8b-56d7-a5d3-91a16a8c83f2 |  | note | – – – – – – – – – – – – – – – – –
label | 4b99bbe9-e668-5a74-a490-8de090132ea8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 56df590f-ed30-5984-8823-2b7b26af2791 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pile Extension
label | 6bcdf356-a2cd-5346-ad30-4d1f762d0533 |  | note | REFERENCE: 605.10 (c) BTN 023 - 3.2.7 605.04
label | 62870004-971c-5940-8d7e-37403dd55344 |  | note | – – – – – – – – – – – – – – – – –
label | 764f93b4-6715-5525-a20b-761db3e124d2 |  | note | ACCEPTANCE CRITERIA: precast extensions may be used provided that
label | e5bcb404-d17b-52e1-ab7c-317298857fa5 |  | note | ○ the mechanical joints must comply with the requirements of AS 5100.3 clause 6.4 and BTN 023
label | 48f3c347-4fdd-53c4-b8d6-c28a52fad5f5 |  | note | ○ design of mechanical joints must comply with the durability requirements of AS 5100.3 Section 4
label | e3e0239a-9476-58bd-bfa1-f886166a58f0 |  | note | ○ the precast extension must have a minimum length of 5 metres
label | 8259d19b-1465-5ddc-93c6-79088ad4d49d |  | note | ○ the joint location is determined by the structural design engineer.
label | 56a13d6e-2245-5202-950c-6a81d03c0ddf |  | note | ○ Mechanical joints must not be located within 5 m of the underside of a pile-cap or in aggressive groundwater
label | b7cf47e2-8903-54d9-bdbc-b7bb39316bff |  | note | Driving shall re‑commence as soon as the splice is completed.
label | 8d2ce9a7-6668-54e9-b5fd-db898a80906d |  | note | – – – – – – – – – – – – – – – – –
label | 29bedf3c-bc37-5205-bed7-1152f4e1442c |  | note | METHOD: Visual, Measure
label | 682f203e-870a-58d4-a349-177e325be88f |  | note | – – – – – – – – – – – – – – – – –
label | bc3e6f80-aca6-5aa3-b8bc-e48805c1109a |  | note | FREQUENCY: When Applicable
label | 718e45ee-c114-55ea-995b-1b48504af066 |  | note | – – – – – – – – – – – – – – – – –
label | c42a1981-bf4e-568f-8cab-c1a74a903529 |  | note | CATEGORY: IP
label | 18a1f2a1-1308-5ade-8b3e-b638ec57412c |  | note | – – – – – – – – – – – – – – – – –
label | da7b1239-aaa0-59e9-b4c2-ee0b1fda0711 |  | note | RESPONSIBILITY: SE
label | b0d129af-04d2-5417-9056-363c42232775 |  | note | – – – – – – – – – – – – – – – – –
label | 029b866e-bb11-5cd0-817e-82181c491b31 |  | note | VERIFYING DOCUMENTS: This ITP
date | 8c713a69-564a-560e-90ec-77732b77daee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pile-Ultimate Capacity- HILEY Formula
label | cc5296fd-1b82-58f4-9f71-4f920ff8fede |  | note | REFERENCE: 605.05 (a)
label | 9fed1744-5ad3-5dd4-9b24-a7a545bf5daa |  | note | – – – – – – – – – – – – – – – – –
label | 56800022-0a36-553a-a8a3-99023145eccc |  | note | ACCEPTANCE CRITERIA: Piles shall achieve the specified ultimate load capacity.
label | 77e4887c-cfb7-5816-afd4-6c68772dadbe |  | note | If using Hiley Formula is permitted:
label | 469d011e-01ad-53f8-8f73-f5a04d1f7ad4 |  | note | ○ The values of the coefficients EF, E and C1, which are dependent upon the type of equipment used and the rake of the piles, shall be nominated by the Contractor and reviewed by the Superintendent.
label | d5064d3a-42de-5922-ade7-34ae2705bb76 |  | note | If using Hiley Formula is permitted:
label | 33521173-f005-5b6f-9636-01cd06db2d3a |  | note | ○ Coefficients C2 and C3 shall be measured by the Contractor for each pile during driving simultaneously with the measurement of set per blow.
label | bda8052c-3905-5cd9-a057-1df728174f78 |  | note | Contractor ITP to be attached:
label | ca302d23-4bf3-5b77-a816-cf9901bef2db |  | note | – – – – – – – – – – – – – – – – –
label | 1c359097-585d-5665-88f2-4252fcd0a5d1 |  | note | METHOD: Document review
label | 51467be7-d0a6-5085-84ac-d5251b07fdc2 |  | note | – – – – – – – – – – – – – – – – –
label | 2fec8a7c-e3b3-548b-9bcd-d94c39390b1c |  | note | FREQUENCY: Each pile when permitted
label | 51fdf74e-35a6-5874-af85-c6a765537d82 |  | note | – – – – – – – – – – – – – – – – –
label | 798fbbeb-7a73-5741-b4e5-06e10642cfb5 |  | note | CATEGORY: IP
label | 8476bcb2-aad7-5e6d-b592-05786e9d4caf |  | note | – – – – – – – – – – – – – – – – –
label | e612b249-b66b-5b83-a83b-ed699f2a1d9e |  | note | RESPONSIBILITY: Nominated Authority
label | dd22cb5e-7600-50b3-bdda-59c142d79c8b |  | note | – – – – – – – – – – – – – – – – –
label | 1801183f-2f9e-5aa8-8abb-6484322eb4c0 |  | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | 60f64f72-728d-510f-99d1-29bbd45226e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pile-Ultimate Capacity- Wave Equation-Other than the first pile
label | 8700e292-c1c6-57c2-b8a3-08c9b3070ee1 |  | note | REFERENCE: 605.05 (b) I, 605.07 (b) ii
label | e19013d9-00d1-5f88-84fe-b8d4044c63b4 |  | note | – – – – – – – – – – – – – – – – –
label | 4c1ba188-af6b-57ef-83a2-94b20eaf3796 |  | note | ACCEPTANCE CRITERIA: The driving criteria for each pile group shall be determined by testing the first pile driven in each group in accordance with clause 605.07(b)(i).
label | b7d94dfc-266d-57f1-b614-0eac6d31f714 |  | note | ○ All piles within that group shall be driven to a set not exceeding the driving set as determined by the PDA test on the basis of wave equation analysis.
label | 2b11bad4-63fd-502e-8139-582b36f96e59 |  | note | ○ Refer to Pile driving record
label | 015e0409-e657-5305-a835-4bb26811ff8d |  | note | – – – – – – – – – – – – – – – – –
label | efc5819d-6ac5-5d2e-b7b4-6ba11586e74f |  | note | METHOD: Document review
label | fcaeebd0-6a31-5489-98a2-a0e2c8fe0105 |  | note | – – – – – – – – – – – – – – – – –
label | 8dab6648-f631-5021-bd70-58d61446d277 |  | note | FREQUENCY: Each Pile
label | f0687879-97c4-56fd-9833-a1a3fc5a7a1f |  | note | – – – – – – – – – – – – – – – – –
label | 67b494d4-4dae-58d2-9fc5-a3f5738f31bb |  | note | CATEGORY: IP
label | c37dade3-c883-58ba-8d67-9dec5a40f37a |  | note | – – – – – – – – – – – – – – – – –
label | 424ed586-3448-52ce-a164-e01cbd6dad82 |  | note | RESPONSIBILITY: Nominated Authority
label | fe9d46af-3658-55f2-8367-aa728e8d7c53 |  | note | – – – – – – – – – – – – – – – – –
label | 45286c4e-981b-58fd-82f4-6587ff6b05e9 |  | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | bdb6ea60-1c01-5797-893d-e7f78c9e28cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pile driving records
label | 4721155c-738d-5b18-95ae-05047a699b25 |  | note | REFERENCE: 605.06 AS 2159 Clause 7.7
label | 84b5b30d-d3da-5f25-83c0-8b48682e23d9 |  | note | – – – – – – – – – – – – – – – – –
label | 155c1206-536e-5dd7-851f-2ee41d23cc5d |  | note | ACCEPTANCE CRITERIA: Pile driving records shall be in accordance with Section 7.7 – AS 2159. The following records must be retained for each pile driven:
label | e49e9de1-fb24-5126-985d-7532af7118b8 |  | note | ○ Sequence of driving in th pile group
label | 2ddb30f8-5e63-57d9-93d6-22c0f780484d |  | note | ○ length of each segment prior to driving
label | b7218dc9-ad13-5299-8be2-0df66a473c6e |  | note | ○ date of driving
label | cd22c86b-a3e6-565b-99f6-2587024a3d3a |  | note | ○ Final toe level
label | 8a7587b2-cd8c-5869-856c-c3af5a8e0f24 |  | note | ○ set measurements for the last 10 blows and temporary compression for one of the blows
label | f989dc77-2368-51a3-abd3-b2ee82a242cf |  | note | ○ calculated ultimate pile capacity
label | c68e7e67-3173-5300-86ff-70ccd48adec4 |  | note | ○ measured stresses in the pile.
label | 11d4a591-4d4f-549a-a045-c34ba9c75100 |  | note | Attach: pile driving record
label | d7496b7c-9a36-5f8a-8c20-eba19cfae6aa |  | note | – – – – – – – – – – – – – – – – –
label | f23f8234-e867-58fd-ac61-393feb6a1a4f |  | note | METHOD: Document review
label | 61460c92-72e7-5894-bb81-b3dc45cc1bb5 |  | note | – – – – – – – – – – – – – – – – –
label | 14c439b8-6cae-5def-acf1-9e2ebac92d0e |  | note | FREQUENCY: Each Pile
label | 251b0fc1-624c-5004-9161-42edd0f710f1 |  | note | – – – – – – – – – – – – – – – – –
label | c14e2805-ab34-5a07-93e3-3456f5be790d |  | note | CATEGORY: IP
label | eecb09bb-811e-5171-94ad-0e24cd073440 |  | note | – – – – – – – – – – – – – – – – –
label | da0d1b62-4a65-5ff1-8e10-bd92b0fbb440 |  | note | RESPONSIBILITY: Nominated Authority
label | cc45e053-7672-5385-9c65-b9116cbeaaee |  | note | – – – – – – – – – – – – – – – – –
label | 7b323c10-e6f9-56b7-b12f-fc3c2c34b97b |  | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | 1d7dc09f-07d4-5556-842e-bbfa9e29f8ea |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Re-Strike test
label | 906ca8be-c1e9-5e6d-893c-e9d10a5d67c3 |  | note | REFERENCE: 605.04, 605.08
label | a204395a-a11d-5bd2-a5ca-0b8b0b711926 |  | note | – – – – – – – – – – – – – – – – –
label | f125c49d-ee81-5262-9a63-c613671e9723 |  | note | ACCEPTANCE CRITERIA: If the ultimate load capacity is not achieved at the specified level, the pile shall have a restrike test undertaken in accordance with clause 605.08 – Restrike Test. If directed by the Superintendent, the pile shall be driven until the specified ultimate load capacity is achieved.
label | 0bf9af59-dddd-5962-ab17-37f56e8882b9 |  | note | ○ Restrike testing shall be conducted not less than 24 hours after initial driving.
label | fb9de572-8b86-5019-8404-f83a3fcba741 |  | note | Attach: Re-Strike record
label | 9b4b474f-209e-5321-9469-1d188417504f |  | note | – – – – – – – – – – – – – – – – –
label | aaf970ca-05d6-53d7-a4dd-87e954e8a0fa |  | note | METHOD: Document review
label | 59ae437e-10ac-5a0d-99a5-7f6a2b3ada3f |  | note | – – – – – – – – – – – – – – – – –
label | b54cb0ad-fa44-502d-9a49-c7e62ebf6656 |  | note | FREQUENCY: When Applicable
label | c48663e3-fa56-518a-bae7-18178ff0195e |  | note | – – – – – – – – – – – – – – – – –
label | ce97b5b9-cb71-5899-8f3d-7dd896034bad |  | note | CATEGORY: IP
label | 5aafecdc-9455-5c2d-9cba-bf40840d38e8 |  | note | – – – – – – – – – – – – – – – – –
label | 6117468d-b086-54a7-b036-a340946c9d39 |  | note | RESPONSIBILITY: Nominated Authority
label | e66a4fe1-3061-5d08-9170-4e489dcf24e4 |  | note | – – – – – – – – – – – – – – – – –
label | 75d407c3-6b57-5347-abee-b3c6e71c8460 |  | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | d773dfad-7894-5044-866c-2d52abd1fef4 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile testing-High Strain DynamicTesting
label | 92472aed-194c-57db-b021-20d9b03eb3f9 |  | note | REFERENCE: 605.07 (b) I AS 2159 Appendix B
label | 37e22a99-46de-53e5-91ae-12e0375bb750 |  | note | – – – – – – – – – – – – – – – – –
label | 5e789bd8-3750-5599-890f-df9cd025b5ec |  | note | ACCEPTANCE CRITERIA: High-strain dynamic pile testing shall be performed to confirm that the design pile capacity and integrity has been achieved.
label | a61c2db9-b9ea-50c6-b2d2-42e4b1398c70 |  | note | ○ The pile driving system shall have adequate energy to mobilise a test pile by a single hammer blow.
label | 2590526a-d21c-5261-9d74-6d19770a6e96 |  | note | ○ Testing shall be carried out by use of a PDA or approved equivalent and data obtained from each test shall be analysed using CAPWAP or TNOWAVE or approved equivalent.
label | a7d155a3-776a-520b-bdeb-cab8ab4ef227 |  | note | ○ The driving resistance and corresponding set per blow of the test pile shall be measured during PDA testing to extrapolate the results of the test pile to the piles in the pile group.
label | 72a1782e-a036-5b56-857e-237e88563c57 |  | note | ○ The test results are required to demonstrate meeting the acceptance criteria shown on the drawings.
label | 892c9e70-be3c-5767-8bc9-810a865e82d6 |  | note | ○ The measured ultimate capacity of the test pile shall be equal to or greater than the pile test load shown on the drawings.
label | a8b13f6e-cbe1-5d6c-b865-204f756ae793 |  | note | ○ Pile testing shall be carried out in the presence of the Superintendent.
label | 6fded778-b13f-585d-8273-cf5b9e735509 |  | note | Attach: High Strain dynamic pile test results
label | 443b60b5-6e7a-5fb1-b760-d1ca850554f7 |  | note | – – – – – – – – – – – – – – – – –
label | ff79a819-2983-57e6-8c13-427961acb766 |  | note | METHOD: Test, Document Review
label | 33db5d92-0aa3-5c68-8b56-9fe1f960df85 |  | note | – – – – – – – – – – – – – – – – –
label | 6b71ef6c-9e86-53b1-b390-37a9a97775ab |  | note | FREQUENCY: When applicable two test per group (First pile and other nominated pile)
label | a4966aa1-0ea8-5065-9b8f-e9b375b076b7 |  | note | – – – – – – – – – – – – – – – – –
label | e3ace820-0893-5046-a6fb-e686d532f65c |  | note | CATEGORY: HP
label | 72af29d8-04d5-5f36-8509-94e784004804 |  | note | – – – – – – – – – – – – – – – – –
label | ec961011-ea9f-50e5-acea-b47851e08173 |  | note | RESPONSIBILITY: Nominated Authority
label | 37325c10-2784-55a7-9bf9-88b1350ed1d3 |  | note | – – – – – – – – – – – – – – – – –
label | fde88c36-9473-5f88-a281-e45558d9f6b1 |  | note | VERIFYING DOCUMENTS: Contractor ITP/Pile driving record
date | 27d5d7c6-e6a8-5ae1-a3cb-2404ba17a022 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 Pile -Driving
label | d9ec253f-c910-57fd-bbae-ab1f89d6bf25 |  | note | REFERENCE: 605.04
label | 53201375-22a7-5eb8-9bc6-5081785c1a18 |  | note | – – – – – – – – – – – – – – – – –
label | f48ffabb-e82d-5d7d-b8ee-fe6760553f3f |  | note | ACCEPTANCE CRITERIA: Piles forced up by the driving of adjacent piles shall be re driven to the specified toe level.
label | eb1a56fe-7647-5f4a-a220-ca1962945b75 |  | note | – – – – – – – – – – – – – – – – –
label | 46551260-c528-56d1-95b8-8b40d5fa8fe2 |  | note | METHOD: Measure
label | 281b057c-bf06-5d21-903b-aa08af5b574d |  | note | – – – – – – – – – – – – – – – – –
label | 4b49d649-59ad-515c-a108-e86d029aa652 |  | note | FREQUENCY: When Applicable
label | 97857bdf-ab5d-586a-8766-420c27f92691 |  | note | – – – – – – – – – – – – – – – – –
label | 836ff675-2307-5e2c-bb08-513ce19796f7 |  | note | CATEGORY: IP
label | 92cb50ca-94f1-5bca-8972-dcdbc10ad6f9 |  | note | – – – – – – – – – – – – – – – – –
label | 582982c2-ee88-5675-977a-0fe79b4196c2 |  | note | RESPONSIBILITY: SE/PE
label | f035f7d3-9404-560e-8913-ff865472eda9 |  | note | – – – – – – – – – – – – – – – – –
label | 1282ee90-8500-569e-96ae-4228bf7e7a38 |  | note | VERIFYING DOCUMENTS: This ITP
date | ae3d093f-3f4a-59f5-81f7-22437c73fd1a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 6235fbc0-8ddb-5d8d-996f-d5f9a4e61731 |  | note | REFERENCE: VR 605.04 (c)
label | e4d3bae2-b459-53d0-9bbf-1dfcf7f6d84a |  | note | – – – – – – – – – – – – – – – – –
label | 01bc05ef-eccb-5460-9c80-73639487aeb7 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 4e772518-eed9-5e37-8e69-8e59e0886d62 |  | note | i. Centre of pile head plan location = ±50mm
label | 8b1661b5-50bc-5285-8362-a58189a955e8 |  | note | Attach: Survey As-builts / Survey Report
label | 0dab335c-ea59-5069-bda0-116ffbe8129a |  | note | – – – – – – – – – – – – – – – – –
label | 59030b0c-719b-5b29-98bf-5e81a7611a5a |  | note | METHOD: Document Review
label | 9df3fa37-d006-56e0-ab5a-f0125ee75cc9 |  | note | – – – – – – – – – – – – – – – – –
label | 735d030d-3188-52c1-92ce-5e4cd8ec1104 |  | note | FREQUENCY: Each pile
label | ceab0815-ad48-58dd-8944-5e1aa494ede5 |  | note | – – – – – – – – – – – – – – – – –
label | 288dd536-6c63-5f38-8dd3-d6ecbf2816f9 |  | note | CATEGORY: IP
label | 2b74ecf5-ef3e-5395-9034-d09dbb95d61f |  | note | – – – – – – – – – – – – – – – – –
label | 9fe2de1e-91cb-5dc4-bb4f-3663aa6eb071 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 90f6931f-bcf1-5076-acf4-b3b4da048f5e |  | note | – – – – – – – – – – – – – – – – –
label | e2e6a248-79c8-50ce-b2a6-9d4478d63db5 |  | note | VERIFYING DOCUMENTS: This ITP
date | da347da8-8656-5576-b96e-1bdf37c852a9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | dd55c564-6f3c-5187-9c6a-790c7cbdeefa |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | da1bb674-22f7-5684-b8f9-d47bb73d93b7 |  | textbox | Name:
text | 26e32928-52aa-526a-8b82-d7ef117e8a77 |  | textbox | Position:
date | d47bee62-79bd-59e9-8629-7778119c8619 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing | itp |  |  |  | Yes | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing Rev 0 | 6c87b5eb-de3d-467a-a162-126d74a04804
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ec9d73c8-ad39-520b-ae67-0fba6f606d6c |  | note | Document Title: ITP-CIV-SSB-Rail Delineation Temporary Fencing
label | 332b2197-155a-5209-a978-753baacc2640 |  | note | ITP Description: Rail Delineation Temporary Fencing for Camms Road
label | e9b41770-43a8-598b-b852-e34148cb9f5f |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | b8f52ffa-a427-5227-92c4-adb0d6c3ff40 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | c77a6e1d-3785-559b-a88d-eb1c9bbb8e1b |  | note | Revision Number: 0
label | 177694cb-fb29-553a-abae-153c51ca0e2b |  | note | Revision Date: 11/08/2023
label | c185b33b-1b7d-51fd-94a9-22b0239a8f74 |  | note | ITP created by: Isaac El Zayat
label | d9c7c88e-04bd-5392-9ba2-c3b401f16996 |  | note | ITP approved for use by: Aldrin Guinchoma
label | ce94261a-8749-5de5-b86a-5ad6e0f26349 |  | note | 1.1 Non Dependent
label | 2e4290a9-27c0-5938-89c6-1aaf547955db |  | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete
label | 4a78021c-33ea-5853-af05-31394837c17f |  | note | REFERENCE: IFC Drawings
label | a62c25db-85fd-5d30-8415-32b9d7e61eb8 |  | note | – – – – – – – – – – – – – – – – –
label | 21e60ba6-dddb-51fd-8acb-469ea603df23 |  | note | ACCEPTANCE CRITERIA: 32MPa concrete to be used as per IFC drawings.
label | 09c81732-154d-5489-b745-d121bf8ea13f |  | note | – – – – – – – – – – – – – – – – –
label | 5bc24c93-ac54-57e0-b010-2acad315b789 |  | note | METHOD: Document Review
label | dd595eb5-5f7b-5640-b440-52335ab84a8c |  | note | – – – – – – – – – – – – – – – – –
label | c2daac0a-1ebd-548c-9881-58eb26a2f631 |  | note | FREQUENCY: Each Mix
label | 07933187-3632-5217-9f5a-83b863d6a1e8 |  | note | – – – – – – – – – – – – – – – – –
label | 2874d2cd-74f4-59b8-9717-7a78b49d2032 |  | note | CATEGORY: HP
label | f0d3cef4-5d03-5dd9-b7fd-8c6102e39f7c |  | note | – – – – – – – – – – – – – – – – –
label | d542df31-513c-50c1-b84f-e2796a7bc1bb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 26b06228-a51c-58c9-baa8-839d816614b2 |  | note | – – – – – – – – – – – – – – – – –
label | c81bc904-0551-50db-915b-f4a72273219d |  | note | VERIFYING DOCUMENTS: Certificate of Compliance
text | 4a44364c-e899-5036-b4e9-506466180010 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Steel components
label | b30eeef2-ffc4-5bde-b6f3-f677f0280087 |  | note | REFERENCE: IFC Drawings AS41000, AS1163
label | 285fecec-9482-5e69-b491-d2745eb68497 |  | note | – – – – – – – – – – – – – – – – –
label | f4475997-e8b4-5632-9fed-41c83671f1ca |  | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | bd682eda-b412-5082-b1a5-97a96839c744 |  | note | ○ Steel section sizes must be checked on site.
label | f5ff98ce-241e-5bed-9957-084504462119 |  | note | ○ Steel posts to be CHS with a grade of C250
label | f9479c56-3e9a-53d5-a606-7aca77fd7919 |  | note | – – – – – – – – – – – – – – – – –
label | cc18b9df-8005-5c8c-aa54-f8f4fafc15a5 |  | note | METHOD: Document review, Visual and Measure
label | f0504c31-21c3-5d09-ab0c-4aeed7292947 |  | note | – – – – – – – – – – – – – – – – –
label | 8e6ce503-9ea9-5336-985d-d0091fa79452 |  | note | FREQUENCY: All elements
label | 55631e09-091d-5ee1-bb43-ed81790ae083 |  | note | – – – – – – – – – – – – – – – – –
label | 6233ec51-54d9-5e81-9f93-38427557ae59 |  | note | CATEGORY: IP
label | a3200242-9e7b-5939-b566-d9ace19f6bf5 |  | note | – – – – – – – – – – – – – – – – –
label | dd60bcb9-5b44-5c75-a2d9-27e1b3d19e58 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ea0e1a05-0360-54ee-b72d-4b9fd7ed6665 |  | note | – – – – – – – – – – – – – – – – –
label | 0cd153f9-7c3e-5709-8599-a28bd4e0382a |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
text | 71660e72-f831-5b48-9803-316adc293132 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Excavation works
label | 1ce32fc0-60cc-52d3-9e16-f6fbd5a2ee8b |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | 551e9f4b-b6a6-5893-bd5e-e1b5ad307ff7 |  | note | – – – – – – – – – – – – – – – – –
label | 9cfed8be-e4c3-56e4-a366-d6ceb5c5fbe5 |  | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine track and comply with PTDT requirements.
label | c66e598c-d606-5119-b4e9-217dd99b5b64 |  | note | ○ Follow asset owners guidelines for work around their service.
label | 1c85925c-5e89-544d-836f-0e747618ede6 |  | note | ○ Excavation must use Non Distructive Digging in the rail corridor
label | f1c79e83-1753-542e-8977-4032d01e1169 |  | note | – – – – – – – – – – – – – – – – –
label | ebda8d61-c159-515b-bbfd-f057547b09ea |  | note | METHOD: Visual
label | 862645ee-f440-56aa-9056-abcd1fde8457 |  | note | – – – – – – – – – – – – – – – – –
label | e6482c43-47bd-5f29-ae18-b4df4dab5759 |  | note | CATEGORY: IP
label | f16f4022-deb7-5b4f-809e-04afc50f4055 |  | note | – – – – – – – – – – – – – – – – –
label | 711cbbbe-b1cf-59af-8207-1412e798439a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0a27d7ac-d712-5826-ab89-39ef05f97a47 |  | note | – – – – – – – – – – – – – – – – –
label | 55d9347b-3565-596e-90b3-c41882558d96 |  | note | VERIFYING DOCUMENTS: This ITP
text | 86daf07d-3f50-5c62-9824-635b7ae355f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 8631d05f-4b77-5cb5-9a2d-0fdca28fbccb |  | note | REFERENCE: IFC Drawings
label | 0fb51cb3-0c09-5d3e-a144-d348f737ac63 |  | note | – – – – – – – – – – – – – – – – –
label | 4831ba62-74d1-5b82-abf5-1fcde34f728b |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | a25fcc91-cf50-5466-ae17-8e90440aa4ad |  | note | ○ Offset checked against the running edge prior to installation of posts.
label | 010a4776-141c-519c-a941-e781468cee78 |  | note | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | 9d5e1af0-75ab-5ee7-b50d-3cf40000d2a2 |  | note | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | f9a472db-2fbc-5f7b-94b8-33f4b004db0c |  | note | – – – – – – – – – – – – – – – – –
label | f0f11594-9290-540c-821d-a636023e8417 |  | note | METHOD: Measure, Visual inspect
label | d54c7543-6046-5d85-b387-0f5bebe4c050 |  | note | – – – – – – – – – – – – – – – – –
label | 67d7ab01-ceff-58dc-9bbf-a459edda10e2 |  | note | FREQUENCY: Each element
label | fd0ac6b1-b7e7-5c20-8deb-5181876a1a3b |  | note | – – – – – – – – – – – – – – – – –
label | de202cc5-3c9a-52ea-a7fc-6dcecd15d817 |  | note | CATEGORY: IP
label | 7c4b3350-8bca-5cb2-947b-32bbefe6468d |  | note | – – – – – – – – – – – – – – – – –
label | b476da41-ec15-5af9-bcce-3afb998d1638 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | a969ae34-013e-5f74-ae1d-f2e8aa39614b |  | note | – – – – – – – – – – – – – – – – –
label | 548d3a69-cde6-5187-b0ca-804a85d8c46a |  | note | VERIFYING DOCUMENTS: This ITP
text | 26f9c3dc-51d4-5760-87ca-bbdef40ab0db |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Ground Conditions
label | 726fb64b-4e44-5b85-aa4e-068072eba8fe |  | note | REFERENCE: IFC Drawings
label | d0f466e2-f62a-5fec-b27f-6d89e091e94c |  | note | – – – – – – – – – – – – – – – – –
label | 72d01026-9c8f-5d36-938e-8dff910815a4 |  | note | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 2c866593-2b41-5404-a7bd-e393b36b50b9 |  | note | – – – – – – – – – – – – – – – – –
label | 69d289fe-53d7-5050-846b-71cd1da71a36 |  | note | METHOD: Visual
label | a52c2c35-2bcb-5b69-87ec-77fa193e7e6b |  | note | – – – – – – – – – – – – – – – – –
label | c34a4ba0-48be-550e-9b5d-ae9fe023ba6a |  | note | FREQUENCY: Each post
label | 64efbcb2-91e0-58cb-9480-480eb5eb5071 |  | note | – – – – – – – – – – – – – – – – –
label | a7752b9d-5386-55c7-b13a-aa8dded4f51b |  | note | CATEGORY: IP
label | 6e80c0e3-be96-5699-a2bf-a2ad70864ff6 |  | note | – – – – – – – – – – – – – – – – –
label | a27aae94-0de2-596f-b0e4-8a282cbd07dc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ee3fbe81-e3d8-519b-a274-8632be3c0bc1 |  | note | – – – – – – – – – – – – – – – – –
label | f80cb3c5-5ecf-5343-b30e-fc7ecdaa892a |  | note | VERIFYING DOCUMENTS: This ITP
text | 9d9c53a1-1522-5a00-92f1-3d26f5b6bd47 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Post Foundation
label | 3446ceea-4454-5f9c-8f53-5d0f274d8295 |  | note | REFERENCE: IFC Drawings
label | d33f6558-c39b-54ff-8a50-64bd78e181c1 |  | note | – – – – – – – – – – – – – – – – –
label | d4a82137-26ff-55ed-958c-9080ce3eb96f |  | note | ACCEPTANCE CRITERIA: Concrete
label | 69763eff-b431-54a0-a7b3-2c0fa6fe2564 |  | note | – 300mm Dia
label | 7a7a2493-13eb-58ad-a6cf-2352584efd44 |  | note | – 1000 mm Depth
label | 1a16fcd6-b039-5d2f-b59f-9eb8ba821da0 |  | note | CHS Sleeve:
label | 9da1f657-cfe0-5c42-854b-db649e58b2a1 |  | note | – Depth 1400
label | 91c3dbf1-7e9c-5a81-b229-5d2455ee860b |  | note | – Other Dimensions as per IFC
label | a09fd334-165d-566b-80fb-246a3ee96860 |  | note | Direct Driven:
label | e94e8e57-150d-5d73-bd08-8d70b9cf06c4 |  | note | – 88.9x4 CHS
label | 2b040436-a7b0-54db-8ac4-5d60a9d0f8c2 |  | note | – Depth: 1500
label | f9759267-9b29-55b0-8ecc-86d26cb774a8 |  | note | Spacings:
label | 55dc6496-5687-5dbe-bdbf-33eb723097f0 |  | note | ○ Typical: 2700 max
label | 9798de3c-e4f9-5669-8a67-89331b703fe9 |  | note | ○ Gates: 1350
label | ec307f70-e980-53b9-923f-4c4d45ba214a |  | note | ○ Refuge: 1200
label | bea79e93-a762-5651-a18c-a15f20929811 |  | note | – – – – – – – – – – – – – – – – –
label | a02bce53-cc42-5b2b-8678-f11f65d3b360 |  | note | METHOD: Measure
label | 5347af57-0498-5b28-bfe2-dae14be60741 |  | note | – – – – – – – – – – – – – – – – –
label | 7588c96b-c495-5be8-a991-420fd1a1af19 |  | note | FREQUENCY: Each footing
label | 65e52681-7886-5181-9433-111e3176e3ef |  | note | – – – – – – – – – – – – – – – – –
label | e39cb3c0-0c0a-5514-918c-516a4ad99d24 |  | note | CATEGORY: IP
label | 049ce94e-ecb4-5aba-b96c-fe761f795f00 |  | note | – – – – – – – – – – – – – – – – –
label | 21405875-fa14-5d7b-86f8-18a1118e33a9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fe16ac70-7456-5b60-8204-4db30b652b16 |  | note | – – – – – – – – – – – – – – – – –
label | 8bfa800c-5b72-576d-91d6-8833b5361624 |  | note | VERIFYING DOCUMENTS: This ITP
text | 453d66a5-56f2-5f07-96b8-fea87c00b7e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Post Installation
label | 082a1f3e-6519-5fd2-bbc7-301904cfc174 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | b25962d9-92da-54fc-b369-67fe42bd4181 |  | note | – – – – – – – – – – – – – – – – –
label | 94a329ec-3b7d-54b9-befe-8032f0ce7967 |  | note | ACCEPTANCE CRITERIA: Up track: Minimum offset 3000mm from centreline of track.
label | eda6477e-cda3-52de-96f1-72bebfb46cf8 |  | note | ○ Down track: Minimum offset 2200mm from centreline of track.
label | 9d8f9fa4-6c24-55f1-9507-291b923586fd |  | note | ○ Maximum post spacing to be 3.1m
label | fe82249f-ff33-5e38-abe3-c0937cde5852 |  | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
label | 88de0b25-10af-5a39-9413-1637aa81dffc |  | note | ○ Max. post height 1800mm above ground level.
label | 6a5e3c06-c080-5298-9b12-4b8538ff4378 |  | note | ○ Vertical Tolerance: ±20mm from the design line.
label | 0d1149b6-cb4a-5e48-a81b-4b6e43354719 |  | note | – – – – – – – – – – – – – – – – –
label | 2c436b2a-b0ea-54cf-b954-23175f6a7b5f |  | note | METHOD: Measure
label | 07bbe768-204c-5c2a-9465-34713eb521d2 |  | note | – – – – – – – – – – – – – – – – –
label | 18b27c06-1340-5aa1-9c2e-3d3e218a1f3c |  | note | FREQUENCY: Each post
label | 80364c84-0f52-5381-a147-8b4492919e78 |  | note | – – – – – – – – – – – – – – – – –
label | 25c88331-8888-5265-a381-1b5e7dddd042 |  | note | CATEGORY: IP
label | de2c5619-69ab-5243-852c-b2163eca0363 |  | note | – – – – – – – – – – – – – – – – –
label | f0163aa8-6941-5a02-b45c-0b5b59d2e24f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 36bffe66-b5d5-5e00-b9f5-df0a2f0eff7a |  | note | – – – – – – – – – – – – – – – – –
label | 5c14e2cd-1c86-52f2-a140-691a108a02cc |  | note | VERIFYING DOCUMENTS: This ITP
text | 68904b44-93be-5e16-b69d-79e08f68b4bc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Chain Wire Mesh Installation
label | 25b27bcd-72fb-581c-8bc6-110af0351257 |  | note | REFERENCE: IFC Drawings
label | fae80f24-5c69-597e-b80f-2ab9e75f90ae |  | note | – – – – – – – – – – – – – – – – –
label | a9ce0599-a9a9-5770-ad24-05199a46193f |  | note | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | 5c4b5526-308c-5dd4-9f44-6d22c98bb24e |  | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | 540b7f55-8037-58a8-94d7-8b85ad33a235 |  | note | – – – – – – – – – – – – – – – – –
label | e807892d-1672-5464-8ec5-53fc2182dadb |  | note | METHOD: Visual
label | 035c8f11-bf16-5fd9-ae50-d29e8af16028 |  | note | – – – – – – – – – – – – – – – – –
label | bdae91cf-a3b9-528b-a88a-7f2d7ebc5077 |  | note | FREQUENCY: Each element
label | c00ccefb-4779-5061-ad2b-894c76e39bc2 |  | note | – – – – – – – – – – – – – – – – –
label | fc67b590-b253-52ea-8af4-8c143dbddf67 |  | note | CATEGORY: IP
label | b25b21ec-6ec7-5873-bbb0-663d3c31426f |  | note | – – – – – – – – – – – – – – – – –
label | 07fdacb9-2f00-552d-a8f0-93bafa433583 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 449a7ba5-2215-581f-a5f5-a059cc39cc0f |  | note | – – – – – – – – – – – – – – – – –
label | 07181ad3-457d-50ba-8b94-77959cf1197e |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b37dd69-644f-59aa-b5ef-f3e92a1be07b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Bracing
label | 71254aab-1833-5d22-ae64-4ac53333b449 |  | note | REFERENCE: IFC Drawings
label | 8db5cbf3-e02e-5e78-98ff-0840bfaa2376 |  | note | – – – – – – – – – – – – – – – – –
label | 0ffdd3f6-0526-56ab-a249-a901d8c01987 |  | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 1361af66-5e89-5acf-8fc8-dd17bd950b0d |  | note | ○ Bracing to be installed on both sides of the fence at the fence corners
label | ca9053e3-fa46-56aa-8dd2-094b638f2529 |  | note | – – – – – – – – – – – – – – – – –
label | d9833b19-b1a1-55b0-9847-cef5fa705727 |  | note | METHOD: Visual
label | e395b762-1873-5283-ace1-2e179d2c7d75 |  | note | – – – – – – – – – – – – – – – – –
label | 25b40fb2-4287-5965-8f5c-6501eb4c3a74 |  | note | FREQUENCY: Each element
label | 21608c98-c365-5fd3-b1cb-d1614602bef6 |  | note | – – – – – – – – – – – – – – – – –
label | 5270e350-4b4d-536a-bbfa-f2dbdb52456f |  | note | CATEGORY: IP
label | a9d8903a-83fe-5c6e-a1cf-9a9c1186fbc9 |  | note | – – – – – – – – – – – – – – – – –
label | b9c9fd1e-5bb3-52a1-ab2b-776de3ade79a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1acdc240-a508-5f84-b79e-d2ebc25b6ae2 |  | note | – – – – – – – – – – – – – – – – –
label | 246344ef-1aab-5dca-8ed8-a9968d355a91 |  | note | VERIFYING DOCUMENTS: This ITP
text | fa8dcdd2-e4a6-5f94-8074-717e1be4d324 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Refuge Installation
label | 4840f0dd-5f59-5971-a68e-f23d6b4e8e5d |  | note | REFERENCE: IFC Drawings
label | 97cd7143-95d2-5c79-b2bb-67fcf3d7970b |  | note | – – – – – – – – – – – – – – – – –
label | e01de92e-1f3d-586c-acbb-6ef4c55345bc |  | note | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | 9111e748-586f-57f1-a4f8-fb97a872a905 |  | note | ○ No chain wire mesh to be installed at refuge access.
label | 45f24409-130c-5f5a-a9b2-3f600de23904 |  | note | ○ Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
label | 61339afc-d051-5967-a711-e2ccdb16a49b |  | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | 442265e2-156e-5eab-847b-5d4317d1bb48 |  | note | – – – – – – – – – – – – – – – – –
label | 803f6c62-0e48-5575-8c9e-9152f79f4caa |  | note | METHOD: Visual
label | 422a636f-2cfc-5326-8143-bea683196870 |  | note | – – – – – – – – – – – – – – – – –
label | fc27830e-e20e-563f-aaf7-16b46286d066 |  | note | FREQUENCY: Each element
label | 34cf5c02-e8d1-571e-8e45-7d838cd95e41 |  | note | – – – – – – – – – – – – – – – – –
label | e08049ef-47d0-5b2b-8069-97c81c7a08bb |  | note | CATEGORY: IP
label | c24f8841-594e-5dbe-83df-7fa5d12b4f57 |  | note | – – – – – – – – – – – – – – – – –
label | 9fc41de0-8891-51ed-a388-73f4e1cd922a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 347699e2-111a-5a5c-8dbc-faed195487d5 |  | note | – – – – – – – – – – – – – – – – –
label | 0d31a6fc-fc60-5371-8217-e0e85cd99215 |  | note | VERIFYING DOCUMENTS: This ITP
text | 777b63df-8631-5936-a83d-efdc3439c140 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Refuge Signage
label | 3e53b2b0-9ba6-5081-9a2e-388ab3f85fae |  | note | REFERENCE: IFC Drawings
label | 6ab36f94-3c39-59b4-b158-98d4fae7d423 |  | note | – – – – – – – – – – – – – – – – –
label | 9c2bb6d7-0827-5281-9955-0ece193d0ecc |  | note | ACCEPTANCE CRITERIA: Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | 1ba18b0f-f949-5822-b09a-f4d0d7c3a0c5 |  | note | – – – – – – – – – – – – – – – – –
label | 5c5c0056-e5c9-58f2-8772-9bcfefb70014 |  | note | METHOD: Visual
label | 485e5f83-95ec-5d8d-b9fa-1ec40e15bfee |  | note | – – – – – – – – – – – – – – – – –
label | eeb18d1f-4a57-5333-919f-08d3f31e7074 |  | note | FREQUENCY: Each element
label | 21fa4787-049a-53db-8a93-8baa13235d95 |  | note | – – – – – – – – – – – – – – – – –
label | a00dfc65-6ac2-5005-9a7d-6baf9b9ccb9e |  | note | CATEGORY: IP
label | d78ce728-8a31-5b25-886b-315f8234c1cf |  | note | – – – – – – – – – – – – – – – – –
label | 5c07eeb4-ad47-52fc-9d47-3d0e436d6b75 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 70e8cdd7-cde7-54db-9566-87bd8ccec541 |  | note | – – – – – – – – – – – – – – – – –
label | 1c0c96a6-1d9c-51e9-80c1-14bc3eaf20d0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5dccd4a1-47fc-5f80-9951-f2acdef52245 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Fence Height and Track Clearance
label | 6a6506f1-2d58-57e1-a2fc-5c0e477363b0 |  | note | REFERENCE: IFC Drawings
label | a8e38ac5-1cc8-5694-9a53-e8b30f6cfc33 |  | note | – – – – – – – – – – – – – – – – –
label | 7c740cca-0c63-5343-af82-46aa48537023 |  | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | e2530150-c500-5640-aa8b-29a6a51c6546 |  | note | – – – – – – – – – – – – – – – – –
label | 8193ed29-aa06-5903-82fd-fcb330606f83 |  | note | METHOD: Measure
label | 1e133529-02a1-5945-a91e-88617807a13a |  | note | – – – – – – – – – – – – – – – – –
label | b207691f-0b40-584d-b6de-d2de0570da84 |  | note | FREQUENCY: Each lot
label | 82ab422c-c9ea-57f2-b6b6-3d37d13d55b0 |  | note | – – – – – – – – – – – – – – – – –
label | 31dd574a-360e-5955-b22a-0a312cdf1c9f |  | note | CATEGORY: IP
label | 0d5bae00-7c04-5e8c-8a82-f6dd5146dfb9 |  | note | – – – – – – – – – – – – – – – – –
label | 371fb225-c4a6-5243-8443-8864e5b45cf7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fbff6749-f858-54a7-b125-e81b8946985b |  | note | – – – – – – – – – – – – – – – – –
label | f2cd56e6-ed3d-5088-a7e5-18d87391f842 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1e6d8259-d4bc-540c-9af5-6d3036a9b1ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a7d23049-ba58-5a14-bbb6-13932c5e539f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 316b3e8f-8b54-5352-b4c8-6d45b1c48767 |  | textbox | Name:
text | ec28943a-8618-536a-aa52-cbab2b8edb92 |  | textbox | Position:
text | 81aec31c-8625-532c-b7e0-471a8a120913 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-135-CIV-Stormwater Pits and Pipes Installation | itp |  |  |  | Yes | ITP-135-CIV-Stormwater Pits and Pipes Installation Rev 0 | 6d97ff78-6114-43f5-8f64-9ad28419ca27
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 04391565-ddfd-5b82-89b5-bb09c68eac13 |  | note | Document Title: ITP-135-CIV-SSB-Stormwater Pits and Pipe Installation
label | a29bc45f-cd00-5623-ab9b-7e197a4fcf05 |  | note | ITP Description: SSB-Stormwater Pits and Pipe Installation
label | 1c5663e7-7418-51e2-a0cb-3b7a667e2986 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | e1c5ce1f-36b3-5d1f-a164-0585099559c4 |  | note | Discipline (e.g. CIV/STR/RAIL): 135-CIV
label | dbe53d57-1794-5d9b-886e-664a75d31955 |  | note | Revision Number: 0
label | a886a32c-0648-5438-a2ec-9a04233ea81e |  | note | Revision Date: 30/01/2023
label | 159d90f8-ab07-54df-a56b-3b4e3d9ebcc8 |  | note | ITP created by: Hiruni Wickramarathne
label | 4e750cca-2183-529f-924b-89df6e11432e |  | note | ITP approved for use by: Victor Mira
label | 5780151d-c157-5b44-aa29-ab86a8a107f3 |  | note | 1.1 Non Dependent
label | 5d6e6f9b-0bc4-552c-8512-a5b49529ea0b |  | note | Reference: VicRoads Section 701 (May 2020)
label | c1e73bf9-74b9-5fc2-922b-cabb8088cb2f |  | note | 1.2 Non Dependent
label | 82174e2f-3ce6-5ad7-95d2-4b7c4ae5b25a |  | note | Reference: VicRoads Section 705 (June 2021)
label | babd2626-561e-5333-90c8-5197045d916a |  | note | 1.3 Non Dependent
label | 7074a2e0-9ea7-5694-89e1-e800cbadb861 |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Materials
label | 40551439-2dce-53ac-a8b7-36b844ba543f |  | note | REFERENCE: Respective separable package Materials and CCTV ITP
label | 19b9881d-f2e2-5329-9604-e32f348cb43b |  | note | – – – – – – – – – – – – – – – – –
label | c5b5f5b2-072f-5ad6-a9e0-84ce1af469f0 |  | note | ACCEPTANCE CRITERIA: Materials are as approved in the main ITP
text | e6b7ad4e-d799-5438-9b1c-05aaaa7a1ed2 |  | textbox | Enter: Separable package Lot number:
date | 45428f51-20e2-5750-8e01-69d90334217a |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out - Pits & Pipes
label | 7b878672-94e7-5fdc-bc51-542aa87f0586 |  | note | REFERENCE: IFC Drawings Section 701.10
label | 0e5bb542-fde1-5f68-bec8-c6f624036461 |  | note | – – – – – – – – – – – – – – – – –
label | b1af9fd1-7547-5d4c-aed9-5ccb0c1cad56 |  | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | de502132-3162-50bc-9485-aeb13cf01171 |  | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | ff0e1dcb-e2d2-5e7b-aaf6-7045bbed7971 |  | note | – – – – – – – – – – – – – – – – –
label | 97529a07-5475-5287-afce-8f1f35ca498a |  | note | METHOD: Survey
label | f6f4a246-9711-5122-98a9-40651d6355b6 |  | note | – – – – – – – – – – – – – – – – –
label | aa373280-c807-59af-b5fa-091a41b64297 |  | note | FREQUENCY: Each Lot
label | 640a9e65-a0f5-5f40-b83e-8a9d7e8ececb |  | note | – – – – – – – – – – – – – – – – –
label | 79143b4b-8867-5a97-9cc2-c8e57c099646 |  | note | CATEGORY: HP*
label | 8c0ba418-0849-5c3e-96a3-cac0979eeeae |  | note | – – – – – – – – – – – – – – – – –
label | eca945b2-5f35-5066-9608-988ae6b1b5b5 |  | note | RESPONSIBILITY: PE
label | 11e6e400-c390-5586-b6f3-2eb7d2a61d65 |  | note | – – – – – – – – – – – – – – – – –
label | 14787b91-506b-52c3-ac9d-903b0045ddfa |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
date | 49ad363c-3f36-5804-b8ba-bca714f3f914 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Pits - Excavation
label | 2d810f6e-55d5-5509-9f19-865246ffb0aa |  | note | REFERENCE: IFC Drawings Section 705.05
label | 70fb46c8-19ff-5756-8674-fb87336fd600 |  | note | – – – – – – – – – – – – – – – – –
label | 2e3fb576-6d90-55dc-bb92-925d1955f8b8 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | edfd5833-0d1b-54f2-b609-9f2c8e4dbdad |  | note | – – – – – – – – – – – – – – – – –
label | e1692ce4-197b-5f62-aa28-f60fa09e93ad |  | note | METHOD: Visual inspection, Measure
label | 718f690b-f98b-5b95-8d00-3cc976240515 |  | note | – – – – – – – – – – – – – – – – –
label | 612a337d-1410-5231-a9ab-88fdd8c3b64b |  | note | FREQUENCY: Each Lot
label | 615790b2-d2fd-50e9-9d20-db86f46bb3be |  | note | – – – – – – – – – – – – – – – – –
label | 5cc56e29-7575-5600-bb61-701f230a261c |  | note | CATEGORY: IP
label | 415e9976-0e1b-5a76-9a23-6b82d00d6552 |  | note | – – – – – – – – – – – – – – – – –
label | 2cdfa91f-3006-5074-a6ef-c7d113de6d75 |  | note | RESPONSIBILITY: SE
label | 50d8f4fb-e91b-5d2c-a16f-b0ec965e1fdc |  | note | – – – – – – – – – – – – – – – – –
label | 3ad52cc8-fd6f-54a6-87bf-706a84bf4540 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0436414d-8b83-51c9-901b-87a1b2c102b4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pits - Placement of Bedding Material
label | 64af1d77-0b7d-56bd-87d5-2aaa5f5e86d5 |  | note | REFERENCE: IFC Drawings Section 705.05
label | 5da49dad-c1f1-5f59-95ca-9f63f140e1ee |  | note | – – – – – – – – – – – – – – – – –
label | 1266dac8-acf9-51b0-a380-4e1b6a9f19f0 |  | note | ACCEPTANCE CRITERIA: Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | 0a15d195-3abb-5f7e-be38-b4b4b5cec7fa |  | note | > 80mm for clay foundations
label | 38b7964c-940a-5268-b18f-6c33601d047c |  | note | > 150mm for rock foundations
label | 43020139-085e-55cd-b4ea-33f0e8ee926a |  | note | – – – – – – – – – – – – – – – – –
label | 997c49d7-a930-51a2-9cb4-42106682928e |  | note | METHOD: Visual inspection, Measure
label | 0e9ff813-7b52-5df7-beb4-54aed1040e7c |  | note | – – – – – – – – – – – – – – – – –
label | 9f9d2fc9-63e2-5d33-90be-cc2aa98772aa |  | note | FREQUENCY: Each Lot
label | f4bfcacc-8245-5137-988e-b939e07945d0 |  | note | – – – – – – – – – – – – – – – – –
label | 124ebaf6-5445-59d9-95c1-58bafb29c0c1 |  | note | CATEGORY: IP
label | 62117805-e8c2-523c-856f-ee73cbc78212 |  | note | – – – – – – – – – – – – – – – – –
label | b54502a2-0b81-5043-81c1-18ae88806e7a |  | note | RESPONSIBILITY: SE
label | 8fe1969b-7ce3-5f38-b0bf-7d2ec0de08d1 |  | note | – – – – – – – – – – – – – – – – –
label | 2386f4ab-336f-5a10-90e0-064f26779367 |  | note | VERIFYING DOCUMENTS: This ITP
date | 0d9875b8-b2ed-5ee1-82ca-de8044b66ae8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
label | 458bc05b-ff69-537c-ada8-493f83f33168 |  | note | REFERENCE: IFC Drawings Section 701.10
label | e896b6b0-f6e2-54de-a56d-f0d156f0b873 |  | note | – – – – – – – – – – – – – – – – –
label | ce331d73-f80d-5ad9-9a86-f13d0b82ff86 |  | note | ACCEPTANCE CRITERIA: Survey pick-up to verify:
label | d6171753-04da-5b87-b2f9-39bbcad8bfbb |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | b2c3186c-f271-5a14-aa84-7a7afd05fd17 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | d7068f62-f420-50b8-bf08-684bdbce3d7b |  | note | – – – – – – – – – – – – – – – – –
label | e0b0a2d7-3c29-5242-bc37-8c10ee08894c |  | note | METHOD: Visual inspection, Measure
label | 8504748c-b769-5f0a-bef5-befac6cf1724 |  | note | – – – – – – – – – – – – – – – – –
label | f515c9ad-bef5-54d2-b2ee-7d9ab612423c |  | note | FREQUENCY: Each Lot
label | f6ea2bf8-8ece-5d44-80fc-688bcfaf26e3 |  | note | – – – – – – – – – – – – – – – – –
label | 1d585d52-e33f-55a0-904a-ca9bd5d600e5 |  | note | CATEGORY: IP
label | 96aae33d-30f8-5be2-aace-f82a1be302ee |  | note | – – – – – – – – – – – – – – – – –
label | a7949f3b-571a-5384-8478-62a93071151c |  | note | RESPONSIBILITY: SE
label | 35c5212c-b86c-54b0-86f2-bc3de4d9015a |  | note | – – – – – – – – – – – – – – – – –
label | 3365d77d-e779-52ed-b8e2-964726fde686 |  | note | VERIFYING DOCUMENTS: This ITP
date | b4260dde-be17-54c9-b247-8def34a6ba7e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pits - Cast in Place Drainage Pit
label | 609e6698-6318-55c3-90f9-6350d3c4dbfa |  | note | REFERENCE: IFC Drawings Section 705.06, Section 610, Section 611
label | df480bbc-141c-552e-a698-a5a406dcf573 |  | note | – – – – – – – – – – – – – – – – –
label | 69a7b3a0-c135-5407-ae84-222c2c80887c |  | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | ad1e1f63-0a63-593b-8c67-e383f5457f5c |  | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | e36d40d3-2b11-5924-93d4-e9df3af5ad9f |  | note | – – – – – – – – – – – – – – – – –
label | 8fd86456-3651-5116-9c35-29f949ee3266 |  | note | METHOD: Survey, Measure
label | 6e3447ee-cb17-55b5-9eb1-7a0f4e06e997 |  | note | – – – – – – – – – – – – – – – – –
label | b35b1d54-04b4-5413-8bfa-440113cd9080 |  | note | FREQUENCY: Each Lot
label | bb5e8bf5-6461-5e01-9f0e-acc881610268 |  | note | – – – – – – – – – – – – – – – – –
label | e4f1d45d-4d40-597e-852d-79eaf02f28d0 |  | note | CATEGORY: IP
label | 82291ad5-0d06-5eca-a2ea-7b7de234d0ef |  | note | – – – – – – – – – – – – – – – – –
label | 3006fcca-e6c8-57ef-9f01-a069a825c596 |  | note | RESPONSIBILITY: SE
label | 759288ff-fdae-5d35-890b-f42f7c48d3f8 |  | note | – – – – – – – – – – – – – – – – –
label | 20da4cec-f9ba-52fe-b056-cd933ff2a708 |  | note | VERIFYING DOCUMENTS: This ITP
date | 56f2a906-4b3e-5585-8f23-4bac2a8f27d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pits - Jointing & Drainage Connections
label | 0d64d62c-f8d0-5f15-9ce4-eca303654dc8 |  | note | REFERENCE: Section 705.11
label | 77e43547-a14d-54e5-8a5a-58fcb16ad733 |  | note | – – – – – – – – – – – – – – – – –
label | 27566d09-5a9f-54a2-bc1a-0763197cfafd |  | note | ACCEPTANCE CRITERIA: All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | 261c9ed4-f8c8-5fc7-ba54-bcd5f481c749 |  | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | feb3d6a1-b78c-5a78-b808-970d936fee75 |  | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 6260fa4a-6c81-5458-89fa-2e980990d847 |  | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 1f93aa24-bafa-55bf-bc79-a4d3ddb4153e |  | note | – – – – – – – – – – – – – – – – –
label | 3c73f5b6-5cf1-5c8c-bf99-585e9aeb0597 |  | note | METHOD: Visual inspection, Measure
label | eeef3e09-4b13-524c-a998-7397551cd093 |  | note | – – – – – – – – – – – – – – – – –
label | d0e84b29-ce2e-5a49-b7c9-0c2b9b72c290 |  | note | FREQUENCY: Each Lot
label | 2c48f7d3-7626-565e-a08b-ef302001ddb5 |  | note | – – – – – – – – – – – – – – – – –
label | f434d0d4-36aa-572b-b495-d5906ffe7d5e |  | note | CATEGORY: IP
label | d5461670-60ea-5d94-aca2-5f00377de2a4 |  | note | – – – – – – – – – – – – – – – – –
label | 2b4cbe56-59f1-5d88-88a3-1b34f532fe6d |  | note | RESPONSIBILITY: SE
label | bdb7afff-7aac-5774-abc6-3f098e349184 |  | note | – – – – – – – – – – – – – – – – –
label | 04df2716-989d-5249-967f-0515f3c8d6b8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 497fb7dc-0535-5b4b-9bb7-93c74fb579b6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pits - Shaping of Floor
label | bc7bddb5-fbf3-5d02-95e3-7d81b60255ed |  | note | REFERENCE: Section 705.13
label | 3a74d8aa-a833-58c4-ab55-30a7e8a61e72 |  | note | – – – – – – – – – – – – – – – – –
label | a03b88e8-13ad-53a3-a318-03627df242da |  | note | ACCEPTANCE CRITERIA: Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | 2d2d6cfa-64fc-5764-a73e-c82ec7e21a81 |  | note | – – – – – – – – – – – – – – – – –
label | af024222-65f4-52fc-a451-4de179bfa5a1 |  | note | METHOD: Visual inspection, Measure
label | 11d7eaae-1bdc-5497-a77a-4e3f1d799fbd |  | note | – – – – – – – – – – – – – – – – –
label | 332ffd7b-f366-53d7-87b1-17dd3eae8044 |  | note | FREQUENCY: Each Lot
label | 04145651-f3fd-50e2-bfac-d9fa5e863699 |  | note | – – – – – – – – – – – – – – – – –
label | fe2f15c3-9d3e-5544-a45a-f4f061424a89 |  | note | CATEGORY: IP
label | 2f53112c-b277-51e7-bbea-37ae31b88ebf |  | note | – – – – – – – – – – – – – – – – –
label | 59823087-6bc1-51e3-b517-0398495cd63c |  | note | RESPONSIBILITY: SE
label | e9ba0f59-87cf-56df-89aa-ec71944b1ef6 |  | note | – – – – – – – – – – – – – – – – –
label | 7d144958-0a45-5b94-95a4-35d3d973f857 |  | note | VERIFYING DOCUMENTS: This ITP
date | 75b726e1-948f-533e-b9d4-ea321011e74b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pits - Step Irons
label | 5dd02c15-72c5-5a59-81df-eeff467ae177 |  | note | REFERENCE: IFC Drawings Section 705.12
label | 448f41b6-f666-51c3-a962-83e1855323ae |  | note | – – – – – – – – – – – – – – – – –
label | 9c87880b-fe88-52b4-a1b2-0f6b47f906c8 |  | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | 781ee137-d1fb-5778-b7da-4b8d1b606fd8 |  | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | 01d9aea7-6d72-51cc-8fa3-ecda6227b23e |  | note | – – – – – – – – – – – – – – – – –
label | 60ea98f3-3617-5147-8ef3-2f2e84e9ff9c |  | note | METHOD: Visual inspection, Measure
label | a5148cc5-9602-57fa-81d8-780aad3a2a37 |  | note | – – – – – – – – – – – – – – – – –
label | 105e23c4-ff01-555a-83a8-d788fa97c6c0 |  | note | FREQUENCY: Each Lot
label | a14fba4c-4cf1-56d7-b279-ae817eb19309 |  | note | – – – – – – – – – – – – – – – – –
label | ed2726db-f490-5073-986f-487fb1d7e79c |  | note | CATEGORY: IP
label | 226e2509-fa99-5b17-8899-3a31dd5fb32e |  | note | – – – – – – – – – – – – – – – – –
label | 83e8489c-3c14-5d53-ad38-c6581634dd1d |  | note | RESPONSIBILITY: SE
label | b127bda3-6f73-5c3e-9ec0-c5e2e21e4d5c |  | note | – – – – – – – – – – – – – – – – –
label | 5bc906e4-cc10-52ab-9a30-41b64ae2a084 |  | note | VERIFYING DOCUMENTS: This ITP
date | 742f6b20-9472-54e9-b3f3-b2fb2f3413fa |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pits - Fitting of Covers
label | edc0f83b-6b2b-52c0-816e-4ec5b707b958 |  | note | REFERENCE: IFC Drawings Section 705.17
label | fa91a51c-7681-5451-9f2e-169cb4c2cd58 |  | note | – – – – – – – – – – – – – – – – –
label | 798c698b-b40a-57ca-b416-bd7e3b98cb2e |  | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | af428cff-3c6f-5923-abfe-a78e17140e39 |  | note | ○ Height shall be within 10mm of the design level.
label | 98625480-ecf8-5f48-bf78-9bfb2961ebfc |  | note | – – – – – – – – – – – – – – – – –
label | 04778c0d-11d1-5bdb-bb37-9d9ab0490014 |  | note | METHOD: Visual inspection, Measure
label | f888998f-db01-5448-a301-4bcc74003a73 |  | note | – – – – – – – – – – – – – – – – –
label | d76b92b8-e81c-5296-ac0d-4fa138f55c3d |  | note | FREQUENCY: Each Lot
label | e87e8498-9c50-51c4-adf2-31780cc3b3c5 |  | note | – – – – – – – – – – – – – – – – –
label | ab9610af-a42c-5efe-9629-3c5fc95ceb06 |  | note | CATEGORY: IP
label | 0a1fc520-97e5-567a-bc5b-0d52dc7530f6 |  | note | – – – – – – – – – – – – – – – – –
label | 0486bc07-c117-5cef-ae2f-c73105f502d1 |  | note | RESPONSIBILITY: SE
label | b0626317-139f-5e83-b79b-58d31b27c5db |  | note | – – – – – – – – – – – – – – – – –
label | 7d5ce0a6-26ca-55aa-b411-116ac9827e65 |  | note | VERIFYING DOCUMENTS: This ITP
date | 74996fca-3785-509c-a39b-3e856b2dc7b8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pits - Pit Lids
label | 50aadc2b-916b-5fc3-bae7-295d2212acd9 |  | note | REFERENCE: IFC Drawings
label | 501ef372-e25c-5035-8a01-832376335468 |  | note | – – – – – – – – – – – – – – – – –
label | 192a0c8c-001d-55e0-bfdc-481598f424ae |  | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | e8d8a7a5-111c-5cb7-a616-7ec47fe8d96a |  | note | – – – – – – – – – – – – – – – – –
label | 4cdb6932-f84b-5938-8efb-be66e9b0a2aa |  | note | METHOD: Visual inspection
label | a5ff5dab-7b49-5307-b0cb-937335f7b31e |  | note | – – – – – – – – – – – – – – – – –
label | 69d565e8-5aaa-57ae-b339-e837eb7ccfaf |  | note | FREQUENCY: Each Lot
label | 40654cc2-9ea0-5db9-a70a-f86a0db207ba |  | note | – – – – – – – – – – – – – – – – –
label | cc327ba1-b123-5563-bcae-54afef8572c1 |  | note | CATEGORY: IP
label | 8331a104-f7e7-5fa6-a6d2-547a7fdc98ef |  | note | – – – – – – – – – – – – – – – – –
label | 50b148ce-7272-5c0f-9a3e-c1db3a9cacc6 |  | note | RESPONSIBILITY: SE
label | 9c0b9f5b-356e-52f6-912c-fc08778de89b |  | note | – – – – – – – – – – – – – – – – –
label | 7385f7ff-b8eb-559c-ba7b-a05263e5390c |  | note | VERIFYING DOCUMENTS: This ITP
date | a74c7e0e-564d-58d4-8891-4e187fe34b0e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
label | 8bdaa3aa-29f9-5d5c-ae61-c709d13d8ffa |  | note | REFERENCE: Section 705.18
label | 74fcdf24-3240-5cca-9995-ee6a9871b189 |  | note | – – – – – – – – – – – – – – – – –
label | 77aee714-2611-54ca-b653-b3099b2b43a9 |  | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 9fbb6f72-a621-5960-a46f-1e2a3e5a6b06 |  | note | – – – – – – – – – – – – – – – – –
label | 177f6e43-8aa2-5965-a6ab-6505d28cf0cf |  | note | METHOD: Visual inspection, Measure
label | 63932334-db7b-5bd0-b6b8-3438048083c9 |  | note | – – – – – – – – – – – – – – – – –
label | de762caa-8398-5364-b16c-2128b058d6d9 |  | note | FREQUENCY: Each Lot
label | e23c8a2d-92bb-58a6-a00c-d3c41490f7a8 |  | note | – – – – – – – – – – – – – – – – –
label | dd2b3275-414b-5acd-a6ef-5d548191f728 |  | note | CATEGORY: IP
label | 645490d1-0b4f-5cc0-86f2-5ecbd440b39f |  | note | – – – – – – – – – – – – – – – – –
label | 932495fd-b823-5d3a-8e5d-300f17108cbf |  | note | RESPONSIBILITY: SE
label | 38323c65-cafe-57b8-ba7d-6b47a9d064f1 |  | note | – – – – – – – – – – – – – – – – –
label | e130590c-d1cd-55ec-afe1-42e033f408ab |  | note | VERIFYING DOCUMENTS: This ITP
date | c2d42cda-786c-51cf-8f4d-84845a999ecc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pipes - Trench Excavation
label | a1463092-5606-5496-b176-651530309ec5 |  | note | REFERENCE: IFC Drawings Section 701.15
label | f0d641a3-f0bd-53a1-9a5f-dcbb2777d0aa |  | note | – – – – – – – – – – – – – – – – –
label | 26fa592e-010e-58b6-ba1c-70ed07d252bb |  | note | ACCEPTANCE CRITERIA: Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | 297a2a4b-f372-5a4f-bd89-5b767c4ec2d7 |  | note | > 300mm, < 600mm for RCP
label | 4ebbd5ce-815e-59cc-8c9b-91ff751b505f |  | note | > 150mm for Flexible Pipe
label | aa6cb807-e3e8-54b0-b444-7d2e94ba03c7 |  | note | ○ The base of the trench shall be compacted to refusal using mechanical plant.
label | 66f76f46-21c8-57fd-bdc6-ead0401cac02 |  | note | – – – – – – – – – – – – – – – – –
label | 33cfb1e7-53d7-5dab-bc32-b57e2d1855bf |  | note | METHOD: Visual inspection, Measure
label | 42430b2f-b050-5a01-ac6d-9f67b33e348d |  | note | – – – – – – – – – – – – – – – – –
label | 2ad2fbfd-45f3-564a-b7c6-c75b88153ed1 |  | note | FREQUENCY: Each Lot
label | 05551ec1-83b5-5dd1-9a5b-323b999bc4e9 |  | note | – – – – – – – – – – – – – – – – –
label | 2d39d301-36e3-58b9-ac51-857d83873d39 |  | note | CATEGORY: IP
label | 05e121ad-9fac-5cde-bf8e-a16f9c0e8879 |  | note | – – – – – – – – – – – – – – – – –
label | bc3d3b8b-bf3d-5918-979a-31db01cafa0c |  | note | RESPONSIBILITY: SE
label | a2307047-e7f9-5f02-9629-9e78084b7ad2 |  | note | – – – – – – – – – – – – – – – – –
label | 62c27364-2321-5fcf-a00d-b9ebedf6bec7 |  | note | VERIFYING DOCUMENTS: This ITP
date | 65d3aaa7-52e1-58b8-9a8d-04112b6926c8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pipes - Bedding Placement
label | ac3d6f44-6c21-5004-a6bc-84492a3ef895 |  | note | REFERENCE: IFC Drawings Section 701.16
label | 6799b2c5-dd59-5092-a4c1-8b994591aae8 |  | note | – – – – – – – – – – – – – – – – –
label | 5860d7ce-d804-5e76-b01e-97b29e6bc237 |  | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | 1c5cae2f-5af6-53e7-a2db-f52df51f9a4a |  | note | > 100mm where D<1500mm
label | dfdaf92c-f7f5-51c7-9f0b-ec432124fbc6 |  | note | > 200mmwhwere D≥1500mm
label | 2dad76fb-3ac1-5a9e-a78e-a8f2488feee9 |  | note | ○ Bedding material shall be placed and compacted in layers <150mm loose thickness
label | 5e20a4e3-7a82-5a3f-ab7b-cdc9ff507d23 |  | note | – – – – – – – – – – – – – – – – –
label | 4cb251dc-0c1e-5ca2-85aa-458f47b1fe1f |  | note | METHOD: Visual inspection, Measure
label | 7fab2cd9-5192-57b3-9d66-ceb993c3bfd3 |  | note | – – – – – – – – – – – – – – – – –
label | 75fa4392-b9b6-5c67-a057-889e4d017411 |  | note | FREQUENCY: Each Lot
label | fc593a07-7a66-5701-ad28-9d8a08b6a884 |  | note | – – – – – – – – – – – – – – – – –
label | 2ba3133e-f5ca-52c1-905d-54c976bdf442 |  | note | CATEGORY: IP
label | b0577772-2466-5531-b1d1-826b34d14710 |  | note | – – – – – – – – – – – – – – – – –
label | 8d5e134e-1825-560d-bdc2-8b859a02406d |  | note | RESPONSIBILITY: SE
label | d111d644-9c67-596e-8c1d-1bd0d17c5c99 |  | note | – – – – – – – – – – – – – – – – –
label | 7acd55ea-b7cc-5549-abe2-173ee6fd232b |  | note | VERIFYING DOCUMENTS: This ITP
date | 7908cd69-b9e2-51a7-9cd3-8a6067ab13f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pipes - Bedding Testting
label | 357ef94f-93d9-53f9-8942-2370391ddfe1 |  | note | REFERENCE: IFC Drawings Section 701.20
label | de978ca2-ee71-5ae4-aec0-04ca9208041e |  | note | – – – – – – – – – – – – – – – – –
label | 94b2e6bf-1a0e-52a7-b32e-c58504bfdd1e |  | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill). The number of tests per lot shall be three
label | d26be425-3de5-57f3-8709-d56600a89c7e |  | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | a87f6a72-6411-5078-9942-257eb00b495f |  | note | – – – – – – – – – – – – – – – – –
label | 28e87581-6126-5b6e-9f15-a7480cbfdaf0 |  | note | METHOD: Compaction Test
label | df6f56d3-ca6b-508f-82e7-192b2bed6b5f |  | note | – – – – – – – – – – – – – – – – –
label | b7993350-6503-5247-ba7b-eba98056e5ef |  | note | FREQUENCY: Each Lot
label | 0cd184fc-5ce3-5eba-b14e-611c9b21d436 |  | note | – – – – – – – – – – – – – – – – –
label | 0a573f6e-17b3-561b-9cca-bbfd461c2a2e |  | note | CATEGORY: IP
label | 1ffcb4ac-537d-59c5-a794-b60d48ceb221 |  | note | – – – – – – – – – – – – – – – – –
label | 14564162-7810-56d1-9ee2-fd0e2fac0889 |  | note | RESPONSIBILITY: SE
label | c592267b-c6af-5ba7-a52f-84c095544999 |  | note | – – – – – – – – – – – – – – – – –
label | f04e8044-4e42-5918-afa3-5477cf00f527 |  | note | VERIFYING DOCUMENTS: This ITP
date | 5e46c042-b1c8-52a9-a5a1-4eb855afc638 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pipes-Placement of Pipe - Flexible Pipe
label | 861afdc8-bc33-59c3-81b9-ae1bcf4fe86f |  | note | REFERENCE: IFC Drawings Section 701.17, Section 701.22
label | edd19266-2aa3-5b65-a23f-1a26fa0e155c |  | note | – – – – – – – – – – – – – – – – –
label | e19a2ef3-cb66-5dc7-9fff-d21d6878bfca |  | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | ec07afc8-ab64-5b3c-96b3-51dd388e92cc |  | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 44910d46-81fd-5fca-8a91-177ee1defebd |  | note | – – – – – – – – – – – – – – – – –
label | 16286394-5e06-55c6-93a3-01b830726294 |  | note | METHOD: Visual inspection
label | eaa23ad4-ebac-5f7f-b596-1282a7daeba4 |  | note | – – – – – – – – – – – – – – – – –
label | b5e6febb-7fd5-524a-b633-970fc9aa942c |  | note | FREQUENCY: Each Lot
label | e5ce1914-6afc-511a-8141-37911fb26059 |  | note | – – – – – – – – – – – – – – – – –
label | 6eff7d26-3e87-5b60-8c7a-d88e3c54b274 |  | note | CATEGORY: IP
label | 7464998c-0ea9-5412-8e7e-62b19289d4e6 |  | note | – – – – – – – – – – – – – – – – –
label | 05516062-1f12-5953-bae4-270d6880a197 |  | note | RESPONSIBILITY: SE
label | 8829ebcd-9dac-522c-9c8d-fd52e208b0a7 |  | note | – – – – – – – – – – – – – – – – –
label | a68ced0d-2bad-5c60-84d7-0d3a8ab4b1cc |  | note | VERIFYING DOCUMENTS: This ITP
date | 287a57f0-8617-55bf-8be4-3a4618e0fb29 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Pipes - Lifting Holes
label | 7d592c8b-eb5c-546e-8de3-9398804b56d7 |  | note | REFERENCE: Section 701.18
label | 703cd847-5def-5868-b123-f79145bf292f |  | note | – – – – – – – – – – – – – – – – –
label | 1141b5a5-00d6-567e-9002-7a647940bb8c |  | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 07595bf6-38d6-5591-8d98-018d956aa6b2 |  | note | – – – – – – – – – – – – – – – – –
label | a120d573-1a4b-55e8-ba95-37e39bedaabf |  | note | METHOD: Visual inspection
label | 9a871ad1-289e-59d7-bbbf-cfa6020fa048 |  | note | – – – – – – – – – – – – – – – – –
label | 071964d8-cfca-515e-b99b-f418252b9ff4 |  | note | FREQUENCY: Each Lot
label | cce80615-47f1-5e8a-a212-e9761170d0d8 |  | note | – – – – – – – – – – – – – – – – –
label | a52041a3-c76f-5a2e-a9cd-cf5957ff70f3 |  | note | CATEGORY: IP
label | f1932905-c9c3-5cac-8318-a5a928630b76 |  | note | – – – – – – – – – – – – – – – – –
label | 95ec6fc8-ff84-5f15-b09d-baec895dcbed |  | note | RESPONSIBILITY: SE
label | 8af52a63-1b96-5d77-ad9b-62253f9108de |  | note | – – – – – – – – – – – – – – – – –
label | b13d0800-5fcf-55b5-a50a-9f174b0bad1c |  | note | VERIFYING DOCUMENTS: This ITP
date | 12284204-4fbd-5f34-ba8f-2c6e692a48da |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Pipes - As-built survey pick-up
label | 3b8be892-f21b-5d58-97c1-c65e45a3a212 |  | note | REFERENCE: IFC Drawings Section 710.10
label | 0d3bcdde-d63a-5d01-a70d-c68406f2aef0 |  | note | – – – – – – – – – – – – – – – – –
label | d83eba63-105c-5a27-96f9-8060212bc7a1 |  | note | ACCEPTANCE CRITERIA: Each run of underground drainage shall be Survey verified prior to backfilling.
label | 892ad12f-529f-57a4-8acc-659fb507fb17 |  | note | – Offset pits to kerb +/- 20mm
label | bf2e742d-b948-5722-9d5c-e3a5fc7f9529 |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | d16fde89-66ce-5620-869b-6378d1028ea4 |  | note | – Invert level of pipes at pits +/- 50mm
label | f502bbcc-ab87-5cf0-a297-77631d3dc63a |  | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | 6c3eda35-e23f-57e6-80d4-aea5c1929148 |  | note | – – – – – – – – – – – – – – – – –
label | 230d2595-808f-59c2-b3c8-17ddebf90e28 |  | note | METHOD: Survey
label | f137af92-4eff-5f2d-ab63-59786d907bc4 |  | note | – – – – – – – – – – – – – – – – –
label | b7616ea3-a8f3-5886-b498-abe8634c35aa |  | note | FREQUENCY: Each Lot
label | 31b92d13-fccd-502d-a130-d89297c18b45 |  | note | – – – – – – – – – – – – – – – – –
label | 0e1632ae-e251-5cbb-b7ad-a2e704a55650 |  | note | CATEGORY: IP
label | 4994d53b-dd57-5a75-b8e7-339976719e34 |  | note | – – – – – – – – – – – – – – – – –
label | e7364b02-5362-5234-ae13-33326c100cc9 |  | note | RESPONSIBILITY: SE
label | 1e691812-b602-5f82-8185-583a18993683 |  | note | – – – – – – – – – – – – – – – – –
label | f6383bc5-f1fe-558d-b481-1bcd7364cdd8 |  | note | VERIFYING DOCUMENTS: This ITP
date | bbb8884e-eaa3-5b92-9794-da7891bcf53c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Pipes - Backfill Placement
label | 377188da-4956-5ad2-94d9-de472b701cf3 |  | note | REFERENCE: IFC Drawings Section 701.16
label | fbf84ebd-efce-5b6e-839c-6d5ef49d6a6b |  | note | – – – – – – – – – – – – – – – – –
label | 665909ef-1a05-5b65-8bf8-687ab108dcb7 |  | note | ACCEPTANCE CRITERIA: Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | cf07057d-8aab-513f-afb5-1cbe745c8eab |  | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | d0b7667f-f705-5928-92ad-dfd613b4c412 |  | note | – – – – – – – – – – – – – – – – –
label | 6be27db9-0dd3-5493-b420-1f81aa543317 |  | note | METHOD: Visual inspection, Measure
label | b71c8e4b-f354-5817-990f-0fda4a79dc82 |  | note | – – – – – – – – – – – – – – – – –
label | 7d676f50-22ef-51fb-8b0a-f908b7fa2187 |  | note | FREQUENCY: Each Lot
label | c4e239bb-171a-54b7-9eb4-0f646b3d31e2 |  | note | – – – – – – – – – – – – – – – – –
label | 3919dfe0-75c5-5f47-9e31-fe4c29ff8546 |  | note | CATEGORY: IP
label | 6a1c15f4-7ea3-5b13-a308-a3eddf8b2d78 |  | note | – – – – – – – – – – – – – – – – –
label | 63af109a-b6f9-5bf1-a6af-e3ef13510c05 |  | note | RESPONSIBILITY: SE
label | ff3ab324-383e-5842-8a2d-406d21979164 |  | note | – – – – – – – – – – – – – – – – –
label | 13d2eea5-85a9-53e4-a64d-d41d36636788 |  | note | VERIFYING DOCUMENTS: This ITP
date | 776ba891-6555-5eb7-9c03-c829d95609b7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Pipes - Backfill Testing
label | ecff3aa9-25c9-51dc-85e3-912c0caebe93 |  | note | REFERENCE: IFC Drawings Section 701.20, Section 701.29
label | 80dfd554-7aa8-5211-8ed3-70c33ec15de7 |  | note | – – – – – – – – – – – – – – – – –
label | 0e1abed8-a51e-51e7-863d-43bed9209fff |  | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 15655407-923f-5050-bb23-1b853ee8932e |  | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 78a136ac-d489-51ba-bf16-ddb7fd2260fd |  | note | – – – – – – – – – – – – – – – – –
label | 0cd7e1d9-301f-54eb-b127-33fe054dd6be |  | note | METHOD: Visual inspection
label | f7d471a1-6b07-5b60-a8aa-ce59eac59c52 |  | note | – – – – – – – – – – – – – – – – –
label | a99e0168-54a8-5a9b-affe-edc77d09605c |  | note | FREQUENCY: Each Lot
label | 3b414779-eaf9-52b7-93b4-27d179c76caf |  | note | – – – – – – – – – – – – – – – – –
label | 68b0465a-f4b2-57bc-8c51-365b0063ad08 |  | note | CATEGORY: HP*
label | 25786544-96fd-5243-a293-fedd3717175f |  | note | – – – – – – – – – – – – – – – – –
label | 3639baaa-b831-51cb-b394-88b7688bef0a |  | note | RESPONSIBILITY: PE
label | 2c8bf7c3-a24e-5b1c-9085-a6acc4817efa |  | note | – – – – – – – – – – – – – – – – –
label | 169a8a2c-2c94-5063-8cd9-64b06b0f9dc2 |  | note | VERIFYING DOCUMENTS: This ITP
date | 454803be-d5b9-58ec-a6cb-6294c5b986b3 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | 4e959b29-8ec2-59e7-9214-c1b594c5f70f |  | note | REFERENCE: Section 701.28, Section 701.30
label | aa4c8b68-91e5-5cf5-8cd6-fdea51891fca |  | note | – – – – – – – – – – – – – – – – –
label | 616a7114-b409-5c42-a4a4-f4d846526651 |  | note | ACCEPTANCE CRITERIA: Refer to Respective CCTV and Material approval Lot
text | c8563f6d-d0bf-57bd-aaa5-76da25956ac1 |  | textbox | Enter CCTV and Material approval Lot number: [Text Box]
label | 04a7445b-767a-5c34-ac4d-393ba8e521f8 |  | note | – – – – – – – – – – – – – – – – –
label | bb93bb93-32c0-5a56-b067-ece9d1f5c43c |  | note | METHOD: Record Review
label | 1db6afec-9d12-5eeb-88f2-ce8403e090c0 |  | note | – – – – – – – – – – – – – – – – –
label | 2a952972-ae55-54dd-a18b-8f0d3415d3bc |  | note | FREQUENCY: Each lot
label | 4fd9cfd0-a931-5fd9-9325-189b26137b9d |  | note | – – – – – – – – – – – – – – – – –
label | 5283c573-ae8b-5382-8bbe-9c2b4a311b78 |  | note | CATEGORY: HP
label | e9acc9c1-d45a-5d98-82d1-4703b010ab88 |  | note | – – – – – – – – – – – – – – – – –
label | 7820f300-6964-5eab-bac0-b8973a6679b2 |  | note | RESPONSIBILITY: Nominated Authority
label | 83639742-907b-5788-9d25-7fbf2e6deebf |  | note | – – – – – – – – – – – – – – – – –
label | 83f141c2-4bf5-5757-9b0a-f8e54e6fd564 |  | note | VERIFYING DOCUMENTS: This ITP, CCTV Reports
date | a7e446c9-17b5-50db-b628-37529836ae4d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 As Built Survey
label | ac4bf227-e29d-5ca4-b4c5-d5128d802c5c |  | note | REFERENCE: Section 701.10
label | 8f4203d1-68f5-5b60-b1cd-3749142c122a |  | note | – – – – – – – – – – – – – – – – –
label | 8585ed51-db2e-5cda-95fd-b7ebaf50c5a9 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 305a0baa-6542-5126-b5a8-d66e5342e435 |  | note | Attach: Survey conformance Report
label | c0c27a5c-12de-55fd-9991-009d014002d2 |  | note | – – – – – – – – – – – – – – – – –
label | cfa9c418-44b4-5171-8468-8fffe3ba4e06 |  | note | METHOD: Document Review
label | 6e8fadd7-afc5-52e4-a4dd-50181f441d0e |  | note | – – – – – – – – – – – – – – – – –
label | f548025d-bc90-553d-b07a-c99525e5d5aa |  | note | FREQUENCY: Each lot
label | e5b6fade-9b6a-5b71-8eaa-66af34ff61b9 |  | note | – – – – – – – – – – – – – – – – –
label | 8d62d037-f20b-5dea-a036-8bf380522f93 |  | note | CATEGORY: IP
label | 25c46a9b-d0a0-535f-b646-e7ffed017b7a |  | note | – – – – – – – – – – – – – – – – –
label | fd8c95ca-bf16-5dd1-b755-c8918acdea2f |  | note | RESPONSIBILITY: SE
label | 7d287b7b-4d13-5999-bac5-be69edb0e15a |  | note | – – – – – – – – – – – – – – – – –
label | 96e0f7ea-d1c3-562c-8a64-8594762250a4 |  | note | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
date | cb10bad2-9bd4-5aba-9e2e-9988c2227bbb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Repairs to Damaged Pipes
label | 0ac072ff-c7a2-5be7-af55-c5a34e2ada1d |  | note | REFERENCE: Section 701.31
label | 683bff01-5bf1-5b3f-bc29-651237a0932e |  | note | – – – – – – – – – – – – – – – – –
label | 5b67f1b4-3063-5dc8-97b4-35cda1e5d7fc |  | note | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | 78b7aa52-6cd6-5a7b-a610-650def9f1cd4 |  | note | ○ cracks wider than 0.5 mm
label | 15e592aa-f895-51e9-a6aa-dccbc5ab8656 |  | note | ○ spalling of concrete
label | 9154b395-f705-5e47-939c-9b30f4d357f2 |  | note | ○ exposed reinforcement
label | b1420640-b359-5147-9b0b-d0dfed62e269 |  | note | ○ joints that are not fully engaged.
label | 2cbf9bd6-4e4e-5154-aea5-14fd7a81d457 |  | note | Any pipes with defects greater than the following limits shall be removed and replaced:
label | 14924b46-54fb-563e-974c-63ff508ceb65 |  | note | ○ longitudinal cracks greater than 2 mm
label | 2267ee54-6234-5992-9c66-48d262628423 |  | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 78734db6-c593-5a69-bf3d-7b0a84a97896 |  | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | 4b686584-f1af-5659-8173-ad62aefd0c67 |  | note | ○ penetrations with area greater than 400 mm2
label | 5febb688-00d2-5bac-85c6-d40ad9b4231d |  | note | ○ pipe joints that are separated.
label | cc3d03e7-88eb-57a3-8b70-bdbbdf45007d |  | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | 2dd8defe-30de-5bfa-acb5-49ef08a2bd19 |  | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 5887dd39-64bc-52c8-8dd5-337d6dd77808 |  | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | 1cf38c8e-c4bb-568a-8a8a-08427b1e6244 |  | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | ff9788fa-b3dc-5a42-ba6d-754b626a58c6 |  | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | b2813dfd-29a2-5552-87e8-ba502f3e1d17 |  | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | e68d66ec-30e2-545f-a38a-e240b982abfa |  | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | dabf3ff7-37d1-52bd-b38d-656b71e4f25c |  | note | – – – – – – – – – – – – – – – – –
label | 36533370-6300-5273-b7c8-ee50b21e4082 |  | note | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | df70032a-fb2e-57a2-b68c-8e1429e9d69e |  | note | – – – – – – – – – – – – – – – – –
label | 8754990d-a75d-5f5d-961f-84b8b9c59b42 |  | note | FREQUENCY: Where applicable
label | 8cdbb2fc-a769-5fbd-b2c9-c172e810d9d8 |  | note | – – – – – – – – – – – – – – – – –
label | f4355d79-07b9-51b9-91d2-182cfa2b4fe7 |  | note | CATEGORY: HP
label | 18398917-6145-5776-9a5f-340063985ad8 |  | note | – – – – – – – – – – – – – – – – –
label | 6338928d-e074-54cb-9f3c-11a80325a141 |  | note | RESPONSIBILITY: Nominated Authority
label | 44f34830-8dd0-51f9-9b33-69a85c75f1af |  | note | – – – – – – – – – – – – – – – – –
label | 44f45f1c-ae05-5342-8b6c-1be6ac9e11ac |  | note | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | 0df6f47e-f85e-5b7f-b9dc-77667b3d9a2b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 681fb432-530e-58ac-af25-eaf1917953d9 |  | note | REFERENCE: MRPA Quality Management Plan
label | 15e89e84-e83a-54a6-afe0-a35491cad461 |  | note | – – – – – – – – – – – – – – – – –
label | 732dd6e1-745b-57d7-a24b-ee916e569d01 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 680b97b4-c3ed-5d59-acaa-8c53d0730abe |  | note | – – – – – – – – – – – – – – – – –
label | 6d876135-66b4-5549-955d-1539ae7c6928 |  | note | METHOD: Document Review
label | 7e902bcb-ac38-561f-9841-1e99c909ea5a |  | note | – – – – – – – – – – – – – – – – –
label | e64f47ab-b14f-53f5-aae0-fe8177f45b02 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 08bb4ab2-0702-58fb-916d-87ca8947838a |  | note | – – – – – – – – – – – – – – – – –
label | e1f5500a-9673-5539-828c-a9e48382f795 |  | note | CATEGORY: HP*
label | 69f21e10-6cd6-5a17-a703-dc066c0d46b6 |  | note | – – – – – – – – – – – – – – – – –
label | d98eb0fe-ddbf-5b13-b237-989ab46c02ec |  | note | RESPONSIBILITY: PE
label | cf743bf5-17b1-5fbe-a231-8ffcccbf817b |  | note | – – – – – – – – – – – – – – – – –
label | a1927ae5-d1e8-5578-9607-ba85632ba99a |  | note | VERIFYING DOCUMENTS: This ITP
date | 6ee37e75-2a38-58dd-84eb-5f739d35c300 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 01835ab7-f82a-5ace-82a0-f426d326f9ae |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c5352df0-bb0a-52dd-a345-c8be499cf59d |  | textbox | Name:
text | 4df9ed7c-f7db-5634-8501-fa6b20f42c80 |  | textbox | Position:
date | a8acc463-2cff-5655-a5c3-576d7ef680e2 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-106-RAIL-SSB-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-106-RAIL-SSB-OHLE Wire Regrading Rev 0 | 6e7846ae-e24d-4d39-8a81-a9f6134d8075
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 8de54cd4-256e-5be9-bf65-908760af92d6 |  | note | Document Title: ITP-106-Rail-SSB-OHLE Wire Regrading
label | 0173dcda-9f4a-5484-8372-7e9f756d9b86 |  | note | ITP Description: OHLE
label | f82d15e1-4cda-5e70-82c2-f1e783aca1ba |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 125f75bc-088f-5c1d-9f6f-8a625716b9f7 |  | note | Discipline (e.g. CIV/STR/RAIL): OHLE
label | fe67e6af-66b9-5db5-a15a-d1552f189d51 |  | note | Revision Number: 0
label | ee515a32-9e01-58cc-97fe-7ad23c1f6104 |  | note | Revision Date: 26/06/2023
label | bbac6e7a-dc5a-5a47-bd6c-6a86c8d47562 |  | note | ITP created by: Nikhil Siram
label | 2c265608-5309-55b2-814c-fda78193ef46 |  | note | 1.1 Overhead Line Electrification
label | 2f8cc59a-1656-5e4b-942f-e4bb9e4ffb98 |  | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
label | 3a2c2a1a-30cc-5bae-a740-70c789a05698 |  | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 518b4d20-978e-5575-934e-397640590d9d |  | note | Reference: VRIOGS 001 AS 4100
label | 24b42bfa-9112-5254-90ad-14fb011468eb |  | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
label | ad145d9c-69da-5b28-b1fd-4d09880793e1 |  | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1)
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Procurement Materials delivered/collected to stores/Site.
label | 32c7e9d7-eef2-513f-ab30-697b0cc8bcf6 |  | note | REFERENCE: Contractor - Site Material Control procedure. Cat5 Material received -Camms and Camms Tracking sheet
label | 7979c0ff-c668-5901-9c62-e3498f3b848e |  | note | – – – – – – – – – – – – – – – – –
label | 114a9586-69b7-55c2-8109-0c2f2a4968cd |  | note | ACCEPTANCE CRITERIA: Ensure materials are delivered/collected as required. Certificates of Conformity provided by MRPA
label | 6c251d2d-82b3-5928-93ad-3ca43be7195a |  | note | – – – – – – – – – – – – – – – – –
label | 89022edd-a91f-589f-88a5-be988d0b65fb |  | note | METHOD: Document Review
label | 65090fa0-0130-5fa8-af10-9d005a9c6240 |  | note | – – – – – – – – – – – – – – – – –
label | d0e35f51-8a59-5174-bc34-524611f272db |  | note | FREQUENCY: Once for each supplier, prior to works start
label | 9fc43839-2aa3-55db-ac8b-e64a7f08a622 |  | note | – – – – – – – – – – – – – – – – –
label | b4d3bd8c-1383-5c56-9562-055e82d86276 |  | note | CATEGORY: IP
label | 0e707311-bbb1-5314-8860-bb63353848a7 |  | note | – – – – – – – – – – – – – – – – –
label | ee967925-bd7b-50cd-9a39-1f94313e3768 |  | note | RESPONSIBILITY: MRPA Issue CAT5 Receive
label | d494ff61-1c43-55cf-98e2-1990d89f5ddb |  | note | – – – – – – – – – – – – – – – – –
label | 8fac4128-e649-5102-827b-713dbed5fc60 |  | note | RESPONSIBLE PERSON: MRPA
label | 6040122e-70d8-534d-a1db-86af4d361e74 |  | note | – – – – – – – – – – – – – – – – –
label | 1df21b99-980c-59cf-90ef-8d4304749753 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | f176856d-420b-5744-b63b-da6a8ba0eacd |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Produce Work Package Plan
label | 1fcdb60b-77d4-5b37-a4bf-5dd3302840ff |  | note | REFERENCE: Work Package Plan WAP_BR_184
label | 5637db4b-72c4-5f20-a58a-389f79f45d19 |  | note | – – – – – – – – – – – – – – – – –
label | 26a914c2-72e0-5dbd-9916-1b39e166bd5d |  | note | ACCEPTANCE CRITERIA: Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | 45ba5fac-ad2a-52d4-83d5-624af939f715 |  | note | – – – – – – – – – – – – – – – – –
label | 107b1085-28aa-50f4-99c9-e4a611910be8 |  | note | METHOD: Document Review
label | 85f7bdae-147b-5f12-92c1-e71ad6910ba1 |  | note | – – – – – – – – – – – – – – – – –
label | 73e1ca89-4f69-5852-9f13-1a124b3ff193 |  | note | FREQUENCY: Prior to Works Start, TBC in accordance with MTM Standards
label | 95330590-c241-583a-8178-ae647d55cfb9 |  | note | – – – – – – – – – – – – – – – – –
label | d996192c-f66b-5c80-ae22-93a1281c6df4 |  | note | CATEGORY: HP
label | c695fb30-5351-56dc-8251-caaa4f801de1 |  | note | – – – – – – – – – – – – – – – – –
label | 83a8dd56-9094-504d-99e8-cbc868956ad2 |  | note | RESPONSIBILITY: MRPA/CAT5
label | e83d086c-5886-548f-8bd6-f8294d5cf238 |  | note | – – – – – – – – – – – – – – – – –
label | cc1495af-3b6f-554f-a3e3-a7bc60a3c107 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 068eab42-87c1-5c6f-b5a1-8ecbd8de1a99 |  | note | – – – – – – – – – – – – – – – – –
label | 288330c6-7a1e-5150-8c7b-a7698679abe0 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | dd5f1f44-faa8-578d-b068-1667b4b929f3 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Approval of IFC drawings
label | 553c38a1-98a5-5f97-873a-db178efd365f |  | note | REFERENCE: Contractor Design Management procedure. MRP-DPK-089-00-ETN
label | d21d21fb-e0de-58de-b6dd-d223c74f3bcd |  | note | – – – – – – – – – – – – – – – – –
label | 6c9f6581-c6e9-5b8c-8ef9-1d5f2bbd369d |  | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
label | 0e68750c-ad34-55e3-993b-551f37b3bbeb |  | note | – – – – – – – – – – – – – – – – –
label | 068ac861-7289-5264-8971-0f0f7c460bf0 |  | note | METHOD: Document/Drawings Review
label | 843a8784-e260-52ca-9554-950e75f7535b |  | note | – – – – – – – – – – – – – – – – –
label | c1df354e-03ee-5050-9f23-3df0e0270dad |  | note | FREQUENCY: Prior to Works and at regular intervals. TBC in accordance with MTM Standards
label | d8ce4062-1f55-5f56-b00c-e3bbb183daba |  | note | – – – – – – – – – – – – – – – – –
label | 177049d9-310c-5eb8-a618-3ccd4013ff5d |  | note | CATEGORY: HP
label | e8b5a6ad-ab2f-5723-b5cb-ead8d1fe3a30 |  | note | – – – – – – – – – – – – – – – – –
label | 61c0d0f3-220a-563a-8315-1b3c3eeddec5 |  | note | RESPONSIBILITY: MRPA/CAT5
label | a78200c7-7882-5ab0-bb78-03d1fb6b4f83 |  | note | – – – – – – – – – – – – – – – – –
label | 0c9b721f-46b4-5ae6-9bf0-a8b6d9b5581d |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 3abaf707-4826-5aef-95bd-8e306eeffc9f |  | note | – – – – – – – – – – – – – – – – –
label | 9464ce7e-b759-538c-9fe6-045788e04f9a |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 0cf1c1e1-eb5b-5491-9d8f-28b38e74313c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Task Specific Permits
label | ae27d8d4-3507-59dd-9fed-1061d3744b8f |  | note | REFERENCE: Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
label | c221506d-b619-5996-8cfa-df750721c906 |  | note | – – – – – – – – – – – – – – – – –
label | e502e688-1544-53eb-a9fd-9491d0a1f21a |  | note | ACCEPTANCE CRITERIA: Ensure all task and activities have relevant permits issued and received.
label | b20c7aa0-914b-540c-a2cf-bab0636f0576 |  | note | ○ Task Permits to be generated and signed off by appointed person.
label | 899c0f35-5368-5910-bf2c-389fa8078357 |  | note | ○ Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | 44f25b51-3b24-5cca-9f61-1c39b0fd4cf5 |  | note | – – – – – – – – – – – – – – – – –
label | 4c43779b-3fe1-5071-bc2a-a5e6a7e0fa54 |  | note | METHOD: Visual, Document Review
label | 6dfc9e8f-9a93-5cfd-b298-8fe226577404 |  | note | – – – – – – – – – – – – – – – – –
label | 43452a32-5ccf-5919-9a29-e92b73946346 |  | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
label | 6ee19b3a-548d-50d8-907e-e0744fdc2571 |  | note | – – – – – – – – – – – – – – – – –
label | 3412af54-87da-5793-8773-51e60194b48b |  | note | CATEGORY: IP
label | 05b2dc91-32c5-5212-9f9d-9b5be3f29896 |  | note | – – – – – – – – – – – – – – – – –
label | 1d32d0b8-ecc8-5e16-8fe0-0293ab9ee556 |  | note | RESPONSIBILITY: CAT5/MRPA
label | c0358cfa-911c-5cb8-be81-863a3c2d87a1 |  | note | – – – – – – – – – – – – – – – – –
label | 88c2e217-b225-54b3-8486-924c0dcc4971 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 0581c454-2fb8-5773-bcd2-ceec6066b462 |  | note | – – – – – – – – – – – – – – – – –
label | 9725c8bc-3ccc-5755-95c8-b1cb00e4b515 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 13f7910a-8d55-57e6-847e-6fe9a6d4e5af |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Cantilever assembled.
label | e4ed99bb-fdc2-51fe-bf4e-9f7975ad00c7 |  | note | REFERENCE: Cantilever assembled as per IFC design.
label | 3323c665-e782-58a3-9d26-677b7431f049 |  | note | – – – – – – – – – – – – – – – – –
label | ddaaced1-766f-5864-9e00-42051247bd56 |  | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | 2303c2c9-16f6-5717-a706-251f4f4f9eb1 |  | note | – – – – – – – – – – – – – – – – –
label | 533f681f-a287-56da-a411-964b90b365a3 |  | note | METHOD: Visual, Document Review
label | 767013c8-0348-51e6-aa31-94586a892c43 |  | note | – – – – – – – – – – – – – – – – –
label | dce2d28e-fefa-54d2-beff-77afaecb3e18 |  | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
label | 2c6a60d7-6601-525e-b551-454ea839d747 |  | note | – – – – – – – – – – – – – – – – –
label | 2f320419-687f-5b5e-8e19-1328e0c76663 |  | note | CATEGORY: IP
label | b2ec7724-e884-52ec-8d84-e5bd5202b2e8 |  | note | – – – – – – – – – – – – – – – – –
label | e53cf6f1-9e40-5885-87c5-7cd9bfd89ab3 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 67f52306-b995-5bf3-b4c7-e20c076d03cb |  | note | – – – – – – – – – – – – – – – – –
label | 6dd885a9-98f3-5837-b487-d47fd3e07119 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 32cbf425-d65e-5634-bf4a-48921d1c7ab0 |  | note | – – – – – – – – – – – – – – – – –
label | 7b014b0c-7b0c-5c61-b21b-73129141d952 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 1e28cdfe-7df8-54f5-b857-92ab69b478f8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Pre-Installation check
label | 7be86ea6-2510-5d27-aac6-5f17425c823f |  | note | REFERENCE: IFC wiring layouts, IFC cross sections and BOQ. Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | 4aa4cd36-c961-53c6-9afb-67e13a95acc7 |  | note | – – – – – – – – – – – – – – – – –
label | 294713f9-6cb5-5d4c-87c3-4bab1ad574a1 |  | note | ACCEPTANCE CRITERIA: Ensure that locations matches most relevant IFC drawings
label | bdfe59a5-21f7-5888-b7df-32c764f14133 |  | note | – – – – – – – – – – – – – – – – –
label | 22ef5149-e66d-5d36-9d34-c42ced376a9b |  | note | METHOD: Visual, Document Review
label | d2dff423-2012-545c-8e88-8f49aaeeac4b |  | note | – – – – – – – – – – – – – – – – –
label | 79c92b22-b3dc-5f92-b08a-3c0a99676783 |  | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
label | 2009504e-f06f-54d1-b291-1cf099bba634 |  | note | – – – – – – – – – – – – – – – – –
label | 7b4d8bbb-240f-5297-968f-76d8c4c380a8 |  | note | CATEGORY: IP
label | 78dd1877-ceae-524c-89b1-285f27f494fe |  | note | – – – – – – – – – – – – – – – – –
label | 1db834f3-efa9-5d7a-972c-e38a5b9ab614 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 5d151510-1ece-5123-bcb3-53347e42ecea |  | note | – – – – – – – – – – – – – – – – –
label | 43820e00-4971-5827-9dc4-b478bcd10151 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 9125e1a4-a2cc-5013-b49c-c48fe1355092 |  | note | – – – – – – – – – – – – – – – – –
label | e5855140-622a-5ccf-aa30-b42b9798312e |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | feddfa15-c3b0-5efd-a18c-05ec373b9c63 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Cantilever installed.
label | 0977ba1c-bd4a-5ff1-898e-af6365a57368 |  | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | 35e7173f-9fb3-56f2-b376-fbcd33ebd602 |  | note | – – – – – – – – – – – – – – – – –
label | c7920609-f574-5fb6-ac27-0a521c525007 |  | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
label | f08acc08-5f2b-5994-88a5-85c522fc1ae6 |  | note | – – – – – – – – – – – – – – – – –
label | 043671a3-f2d8-5daa-a044-c23f41fadea0 |  | note | METHOD: Measure, Visual
label | a68914bb-239b-5a35-a9ee-5b5ee9672fcc |  | note | – – – – – – – – – – – – – – – – –
label | e58bb989-c05b-588a-8467-3add1a3e4aa1 |  | note | FREQUENCY: Each OHLE Structure
label | 0fdf4cf9-e8dc-5997-a4b9-8c58f8352bc4 |  | note | – – – – – – – – – – – – – – – – –
label | bed921fb-b0e6-5c1e-acf6-4677a5570aec |  | note | CATEGORY: IP
label | 5c95b3e2-83c1-5e73-91dc-fc035a17aec1 |  | note | – – – – – – – – – – – – – – – – –
label | d2866877-cc29-5fea-960d-43cb654a68d8 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 1e8136a5-7ba7-5877-8a18-f3cf89220a17 |  | note | – – – – – – – – – – – – – – – – –
label | 5ba04593-b48f-5900-9407-303a0f2d94df |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 553fad17-5b11-5638-b3d4-fe9ea57a2195 |  | note | – – – – – – – – – – – – – – – – –
label | c52f2c90-8ed2-5b75-8a2a-3705436da32e |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 84e33ea2-0477-53a4-b0f3-6c255f4c8c7c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Install SPS to correct height / position relative to track
label | 680192af-6c94-5168-b841-82639eefe045 |  | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | 43fa809c-dbbe-5200-99f4-783a40187beb |  | note | – – – – – – – – – – – – – – – – –
label | 9aec2775-b28b-5650-983e-fd60d6597867 |  | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | 00f15125-6a05-5f5b-b943-ecd75a3b46f5 |  | note | – – – – – – – – – – – – – – – – –
label | 53809025-0e6c-5de1-b538-3515b90507af |  | note | METHOD: Measure, Visual
label | badbe591-0096-516b-8ca7-0818cfa9e72c |  | note | – – – – – – – – – – – – – – – – –
label | dd108c07-805c-5c43-a0b2-2a9ad7c9b95f |  | note | FREQUENCY: Each OHLE Structure
label | 09c4ad43-577e-5fad-aa17-55562dfb34b5 |  | note | – – – – – – – – – – – – – – – – –
label | eba10c0a-5f06-502c-aacb-147ccff2824c |  | note | CATEGORY: IP
label | c3ffa07b-06b1-5f90-924b-718347eedb9a |  | note | – – – – – – – – – – – – – – – – –
label | e37ca71b-bbaf-54b7-bc86-e2df990539f5 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 0a872d52-5590-58ed-b388-c7bafb7cd917 |  | note | – – – – – – – – – – – – – – – – –
label | c4fdfa2b-7a97-59c5-9032-a14be5b120c6 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | b67d9055-10ad-535a-92f5-0c90db208e44 |  | note | – – – – – – – – – – – – – – – – –
label | f1ae3bed-496a-56fb-a23b-f9982b0976d9 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | c29b6f6c-fa02-5990-bfe3-ddf845ff219f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Cantilever checked once installed.
label | ebfcbd2b-cf60-5031-ab76-c0586b973ed1 |  | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
label | b9e70a90-c6ca-548d-8058-a787ec4428e5 |  | note | – – – – – – – – – – – – – – – – –
label | ff576ec2-7553-5b5a-9e0e-77fdf8b4d7c5 |  | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
label | 9aed3750-eab9-5e48-8256-a1255668c07b |  | note | – – – – – – – – – – – – – – – – –
label | 24cc0f59-a634-583c-b902-3638ab10f6f2 |  | note | METHOD: Measure, Visual
label | a4252b0a-47df-5471-962a-11e00ee0670a |  | note | – – – – – – – – – – – – – – – – –
label | 1ebc1b3c-d70d-52b3-b0c5-cbc8a809b4a7 |  | note | FREQUENCY: Each OHLE Structure
label | 35072d99-9a86-50db-a20b-b88c3682a620 |  | note | – – – – – – – – – – – – – – – – –
label | 421cada0-e034-5b4b-b1f9-066d224aea16 |  | note | CATEGORY: IP
label | 8a345251-64ea-5e52-9e79-2483270509f4 |  | note | – – – – – – – – – – – – – – – – –
label | 054f01c8-3f9f-500c-ad8f-a5bd7cbaac85 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 318af586-a314-5ac0-9cd3-16b53b800c51 |  | note | – – – – – – – – – – – – – – – – –
label | 0776c0c1-bf21-5452-8b5b-f2af07312be4 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | a5afab66-7d88-5b99-ba74-aacb93bf5365 |  | note | – – – – – – – – – – – – – – – – –
label | 82370b4a-45c1-5b42-aa63-4e6812f448d2 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | f6be6c12-673d-5c02-a693-40ca78c20079 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Installation of wire supports at the correct height and stagger.
label | 6ecb80ae-7eb1-5f73-8e07-ff8ede5d36d8 |  | note | REFERENCE: Install as per design drawings.
label | fe123e1b-74b7-5b17-a6ff-e7af6287fa41 |  | note | – – – – – – – – – – – – – – – – –
label | 322a3dea-d32c-5252-862e-5075514366d1 |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | 3ab2580c-61f0-530d-86c4-dd6b69e60fe5 |  | note | – – – – – – – – – – – – – – – – –
label | 716e87d3-7144-55db-90ce-8c42f1c4ad9f |  | note | METHOD: Visual
label | e35442d3-df82-5cfa-9862-a45b04f80736 |  | note | – – – – – – – – – – – – – – – – –
label | 3edf960e-8d79-5d51-9319-25648ff149c1 |  | note | FREQUENCY: Each OHLE BWA structure
label | c79a7e90-36e3-5e34-a6d3-0ee73ba02bcc |  | note | – – – – – – – – – – – – – – – – –
label | 9a3f639a-693a-5cb7-a79a-72e8387d4c04 |  | note | CATEGORY: IP
label | ec8cf4e8-675a-53e9-84e0-9aa250b8877c |  | note | – – – – – – – – – – – – – – – – –
label | 303a6443-59d9-5c17-a12f-c79db2f6a0e1 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 1c959f16-8150-54d3-8b17-2d12635a2c4d |  | note | – – – – – – – – – – – – – – – – –
label | a0e3f832-1fbe-5f61-82dc-be037c0c3186 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 9b7f0be7-ea90-5469-a8e2-7cf325175640 |  | note | – – – – – – – – – – – – – – – – –
label | ffee7b0f-856e-50da-ae59-2c8309116ee7 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | fe121d03-29e1-51ed-a21f-39aa40526832 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Installation of small parts
label | 75ac6e90-cccd-579b-b87a-b3c0f5058697 |  | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
label | 9034acdc-fe77-549e-a22f-a1f822c68af9 |  | note | – – – – – – – – – – – – – – – – –
label | 37dabfe6-79ca-568b-bf8e-59836efa353d |  | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
label | f97be056-c43c-50ea-957b-b4b2b15ba24d |  | note | – – – – – – – – – – – – – – – – –
label | 74a62932-fa5e-539e-9342-c4aa453ee8da |  | note | METHOD: Measure, Visual
label | e0d13fdd-c6e8-54b7-bfcd-52394ee5b042 |  | note | – – – – – – – – – – – – – – – – –
label | a039bc2e-34ee-59cd-83f5-be9676d11ce4 |  | note | FREQUENCY: Prior termination
label | 11efae9d-84a4-59ad-9b81-3c2ae36b2150 |  | note | – – – – – – – – – – – – – – – – –
label | 00fb76c9-d31c-5c53-8a8a-1ece75133153 |  | note | CATEGORY: IP
label | 2ea0546e-4f44-5603-bb17-53a0c5625855 |  | note | – – – – – – – – – – – – – – – – –
label | 7edc3398-d9d4-5d20-bfa4-6da9e7f2b858 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 5c0768d7-3874-5682-950e-bf1ab7444bf8 |  | note | – – – – – – – – – – – – – – – – –
label | cb03a1b2-4a19-5ba9-989e-b279bd49f87a |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 4214bc4d-ea95-5353-be25-aa59a5c4cc9a |  | note | – – – – – – – – – – – – – – – – –
label | b950d760-c0b1-5b07-abe0-9ff3cf7d46b3 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 808ae318-e5fe-5e11-840d-102e0b61679b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Complete Clearance Checks
label | aaf8e40b-7380-5aec-b41d-d9233a8b74dd |  | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
label | ef994ccd-1304-5ae3-ba78-88742f1eaa6c |  | note | – – – – – – – – – – – – – – – – –
label | 1a2f2d08-0324-59f1-b9e6-2e92fe0c1c3c |  | note | ACCEPTANCE CRITERIA: Visual inspection for clearance and wire staging from Hirail EWP
label | 8e5ad01c-29a6-50ad-93e7-4a50fbd121db |  | note | – – – – – – – – – – – – – – – – –
label | 362aca34-d3c1-5d6e-bab5-bc7449b27ef4 |  | note | METHOD: Measure, Visual
label | 223756cb-2c60-592e-8385-2d1832519767 |  | note | – – – – – – – – – – – – – – – – –
label | 5b59f61a-06fc-5c7c-a5b7-881c7d5b1a7d |  | note | FREQUENCY: Prior termination
label | 1ee6bf9e-ceb1-5911-a58c-92f850eb908b |  | note | – – – – – – – – – – – – – – – – –
label | 2c79ed84-5b41-57ce-b72a-c183cae1d99e |  | note | CATEGORY: IP
label | b150012f-ce1f-55e5-9a50-c2f539536956 |  | note | – – – – – – – – – – – – – – – – –
label | ffb920ca-3d5f-5e6e-89e7-6cd951d3b660 |  | note | RESPONSIBILITY: CAT5/MRPA
label | a1aa9c1a-7b9f-5350-ab34-dad47f6ef5cc |  | note | – – – – – – – – – – – – – – – – –
label | f3adc9cd-68fb-573f-af0c-f3e83ff475f5 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 6c9d9092-bff3-54ab-8f58-e5a34135e05e |  | note | – – – – – – – – – – – – – – – – –
label | b0fb4232-c40e-5e72-b0ac-9985b693adf9 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | abe7122a-88d3-5d12-b9ff-abcd9e166387 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Comnplete Pan Run Test
label | c90bbf56-12fa-5b08-acc8-ce47a16f3e9d |  | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
label | ca6ed2b2-3d8a-5502-8654-0e163899291d |  | note | – – – – – – – – – – – – – – – – –
label | 49f0f55f-5eee-597e-aad4-3cfd1b931dfc |  | note | ACCEPTANCE CRITERIA: Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | bf991b64-19f2-5d5d-8f62-9ce6a4367fed |  | note | – – – – – – – – – – – – – – – – –
label | 75fdf6ab-80db-5746-b6ec-1ea28402e97b |  | note | METHOD: Measure, Visual
label | 34c931e0-13fa-5f92-8751-67f9182d0f9d |  | note | – – – – – – – – – – – – – – – – –
label | 79d8a5f1-316f-5097-8941-d13a73f5b10f |  | note | FREQUENCY: Prior termination
label | ac37f645-ae95-54d5-82ee-64fb46ca1aa3 |  | note | – – – – – – – – – – – – – – – – –
label | d48a166e-16da-52d7-9570-8b4b62547d26 |  | note | CATEGORY: IP
label | 6f54ab35-b6d7-5171-a6e0-c97a85a3c5c2 |  | note | – – – – – – – – – – – – – – – – –
label | c9d58b3b-3729-5680-8e41-ff3375e2f8a7 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 6ecfe790-589c-5edd-a849-d5401de36a2a |  | note | – – – – – – – – – – – – – – – – –
label | d73499a7-9413-5bca-b1df-f66eb6297b5b |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 474248f5-7631-59f2-b71d-f082b3b6703f |  | note | – – – – – – – – – – – – – – – – –
label | 7d45b0fd-a82e-5df6-93cf-87b5c72c0dcb |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 27af6476-ee76-5f73-8c78-865fc37081a7 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Defects/Temporary Works
label | 60f32d68-bb50-59e5-8ecc-d1cbceb54790 |  | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
label | 9ef517f9-ea66-58b4-bf29-f52425a52252 |  | note | – – – – – – – – – – – – – – – – –
label | 53af6d5f-8b6e-5b3d-8e27-2609babfa44c |  | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
label | 10c49235-1c19-553d-9fae-314f7272c367 |  | note | ○ Defect list to be provided at the end of Occo identifying planned work to rectify
label | de2cc0e2-0504-528b-b71f-83ea692ff521 |  | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | aba03e6e-a7fa-5b89-944b-5e431657ca24 |  | note | – – – – – – – – – – – – – – – – –
label | 3c6fa44e-6ab0-5f4c-a6b6-ad1798fc8ae8 |  | note | METHOD: Document Review, Visual
label | 377b46c5-7272-5bc8-b3b9-bf26665fff91 |  | note | – – – – – – – – – – – – – – – – –
label | 0c8555ba-c95c-5759-8f70-8a2bfda8f521 |  | note | FREQUENCY: Each OHLE Structure
label | 09035ba6-c9ca-5ecd-a3d4-d90e696bef1e |  | note | – – – – – – – – – – – – – – – – –
label | 4f4c1c50-cbff-5c8a-9fc5-e7717d4c3516 |  | note | CATEGORY: IP
label | 1d51441c-88c5-54fa-89ad-2d2a9138c577 |  | note | – – – – – – – – – – – – – – – – –
label | 5dc962cf-872c-5d84-b3a3-712a5e58c2b6 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 95b6197e-589a-5684-9f31-ae3dd6cf7805 |  | note | – – – – – – – – – – – – – – – – –
label | 8f80780a-8b7d-56f9-bbdf-f4fd45d1c926 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 5c07d9a8-7809-5752-8a2e-2e000b5a924b |  | note | – – – – – – – – – – – – – – – – –
label | 3ff0be60-ba58-54ff-992a-80e6542ea7bd |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | b0d7b6e3-f71f-5014-ba19-95193fbfccbd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
label | c9fb323a-8579-5ae8-95b2-535a0b391467 |  | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
label | ed3536f4-dd4c-59cd-ae30-e4fb7dbc783d |  | note | – – – – – – – – – – – – – – – – –
label | fde08d7e-952d-5840-823d-8144a6307329 |  | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client. As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | d5a70258-abe5-5e29-ad19-6221c4afdc2b |  | note | – – – – – – – – – – – – – – – – –
label | 8489ffab-7437-5a31-a85e-8c04a9f9421c |  | note | METHOD: Document Review, Visual
label | 25a8fb9c-1dbd-52f1-9bc2-e328965a9fc7 |  | note | – – – – – – – – – – – – – – – – –
label | 6e8cbbd0-248e-5792-8308-a29a2c46dec3 |  | note | FREQUENCY: Each OHLE Structure
label | b347afe7-892e-5ba2-8ed2-0f737f5eb7ea |  | note | – – – – – – – – – – – – – – – – –
label | ff6ded0a-509d-502a-a25a-75a6cb73bd93 |  | note | CATEGORY: IP
label | c2868694-2498-52bb-b7be-10f486999484 |  | note | – – – – – – – – – – – – – – – – –
label | 66f99049-1cb1-5c52-89a3-70a9e07798b3 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 0c6594c7-6b61-52a1-bfbe-910197798316 |  | note | – – – – – – – – – – – – – – – – –
label | 125bd639-befa-5888-b5ca-adf0dfc786f6 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | e156902c-babb-5310-8535-024c8dacfb35 |  | note | – – – – – – – – – – – – – – – – –
label | e41236ad-e8ae-5915-9d60-6504a96e2d39 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | e02c92ef-6094-5386-85b2-4aa33eea0035 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 63f8b3e0-4dc5-575b-8467-b4eb20f8e5a4 |  | note | REFERENCE: MTM Quality Management Plan
label | ecbbc35b-f273-5ac0-bfa1-36a00e9b9d61 |  | note | – – – – – – – – – – – – – – – – –
label | 10d75c11-0393-5a34-a675-aa5fdc2acab1 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 00ffc811-6368-55ec-b24a-c873467f9ada |  | note | – – – – – – – – – – – – – – – – –
label | c0599f81-f10e-5903-80d8-06d24b674bcc |  | note | METHOD: Document Review
label | 7d5f31ad-21be-504f-ad8a-adda40a9343a |  | note | – – – – – – – – – – – – – – – – –
label | 9bd6e7c5-2150-54c1-8c5b-0eda4f4f5106 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 096eba4e-ba95-51c4-a2fa-a101c607b4e9 |  | note | – – – – – – – – – – – – – – – – –
label | 697eb82a-857b-5a68-9cf3-a4bf8a406b80 |  | note | CATEGORY: HP
label | d93e89cd-3184-5973-a14f-080879603bb3 |  | note | – – – – – – – – – – – – – – – – –
label | fe5e2659-08cb-583b-9cb8-de8041ebd8a3 |  | note | RESPONSIBILITY: CAT5/MRPA
label | 942c71b1-7beb-582a-98c0-04c5d27b089e |  | note | – – – – – – – – – – – – – – – – –
label | c14d8b72-3ce6-5b19-8756-ced89cff6d02 |  | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
label | 9e15c119-c995-59a3-99af-4354d3414dd2 |  | note | – – – – – – – – – – – – – – – – –
label | de667435-563c-51b5-a3a2-e59f2add4801 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | e6d6c50b-a341-581b-8388-e00ec243398e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | d7da4bf3-81dd-59a6-b208-b80678e74b9e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d9c77843-bb8b-59fd-871c-590705eee9db |  | textbox | Name:
text | 2e7992c4-29a9-5050-a52b-88c0fb754fcc |  | textbox | Position:
date | 16cdf6b0-3cf4-5ecb-a978-ae5c978a032d |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-111-CIV-SSB-Type A Fill-Road | itp |  |  |  | Yes | ITP-111-CIV-SSB-Type A Fill-Road Rev 0 | 7710b727-a508-445a-a3cf-8ec8891cb8d7
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 7b0ed01d-9e0b-597b-afe9-a2d538472855 |  | note | Document Title: ITP-111-CIV-SSB-Type A Fill - Road
label | 6fe550ff-54ba-5d42-b23f-df913b180904 |  | note | ITP Description: SSB-Type A Fill - Road
label | 5422bfce-4876-56f3-b3c3-1d18c601e2b5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | a98a1fa1-b9c0-5f71-8e74-fb43b938dada |  | note | Discipline (e.g. CIV/STR/RAIL): 111-CIV
label | 7c288a76-7a42-59ad-a854-2982329dfcee |  | note | Revision Number: 0
label | 7214c815-d3fd-5df7-9cbb-3b089280e258 |  | note | Revision Date: 24/11/2023
label | a2b2170c-4a14-5bb6-b995-b38f41794ad9 |  | note | ITP created by: Hiruni Wickramarathne
label | 7438f737-42ec-50b3-83e7-d21fc2d0d8a5 |  | note | ITP approved for use by: Victor Mira
label | f04380e6-eea5-5900-aa28-8fe12b139f70 |  | note | 1.1 Non Dependent
label | b304ae4f-f74b-591d-aa72-af80b6d87b3f |  | note | Reference: IFC Drawings VicRoads Standard Section 176 (Sept 2008), VicRoads Section 204 (Dec 2015) Code of Practice RC500.20, Code of Practice RC500.5
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Material Conformance
label | 6acbc758-3ac4-58c5-8d91-6d8ec4425cdc |  | note | REFERENCE: Section 204.04 b) Table 204.041
label | 20b259fd-04bd-5cfa-beeb-c6400f6c1b0c |  | note | – – – – – – – – – – – – – – – – –
label | 0ab54a7f-d13e-52fc-9626-831e2bee91c6 |  | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 8814ed27-cb56-5c47-b8df-1f796d7b44c5 |  | note | ○ Assigned CBR≥ 6%
label | c618994f-d815-5619-ad3e-9a59a56a2e78 |  | note | ○ Swell ≤ 1.5%
label | 694f3ddf-68e9-54a3-83dc-4479451a0e81 |  | note | ○ Permeability ≤ 5X10-9 m/s
label | 69006073-20fb-5fcc-a3df-1dd9f8ce972e |  | note | Grading:
label | 74bce88b-c0af-5212-9be7-465a0d7e3c24 |  | note | ○ 75.0mm 100%
label | 78b3a598-0963-57d1-918b-ba7ff61f0e0e |  | note | ○ 4.75mm 40-80%
label | 4f903566-f292-5f96-bf58-5b891e2ba92c |  | note | ○ 0.075mm 10-40%
label | 2963c0cf-ee05-58a8-b763-155017182ead |  | note | Reference: Material approval in Teambinder:
label | 3b66f8b4-f673-51cb-a246-f7d152767690 |  | note | – – – – – – – – – – – – – – – – –
label | 736640ed-1f3b-5f7f-a696-519dff88f0f6 |  | note | METHOD: Document Review
label | baa79aea-e7f4-5a81-997a-62185a24c3fe |  | note | – – – – – – – – – – – – – – – – –
label | 5b07538f-43e2-5702-a1d7-58e685dfc7a4 |  | note | FREQUENCY: Once, for each material type
label | 7273d381-0e52-52fd-9d72-7c3735bfb239 |  | note | – – – – – – – – – – – – – – – – –
label | 619a3365-2507-5146-8966-f72f7806eb51 |  | note | CATEGORY: HP
label | c3c02877-a7b1-5cb0-82e0-5eae89dff17f |  | note | – – – – – – – – – – – – – – – – –
label | 1983c06f-c615-5d61-b7dc-5bf901de9029 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | ad568569-8f14-550f-a411-5d225eb74987 |  | note | – – – – – – – – – – – – – – – – –
label | e1fad065-288b-508f-8d13-516c56dfa2d3 |  | note | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
date | b3af119e-c18c-5984-85d5-f99fe9ec98fc |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Pre-Commencement of Fill Works
label | 4a08799e-7c61-593f-9d0c-5ee8d6e9cffb |  | note | REFERENCE: Section 204.10 (b)
label | b3f33c00-1d58-505c-b28e-880c5bc42226 |  | note | – – – – – – – – – – – – – – – – –
label | 3fe2711f-3dc3-5b55-bc56-7e1862865da4 |  | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | bac81c96-bc7a-5ce1-bf65-8f8eb7b93209 |  | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | a779dc1c-c10b-5fd4-9b1a-e15cae73b8e8 |  | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 08724628-a985-5364-8842-a39f09b268b8 |  | note | Reference: Subgrade Preparation Lot Number:
label | e67b390f-237f-518a-af4f-40afc039af30 |  | note | – – – – – – – – – – – – – – – – –
label | 50664ae8-9536-5293-91e0-c9a455a8f831 |  | note | METHOD: Visual Inspection
label | 7d3ea42b-02de-5cbf-9146-0b6945bd0257 |  | note | – – – – – – – – – – – – – – – – –
label | 6e3eab20-2014-567d-badc-f8f5d3d9ce1d |  | note | FREQUENCY: Prior to commencement of fill works
label | 108d055f-61cd-57ec-9167-e04e1100f0f0 |  | note | – – – – – – – – – – – – – – – – –
label | 68d97ba9-f134-5278-ab2e-6fa2b854273f |  | note | CATEGORY: HP
date | 64c2ede0-5d98-5e4e-b854-b799a4232c28 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out
label | fed94f2f-3a7f-50c1-bc9a-a3827c566d82 |  | note | REFERENCE: Design Drawings
label | c9137c68-7d3e-5b85-b4d5-047c01d397f0 |  | note | – – – – – – – – – – – – – – – – –
label | 779f660a-e905-5840-9141-4c42ffe5fd3e |  | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | 650150fd-074c-5dbd-878f-1c92c1328e02 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | e77a37e2-84ca-5053-a62f-a3f6cbe2ff94 |  | note | – – – – – – – – – – – – – – – – –
label | 74f2e95e-0046-585a-b4dc-f6e7ee3d5a3e |  | note | METHOD: Visual Inspection
label | 719bad39-89ca-5a05-b1b5-9cb111b2abcd |  | note | – – – – – – – – – – – – – – – – –
label | 470d44b0-9cf7-5649-b6e4-27c87efaac82 |  | note | FREQUENCY: Each lot prior to commencement
label | c551f42d-cb62-5511-b91f-6d61640db3c7 |  | note | – – – – – – – – – – – – – – – – –
label | e0358141-1b7d-5c8f-9e2c-d953682f3ff7 |  | note | CATEGORY: HP*
label | 49809648-97c5-5d43-8e09-ed90024ecd4c |  | note | – – – – – – – – – – – – – – – – –
label | 2bee308f-f3b1-55f7-8746-ec9b49ffface |  | note | RESPONSIBILITY: PE
label | fa242a4d-fcc9-53a6-a185-87c46b4c76a3 |  | note | – – – – – – – – – – – – – – – – –
label | 5fa6a548-9979-5791-89e6-b5582839f85a |  | note | VERIFYING DOCUMENTS: Signed ITP, Lot Map
date | 67553c64-6303-5111-8772-943dd997657c |  | date | Date Completed:
checkpoint-group |  |  | section | Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 Placing of Fill
label | 60492459-c74d-51e3-b789-2b25ab1be999 |  | note | REFERENCE: Section 204.10
label | ea2fd678-a0f6-58bb-8331-53415d6768b4 |  | note | – – – – – – – – – – – – – – – – –
label | 7173c115-5896-5419-801e-1b935abf5038 |  | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 2f486c07-30b2-5e82-9a57-5dc655d62562 |  | note | – – – – – – – – – – – – – – – – –
label | 13503d29-6960-5b2a-b6bb-18ac62c2d570 |  | note | METHOD: Visual
label | e1c80533-1e2e-5d99-80ed-197a8257ba19 |  | note | – – – – – – – – – – – – – – – – –
label | d322a590-a1a6-5172-be0f-da69208948b0 |  | note | FREQUENCY: Each Lot
label | 01550c45-da43-5399-834d-a6c96a110d43 |  | note | – – – – – – – – – – – – – – – – –
label | a283b000-c03e-5d4e-8890-128fcadb5418 |  | note | CATEGORY: WP
label | 0a335f52-eadf-5e79-a2bb-c34d3ea3dfa5 |  | note | – – – – – – – – – – – – – – – – –
label | b3ae8c3a-0f85-5058-9d5b-6432b25409d9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 871041d5-6484-5904-8699-2dcde80cabdf |  | note | – – – – – – – – – – – – – – – – –
label | 16f86063-14b3-5d45-b939-0edf0dc45b1e |  | note | VERIFYING DOCUMENTS: Sign ITP
date | fc6ddce3-abca-56de-bd25-7eee676748d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Test Roll
label | 8840c685-d301-5cfa-8d01-0b01e70d6f46 |  | note | REFERENCE: Section 173.03, Section 204.12
label | 0c1b5e23-8c4b-5df8-915f-dd001de84c08 |  | note | – – – – – – – – – – – – – – – – –
label | 64fe781b-ab5c-5022-a0cc-cd592c91f1dc |  | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 46219b2a-72f5-540f-96d3-b345a06c7e94 |  | note | – – – – – – – – – – – – – – – – –
label | 0d9af085-ddf2-58c1-be3e-eccdac2665ed |  | note | METHOD: Test Roll as per 173.03
label | ba8d83e6-5976-5b68-9a39-d2ab6627d309 |  | note | – – – – – – – – – – – – – – – – –
label | cf2b24ef-6f02-5913-aa5a-1b386f12b413 |  | note | FREQUENCY: Each Lot/Layer
label | 5d58a843-7843-5b28-bab4-d79be91a175d |  | note | – – – – – – – – – – – – – – – – –
label | 6a88659c-6568-5248-a1e1-7b0f83cd726b |  | note | CATEGORY: HP
label | eed56307-6388-5c39-a412-32e2549f6e27 |  | note | – – – – – – – – – – – – – – – – –
label | 0995a9da-db55-5dc3-9bcf-465365aa3346 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | c0895674-ff20-5a66-b0dd-b73868dfaa0b |  | note | – – – – – – – – – – – – – – – – –
label | a9b83bbb-1926-5407-9e72-e9db5b0f974a |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 72da1e38-9bb1-5362-a1ec-bc9e7b0df082 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Compaction Testing
label | f451855a-855d-5d07-9e6b-0ef6c8b0c9be |  | note | REFERENCE: Table 204.131, Section 204.14 c) Table 204.142
label | 3a496e3f-dbdd-500e-be23-dbf86fe5dc97 |  | note | – – – – – – – – – – – – – – – – –
label | a2225958-b491-501b-a058-ccfe27744a7a |  | note | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
label | 218292b8-3d16-58a0-ad73-70be755fd97d |  | note | ○ Standard Compactive Effort
label | 038b2eb8-3b1f-5b3e-9d2f-36814476c34e |  | note | ○ For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | b4706ebb-6546-5ea9-8f30-8ca8d2550000 |  | note | Compaction and Moisture content
label | 5a3a0ec1-16df-51b4-9f1b-ec4bd4f0056f |  | note | Scale A: Characteristic Density Ratio 99%.
label | 99f1c526-eefe-572f-85e7-a8ff58b51c1c |  | note | Scale B: Characteristic Density Ratio 98%.
label | ff0b6cdb-8f0c-5d7e-afd2-5aa2d62e2c71 |  | note | Scale C: Mean Value of Density Ratio: 100%
label | e21a7543-ef78-599f-b4f6-2a9203d8990e |  | note | Lot size - the lesser of one day's production or 5,000sqm
label | 59615c60-9771-592e-acb4-40cca4aad1bd |  | note | ATTACH: COMPACTION TEST RESULTS
label | 80955259-9b2e-5c4f-a76a-cb95cfd7d059 |  | note | – – – – – – – – – – – – – – – – –
label | 5a24eabb-1115-5dca-bebd-ae809e75bafe |  | note | METHOD: Review Document
label | faac6a7a-2cb0-5a71-abfd-978ca4f226da |  | note | – – – – – – – – – – – – – – – – –
label | 4939a9c6-09ac-5687-aa23-4ef6b1df9a1c |  | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 2b322580-a443-5b13-bbe3-66487754c7de |  | note | – – – – – – – – – – – – – – – – –
label | aa614b63-c0d0-59a4-a0ff-c5950a813f11 |  | note | CATEGORY: IP
label | c0916bba-1737-5a6e-a14a-c44f4f2f4dae |  | note | – – – – – – – – – – – – – – – – –
label | 4c0d724a-3c0e-5984-88bb-3b3d409ac88e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 22ba17a5-0883-5ea2-b51f-00e606a8a5e5 |  | note | – – – – – – – – – – – – – – – – –
label | c2a4570f-9e23-5f9f-a932-88e0bf614e66 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
date | c012431a-0700-55ba-ad65-a9b491e48c74 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Preparation of final surface
label | e9353454-f7fd-5450-be8c-352c21a21e64 |  | note | REFERENCE: Section 204.15, 204.03 (g)
label | 44fee8d8-838f-53b4-b555-56ac10af2953 |  | note | – – – – – – – – – – – – – – – – –
label | 43cf727f-3709-5eaf-8370-189abdb74580 |  | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 87c8fc5f-d69a-559e-b29b-6a1a3e5b7a5f |  | note | – – – – – – – – – – – – – – – – –
label | 4aebfe75-02eb-59d8-ab9e-e729682b451c |  | note | METHOD: Measure
label | b733d541-0c66-50bb-a3d1-66bff4d4721d |  | note | – – – – – – – – – – – – – – – – –
label | 7e85bae6-9d56-5246-bf1e-c2faaabee780 |  | note | FREQUENCY: Top layer
label | b391a4d4-e1d3-5594-998e-11f2f4cf1ff6 |  | note | – – – – – – – – – – – – – – – – –
label | 483edbbb-df70-54f6-910c-21bd01a1bab5 |  | note | CATEGORY: IP
label | e54b36d9-47da-5c42-8b91-6028680475a7 |  | note | – – – – – – – – – – – – – – – – –
label | e6fb281e-5c96-5013-a938-500c42dc1d85 |  | note | VERIFYING DOCUMENTS: Signed ITP
date | 0d80a005-ab7c-504d-9023-14a577259da1 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.2 Survey Conformance
label | 9c097bef-69ad-5139-8848-04f1fef504d4 |  | note | REFERENCE: VicRoads 204.03f,g and h
label | 45b9427e-0fa7-5633-83a9-e0bb8709ee6e |  | note | – – – – – – – – – – – – – – – – –
label | 995d00e9-931f-5531-9042-240c317d9276 |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 741f145c-eb18-599f-b9b3-88c314dc5907 |  | note | Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 3df30cdd-810a-589f-b5fd-fd0b6466a6b6 |  | note | – – – – – – – – – – – – – – – – –
label | 89ca628a-1c89-54e6-9a77-e61bf9e58691 |  | note | METHOD: Document Review
label | 74c5f0d6-65c9-5cff-aa88-dd698bff4286 |  | note | – – – – – – – – – – – – – – – – –
label | 3a5ae890-0dc2-58e3-9ef0-667481f0b5f3 |  | note | FREQUENCY: Top of Type A/Verge
label | 4e42c783-bbbc-5e9b-8bc6-197c2d727e50 |  | note | – – – – – – – – – – – – – – – – –
label | 0298cd73-dd40-5b0c-8e39-7ffa095b04c3 |  | note | CATEGORY: IP
label | 85fe74a4-e5c8-50b5-a0d4-1d072c42e666 |  | note | – – – – – – – – – – – – – – – – –
label | 1091be68-223f-5b20-915d-59820a05bea1 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 97b60292-6e5d-55f8-8127-16a49c96735d |  | note | – – – – – – – – – – – – – – – – –
label | ae4b5b3f-43fc-5298-ade3-316d961caeeb |  | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
date | 09648b85-dbdd-58f0-8c5c-095b0ba71843 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | f97f234b-687c-5f43-a574-a46115951f20 |  | note | REFERENCE: MRPA Quality Management Plan
label | 4a8b89ba-9c0f-537c-bd86-2d1c711b1280 |  | note | – – – – – – – – – – – – – – – – –
label | 97c60bad-e515-5611-abf5-9f1684c25fbe |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 1d350e50-a689-5ddb-93cf-b211d729a2e9 |  | note | – – – – – – – – – – – – – – – – –
label | 9201dcc2-2cd3-59bd-b552-c9d7b0b4fdb5 |  | note | METHOD: Document Review
label | e4e1c6f5-10d2-5d0e-bbb3-f8c90ce722f6 |  | note | – – – – – – – – – – – – – – – – –
label | d3637be9-0153-503a-8588-6d8b550d8c0e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 6301a7d0-0800-52f0-a115-aec07c437b0e |  | note | – – – – – – – – – – – – – – – – –
label | b313e75b-b42f-5e8b-88b9-896c5d576daa |  | note | CATEGORY: HP*
label | f82d6b40-706b-51bf-9d5e-08016ac8e899 |  | note | – – – – – – – – – – – – – – – – –
label | 97a3de9d-ce43-5e8a-8650-6dfc126a1744 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7f13bf6d-f681-50a7-87d5-b191293c12b2 |  | note | – – – – – – – – – – – – – – – – –
label | ff6ee77d-a0f6-59b3-a707-a7c4b29d7eda |  | note | VERIFYING DOCUMENTS: This ITP
date | 6b4f6877-b1c9-566a-b869-1890ae6b5d1c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 689d0967-d554-5b51-9756-696bd1dc47ee |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2ace93ea-daca-5f74-ae4e-3657a2ae19da |  | textbox | Name:
text | a46217eb-0ba3-5b9e-880d-73e786916a2b |  | textbox | Position:
date | 19089550-f35f-5e85-9eaa-fb62f588ace5 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-156-STR-SSB-Precast Barriers and Kerbs Installation | itp |  |  |  | Yes | ITP-156-STR-SSB-Precast Barriers and Kerbs Installation Rev 0 | 9170ed7b-cf17-4f3c-a3f9-ff77fbe27fab
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | d08aa2f1-ec01-50aa-aba1-1235a862e4ab |  | note | Document Title: ITP-156-STR-SSB-Precast Barriers and Kerbs Installation
label | 9871d9a4-143e-5b28-98b0-6f9c0a613e3f |  | note | ITP Description: SSB-Precast Barriers and Kerbs Installation
label | 4efa41c6-cb84-5a78-a7b5-cc4a5ed0fd44 |  | note | ITP Number: 156
label | a468f3f8-34a1-5e51-b5b2-7147b0dafae2 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | d1c87a08-9041-5dcc-a539-800005b9fe3b |  | note | Revision Number: 0
label | 374252c5-a706-5d90-ae02-d9f91d5e1eab |  | note | Revision Date: 1/05/2024
label | e303e248-a83a-59b0-8cb6-d885d48eb710 |  | note | ITP created by: Justin Kreinberg
label | a64f6df6-f028-5634-a46a-0108d18b4520 |  | note | ITP approved for use by: Victor Mira
label | 33dcdf65-9d41-5ff6-bd64-5a1013d3b362 |  | note | 1.1 Non Dependent
label | f480890f-5854-554c-a91f-c8a43e079856 |  | note | Reference: VicRoads Section 610 Feb 2020
label | 497d3184-110f-532d-b712-96bf99d40c9d |  | note | 1.2 Non Dependent
label | fa8c50b3-42ac-5c61-bc1a-026e1032bb2f |  | note | Reference: VicRoads Section 620 May 2009
label | fec758ce-b9ce-5217-8132-fb2e45e71115 |  | note | 1.3 Non Dependent
label | ea427b1d-5b38-535d-866a-11258e35bf2d |  | note | Reference: VicRoads Section 630 October 2013
label | 7960a660-ab89-5532-9195-f73cbc838d3a |  | note | 1.4 Non Dependent
label | e58d37a1-1d95-5a6f-805e-c4748637024e |  | note | Reference: VicRoads Section 670 October 2013
label | c80244be-8808-5cb1-a5db-9e118b6ba908 |  | note | 1.5 Non Dependent
label | f3e29cf4-fd8a-531f-b5eb-4e7f89e18b76 |  | note | Reference: VicRoads Section 671 October 2013
checkpoint-group |  |  | section | Preliminaries Materials
checkpoint-status |  |  | checkpoint | 2.1 Grout
label | d9c31691-15db-53fe-bf0a-4460632626e7 |  | note | REFERENCE: MRPA Quality Management Plan
label | 897082e3-6c5b-5c44-98e3-afa85493ba02 |  | note | – – – – – – – – – – – – – – – – –
label | cfb1fc95-65d5-5712-9174-971f195f5761 |  | note | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
text | 5747774a-aac1-5835-9bde-8518846ab133 |  | textbox | Enter: Teambinder Material Approval number
label | 1d1f6d5c-0a17-59ad-af5a-beed817951a5 |  | note | – – – – – – – – – – – – – – – – –
label | b043a557-46d0-53b8-8e3e-daad11a4d363 |  | note | METHOD: Document Review
label | 59a75825-e9f0-5a82-9989-e4f8ee3668f9 |  | note | – – – – – – – – – – – – – – – – –
label | 79be6cbc-aa5b-55ec-8a0c-0ea9e9194364 |  | note | FREQUENCY: Once, for each product
label | 330eccba-1ecd-59bc-8705-a06820e43ee2 |  | note | – – – – – – – – – – – – – – – – –
label | 2e6b0a4f-b3ac-53d6-8c5b-cf21945ac2e1 |  | note | CATEGORY: HP
label | 883c18a5-dde5-5013-bce0-835e6ebf36e5 |  | note | – – – – – – – – – – – – – – – – –
label | 52f4866a-e633-5efa-9845-1cd72055e0ed |  | note | RESPONSIBILITY: Nominated Authority
label | 2c0aa53d-7d28-5561-a096-26b0e196f66f |  | note | – – – – – – – – – – – – – – – – –
label | 296155c7-ee95-5412-a3a4-83f35e91ac8e |  | note | VERIFYING DOCUMENTS: This ITP
date | 1dcaa853-6f68-5a88-b186-e38db95b9859 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 212db1cc-e885-5d3b-ad65-33b0f1c60a3e |  | note | REFERENCE: IFC Drawings VR 610
label | 0def5f1a-2df3-5a33-b71e-984a508c9ffd |  | note | – – – – – – – – – – – – – – – – –
label | bd8076fc-bc4a-501e-bae5-6a50e4c989d8 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 42cc1acc-0590-555e-bfc4-7f98f670153b |  | note | i. Certificate of Compliance / Birth Certificate
label | 58fae1c4-4758-551c-a3ae-d1a7f537315c |  | note | ii. Compressive strength test results
label | 8465121e-dfff-5546-b193-a50d202c2acb |  | note | iii. Precast Lifting Design
label | 35f6719c-fa3a-5e0f-afe8-c4bac0281bc0 |  | note | iv. Pre-pour check sheet / ITP
label | 1765c278-d8a3-53f1-b388-0d5ac0f50e51 |  | note | v. Post-pour check sheet / ITP
label | ac14feaf-1437-5cc6-947c-f9ca29ef9ec0 |  | note | vi. Covermeter check record
label | 454f2c8d-f57d-5502-bf77-919ccc5a7218 |  | note | vii. Record of dimensional measurements
label | 1d36bfbe-14a7-574b-bee8-6159b1b7e46a |  | note | ○ These documents are typically stored in a MDR Lot in Team Binder.
text | 415c1537-6250-5bc8-912e-e0fb7cd73a69 |  | textbox | Enter: Teambinder Material Approval number
label | baa9e7fe-c299-5f13-bc95-1a5cbfe12fd9 |  | note | – – – – – – – – – – – – – – – – –
label | 769a1579-9884-5be3-9133-82006ca0b7c2 |  | note | METHOD: Document Review
label | 1b4c3d04-ec91-567d-a4b3-481871314f2c |  | note | – – – – – – – – – – – – – – – – –
label | 23527bdd-87dc-53e5-bccc-d2bbdb09e1a2 |  | note | FREQUENCY: Each element
label | 97b69a18-9617-55c2-9688-1d91fbc2c870 |  | note | – – – – – – – – – – – – – – – – –
label | da34425f-bfbf-5e80-83d9-5808dc8399c0 |  | note | CATEGORY: IP
label | 9a136184-f72e-5708-ba6c-7206b64ad6c4 |  | note | – – – – – – – – – – – – – – – – –
label | 802f9335-0923-5299-8efa-e9d26936393b |  | note | RESPONSIBILITY: PE/SE/SPE
label | f4e19438-ee47-51de-8723-28fb568e22cc |  | note | – – – – – – – – – – – – – – – – –
label | 36041fbb-d043-5dfc-9bc2-6d9ee2d896cd |  | note | VERIFYING DOCUMENTS: This ITP
date | 22337557-5074-5de5-8881-6876117344b9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Bridge Deck / Foundation Compressive Strength
label | 79b9a041-bb08-5f60-bd48-fcf36e91c1dc |  | note | REFERENCE: 671.03
label | 5a86c4fb-6108-5427-b4e9-4ab7ffa5e3b0 |  | note | – – – – – – – – – – – – – – – – –
label | f8f86eb9-0d13-55fd-9ae7-eaa70fde4408 |  | note | ACCEPTANCE CRITERIA: For Preccast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | c7be1a32-0d1b-57c9-8875-c54d15e6570f |  | note | – – – – – – – – – – – – – – – – –
label | 01af9b90-5988-5900-ae54-7ff1790f0582 |  | note | METHOD: Document Review
label | 3b6436bb-c2da-5e28-a0b8-c540112a39c0 |  | note | – – – – – – – – – – – – – – – – –
label | 01bc298b-6f59-562e-b709-775aab7cb097 |  | note | FREQUENCY: Each installation location
label | 4a545cdb-20ab-5b08-b112-a967f8e41efb |  | note | – – – – – – – – – – – – – – – – –
label | fae8789a-97fd-5968-8c05-51a059285f3e |  | note | CATEGORY: HP*
label | ef74b91b-8204-55d4-9ba3-5254aa4f0aca |  | note | – – – – – – – – – – – – – – – – –
label | 85fe9594-03c9-509a-8df7-2b8dfe96efb8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 00a9bb9e-1471-5a8e-a8c2-23e864d87d22 |  | note | – – – – – – – – – – – – – – – – –
label | 688d418a-735d-58f4-9d5a-5ab45fc94a83 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2c29e3f7-2979-546d-8bfb-8bcaf0d28af8 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out of Precast Elements
label | 5d25c919-e0a2-5a7e-9506-d0ab67a065a8 |  | note | REFERENCE: IFC Drawings
label | 4c6d807d-cc40-50f9-8f9d-25aa8237268c |  | note | – – – – – – – – – – – – – – – – –
label | f737cbb4-6927-5848-b2a2-bcbda5811f09 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | 2a4cf415-344c-55ff-bbe1-b01a2d4373fa |  | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | 072240fe-efe7-5bc8-9516-b174a3e84833 |  | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | 4370a4df-ff61-570d-89c2-e9db6ec30c3a |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | e6dab796-f949-51b6-a2bd-3009cf069406 |  | note | – – – – – – – – – – – – – – – – –
label | f827b912-8b6a-5768-86b7-809571e960f2 |  | note | METHOD: Measure, Visual
label | 376a3c45-091d-550b-8a61-2f560b6da77d |  | note | – – – – – – – – – – – – – – – – –
label | baaa1f12-722c-5ea7-b22d-a1c5d4186be9 |  | note | FREQUENCY: Each element
label | 231e0b48-ff43-535a-a02c-04e4fecf470f |  | note | – – – – – – – – – – – – – – – – –
label | 3eb67ac5-89f7-5fc2-9f0e-5688ba60f236 |  | note | CATEGORY: IP
label | 2639531a-6e57-5d7d-9ccc-16c2b412fc90 |  | note | – – – – – – – – – – – – – – – – –
label | 61fc81cd-1c65-56ac-b928-20dc66234c2e |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | ceae31f5-0239-5567-ad04-f53e2205e235 |  | note | – – – – – – – – – – – – – – – – –
label | 2c2fa844-93f2-5aa1-a772-201d2bbeafde |  | note | VERIFYING DOCUMENTS: This ITP
date | 4be7673e-be95-5341-bd24-a8e1b963d9ee |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
label | 5a4e649e-50bc-519b-b925-dcc71559c019 |  | note | REFERENCE: IFC Drawings
label | aacc70e5-0951-5285-b16b-ba94d01e111f |  | note | – – – – – – – – – – – – – – – – –
label | 5a562736-93fe-5c40-9d0f-5103feca0ff8 |  | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | bc9fe870-a888-559f-8f0d-7df41f6ae840 |  | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | 17843f64-80e9-5673-868b-b58f1de294ed |  | note | – – – – – – – – – – – – – – – – –
label | f239350e-a4f9-5ee1-a47e-610d53f05a5f |  | note | METHOD: Measure, Visual
label | ad4d2245-084b-5124-ae92-ceffc214175b |  | note | – – – – – – – – – – – – – – – – –
label | 2d445f2d-7370-533f-b34d-a4202d62da28 |  | note | FREQUENCY: Where applicable, each installation location
label | d07ff0c0-715c-5a2b-bad1-c894106b37d6 |  | note | – – – – – – – – – – – – – – – – –
label | 15a53bac-54af-54a7-90d6-17961937e1f9 |  | note | CATEGORY: IP
label | 84a2eda2-ceab-5390-9838-cc0eb3fdda8f |  | note | – – – – – – – – – – – – – – – – –
label | f9ddf73b-9a5c-59b1-99ac-254891c06763 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | f18aa401-6fc8-5cd4-ae64-36fc9f95c0f9 |  | note | – – – – – – – – – – – – – – – – –
label | 9a79476a-0877-5ad7-ad0b-39e4467f2fd1 |  | note | VERIFYING DOCUMENTS: This ITP
date | ed23d7ab-91c5-50e2-a15e-500f38695b2f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Bitumen Board and Ableflex placement
label | d7994381-1063-5dd9-9a87-2ba869d4ad60 |  | note | REFERENCE: IFC Drawings
label | 8ffb6549-30f1-5cf4-9b91-a256c6c37168 |  | note | – – – – – – – – – – – – – – – – –
label | ce3ae52c-c789-5484-bf21-fba7c17f1b82 |  | note | ACCEPTANCE CRITERIA: Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
label | 1c189a4a-00b1-5d4a-9aa3-82e5cadf45f9 |  | note | – – – – – – – – – – – – – – – – –
label | 9bdebb63-2323-570c-a6f3-270bf8b5e863 |  | note | METHOD: Measure, Visual
label | b068b5c4-c307-5470-a032-eee631ca4091 |  | note | – – – – – – – – – – – – – – – – –
label | 19933a9d-5352-541e-9bd0-b47045012fdc |  | note | FREQUENCY: Where applicable, each installation location
label | 972f2260-3d66-5b69-8907-cc7b76ddabbc |  | note | – – – – – – – – – – – – – – – – –
label | 1af0f8a1-d99c-5c4b-84ff-f3675f33f07a |  | note | CATEGORY: IP
label | 5d492235-0f1b-5db8-a48a-c10dfdb6c88f |  | note | – – – – – – – – – – – – – – – – –
label | d1940ece-1196-5a2b-8eaa-d7ff4ec6c99d |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 7b163b6c-c2d7-5919-90cc-6add01e117a0 |  | note | – – – – – – – – – – – – – – – – –
label | b5f00aef-eb5c-5a39-b737-b51ffa0382c0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 11d41ad7-b1f4-5f96-8102-f0f2e82fe3f6 |  | date | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Precast Handling
label | b16b9932-ea89-51fc-9ff5-04a744ab2f62 |  | note | REFERENCE: 620.07 Crane Lift Study
label | 8bab09c0-78fb-570d-8343-e50a9dec5cf4 |  | note | – – – – – – – – – – – – – – – – –
label | c7ddbd2b-5684-58ff-a8bf-39ef9b21bb70 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | b16088df-bbbe-58e5-ab52-b7084b84dcab |  | note | – – – – – – – – – – – – – – – – –
label | 97e27757-855c-56a1-b49a-c9b351adeb85 |  | note | METHOD: Visual
label | 05aa8c2a-a691-53a5-8053-cd8b05ac6729 |  | note | – – – – – – – – – – – – – – – – –
label | 814ed8ea-cf9d-504a-9ba0-f0bfee3d291c |  | note | FREQUENCY: Each element
label | 6d17ae64-b91a-5724-b434-08fbb91c88d3 |  | note | – – – – – – – – – – – – – – – – –
label | 6f7cc956-5061-5df2-86b2-dfe598e440ca |  | note | CATEGORY: IP
label | e4c1425f-b3dc-5550-9b21-903e516077c9 |  | note | – – – – – – – – – – – – – – – – –
label | d0bb0266-d364-5039-8db5-6b1c68608ed1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a91aa884-95a4-5318-8700-ce99d2a64a9e |  | note | – – – – – – – – – – – – – – – – –
label | e63bb492-e8e5-5b7e-9c1f-21b311541103 |  | note | VERIFYING DOCUMENTS: This ITP
date | d0d293a5-1744-5991-bf33-1281e2ee8d88 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Precast Placement
label | 6aa883e5-8acd-5585-ad6e-0ffe4c696c31 |  | note | REFERENCE: IFC Drawings VR 670.05
label | d377ad0a-8dd8-5ffc-8245-5ac9e6ab29b9 |  | note | – – – – – – – – – – – – – – – – –
label | acad6687-1f07-5761-846d-82f253a59d30 |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | 4ad4b71f-810a-58e1-b070-ce838b37f815 |  | note | Adjustments to be made to achieve following tolerances:
label | 8534de93-23b7-58c7-89f7-78d9b3654166 |  | note | (a) Departure from plan position: 25 mm
label | bccd160a-0340-531e-b1b4-11f461599091 |  | note | (b) Departure from alignment: 5 mm
label | a099254a-9005-5531-9a06-ebd8ce36f245 |  | note | (c) Irregularities in alignment: 3 mm in 3 m
label | 091bf512-5e11-566a-9812-08a496334368 |  | note | (d) Variation in joint gap width: 3 mm
label | 010caf53-969f-5e19-bdfe-2f8d881c3802 |  | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
label | ca227fa4-f6ba-5d63-8cc8-cc3279e79ad3 |  | note | ○ The nominal gap between elements is as per the IFC Drawings.
label | 2d85e32a-2680-531e-8c56-384e3c012cb9 |  | note | – – – – – – – – – – – – – – – – –
label | b70ed531-2ca9-53bf-981b-8136c03b0bbd |  | note | METHOD: Measure, Visual
label | b565ca51-2143-5551-aa3e-4fc4f99e8700 |  | note | – – – – – – – – – – – – – – – – –
label | 4754f328-af4e-51d5-871c-46c1e6dfe8de |  | note | FREQUENCY: Each element
label | ae3fbde3-7121-56dd-8d5c-5acf47735c35 |  | note | – – – – – – – – – – – – – – – – –
label | 9b523707-1556-5f86-bd2c-5def1d1a5edd |  | note | CATEGORY: IP
label | 683fa12a-9d83-55f2-b989-e0cb2cf5df7e |  | note | – – – – – – – – – – – – – – – – –
label | 6007c060-c802-52ef-854a-f9e4b42639ec |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | f1f646d8-f099-5657-b543-dcdba478dea2 |  | note | – – – – – – – – – – – – – – – – –
label | 1198d8e1-e3aa-5cda-94d2-f5fe7e0d479e |  | note | VERIFYING DOCUMENTS: This ITP
date | bece71ad-a5c3-5144-b212-8c4a06d861f0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 909f7494-e7df-57b0-8a9a-ed9ac09a2c97 |  | note | REFERENCE: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
label | 5fd9c675-1e69-5d67-8b98-76627cc80e40 |  | note | – – – – – – – – – – – – – – – – –
label | 96d55797-09a6-5c28-88d6-625c90e62b19 |  | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | bc19aaa1-e2fa-5c36-8143-a792557d8c40 |  | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | b5d53a8a-fef6-52c6-aa86-0823e510b865 |  | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 3756e90c-fd11-5c34-a01e-9dd5669f78ac |  | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | cc802dea-3dc5-5597-a48e-31d77e4483b1 |  | note | – – – – – – – – – – – – – – – – –
label | b5e5db21-ef9d-52bb-a72b-cd7ff0f3e4e6 |  | note | METHOD: Visual
label | 9d73bf7a-24e1-5891-91bf-d81824955b37 |  | note | – – – – – – – – – – – – – – – – –
label | b6c0a596-ceee-5586-8fa4-4b59d63d5263 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 55ee017b-24c0-550b-bfb7-648ff00880fb |  | note | – – – – – – – – – – – – – – – – –
label | ea566c8e-b421-5b0e-ab37-979ac5d6c032 |  | note | CATEGORY: IP
label | 3394fea0-e4db-5f90-93bd-caaf2080a8a2 |  | note | – – – – – – – – – – – – – – – – –
label | 5dd0161a-d6b5-50f2-b415-1776e3391669 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4e532713-bc88-5efd-aef0-7980d4b2b8b4 |  | note | – – – – – – – – – – – – – – – – –
label | ef525d8f-accf-5fe2-b12b-3adf52dd0805 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6d31b18d-f9c5-536e-8762-81fd753be5f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Precast Traceability
label | c1899c43-9a47-51cc-8e15-c8bfd545c225 |  | note | REFERENCE: 620.09
label | cfee65c2-d6e9-5d26-9115-39233f1bcce8 |  | note | – – – – – – – – – – – – – – – – –
label | cff6bc53-941a-5349-9721-27a754ba0e98 |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | 4efdc115-9825-5711-a5f2-b360d30a54fd |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 577cc9e9-ce93-5691-8049-74a28af7b194 |  | note | – – – – – – – – – – – – – – – – –
label | de4635fd-3637-5a64-8849-586c2cf9b6f7 |  | note | METHOD: Visual
label | 3d8dbe0b-4620-5eda-a480-bd695a0bca59 |  | note | – – – – – – – – – – – – – – – – –
label | 928dd693-3fd8-5490-8e38-bd8183d97203 |  | note | FREQUENCY: Each element
label | a757e125-83c7-5a8f-9236-133eefeb848c |  | note | – – – – – – – – – – – – – – – – –
label | c40c0019-2f99-5471-ad40-c5678207d0bc |  | note | CATEGORY: IP
label | f2b0e0df-923c-52d8-b0af-b6ef388ae9eb |  | note | – – – – – – – – – – – – – – – – –
label | 2abe1246-0a14-5b25-9f02-6e0c4e3a121a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8a725725-5d44-5855-b3e8-ec04f8fdb78c |  | note | – – – – – – – – – – – – – – – – –
label | 51150713-db35-561e-aafb-af68c7eb4ecc |  | note | VERIFYING DOCUMENTS: This ITP
date | f0a7ed74-e3f8-50ba-8131-e97149d257fa |  | date | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flowable Grout Pour
label | f1f8cf08-6279-514b-92c8-1867252d693d |  | note | REFERENCE: IFC Drawings
label | f99d29e0-b9cd-51ad-a1af-0c6c008f3768 |  | note | – – – – – – – – – – – – – – – – –
label | bd5c9479-1e77-5ac0-b7d1-44a4c7ab17e0 |  | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | 7d1d44e4-1ac5-5b09-99dd-779ee4bc9fdf |  | note | Complete: Grout Pedestals & Bearings ITP
label | f0f3b92d-4ae6-5976-a4d2-6d9d3a29edcf |  | note | – – – – – – – – – – – – – – – – –
label | f768359e-c10c-5e59-844b-de35132f0bbe |  | note | METHOD: Visual
label | b7897e26-03fd-5346-b296-6f38b1d12ff5 |  | note | – – – – – – – – – – – – – – – – –
label | 835cb4be-00d2-5517-a846-f4b3f7075927 |  | note | FREQUENCY: Where applicable
label | 212d676f-1221-5437-a4c6-6cd531dcb51c |  | note | – – – – – – – – – – – – – – – – –
label | 4f40ca37-c1bd-5f8b-a31c-ea0c6e167614 |  | note | CATEGORY: IP
label | 9eec3ac5-14d5-5bfc-bb70-0197c801deb5 |  | note | – – – – – – – – – – – – – – – – –
label | c33cd5c6-fec7-5e72-9e60-d1c42c6309b1 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 47d2ea2c-58d1-565c-9e5d-7c16da81aeec |  | note | – – – – – – – – – – – – – – – – –
label | d004b9c0-54a1-5b6d-a1a9-b09d52e707d2 |  | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
date | dc208a95-ff11-5411-9af0-9ccf2b3a6e70 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 8fcfdf65-933c-59df-8e9b-058928d8312b |  | note | REFERENCE: IFC Drawings VR 670.05
label | b7b10e6d-39ec-50e7-ac13-637fb0c0fd4b |  | note | – – – – – – – – – – – – – – – – –
label | 86bbb73f-64c8-5773-a337-ec54ef846dc2 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
label | e1082462-4e1e-573c-97e7-043ec18d1ae4 |  | note | (a) Departure from plan position: 25 mm
label | 1562e99c-1ac1-5d60-8c0f-b1f55b5c9f8f |  | note | (b) Departure from alignment: 5 mm
label | e1c2c53b-9fd7-525d-80d1-ede57b4d2c7e |  | note | (c) Irregularities in alignment: 3 mm in 3 m
label | eaadc785-478e-52fd-af39-7c8cfb9d7868 |  | note | (d) Variation in joint gap width 3 mm
label | fd080306-5d79-5b17-84e3-cad41fca6b10 |  | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
label | d811c141-2967-5d90-ac52-d28d61fa27ff |  | note | Attach: Survey As-builts / Survey Report
label | b60eec08-fd40-5245-a01a-cab9f9c40d66 |  | note | – – – – – – – – – – – – – – – – –
label | 1650f1e5-3c8e-5845-88e4-b410b2346d89 |  | note | METHOD: Document Review
label | 98067528-dc50-5cb6-8c87-85d0bd686291 |  | note | – – – – – – – – – – – – – – – – –
label | def1f1ab-0f5f-50c3-95f1-fe55e118529e |  | note | FREQUENCY: Each element
label | 40ad0144-3650-52e0-9bc8-8030cf7e9944 |  | note | – – – – – – – – – – – – – – – – –
label | 9304a1f9-d068-5d21-9655-fdd52ee9d20a |  | note | CATEGORY: IP
label | 23e39ba4-13df-560b-b5f3-e01fbd8905d5 |  | note | – – – – – – – – – – – – – – – – –
label | 38f1e46f-499a-559b-bcde-bf30d06666e8 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | d5f196b5-52ed-5fc1-9109-f15b736caf1c |  | note | – – – – – – – – – – – – – – – – –
label | 9eaaa39e-0e62-56ca-ac3c-e6947a5b7632 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4b0fed15-e5dc-5857-84c8-e44b2c546b1f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | a2e0d750-7939-54cd-9045-c6755dbc0c46 |  | note | REFERENCE: MRPA Quality Management Plan
label | 96ae413c-aad3-5dee-ab3c-b11bbea989dc |  | note | – – – – – – – – – – – – – – – – –
label | ae721f22-ba9c-545d-8e01-27fc431cad25 |  | note | ACCEPTANCE CRITERIA:
label | 672dc227-e7db-5d6b-a9e1-c4cd279c9918 |  | note | – – – – – – – – – – – – – – – – –
label | 67e870b8-56be-54e1-98ac-0931edb04821 |  | note | METHOD: Document Review
label | fba245fd-b344-53a8-bc4f-b45ce8a3acee |  | note | – – – – – – – – – – – – – – – – –
label | a4117d6b-2996-5ceb-b9d7-17f5902f0770 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 4f983282-98ab-57c2-90f5-ccf4567347f9 |  | note | – – – – – – – – – – – – – – – – –
label | b95009bf-07e8-535e-a4cf-cc28e1d8d1b2 |  | note | CATEGORY: HP*
label | 0cbfd7ce-6138-54d1-8f49-3dad56493898 |  | note | – – – – – – – – – – – – – – – – –
label | 34e1ac67-ba10-5b42-a7b7-a1f8b8274b72 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 5e03a34d-37c6-5be9-92ca-1123beaac769 |  | note | – – – – – – – – – – – – – – – – –
label | 77f000d0-44a4-5d43-9884-8cc135541602 |  | note | VERIFYING DOCUMENTS: This ITP
date | b42b793a-0796-5d50-95a8-58e4596219ad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7facc496-327f-5b68-8e2e-9122e2e8d486 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 9c049553-31f9-5ce2-aeef-fdb4150a70c5 |  | textbox | Name:
text | 7f90c40f-d5db-57a9-b2e4-447187cf8d85 |  | textbox | Position:
date | 9aaa9282-67dd-5ec8-ad41-4f2070c41acd |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-110-CIV-SSB-Ground Improvement (Structural Fill) | itp |  |  |  | Yes | ITP-110-CIV-SSB-Ground Improvement (Structural Fill) Rev 0 | 98988600-f109-4162-9d46-623772bc71ac
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 1afd8c2b-b2fc-5b27-90e6-6832699469d3 |  | note | Document Title: ITP-110-CIV-SSB-Ground Improvement (Structural Fill)
label | 53683786-8133-5c98-a723-1221521b30d7 |  | note | ITP Description: SSB-Ground Improvement (Structural Fill)
label | f0ac5ab0-88ae-58c9-9817-6f02c4a479b7 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | b1e4a114-e4c4-595b-9249-c676fbec1daa |  | note | Discipline (e.g. CIV/STR/RAIL): 110-CIV
label | ca0c9f87-b3ec-50d1-9bab-2c3580f80113 |  | note | Revision Number: 0
label | 8f09148c-3abd-57a4-9cd5-95d714cb6b2a |  | note | Revision Date: 27/11/2023
label | 433cd1d2-249d-5580-8270-9c1bec88ad08 |  | note | ITP created by: Hiruni Wickramarathne
label | 861423c7-08c7-5955-bd2d-723970a7aa27 |  | note | ITP approved for use by: Victor Mira
label | 9a4739ce-3918-586c-a9c7-dc97c8f8d90b |  | note | 1.1 Non Dependent
label | 7455affe-0e39-5be8-a5a2-80a073c222cf |  | note | Reference: VicRoads Section 204 (Dec 2015)
label | a406d50d-8d3f-5d91-84e1-726ae9c1db94 |  | note | 1.2
label | 13925f9a-2948-5064-a7cd-ad191428e97a |  | note | Reference: IFC Report and Drawings
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Material Approval
label | a510e2e7-1d22-558d-89d9-72eb50c491c3 |  | note | REFERENCE: Section 204.04 Table 204.041 IFC drawings
label | bdd63e20-b456-5f00-b3cf-448868df87e5 |  | note | – – – – – – – – – – – – – – – – –
label | 73609ffd-1283-58ef-a223-2d4c0b998b16 |  | note | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
label | 2fdf20c5-ff36-55d9-a3c2-8658f52ae0b8 |  | note | Scale C:
label | 9ee370e9-303f-5fd2-86cb-0e33bdc97ca7 |  | note | ○ CBR ≥ 6%
label | 69989c43-55e6-5d6f-b195-d514a73a8906 |  | note | ○ Swell ≤ 1.5%
label | 2944fc49-ce55-572b-8a1d-410a1bb17a83 |  | note | ○ Permeability > 10-7m/s to allow consolidation (where <10-7 m/s, drainage layer or geonet to be provided)
label | ea8ee84d-324c-52f7-810e-28065639f93f |  | note | ○ PI (LL) = 6 - 25
label | b8f99c52-779c-576d-be4a-9b67bf794564 |  | note | ○ Effective Friction Angle = 32*
label | ee9027d8-7064-5c99-9151-c1e3ce152cc5 |  | note | ○ Effective Cohesion = 0-5kPa
label | d216e45d-00af-5297-8067-4489ad6433cd |  | note | ○ Unit weight ≥19kN/m3
label | ebab351b-ae6e-5990-9b3d-8df465f96bb0 |  | note | Grading:
label | c77dd560-5dcc-55b9-b9ff-0e6fc65a3dd8 |  | note | ○ % passing 75.0mm sieve = 100
label | bcd6644f-1e49-535c-bfb6-fe4cd615d7c8 |  | note | ○ % passing 4.75mm sieve = 40 - 80
label | 247ebdc8-c7b7-56dc-9164-e89ee1aa05bd |  | note | ○ % passing 0.075mm = 10 - 40
text | c8b50c2c-5d3f-5066-97d6-28bd3fce0679 |  | textbox | Enter: Teambinder Material Approval number
label | dff70a35-4f71-5979-8764-328eb96bb5c6 |  | note | – – – – – – – – – – – – – – – – –
label | 14eb9469-a93d-5e3e-a446-f88217aef1ff |  | note | METHOD: Review and Verify
label | 44de2753-fa07-56fa-978f-cd79d848de5b |  | note | – – – – – – – – – – – – – – – – –
label | 79db2307-3391-5c42-a6ab-0dbe064c3d35 |  | note | FREQUENCY: Once per material type prior to commence of works
label | 9661e9d1-3059-598b-a4a8-383f61b8adb7 |  | note | – – – – – – – – – – – – – – – – –
label | d6d210a2-3f85-53b4-b9ce-bebe6970e4e8 |  | note | CATEGORY: HP
label | 06ae8c8a-753a-5a21-a8e5-8f8dc1cbb955 |  | note | – – – – – – – – – – – – – – – – –
label | 96c012cb-ebe3-5015-87fe-9ba76e561d28 |  | note | RESPONSIBILITY: Nominated Authority
label | 951eb720-e9fd-5df8-a4d0-87767cd71789 |  | note | – – – – – – – – – – – – – – – – –
label | 4ecb23de-d31b-5dad-a7b9-ff54bda6fcd8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 9540651b-9946-57ac-aac1-fccc334bcf7e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 1e021484-2172-51e7-a7df-d5e8025d3c90 |  | note | REFERENCE: Section 204.03 IFC drawings
label | d0b96f91-ca32-572f-a7ef-c5053b316193 |  | note | – – – – – – – – – – – – – – – – –
label | 5ceeb57d-2455-546c-87da-a20ca7ad052f |  | note | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
label | a830c4df-4929-56cd-b206-ed10cf0e34d6 |  | note | – – – – – – – – – – – – – – – – –
label | a5b0a3a9-20d3-5e85-bcff-1f4f31dbdeb5 |  | note | METHOD: Measure, Visual
label | ff200919-3451-5dd2-9009-2da4b44404a7 |  | note | – – – – – – – – – – – – – – – – –
label | e9d33901-c549-58e2-bd1c-6227b894a5f5 |  | note | FREQUENCY: Each element
label | 4970237e-7e25-54f2-95da-618a67ade4f1 |  | note | – – – – – – – – – – – – – – – – –
label | f4cc4ec6-1b93-5d5d-bf61-e093966d0f52 |  | note | CATEGORY: IP
label | 7eb42b09-08ac-5e01-962a-d9aa2af3d9a3 |  | note | – – – – – – – – – – – – – – – – –
label | 7f58558d-d228-538c-b283-bd5e575d3c0b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2b307a5a-78c8-5bf0-b251-aa234e72adf8 |  | note | – – – – – – – – – – – – – – – – –
label | e976dd7e-15b2-5dc2-9708-dd0c5d5bcd30 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | c15e0622-c768-5baf-a363-09e47f06e391 |  | date | Date Completed:
checkpoint-group |  |  | section | Cut Activities
checkpoint-status |  |  | checkpoint | 4.1 Subgrade Level
label | d73c7ae8-88c3-5c26-ad46-3235b20019c3 |  | note | REFERENCE: Section 204.03 (g), Section 204.03 (h) IFC drawings
label | d574146e-a297-5b65-9f56-41c9f10c4cb1 |  | note | – – – – – – – – – – – – – – – – –
label | b8d8040c-c53d-5cd2-9c33-f8d793eaf910 |  | note | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant Ground Improvement drawings within the following limits:
label | 9521b8cb-15da-5f1f-b128-e0530ac7b714 |  | note | ○ For Scale C: No point of subgrade surface shall be more than 10mm above or 30mm below the specified level.
label | e8b65c28-e7c7-5103-b2af-18097c7a6dd2 |  | note | – – – – – – – – – – – – – – – – –
label | 25e7e71f-a283-57ca-8898-7bc9ab60e502 |  | note | METHOD: Measure
label | d9980e02-8fdd-5aab-90a9-ea08cefcebf1 |  | note | – – – – – – – – – – – – – – – – –
label | 6ab586ac-5c59-5795-a343-a508afd6378b |  | note | FREQUENCY: Each lot
label | 77aef399-e8e3-5be3-8d06-8b16f9ce39d6 |  | note | – – – – – – – – – – – – – – – – –
label | 3e5ba9bd-6551-5c1f-81b9-d13d290aa477 |  | note | CATEGORY: IP
label | 1e22f16a-de74-5339-9472-ad9fd02ec21f |  | note | – – – – – – – – – – – – – – – – –
label | e9617374-a47f-5c29-865e-c21b7e6d4c20 |  | note | RESPONSIBILITY: Surveyor/SE/Site Supervisor
label | 1c78ceff-e33c-501f-bcea-8d3a5f0b9e51 |  | note | – – – – – – – – – – – – – – – – –
label | 50cd297d-9f5a-51a1-a413-2d064b4a299d |  | note | VERIFYING DOCUMENTS: Sign ITP, Survey Pick Up Report
date | 1dbddeb9-9b54-5374-88ce-21947cfb3d50 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Founding Material testing
label | acd72940-9d9e-5252-b66c-66791f82d5d6 |  | note | REFERENCE: IFC Report and Drawings
label | 2be319f1-95fd-536c-9786-a35dceca0b56 |  | note | – – – – – – – – – – – – – – – – –
label | fce75a44-fb4d-5b98-bffa-32c79522b127 |  | note | ACCEPTANCE CRITERIA: DCP test to be carried out on the excavated surface to confirm the strength of the existing material is in accordance with Deisgn values for relevant chainages as below.
label | 87e6638c-6651-502c-aee2-cac4ba0cdc1d |  | note | ○ Min DCP required /100mm
label | 7900b1dc-bcc2-5e06-acf5-94c0e01da8eb |  | note | ○ 10000-10030 : 5 ( South)
label | f73e6fab-1682-5d86-9617-f0633abaf7da |  | note | ○ 10300-10320 : 7 (North)
label | 0d89a1ea-9e46-5165-a3ff-93f5a2ccb5cd |  | note | ○ 10320-10360 : 6 (North)
label | b1dc253d-c3de-5fb3-8482-8743b283f13f |  | note | ○ 10360-10400 : 5 (North)
label | 7bf7d979-56d5-5788-9b23-2e9362559f99 |  | note | ○ 10400-10410 : 3 (North)
label | 4bc4f8d7-12e1-5765-a130-addbaa21c9d3 |  | note | – – – – – – – – – – – – – – – – –
label | 363c00c4-7108-5dba-a708-37b81c05b82c |  | note | METHOD: Document Review
label | 264b7a8f-4e25-5f2d-9be4-852669423b2c |  | note | – – – – – – – – – – – – – – – – –
label | a2341b73-b5a8-56aa-b565-78f5eead40d8 |  | note | FREQUENCY: Each lot
label | ebd126cc-2aa8-5e72-8b10-581aab350f85 |  | note | – – – – – – – – – – – – – – – – –
label | 8129ee78-3bed-52e3-971a-0a66f012c129 |  | note | CATEGORY: HP
label | db1ddd17-4c93-538e-a6f9-5dc947a1d41c |  | note | – – – – – – – – – – – – – – – – –
label | 8ed05b04-2150-54f6-8425-c88ea414fbe5 |  | note | RESPONSIBILITY: Third party Geotech Engineer /SE/Site Supervisor
label | 43199ddf-10ad-5e45-b105-621b46e99865 |  | note | – – – – – – – – – – – – – – – – –
label | aa95297c-e434-5a68-b32c-dcbd26f4b737 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Test Report
date | 4ad1e089-51cd-555a-a2b8-303ff88f1eb1 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Proof Roll
label | be2b0d6d-369f-5ee0-a6d2-fb05384adca0 |  | note | REFERENCE: Section 204.10 (b), Section 204.12 IFC drawings
label | e932ccb9-4af8-5e24-8c0d-23c8998b16da |  | note | – – – – – – – – – – – – – – – – –
label | 25d93995-8104-5320-85f6-45b7744e26b7 |  | note | ACCEPTANCE CRITERIA: Excavated subgrade to be compacted and proof rolled before any construction.
label | c3c357e2-9d36-5282-a68a-1861661fcf58 |  | note | ○ Withstands Test rolling without visible deformation or springing.
label | 38011b9e-693e-532a-8c8d-150b87f29c9f |  | note | ○ No fill to be placed until the area has been reviewed and approved.
label | 89131125-e049-57fe-8dd4-5eaf23e46a7b |  | note | ○ If Proof Roll fail go to section 4.4
label | f50b1daa-b73c-548b-a33a-2d62a920b306 |  | note | – – – – – – – – – – – – – – – – –
label | 3a064b22-d917-538e-94bf-de3ed9e3381c |  | note | METHOD: Visual
label | 76536e14-339c-5133-a926-b5979c95ef1f |  | note | – – – – – – – – – – – – – – – – –
label | 29a44105-d081-5fa5-b30e-549c5d4ed6d9 |  | note | FREQUENCY: Each lot
label | 0baacbb9-d547-5402-b9d5-3ae47c8e4df1 |  | note | – – – – – – – – – – – – – – – – –
label | 8b57d3d1-9f00-5c75-b1f5-0bc830517893 |  | note | CATEGORY: HP
label | df97a84a-c9d9-52ad-810a-c562da063770 |  | note | – – – – – – – – – – – – – – – – –
label | 18582f35-9017-5399-bebc-f7cd62b2fe4a |  | note | RESPONSIBILITY: Nominated Authority
label | be8dfcd7-0591-5f46-a8b9-4249281ccab4 |  | note | – – – – – – – – – – – – – – – – –
label | 31a02151-9420-5b12-a4e1-51355f8df45f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 92e68391-aed7-5d82-bca6-0633f25d508a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Founding Material Inspection
label | ff88d49f-3a3d-532b-8dc6-f1a57b161f7a |  | note | REFERENCE: IFC Report and Drawings
label | 2b19344b-7d61-522a-999f-bb4fdfa70929 |  | note | – – – – – – – – – – – – – – – – –
label | ed0a4f47-7658-5807-b79a-71b1bedaa3aa |  | note | ACCEPTANCE CRITERIA: Geotechnical Engineer shall inspect founding material.
label | 1e2816f0-58e2-5129-b345-a636bbdce704 |  | note | ○ Any areas in Ground Improvement footprint where proof roll test or bearing capacity are inadequate crushed rock shall be placed and compacted into the excavated surface under direction from geotech engineer
label | 917ba2d4-8685-5b83-b0c8-5235d3cbcf10 |  | note | Attach: Geotechnical Field Sheet or Report
label | a1c07dfd-286a-59b7-a7b5-88a8639d2788 |  | note | – – – – – – – – – – – – – – – – –
label | 1be3e270-3d55-513b-9078-fae9c6793441 |  | note | METHOD: Verify, Document
label | 0b12a377-6a4a-5d93-9304-2046772b2989 |  | note | – – – – – – – – – – – – – – – – –
label | aa0168ba-b447-5e53-ae1a-fb1d39c00bf9 |  | note | FREQUENCY: Each lot
label | 7ce7c7aa-bc68-5780-9352-cbe1077f8480 |  | note | – – – – – – – – – – – – – – – – –
label | 3f294ed0-64ab-5128-a1a9-cb23da4aaeb9 |  | note | CATEGORY: HP
label | 0d2d926d-4301-5ec2-ba7b-c951f6099e04 |  | note | – – – – – – – – – – – – – – – – –
label | 38b06337-cc09-5d24-aff5-bc05cf032ab5 |  | note | RESPONSIBILITY: Geotech Engineer /SE/Site Supervisor
label | 0fbfbb69-799a-55b3-a737-e4f8db96dd1a |  | note | – – – – – – – – – – – – – – – – –
label | 96001f41-6af1-5819-818e-ad07777b8f9b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Geotech Report
date | e0006976-9616-5a43-9913-dfad1435a513 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Fill Activities
checkpoint-status |  |  | checkpoint | 5.1 Structural Fill Placement
label | 47b724af-af6a-5e94-bebb-c315a7a3b204 |  | note | REFERENCE: Section 204.10 (d) (ii) IFC Report and Drawings
label | bebf5eef-07f9-5de6-bedd-fcfc3c9e73bf |  | note | – – – – – – – – – – – – – – – – –
label | c5c5b68c-a30d-555a-a9ac-d2d142aaab93 |  | note | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Extent of fill placement to be as per IFC Report and Drawings
label | d34e4349-7ac3-5bd3-b8cf-6c98887ee3c3 |  | note | – – – – – – – – – – – – – – – – –
label | 20fe646d-c7fb-5f72-aeea-924392351adc |  | note | METHOD: Visual
label | 00b3f737-68aa-5d67-84dd-c1b14e1089c5 |  | note | – – – – – – – – – – – – – – – – –
label | 2df46527-3f35-5eaa-8bf3-139569423611 |  | note | FREQUENCY: Each lot
label | 43128893-aa86-5590-a136-fae5e2354d0c |  | note | – – – – – – – – – – – – – – – – –
label | 3520e48b-5953-5311-850d-7fc88e55ffee |  | note | CATEGORY: IP
label | 584ae2f6-4e1f-56c2-97d1-53dc9e1ce916 |  | note | – – – – – – – – – – – – – – – – –
label | 680f9e89-f221-52b0-9295-de4b64606fb6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e9cd5f7b-e260-5937-91c3-f68a69fabce1 |  | note | – – – – – – – – – – – – – – – – –
label | 4724ae6a-a642-56ed-92c2-b1dec31eec4e |  | note | VERIFYING DOCUMENTS: Sign ITP
date | e561bb69-3603-5fb4-8087-448d6984272c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Keying of Layers
label | 90b823e2-81a6-5e36-89a0-a394af15203c |  | note | REFERENCE: Section 204.10(d)(i)
label | 2af87710-8e47-5be3-be62-583f1ed1d74b |  | note | – – – – – – – – – – – – – – – – –
label | 0cab024f-6831-57ab-9272-3dc703017d00 |  | note | ACCEPTANCE CRITERIA: Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | dcbf9679-0572-57a2-875b-50ece5234e0b |  | note | – – – – – – – – – – – – – – – – –
label | 4f9db37e-1d03-5b68-aef2-600cfff82d00 |  | note | METHOD: Visual
label | bd227242-66b8-5cac-862e-152da96affd7 |  | note | – – – – – – – – – – – – – – – – –
label | 0323d662-7488-5d6d-9090-118145ef15ea |  | note | FREQUENCY: Each lot
label | 83fc03e9-1eca-57a5-81eb-c8f6ff243186 |  | note | – – – – – – – – – – – – – – – – –
label | b94e5e0a-f2fa-540b-93fc-42d65bb215c0 |  | note | CATEGORY: IP
label | 85a68a15-a3ff-5c38-bef6-3f6e8acce801 |  | note | – – – – – – – – – – – – – – – – –
label | c6521853-d1e4-5001-8952-3afa9fe52200 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1601e548-8e74-549f-a629-9332651111f7 |  | note | – – – – – – – – – – – – – – – – –
label | a81c18ed-ac54-538e-8a09-999b10aa869e |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 761cc61f-cc84-5817-9eff-946db0b260b6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Proof Roll
label | 582d882d-6d70-53e6-9333-5bc3768d7081 |  | note | REFERENCE: Section 204.13 (b) (i) Section 204.12
label | 1f45786e-78d7-5581-83a7-65e5d2229300 |  | note | – – – – – – – – – – – – – – – – –
label | 698d111b-a84e-5833-bc73-42c552f55dd0 |  | note | ACCEPTANCE CRITERIA: Withstands Test rolling without visible deformation or springing. No fill to be placed until the area has been reviewed and approved.
label | 273f6889-f33b-5c49-8d57-b38f1cbfb4f7 |  | note | – – – – – – – – – – – – – – – – –
label | b260d8c1-9db6-5304-b475-88576186ea13 |  | note | METHOD: Visual
label | 5e301e87-2d7e-5a82-aef4-7a255cfd2f3d |  | note | – – – – – – – – – – – – – – – – –
label | 40bed61a-d2d5-5075-9ff4-cb705ebe1c8a |  | note | FREQUENCY: Each lot
label | e1a2f962-7fd3-5787-99a6-7211c81521b7 |  | note | – – – – – – – – – – – – – – – – –
label | c03c6c8c-37f1-57d8-83b7-ad574edc5551 |  | note | CATEGORY: HP
label | 8d0f61d1-5e84-50f1-996d-5af8014b0792 |  | note | – – – – – – – – – – – – – – – – –
label | f9a18f2a-2d21-508e-bc9f-5ac577b4dde8 |  | note | RESPONSIBILITY: Nominated Authority
label | 9b294082-94e4-50b8-8c9c-819f71985dd6 |  | note | – – – – – – – – – – – – – – – – –
label | cb5ef388-78d3-5e97-a69e-f1bfb62bbb9b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | d12a86cb-c8df-584c-8d53-e5250250e2fd |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Compaction Testing
label | f49ae573-addc-5ce0-9e23-11615e2efae3 |  | note | REFERENCE: Table 204.131 Section 204.13, 204.14
label | b77684dc-33d2-5798-802f-bb6259ed6aff |  | note | – – – – – – – – – – – – – – – – –
label | cf0b3fd2-f7bd-563b-ad19-b20fc9036cc2 |  | note | ACCEPTANCE CRITERIA: Each Lot to be tested for compaction as Scale C requirements (3 tests per lot)
label | bfb72d84-c7de-5de4-9ef6-86d9bf36310d |  | note | ○ Lot = One day's production or 5,000m2, whichever is the lesser
label | db52f007-4065-50a2-bd61-eedd40436ca1 |  | note | ○ Characteristic Density Ratio = 100% minimum
label | c667cf27-83fb-5013-a057-b02a815b2068 |  | note | – – – – – – – – – – – – – – – – –
label | e3a56e4a-52c6-556d-9fef-3c0078973ab0 |  | note | METHOD: Document Review
label | 0b15da88-2d72-551c-99e2-50d274a73f9f |  | note | – – – – – – – – – – – – – – – – –
label | 9275ac65-05fc-5f9d-b0a3-09f69eac3efa |  | note | FREQUENCY: Each Lot unless otherwise directed by Nominated Authority
label | af52ac44-e047-51ee-9f56-c5d12e3f8349 |  | note | – – – – – – – – – – – – – – – – –
label | 0acfa5f6-0ec4-5fd6-95f1-211b940fb58a |  | note | CATEGORY: HP
label | 3104936e-8c0c-5abc-9fd8-1c00d0d62e3c |  | note | – – – – – – – – – – – – – – – – –
label | e40a5845-ceec-585b-b857-957035041034 |  | note | RESPONSIBILITY: SE
label | b80a5ce4-2fdd-5081-8210-a252e74e59dc |  | note | – – – – – – – – – – – – – – – – –
label | 2247f424-8f3e-5f4b-96db-f6d42f87a589 |  | note | VERIFYING DOCUMENTS: Sign ITP, Compaction Test Report
date | 25485214-6e55-502a-9ecf-726077e38413 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Preparation of final surface
label | 0fb068d8-0b48-5d7c-8b0e-b9d9f076d5f1 |  | note | REFERENCE: Section 204.15
label | be074ba7-673a-5cb7-88c1-a21601d64e5d |  | note | – – – – – – – – – – – – – – – – –
label | 29b186fb-604b-5e4f-9032-0d66f2a983a2 |  | note | ACCEPTANCE CRITERIA: The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | 8e73a86e-3ea5-590c-838e-01a7d110981b |  | note | – – – – – – – – – – – – – – – – –
label | c6d0d504-9ee7-5448-8b1d-d2f589a63c96 |  | note | METHOD: Visual
label | cf7d18fd-7de3-512b-b280-f756d90c8348 |  | note | – – – – – – – – – – – – – – – – –
label | 9ecd34ec-1b3d-5cf9-8f26-4df44326b64c |  | note | FREQUENCY: Top layer
label | 0ec42131-47a7-55fb-9bdd-9870c6965d50 |  | note | – – – – – – – – – – – – – – – – –
label | 62dc43a5-5f27-541e-8f71-64e28d22fd12 |  | note | CATEGORY: IP
label | a615cffa-76b9-5290-9473-7623cf21ef25 |  | note | – – – – – – – – – – – – – – – – –
label | fe17f4b8-a994-5c02-8c06-6fc0190706d2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b63ac9d4-ff61-5208-b841-765d05cc3151 |  | note | – – – – – – – – – – – – – – – – –
label | 9b6b9bf2-42c3-5846-9102-7cb779d5fb20 |  | note | VERIFYING DOCUMENTS: Sign ITP
date | 6e7fa9b1-bd60-57bb-a761-46bb3167f5e3 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 33a1c0ea-a1a5-5ee1-af07-d4a403644b7a |  | note | REFERENCE: Section 204.03 (g), 204.16
label | 35a82db5-0fea-540e-b91e-3e8fbd218ce0 |  | note | – – – – – – – – – – – – – – – – –
label | 0640b48d-6a32-53fa-8202-d8058a76dbbf |  | note | ACCEPTANCE CRITERIA: Scale C: Tolerance: No point surface shall be more than 10mm above or 30mm below the specified level
label | 5b60b06c-5e31-558d-9f70-b1c536e0371f |  | note | – – – – – – – – – – – – – – – – –
label | 8a3a9264-e302-5461-83ef-65e94feed7a2 |  | note | METHOD: Document Review
label | 1a7e16ec-053e-5abe-8ce7-f1b48a960611 |  | note | – – – – – – – – – – – – – – – – –
label | 7f39f077-50eb-5495-9844-9ce28201d061 |  | note | FREQUENCY: Each lot
label | 3b155158-ecb7-5938-a1ea-9af2109e57d5 |  | note | – – – – – – – – – – – – – – – – –
label | 468bbba1-b5c0-56e7-ab61-ad895ba881ca |  | note | CATEGORY: IP
label | dcf3dc1a-5ecd-5d2c-8756-7fda93960a5b |  | note | – – – – – – – – – – – – – – – – –
label | 1183ae2a-8574-5a6e-b460-309b174f6c5b |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 62e3b709-9103-5561-8489-309376b96a7d |  | note | – – – – – – – – – – – – – – – – –
label | d592a512-e97c-582b-b5a1-9763b7cd0841 |  | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
date | 59f2ecc7-6cd7-5653-a824-f7f60072dac5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | bd86881e-ab65-5f78-8e54-469da215f14e |  | note | REFERENCE: MRPA Quality Management Plan
label | 4d303343-9c7e-547f-9204-67f2c6ebf82f |  | note | – – – – – – – – – – – – – – – – –
label | 59475e00-246b-5504-97f4-ba9cc23bcb7c |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 6e92d102-48d0-5477-9340-9ebdc629c1a8 |  | note | – – – – – – – – – – – – – – – – –
label | 3f094878-e993-5a40-bdfc-127c804e0f67 |  | note | METHOD: Document Review
label | b9c231c8-74e0-596f-9233-20a541fddaed |  | note | – – – – – – – – – – – – – – – – –
label | 61dd0102-90cc-504e-bbff-2258129c6eb7 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d800afa2-5e98-5098-b25e-1659e6055684 |  | note | – – – – – – – – – – – – – – – – –
label | b3e33fe9-ae3b-50f7-ad26-d22e81c5b079 |  | note | CATEGORY: HP*
label | c08453ee-2a21-55aa-8245-5de7fc98532b |  | note | – – – – – – – – – – – – – – – – –
label | fb076b9e-f723-5888-a076-d93f92508a61 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f4c1f7bb-4338-531f-b415-4e8bda8c6c0e |  | note | – – – – – – – – – – – – – – – – –
label | b096796a-7fc4-5f86-a5c1-609cc24896ef |  | note | VERIFYING DOCUMENTS: This ITP
date | 081299b4-7023-507c-a76f-b31089c3c15b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 79d44fbd-896c-5776-800a-8bc155655d10 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 241d28f2-92d9-572e-baab-545ef3ee2f1b |  | textbox | Name:
text | d96ac934-92b8-5521-8da0-32863e4c1646 |  | textbox | Position:
date | 91bd161f-e4e2-5896-8e3b-40a67cc1a480 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-058-CIV-SSB-Clearing and Grubbing | itp |  |  |  | Yes | ITP-058-CIV-SSB-Clearing and Grubbing Rev 0 | 9d6a1460-07c1-43a8-8237-58c631a15a14
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 31c2a1d4-2c66-582f-ae55-6a049067cc65 |  | note | Document Title: ITP-CIV-SSB-Site Clearing and Grubbing
label | 7afd9272-d2f5-5cd3-b29a-2e919e2d3c24 |  | note | ITP Description: SSB-Site Clearing and Grubbing
label | ff680ed1-e886-5745-87a9-123881da8364 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 441645c8-52f8-58bd-ba79-f6c9219e971d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 287d55c3-2784-5d46-ae64-f160c01ed66f |  | note | Revision Number: 0
label | 3be47f7e-c6c1-56c5-80b0-661b26e99be0 |  | note | Revision Date: 9/08/2023
label | 42a424bc-1537-56dc-9c9b-cc0cc66840ee |  | note | ITP created by: Jason Lee
label | 0f388fee-3b6a-5f07-a2a8-cd9d186bdcf6 |  | note | ITP approved for use by: Jon De Castro
label | a22a7ca3-e2df-573f-a244-40c1a0d40826 |  | note | 1.1 Non Dependent
label | b69f5641-6789-568d-9839-d5a1eca2f7b0 |  | note | Reference: VicRoads Section 201 (Feb 2023)
label | 381faa81-b369-585e-b4cf-250908514234 |  | note | 1.2 Non Dependent
label | 8bc2ff87-dd5f-56b9-bc12-a4c030bb48e2 |  | note | Reference: VicRoads Section 204 (Dec 2015)
label | c174001d-f089-5c10-8ad6-d1ed5269eb43 |  | note | 1.3 Non Dependent
label | 5d265fef-da7e-595e-8d0f-d77467c9297e |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-group |  |  | section | Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 Environmental Controls
label | 9bcdcdac-d9f7-5655-ad44-2bad0007b2d6 |  | note | REFERENCE: MRPA Environmental Management Plan
label | 96ce087d-4861-50c0-b098-49c68718613a |  | note | – – – – – – – – – – – – – – – – –
label | f05db4d9-491c-5350-b981-d67df7b2d0d6 |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities.
label | f15b63c9-df07-5c12-8c42-07db6e747f5e |  | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
label | c98d9431-3a87-5758-85ec-513166153e79 |  | note | – – – – – – – – – – – – – – – – –
label | 03f75504-815b-5edf-a1f8-f17dfa688cc4 |  | note | METHOD: Visual
label | 020e66ae-8b77-5d03-a7e8-ae484351d3ec |  | note | – – – – – – – – – – – – – – – – –
label | e3f030dc-22ee-51fc-9c83-5509a2609d5e |  | note | FREQUENCY: Where applicable, prior to starting Works
label | 9009c487-b2fd-568f-ad7d-b3f10b7c1be1 |  | note | – – – – – – – – – – – – – – – – –
label | d8b44800-a296-5212-ae2c-51c1083aea4a |  | note | CATEGORY: WP
label | 8a1abdd1-37d0-5143-83fe-ee406696dc24 |  | note | – – – – – – – – – – – – – – – – –
label | ad4f93fc-4c7d-5ed5-8d87-85c0a357ae60 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 396ab0a4-5e74-51f3-9ded-44fd7301d23b |  | note | – – – – – – – – – – – – – – – – –
label | 1d75e653-6aef-5922-b6aa-bcf9f55b9abc |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 1de62e4f-a072-5516-b4cb-e15b68f2e17f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Vegetation Removal Permit
label | 5289ee3c-772a-51cb-8de1-7d40d276e461 |  | note | REFERENCE: MRPA Environmental Management Plan
label | ce5be544-4488-5e79-8b70-3128f1440099 |  | note | – – – – – – – – – – – – – – – – –
label | d9394939-87e0-5198-a546-423dd67c26a3 |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat:
label | 155df37b-2f6f-5ece-aad0-2798f8df1e9a |  | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
label | ea8fee6f-a9aa-5f15-92a6-db86eb2315a6 |  | note | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
label | 072fa043-1509-5d34-929d-30813377eaa0 |  | note | ii. fence and sign all sites nominated as No-Go Zones.
label | 0fcd399d-fe17-5a5d-862e-477d7acf3c9b |  | note | Attach: Vegetation Removal Permit
label | 19e7c9e3-3f81-577b-85eb-c994d9f49f6e |  | note | Attach: Ecologist's Report
label | ee01f70a-4106-52c0-ba9f-0e629f7c8b30 |  | note | – – – – – – – – – – – – – – – – –
label | 14edc8af-049e-56d7-a4e5-742586004bdd |  | note | METHOD: Document Review, Visual
label | 163648ae-0f77-5eed-b6d7-854ad249a390 |  | note | – – – – – – – – – – – – – – – – –
label | 7b7c2dda-d8d1-595c-8fe9-10e60929d976 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | 91341cf5-facb-5bb2-bd58-b97cb879ed5e |  | note | – – – – – – – – – – – – – – – – –
label | 6d22d2db-8fa0-54ce-b5e2-ca4cb5635405 |  | note | CATEGORY: HP*
label | 5dba7b3d-39b4-5078-8629-f5662f886c27 |  | note | – – – – – – – – – – – – – – – – –
label | 0866cc46-7de1-55eb-a95c-70bbaee8b80c |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 6f25588a-829b-55e6-ac76-eb5450a88ec8 |  | note | – – – – – – – – – – – – – – – – –
label | ddf3a782-e3a5-5088-8ec6-b31dd2119dbd |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 1e9bdff7-8428-51bd-ae3e-d9914b6e3576 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out / Limits of Work
label | 9df2ee72-5a6b-5988-b669-c2c9e4e3e58d |  | note | REFERENCE: IFC Drawings Section 201.03
label | c45bc1ce-bca6-582b-9ce0-9d9274291309 |  | note | – – – – – – – – – – – – – – – – –
label | ee22e862-16a8-5553-b967-89b2ba63aaec |  | note | ACCEPTANCE CRITERIA: The limits of clearing and grubbing shall be:
label | b4c60fb8-38a8-52e7-92b2-23747a1895f9 |  | note | a. the limits defined on the IFC drawings
label | f54dd88b-bb1b-5c57-bf8c-094d29a2fc30 |  | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | 31362beb-848f-5b21-854e-d85aa02dfbc3 |  | note | c. no more than the width required for completion of the Work under the Contract.
label | 9d13a548-35f1-5c10-a075-8b3b7bcb029d |  | note | – – – – – – – – – – – – – – – – –
label | ecb2eda9-4c13-59e3-84f5-8742f9da22c3 |  | note | METHOD: Measure, Visual
label | 77590177-7a2f-560a-8b1f-c63eed510c00 |  | note | – – – – – – – – – – – – – – – – –
label | ec3872f3-e713-5fb4-8ebc-dc0463d1dadf |  | note | FREQUENCY: Once, prior to starting Works
label | 97692512-4508-5e10-bbe5-f90ea3687cfe |  | note | – – – – – – – – – – – – – – – – –
label | 5a9e7979-6005-59cb-b81b-bd5ecc2b2bb4 |  | note | CATEGORY: IP
label | a693b7e4-21d2-5b2a-91d6-92918f0e31f7 |  | note | – – – – – – – – – – – – – – – – –
label | 5d701ba1-8372-5e36-a5ed-c8444cd9c941 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 78a39e6c-7154-5ac3-a961-8ed372c0e881 |  | note | – – – – – – – – – – – – – – – – –
label | fe2e8694-3b12-556d-a856-13bbdf5ccea7 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 81c5b90f-f5f0-50b8-9d31-4db1bfed32d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Cultural Heritage and Areas of Significance
label | 1ac195cf-bb93-5941-8caa-279f7a3a61a8 |  | note | REFERENCE: MRPA Environmental Management Plan Section 201.10
label | 68e635b5-65a1-5c8a-b743-78fa2356ac65 |  | note | – – – – – – – – – – – – – – – – –
label | f562a2c6-582f-51e9-a21d-8255e13fda6a |  | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | f80acabd-1a08-5488-89a4-cac6c78597d3 |  | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | 509e98a8-7115-5237-b8e6-cede8122a219 |  | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | 6b3bf29c-4875-508b-b72c-d9a268fe4531 |  | note | Attach: Cultural Heritage Report
label | 11b2f4b7-ef57-5587-b836-8bc7d8157243 |  | note | – – – – – – – – – – – – – – – – –
label | 8da9ad42-ec53-5c78-8673-bda8d6cc18cd |  | note | METHOD: Document Review, Visual
label | fe096d8c-5a8f-5423-9363-572bb3d92104 |  | note | – – – – – – – – – – – – – – – – –
label | 456098f2-62bb-5d20-a3be-60ef54061606 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | f195cb62-7959-560f-be0e-e680f3847468 |  | note | – – – – – – – – – – – – – – – – –
label | 50a58e7f-a424-55f7-afcb-8c976079cc87 |  | note | CATEGORY: HP*
label | 992c253e-f24c-5191-8520-d73f8075a170 |  | note | – – – – – – – – – – – – – – – – –
label | 9d89ea46-4cd6-58fd-b4ab-91436d1a1ca7 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | a26cef06-257d-5534-b185-7d9d62111351 |  | note | – – – – – – – – – – – – – – – – –
label | 558ee11d-0270-5dec-8e29-230c016adf86 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | fdbe8ba1-c445-5025-87a8-cc020b5fac0d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Stripping of Topsoil
label | 1c1a6efb-13af-598a-a0af-7c39c8ebb503 |  | note | REFERENCE: IFC Drawings Section 204.05
label | 1948916a-35fb-5568-be16-b9c738d1127c |  | note | – – – – – – – – – – – – – – – – –
label | 4af300ca-11e6-5bab-a9a6-b84fd2671467 |  | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
label | 9901233d-3f90-5957-8ba2-136beee80e81 |  | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ec840400-b930-56ac-8a06-d44cf5037a67 |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | c8529ead-281b-590a-b412-a4db425cd018 |  | note | – – – – – – – – – – – – – – – – –
label | 2d7918f4-ee1f-54ac-8e8d-534f7ffc4413 |  | note | METHOD: Visual
label | c34c9ecb-472e-5467-a6d9-6fd5c62dabc2 |  | note | – – – – – – – – – – – – – – – – –
label | 323eac5b-fd4a-5893-9ce4-60018cc11c22 |  | note | FREQUENCY: Each Site
label | 5012a42a-e3e0-5cd5-8239-4e42a335702d |  | note | – – – – – – – – – – – – – – – – –
label | 96f70a72-b998-5f8b-9339-7c3ab67d5a90 |  | note | CATEGORY: IP
label | 730b59f6-4e1a-504d-87a8-4b18217571fd |  | note | – – – – – – – – – – – – – – – – –
label | 8540d81f-28ee-51b9-a7dd-39107571e6ee |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | d06cb9dd-91a6-5108-8c4c-65119cf2eb4c |  | note | – – – – – – – – – – – – – – – – –
label | 3df6a9f6-363d-5e38-8066-3b8d3eb4104f |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 96c6b0de-cc26-5434-ae3b-0eed931d719c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Stockpiling
label | 0a66492c-ce9a-5a54-a8e0-80bb0f921268 |  | note | REFERENCE: MRPA Environmental Management Plan Section 204.05
label | a49a971a-b417-5573-be91-d4d402323592 |  | note | – – – – – – – – – – – – – – – – –
label | f594bb8d-1375-5cb9-a7b1-0f772fdbb3fd |  | note | ACCEPTANCE CRITERIA: Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
label | 85573849-4670-5690-9cbe-0f1bccbfe38a |  | note | ○ If this clearance is not possible,additional protection shall be provided.
label | 059eb324-8232-5837-9274-d5a7026509ba |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | 7853fed8-d4c2-5657-ada9-74d8ffe0d2ef |  | note | ○ Topsoil shall be re-spread as soon as practicable.
label | e6b91db9-ca9e-5f17-9993-c6cb5564def8 |  | note | – – – – – – – – – – – – – – – – –
label | 1f7c7739-259a-5b58-a977-f909690948f6 |  | note | METHOD: Visual
label | 60f88afb-6cf9-542e-acb4-0114102cbfb7 |  | note | – – – – – – – – – – – – – – – – –
label | 048c3af5-65f2-516a-a574-4ada34cdd056 |  | note | FREQUENCY: Where applicable, each Site
label | ce10b04e-52de-57e7-91e5-167affe06b91 |  | note | – – – – – – – – – – – – – – – – –
label | 7b7c3496-697d-5a06-9dc7-417a7dbc4607 |  | note | CATEGORY: IP
label | 50ad76d2-3ee0-5c5b-bffb-02612ae58a75 |  | note | – – – – – – – – – – – – – – – – –
label | 3bb33179-93e2-5c06-9195-1b874b09a50b |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | a7554a6d-51a1-557d-a095-51f12bfc7f4b |  | note | – – – – – – – – – – – – – – – – –
label | 1ddd2ccf-63c3-5a02-9ce4-98ef838d8a73 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 3ac5c1af-1df1-5ed7-ba9f-e82a32ef07a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Abandoned Services
label | baa303bb-ffbf-5b1a-b2bb-20ee8cd28a82 |  | note | REFERENCE: IFC Drawings Excavation Permit Section 201.05
label | 67812e51-02ac-58d9-ba45-f3428c492c9e |  | note | – – – – – – – – – – – – – – – – –
label | 766f5f82-7f4b-51c1-8bf0-3fbe99ed774f |  | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | db462803-4a5e-5680-8a82-24f80acc3dd2 |  | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | 6b416c3c-6e5c-5833-abad-ca2bd7f5cff2 |  | note | ○ Decommissioned services to be disposed of in a suitable manner.
label | 9ba23c36-153c-5b98-8e73-917544e74edd |  | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | 4cece54c-3d22-5497-bf60-d35b6a73517a |  | note | – – – – – – – – – – – – – – – – –
label | 1c5c4354-7fc1-5642-9257-fa0f93f59873 |  | note | METHOD: Visual
label | 1b01df17-792b-5ac5-8482-8114e8253fcb |  | note | – – – – – – – – – – – – – – – – –
label | 998201b7-7031-5483-a3b3-0f998beab866 |  | note | FREQUENCY: Where applicable, each Site
label | cad2f0bd-237f-5f18-9b55-50bb7068d400 |  | note | – – – – – – – – – – – – – – – – –
label | 926d113d-9141-5192-a717-260edbeeb5f4 |  | note | CATEGORY: IP
label | 026baf7a-53a9-5b66-8457-0c75d0de6dd4 |  | note | – – – – – – – – – – – – – – – – –
label | 1141177c-1beb-58e6-9126-6df75a14776a |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 452ba0c1-8c0c-5884-87b1-257579e57a86 |  | note | – – – – – – – – – – – – – – – – –
label | 697b27bd-abfe-5775-a0db-504948ce8255 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 0c981773-099d-574d-b038-92f4507dd995 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Clearing of Trees and Vegetation
label | b50fd0bb-3afa-5fd3-a7d0-80d14986617e |  | note | REFERENCE: IFC Drawings Section 201.04
label | edda8b12-cb3b-5aa7-8d88-5b85ffcd5bb0 |  | note | – – – – – – – – – – – – – – – – –
label | d99d2fe6-46d0-5cd4-958e-177f640cc09d |  | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertaken outside of the specified limits of work.
label | f29f8dd7-4ced-5da9-900e-eb55bad85780 |  | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | 55e947be-de95-5ec5-a067-3f6a4b512ad2 |  | note | – – – – – – – – – – – – – – – – –
label | f3b42f80-afa9-59b0-8d5c-14b4f8c5ae07 |  | note | METHOD: Visual
label | e6dc1a4d-ab53-599d-95d4-dff5c35fb58a |  | note | – – – – – – – – – – – – – – – – –
label | aae1f575-f75a-54a0-a936-5cff338ebfaf |  | note | FREQUENCY: Where applicable, each Site
label | cf9838ec-2798-5156-a21e-940e1c2ce460 |  | note | – – – – – – – – – – – – – – – – –
label | 9030e0cf-86eb-58ad-8beb-551e35ae8f3d |  | note | CATEGORY: IP
label | 8ccfd5fc-6231-5f0a-8e85-80c11a467004 |  | note | – – – – – – – – – – – – – – – – –
label | 1b73d4ab-7d78-599a-8234-492e336d6054 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 70117845-893b-5ba7-8e55-69a4420333a6 |  | note | – – – – – – – – – – – – – – – – –
label | 5a7707fc-1b78-527a-803f-2fde8c0a039a |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 0e79bb0d-614e-527c-8bcb-0451fb10062b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Grubbing of Vegetation
label | 9b15bc7c-8e62-56bb-b7e9-5ff3e273b76f |  | note | REFERENCE: IFC Drawings Section 201.05, Section 201.06
label | aa3c7b8f-0412-526c-ac72-2a0fd34a1897 |  | note | – – – – – – – – – – – – – – – – –
label | 399ccc37-66da-587d-bf0f-78c2a4974478 |  | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | d0e0f363-2d24-5c50-b007-faa4608f09b2 |  | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | b6a541ee-2e2f-5e02-8c3c-0ad05239c3c9 |  | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | dc9dfed8-14ca-540d-8be5-6f7864cb7492 |  | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | 4123beb9-9bce-5e1b-90c6-865c0b170115 |  | note | – – – – – – – – – – – – – – – – –
label | 47693c78-de49-5131-b9fc-a12360dc84ff |  | note | METHOD: Visual
label | c10eb20d-0fd7-57d3-a6d7-0a1c8ed75bf0 |  | note | – – – – – – – – – – – – – – – – –
label | 0777c875-a576-54b3-b361-402bb6fffcef |  | note | FREQUENCY: Where applicable, each Site
label | d411f435-4c07-537c-9dd8-df509560be3c |  | note | – – – – – – – – – – – – – – – – –
label | 3433eda4-a006-55d8-85ef-8affeca7d325 |  | note | CATEGORY: IP
label | 5be6c186-58ba-53a8-bc16-119b38777b65 |  | note | – – – – – – – – – – – – – – – – –
label | 5542d11c-8f8e-57d6-b136-8d3d7d7eda02 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | c759cfea-f04a-59ae-a9fd-4424149f9e51 |  | note | – – – – – – – – – – – – – – – – –
label | 380d1c7d-1e3b-584f-94bc-ed6ce8899b3e |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 7e9baa61-03cc-5b17-afb8-2b5257e96f9b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Disposal of Materials & Vegetation
label | 29d9058b-8055-5719-89b3-7b2cb8d928de |  | note | REFERENCE: Section 201.07
label | 98f5d6f7-11be-5c4d-b67b-ea979ee9f1d5 |  | note | – – – – – – – – – – – – – – – – –
label | 76b09e1a-9c84-5b7d-b2dd-aa6b964d0c91 |  | note | ACCEPTANCE CRITERIA: Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | 1b4a2841-2d07-5567-8731-712a1b25002c |  | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | d69c8b99-dced-5977-8db8-d3445897ab9f |  | note | ○ Tree trunks and large branches shall be removed from the site.
label | 173ef519-f359-5fae-b35e-c4a08603fd19 |  | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | 6f8bae2d-773d-5585-ad75-82425eaa1482 |  | note | Attach: Delivery Dockets (for Items sent off Site)
label | ce04331f-2967-59bf-9eca-6d3173e14f1c |  | note | – – – – – – – – – – – – – – – – –
label | 20f19455-b349-5872-8b0c-4296ba1183e4 |  | note | METHOD: Visual
label | a951c5e2-feb2-500f-a123-b4ba1fe3ffbd |  | note | – – – – – – – – – – – – – – – – –
label | ed35bcee-8c07-5103-b63a-cf1a86c15b6b |  | note | FREQUENCY: Where applicable, each Site
label | 604da063-34a7-50c7-a360-1e8be23c7bb7 |  | note | – – – – – – – – – – – – – – – – –
label | 5f082774-711b-5095-9db4-d535eae9fcda |  | note | CATEGORY: IP
label | b6a13b3e-1583-5b12-9f5b-85dd382024a5 |  | note | – – – – – – – – – – – – – – – – –
label | df7119ab-a9f2-5447-b355-b9ac261a9b87 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 86fe2415-2f65-5626-ad88-2bd379215a86 |  | note | – – – – – – – – – – – – – – – – –
label | 3476491f-a775-58e6-8e48-c6d1bfac77d8 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 40ddc51b-6a19-5ece-93d9-2825c0443bde |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b519626d-2102-5e97-9124-5918766d9998 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | bdf29a0e-268a-5055-8331-e8ec00eb513b |  | textbox | Name:
text | b23c98d7-b87e-51e6-ae06-943b2c62f739 |  | textbox | Position:
text | ce378ea6-23fd-57f8-a591-49af20f143bb |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing | itp |  |  |  | Yes | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing Rev 0 | aa2068ed-2461-4feb-8e4f-a110771b75e0
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 0973ea16-b617-529e-bd02-919b4601e762 |  | note | Document Title: ITP-163-RAIL-SSB-Rail Delineation permanent fencing
label | 70456dba-cf02-50cf-a3c5-42e45ebf0d1b |  | note | ITP Description: SSB-Rail Delineation permanent fencing
label | 78827f5a-03d1-56d9-be46-3d7bd88edca8 |  | note | Discipline (e.g. CIV/STR/RAIL): 163-RAIL
label | 2c1ac98a-930e-5563-bc51-682ffa830fe8 |  | note | Revision Number: 0
label | b00fbc29-2cf3-5348-aae4-bde31293a3d6 |  | note | Revision Date: 10/05/2024
label | 8830dca6-031c-5cf3-b99c-ad89f549a048 |  | note | ITP created by: Yasna Nicker
label | 2738c1e4-e160-57e3-b0cd-e56b58688211 |  | note | ITP approved for use by: VM
label | f47a4248-f769-5cd5-97b3-f394765c2a58 |  | note | 1.1 Non Dependent
label | ee29c56a-402c-5fd7-95d6-7e0b5db808bc |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Toe Beam and Head Beam
label | aeacb59b-2de6-50c4-8c7e-5aabef16b59f |  | note | REFERENCE: IFC Drawings
label | 88fbc1a3-ee32-50f6-95be-f23035070b21 |  | note | – – – – – – – – – – – – – – – – –
label | 40e4c2b1-b977-55bf-9753-dbdee6f8589e |  | note | ACCEPTANCE CRITERIA: Minimum of 60 MPa concrete shall be used as per IFC drawings.
label | 4b84db25-85c9-552c-b581-5337fe5ca8a0 |  | note | – – – – – – – – – – – – – – – – –
label | b661bd4b-2984-59c2-9c73-66227f188a0f |  | note | METHOD: Document Review
label | fcbbdf42-57fb-59af-abc1-44bcf65c78fb |  | note | – – – – – – – – – – – – – – – – –
label | f7a00750-f003-57ab-9ddf-b02af705e085 |  | note | FREQUENCY: Each Mix
label | 5f0c01af-2b48-54cc-94a7-593c694acb2f |  | note | – – – – – – – – – – – – – – – – –
label | add96c8f-165b-579f-a686-e3ada62d1cd9 |  | note | CATEGORY: HP
label | 9a9a27ea-9ea0-5a6b-95d7-c6a077fb4a86 |  | note | – – – – – – – – – – – – – – – – –
label | 0cd2a428-ab24-5374-ac32-12418226a70b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9c75f429-3128-5833-a42e-8cdd2d156379 |  | note | – – – – – – – – – – – – – – – – –
label | 019b3a17-df41-5c0d-a66c-54c00affa4fa |  | note | VERIFYING DOCUMENTS: Certificate of Compliance
date | 6575f4fd-0b32-5155-9e9a-a4080644f2eb |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Steel components
label | 66efabc6-e5b4-5d10-b623-37550c6e9371 |  | note | REFERENCE: IFC Drawings AS41000, AS1163
label | 4f9f609f-1a0d-54ec-a7ad-1de1c4028b08 |  | note | – – – – – – – – – – – – – – – – –
label | bd9291cc-2be0-5355-ae10-8e708c1905b4 |  | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | 796051dd-1beb-5d50-a570-96349fa834fe |  | note | ○ Steel section sizes must be checked on site.
label | 192b5f09-4195-5e00-8429-3ed08dd0c042 |  | note | – – – – – – – – – – – – – – – – –
label | baa4127e-c72d-50d4-86ae-65467273328d |  | note | METHOD: Document review, Visual and Measure
label | 704cee83-4185-53e3-9194-0b0b4af60bd7 |  | note | – – – – – – – – – – – – – – – – –
label | 7c6cc7e6-3a0e-5b31-a1c4-f1b8dc565272 |  | note | FREQUENCY: All elements
label | cba66196-f9fa-5218-9f1d-0868da7c5ed4 |  | note | – – – – – – – – – – – – – – – – –
label | bd20d227-a1f5-5fda-8541-127b8bca0ecb |  | note | CATEGORY: IP
label | 258633c1-350a-5295-bd3e-f293247365a3 |  | note | – – – – – – – – – – – – – – – – –
label | 7d0114c8-5be6-5ac6-9d5a-236a6ec581aa |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e35b2bea-f060-5d58-a0f6-7cd11ace545f |  | note | – – – – – – – – – – – – – – – – –
label | fe5a8f48-37b4-5466-8467-fa629744eaab |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | ba011d2c-42cf-5257-8960-4325e0401c34 |  | date | Date Completed:
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Excavation of toe and head beam
label | 10c2825d-de0c-52fa-92a2-f2f408e18c3e |  | note | REFERENCE: IFC Drawings
label | 6be806a5-8cdb-53bc-b643-73b57bab83af |  | note | – – – – – – – – – – – – – – – – –
label | e8137548-c4f4-5bbf-a008-d2be0b3c617f |  | note | ACCEPTANCE CRITERIA: Excavation for beams must not undermine track and comply with PTDT requirements.
label | de516e91-27c3-5566-b3ac-667faf82d7f8 |  | note | ○ Follow asset owners guidelines for work around their service.
label | 948f383e-b488-5418-afe1-1468f65b1bfa |  | note | ○ Excavation must use Non Distructive Digging in the rail corridor
label | 25eff27d-0887-581e-9603-d0ff58540a2a |  | note | – – – – – – – – – – – – – – – – –
label | d6edae67-8a12-5e49-bdf6-e8b22b15b9e8 |  | note | METHOD: Visual
label | b5ecc2a7-98ec-52e8-9ea4-11e9b58ab762 |  | note | – – – – – – – – – – – – – – – – –
label | 010c1ff5-fde4-59cc-b034-9ab8bcf1fe34 |  | note | FREQUENCY:
label | c3c39d71-97cc-54bb-9c8c-5fc248dd5e17 |  | note | – – – – – – – – – – – – – – – – –
label | 3aaa5fdd-53d3-5ffc-8d23-631861b2c2b8 |  | note | CATEGORY: IP
label | fd31971f-1a1d-5d00-b14f-a593f09cfbfc |  | note | – – – – – – – – – – – – – – – – –
label | 0b0e0fcf-dcc5-538f-9d15-9a171b9698ff |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f7fa60d5-7cb5-5d99-a8b4-d541af45b9f9 |  | note | – – – – – – – – – – – – – – – – –
label | 46004f3d-aab6-50c7-a759-7ab05891fd0b |  | note | VERIFYING DOCUMENTS: This ITP
date | 202a2de4-ed31-5a21-ae14-2c6286096035 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 20387637-472a-522e-b41b-7c0637148e3e |  | note | REFERENCE: IFC Drawings
label | 0ff8fecf-8155-5535-9739-18f7b7b004c2 |  | note | – – – – – – – – – – – – – – – – –
label | 59583c7a-10d2-5cb6-aecc-a160097954ff |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | f2800f91-e0d4-56af-9b16-2d3466397c33 |  | note | ○ Offset checked against the running edge prior to installation of posts.
label | a0a1e99f-ff26-5b58-8fdf-d0a0fd382231 |  | note | ○ Engineer to verify alignment of posts using string line or equivalent.
label | 75ec1c8b-26ad-583e-bc79-febd5f631967 |  | note | – – – – – – – – – – – – – – – – –
label | 765852ec-f7f8-5a7d-9c62-fad7ef800d52 |  | note | METHOD: Measure, Visual inspect
label | 7b0ca519-d5b6-5b7e-bd8b-8179cdfef62a |  | note | – – – – – – – – – – – – – – – – –
label | dc1018a4-5ad0-5f97-9ccb-bd32c57d8f62 |  | note | FREQUENCY: Each element
label | 020ceb06-7a93-56b5-9dbd-36e55ac9a6fb |  | note | – – – – – – – – – – – – – – – – –
label | 8b9761b2-6bce-5b92-9526-16a57651fb3f |  | note | CATEGORY: IP
label | 5ced95d6-ad8d-5aca-bcf1-27a37e4628fd |  | note | – – – – – – – – – – – – – – – – –
label | b7c4c896-156e-5333-946d-ef41c97985a2 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | fd3dca32-c7cf-5b3f-b9f4-fb04ff87a48d |  | note | – – – – – – – – – – – – – – – – –
label | 49d1b134-117e-5d1d-89e6-9fd264cdc5ba |  | note | VERIFYING DOCUMENTS: This ITP
date | 75ea2762-4cb5-5aeb-b605-345f4139d8e0 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Ground Conditions
label | 661d53c8-0a00-5563-a8c8-700888ff9ba3 |  | note | REFERENCE: IFC Drawings
label | a7b0af25-6c13-59d4-829d-500ee6dcb5a3 |  | note | – – – – – – – – – – – – – – – – –
label | ab743e7c-c100-565f-9b90-3c8a6df9b23a |  | note | ACCEPTANCE CRITERIA: All post foundations/ beams to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 332b379c-e29c-52db-aa4e-ce58c5b63698 |  | note | – – – – – – – – – – – – – – – – –
label | a46497ba-96de-53b4-b946-e2bc0c503ffd |  | note | METHOD: Visual
label | bf06e5d1-0f76-5457-900f-adabb5fa6a50 |  | note | – – – – – – – – – – – – – – – – –
label | 5cc17515-04e2-5414-8fc5-e18a7da35b3f |  | note | FREQUENCY: Each post
label | f333f2e4-dcc1-568c-bab9-45d197985135 |  | note | – – – – – – – – – – – – – – – – –
label | 0a1f7685-cbc4-5775-9b10-6332d26d8fa4 |  | note | CATEGORY: IP
label | 17582ea2-e008-508f-ac62-b68269ca979d |  | note | – – – – – – – – – – – – – – – – –
label | 34042069-df58-5214-bf20-b39d8f2b2990 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 582bf95d-f409-5bb2-977e-ed2c003acd2e |  | note | – – – – – – – – – – – – – – – – –
label | db29b96a-e7ca-5ea5-bf7e-f95f4dfe8ee8 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2354aa0e-f278-54e1-b669-f8101b18f5cd |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Toe and Head Beam Formwork Design and Construction
label | 561e9bd6-9c2f-5ea1-b352-4985be1e1a81 |  | note | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
label | 4313aaaf-e6fd-53c1-9054-1f85917cd53e |  | note | – – – – – – – – – – – – – – – – –
label | 49d2d9cd-c19b-5be9-ba40-c5e3366ffdb9 |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ea4d9de1-27f1-5858-bc51-26fc1efc8817 |  | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | bac4f096-b2ae-59cc-8bb3-98e323ac52f5 |  | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | b8606ad6-d159-52ab-9a9d-fb26f80cadba |  | note | – – – – – – – – – – – – – – – – –
label | b9831a60-22d8-5638-bd1e-f3f349429745 |  | note | METHOD: Document Review, Visual, Measure
label | 17f20886-6dd1-565e-8cd0-b6160b744201 |  | note | – – – – – – – – – – – – – – – – –
label | 51c3fdd0-065e-577c-a308-4f4b41c38155 |  | note | FREQUENCY: Each type of element
label | 4200c11f-6b5f-58fd-8a1c-2366e4871a81 |  | note | – – – – – – – – – – – – – – – – –
label | 58a2f593-44c8-5edc-93ef-e88909baec9b |  | note | CATEGORY: IP
label | def5e369-16f7-5573-9cc4-0fba6542120d |  | note | – – – – – – – – – – – – – – – – –
label | 594743c0-0933-5ccf-a12f-9667e6cade8d |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | fb36e443-78e6-5fb5-ba7c-0c7ef18c6dd5 |  | note | – – – – – – – – – – – – – – – – –
label | fd389c36-1456-5420-a650-d269516f5f09 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | e1276e81-7afb-5442-b80b-edc627836cc3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement (Toe Beam and Head Beam Steel)
label | ff6d145d-d963-522d-bacb-d29ae7f756cb |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | ff3e61bb-25e0-5871-a67e-8733e71686a7 |  | note | – – – – – – – – – – – – – – – – –
label | 0b5331e1-d088-5913-bf98-0898bcda9ead |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 51b64561-13e8-555b-9274-2b350c2ed90c |  | note | ○ Projecting reinforcement is the correct length and location.
label | ab641928-0043-5004-bcf2-1fc7030ca303 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | 1e6e835c-87d6-5327-ac7d-2ad15b695ecc |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | ae490e7d-e8be-5ea7-be37-cc0a17cd4a64 |  | note | – – – – – – – – – – – – – – – – –
label | 82645212-f618-5dca-bddd-7c3600597b28 |  | note | METHOD: Measure, Visual
label | 841bbe94-dc72-55b0-89ab-65ba9ceef64f |  | note | – – – – – – – – – – – – – – – – –
label | 2185a663-ad6c-5e7d-b4d5-af0774410be4 |  | note | FREQUENCY: Each element
label | baebb152-c5f2-5482-b353-1f939892d988 |  | note | – – – – – – – – – – – – – – – – –
label | ed890e63-054f-5689-af6b-49abd920bcf8 |  | note | CATEGORY: IP
label | 364478e5-2510-5056-95cb-609a8d3e18e9 |  | note | – – – – – – – – – – – – – – – – –
label | c3a40a59-cbfa-5193-b8a6-7dfa00f80eec |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8c7357db-ecf1-5b02-8e48-84b4345018a7 |  | note | – – – – – – – – – – – – – – – – –
label | a249ef93-8ffd-57ee-ac3e-f387f9a15f87 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 00f5931a-7090-5412-b478-f2548d352939 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Toe Beam and Head Beam Foundation
label | f5b7f70e-697a-59b5-a5a4-fff9be500ab1 |  | note | REFERENCE: IFC Drawings
label | 6ff87759-9e00-590a-a5fa-2119cad87a80 |  | note | – – – – – – – – – – – – – – – – –
label | 95e87dbe-2ed5-54b2-8d1c-89fb1f90d0c6 |  | note | ACCEPTANCE CRITERIA: Toe Beam Dimensions (Fencing Post Foundation)
label | 4bec0b4f-d3d7-5fc1-8b89-f74230001f79 |  | note | ○ 600mm Depth
label | 00bff26c-574b-5805-8252-6347d8793d8e |  | note | ○ 600mm Diameter
label | 43e6fbc1-f3b4-5f5f-8e2f-a9923bc75613 |  | note | ○ 2405mm c/c Spacing
label | 08c33ab4-6771-53e2-b942-e9014d47c505 |  | note | Head Beam Dimensions
label | 8e5a62de-83cf-5158-af47-682847bd2344 |  | note | ○ 600mm Depth
label | 71436ae2-efec-5d3e-baa0-3ee54c813180 |  | note | ○ 600mm Diameter
label | 6e7b3a47-fc0a-57a4-ac6f-a67ec88716e9 |  | note | – – – – – – – – – – – – – – – – –
label | 3bb16361-c255-5acc-8994-449bc4d6f879 |  | note | METHOD: Measure
label | c5177835-5238-5ae7-b258-1e510a12629f |  | note | – – – – – – – – – – – – – – – – –
label | d63bbc7d-2913-51e5-a3e1-0a5a1cfe81d4 |  | note | FREQUENCY: Each footing
label | 05099656-2a44-5df4-8560-4dcca2a15346 |  | note | – – – – – – – – – – – – – – – – –
label | c21128e4-dfac-58a9-8d2f-30e0443f3d33 |  | note | CATEGORY: IP
label | 2ac08ac5-4d82-572f-96a1-b296118bde55 |  | note | – – – – – – – – – – – – – – – – –
label | f7c7efb3-6b3a-50c3-b748-f078971e32dc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 752c6b6c-b030-5bb2-82b8-9de1e258f93a |  | note | – – – – – – – – – – – – – – – – –
label | dc3d8b7c-4b46-59b7-b3b0-278de8a15259 |  | note | VERIFYING DOCUMENTS: This ITP
date | 6a3fd8ae-30d4-58ac-9eaf-845dddb96116 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Concrete Toe Beam and Head Beam
label | d4864059-543d-5f56-a84a-188c57cfc73d |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | e4a5fe1c-ed07-54ea-ac90-42413f532d7c |  | note | – – – – – – – – – – – – – – – – –
label | 017f5038-577b-58ec-94c9-f093896a1128 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 3e1cb172-9314-5311-9bd9-4fded1824b31 |  | note | ○ 0m³ to 10m³ = 1 sample
label | ba0b0cfd-429a-58cb-b47f-2789dd094a18 |  | note | ○ 10m³ to 25m³ = 2 samples
label | 5f08b246-9e40-53dc-b110-b87cd1015f19 |  | note | ○ 25m³ to 50m³ = 3 samples
label | 9479aa4c-4a44-51bb-bfd5-ad4cbcb9be5f |  | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 3411c44c-3cb4-5c76-b475-36d22822e167 |  | note | – For each additional 50m³ and additional sample shall be taken.
label | 42af09ee-2b4e-5048-9828-0b7978ac263c |  | note | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | d1e66519-8c3c-5fef-888d-112771346f65 |  | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 6c4e5824-d752-56f9-98f0-ac2426989eb6 |  | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 0795a373-9627-57f8-9681-77b1c5e14284 |  | note | – – – – – – – – – – – – – – – – –
label | e3db4cb3-72f3-5b09-9a38-f2e1bc751b7a |  | note | METHOD: Test
label | 421ee960-e460-59ef-bef1-eba082046bea |  | note | – – – – – – – – – – – – – – – – –
label | 0fb5d2ec-a577-5902-b47e-b3f426df6b71 |  | note | FREQUENCY: Each element
label | 1cd70b9a-f8d6-5501-989d-7cbdb8331430 |  | note | – – – – – – – – – – – – – – – – –
label | 177c9303-ee40-58a7-8022-cdcc58fedb3d |  | note | CATEGORY: IP
label | 7c725aed-ab84-5acd-be37-670d066696ca |  | note | – – – – – – – – – – – – – – – – –
label | a2395f8a-f739-56da-bf84-d402015d09f0 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | c963d195-319d-55a1-b621-a3bdc3d48053 |  | note | – – – – – – – – – – – – – – – – –
label | 4312ff3b-aa66-581a-82d7-e76bb1ca7299 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | fc102a83-e40e-5725-b12a-4142e5cdb2ea |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Post Installation
label | 7be0e97e-4883-5935-86fe-335e091b6079 |  | note | REFERENCE: IFC Drawings
label | a7b594ab-48bf-5ba9-8ff0-2d65cee2723a |  | note | – – – – – – – – – – – – – – – – –
label | 269da9cd-b587-53c2-9cd3-1eb100133996 |  | note | ACCEPTANCE CRITERIA: Maximum fence post spacing to be 2405mm
label | 92dd1cca-6db9-53ca-a2d2-4999c47b07b4 |  | note | ○ Max. post height 1800mm above ground level
label | aea03d3a-efc0-508c-8d6f-967ddee2ee75 |  | note | ○ Vertical Tolerance: ±20mm from the design line.
label | 2887e71f-f076-5d0e-8224-ede89d44cc15 |  | note | – – – – – – – – – – – – – – – – –
label | 21e536dc-2314-5985-a031-69b559d7d314 |  | note | METHOD: Measure
label | 5dfb8add-3504-5f04-ac00-d4da44871076 |  | note | – – – – – – – – – – – – – – – – –
label | 828f277c-b0ae-597a-a71c-ecc13d8c08c5 |  | note | FREQUENCY: Each post
label | 1e4add52-d557-59dd-8f50-f713fe230061 |  | note | – – – – – – – – – – – – – – – – –
label | be635949-b9bd-5d41-bee9-db56c5ad7a9e |  | note | CATEGORY: IP
label | e5a96c5a-7ff4-5c95-87fb-a24283feef05 |  | note | – – – – – – – – – – – – – – – – –
label | ab757f79-bb39-5709-8b92-bfb5a9beb1ee |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 885e4fc3-e443-5d8f-8041-fbef380da26c |  | note | – – – – – – – – – – – – – – – – –
label | b5cc3da9-5579-5fe4-a3e6-f858663d47a1 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9d96f368-40f5-5d0e-89d6-5fa1e985baab |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fence Panel Installation
label | 80e3b523-80e3-555c-992c-f3166ab7f84b |  | note | REFERENCE: IFC Drawings
label | b164ced7-9bdd-5685-8d64-e20a91939ad2 |  | note | – – – – – – – – – – – – – – – – –
label | 6a37cf4d-959b-53e4-90cd-6ad7ad2b1479 |  | note | ACCEPTANCE CRITERIA: Galvanised fence panels 1820x2405x55 to be fixed to fence post with 25mm U-clip, using TEK screw. A minimum of 2 brackets must be used and fastened to each post.
label | fffa8d16-11e2-5409-80e8-14457ab5fdef |  | note | ○ Minimum ground clearance under panels 50mm
label | ef82ab79-2a76-52bc-a476-0e3d773ae964 |  | note | ○ Maximum ground clearance under panles 150mm
label | 772a9283-254d-57c1-ac88-be0c562af865 |  | note | – – – – – – – – – – – – – – – – –
label | d0993eea-a94d-5f63-bd48-5669bbaaff0b |  | note | METHOD: Visual
label | aa8af15b-90a8-554d-846b-e4909f483152 |  | note | – – – – – – – – – – – – – – – – –
label | b2b606af-8bb7-5bb1-940d-44df0d415952 |  | note | FREQUENCY: Each element
label | 43be585c-b9ec-5794-8de3-8e0eaf9c19b2 |  | note | – – – – – – – – – – – – – – – – –
label | b9373452-96f4-589e-9e4a-720b74028433 |  | note | CATEGORY: IP
label | fed68a3e-6699-57e0-8060-1f0fd948a9d0 |  | note | – – – – – – – – – – – – – – – – –
label | f2eb4f60-312d-5346-b720-5eca542c3161 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4b76186a-1a69-5941-b439-e45cdd3f94ee |  | note | – – – – – – – – – – – – – – – – –
label | 55e1a19a-02b4-5b84-8020-1b2524a6a5c2 |  | note | VERIFYING DOCUMENTS: This ITP
date | f5ddfad8-7b06-5d2e-b637-929d8b0cb105 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Bracing
label | 893f7922-7e8a-5692-822b-0d9c936e5319 |  | note | REFERENCE: IFC Drawings
label | 98353516-01b1-50ce-9a9c-a9edd3c86eb9 |  | note | – – – – – – – – – – – – – – – – –
label | 7f944f95-b498-544a-beb8-23713f1159a8 |  | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 305b03c4-0a5e-5a1a-aaab-155e9b02d3e5 |  | note | ○ Bracing to be installed on both sides of the fence at the fence corners
label | 73096c2e-4c83-5d42-ac58-202886b91216 |  | note | – – – – – – – – – – – – – – – – –
label | c62cbf9d-cf1e-5b2f-81ea-07147d347cb9 |  | note | METHOD: Visual
label | e5fcf79a-f237-56c1-a1a3-4412b08da91b |  | note | – – – – – – – – – – – – – – – – –
label | d8104b95-218a-56ad-903d-6b5ac81bfb5c |  | note | FREQUENCY: Each element
label | 07f662c5-1d73-5219-99ec-ef7a61208980 |  | note | – – – – – – – – – – – – – – – – –
label | a7328410-fe8f-577f-b34c-ad1a546d9b8c |  | note | CATEGORY: IP
label | d5ec3b50-51d6-54b9-b76c-abea0be336f3 |  | note | – – – – – – – – – – – – – – – – –
label | 1a728f77-dd0f-5e94-9022-8fb6cca93d73 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8630fc16-909c-5865-9cdd-85058f254c0e |  | note | – – – – – – – – – – – – – – – – –
label | 790af7e3-59c4-537e-adb8-14df5d6add40 |  | note | VERIFYING DOCUMENTS: This ITP
date | 4e30d332-652e-5aa9-8882-8b4cefa6a1bb |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Fence Height and Track Clearance
label | 985d91c1-9c8e-53a8-a1c2-927b578554b8 |  | note | REFERENCE: IFC Drawings
label | 54b93a11-521e-5379-b39e-9563dbaf998f |  | note | – – – – – – – – – – – – – – – – –
label | 294bf2f6-282e-5e50-ade4-c1e874d6a1cd |  | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | 9e6a2699-8f24-5dc4-a5d2-27960cfed271 |  | note | – – – – – – – – – – – – – – – – –
label | 7b21073b-b50e-5fbc-9e28-3aaa764904be |  | note | METHOD: Measure
label | 71e28655-d65c-5d3a-8a10-3e39a3f2eba3 |  | note | – – – – – – – – – – – – – – – – –
label | ae2366aa-d5f8-5710-9958-71898105e6a3 |  | note | FREQUENCY: Each lot
label | 451d53e8-06b2-5d1c-91ee-8f96e2056828 |  | note | – – – – – – – – – – – – – – – – –
label | 685819b6-552c-50fc-a613-26169bedbb88 |  | note | CATEGORY: IP
label | 4a0522b3-b862-5463-8804-c6f0d28c297a |  | note | – – – – – – – – – – – – – – – – –
label | f390108c-b1d5-5994-8a09-0e6596129aa2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f3efbd69-a3b7-52c2-81ad-1c67ef4ecb1c |  | note | – – – – – – – – – – – – – – – – –
label | cd427421-e464-5eb0-bfde-a031f742768a |  | note | VERIFYING DOCUMENTS: This ITP
date | 23529bbe-9cfa-5bca-8a01-13e1c1ff6d3a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 32fefd8a-277a-5027-8123-b9e40fc5a18b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | adabfadb-b493-59ba-bddc-c71ada7f8de4 |  | textbox | Name:
text | b0105938-e6c4-55c5-b060-aa8e4c6c4855 |  | textbox | Position:
date | e14a806a-20cf-523c-8a3e-a9bb7b85086e |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-011-CIV-Material delivery inspection-Precast Pits and HDPE pipe | itp |  |  |  | Yes | CHK-011-CIV-Material delivery inspection-Precast Pits and HDPE pipe Rev 0 | af8584e3-9ec9-4fbd-a550-b52eff7a3031
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f3423644-9f6f-574d-82e6-16ecaf29842d |  | note | Document Title: SBS-Civil-Material delivery inspection-Precast Pits and HDPE pipes
label | 5d5b4f4a-2b4b-5a53-a601-5753b5ed27da |  | note | ITP Description: Material delivery inspection-Precast Pits and HDPE pipes
label | 83f8bdc6-8b67-5922-a474-e8eb9f3399a3 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c2fe63f1-6128-59ab-894f-3786675da607 |  | note | Discipline (e.g. CIV/STR/RAIL): Civil
label | 60fc8138-6307-5685-b522-46885e41db5e |  | note | Revision Number: 0
label | af6ac555-a15d-5f14-8ef6-63b33fdd8f8d |  | note | Revision Date: 6/02/2024
label | 517803c3-f23f-5861-9b6f-1b76802b5c96 |  | note | ITP created by: Hiruni Wickramarathne
label | 470691ed-40fa-593b-bcbc-dc697cc8dc9f |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1. Delivery Details
label | a4bb43ea-e95f-5361-960d-5dc3f98768d4 |  | note | ACCEPTANCE CRITERIA:
text | 8b87451f-1987-5274-9c52-61600581075e |  | textbox | Enter: Delivery Docket Number:
text | 86b9082a-584c-5b7b-abf9-6e12e6cf92f8 |  | textbox | Enter: Delivery Date:
text | 81dc5d50-6940-5e00-afb4-87f3664e587c |  | textbox | Enter: Element ID (s):
label | b419d3b4-3fc9-5d14-a42e-081ef63d310f |  | note | Attach: Delivery Docket and packaging Slip
label | dce49324-ae40-56c9-a096-3652311d78a2 |  | note | – – – – – – – – – – – – – – – – –
label | c8c64efe-07be-5f91-9e0a-6632756d6232 |  | note | METHOD: Document Review, Visual
label | d1824b32-12f6-5a32-8437-cd1e3d1730e0 |  | note | – – – – – – – – – – – – – – – – –
label | 65f6f443-242a-53bd-82c8-6d895cb736ff |  | note | FREQUENCY: Each Delivery
label | 86b6d7d2-b7e9-5c3e-a3f3-ce54240540e0 |  | note | – – – – – – – – – – – – – – – – –
label | 1807fc1f-1e59-5df8-9611-2b2223637311 |  | note | CATEGORY: IP
label | dd8a077e-ac45-59cb-b179-063c55c71203 |  | note | – – – – – – – – – – – – – – – – –
label | d07e7776-17b4-5a7b-979c-6714e40f2296 |  | note | RESPONSIBILITY: PE/SE
label | e29001ae-9d5e-5076-8dc9-5958715e7bce |  | note | – – – – – – – – – – – – – – – – –
label | 99dcb95a-dc00-5310-adc9-1481a6c81d37 |  | note | VERIFYING DOCUMENTS: This Checklist
date | e844f74c-0ccd-5199-834e-d8ee25111b0e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2. Packaging Inspection-Quantity
label | bd41ca3e-8525-5174-889d-1ebf2304d980 |  | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | 57735865-9d3a-5dbf-a161-d616e60f1ec8 |  | note | – – – – – – – – – – – – – – – – –
label | 3ca5a2cc-7594-5b49-b4e7-730b0ab2799e |  | note | METHOD: Visual
label | d24adb49-72cd-5dac-b8f5-5dcb2bb41148 |  | note | – – – – – – – – – – – – – – – – –
label | e87e5ecd-d8f5-5029-a905-d646c0b9af0e |  | note | FREQUENCY: Each Delivery
label | a076b8f2-bd2e-520e-be90-bacf58c12753 |  | note | – – – – – – – – – – – – – – – – –
label | 11df2ec1-0890-5e02-8294-1c1f83682594 |  | note | CATEGORY: IP
label | e139600f-2741-595a-8cca-9a2c9a59b9bb |  | note | – – – – – – – – – – – – – – – – –
label | 570fa390-cd6e-5d14-a799-1c1cc38c56f9 |  | note | RESPONSIBILITY: PE/SE
label | f9781b8a-3b7c-5e71-97ba-2b3531ee3123 |  | note | – – – – – – – – – – – – – – – – –
label | 4e278929-b91f-5527-b8a1-81d0f127ddc1 |  | note | VERIFYING DOCUMENTS: This Checklist
date | b23b9f52-89fb-5276-8c8a-3e0ac36f52cf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3. Packaging Inspection-Delivery Contents
label | d18f3413-56a7-5f35-bb5d-2c1792292088 |  | note | ACCEPTANCE CRITERIA: Do the contents of the delivery match the freight list/packaging slip?
label | e5318dfa-e27f-5363-85f2-d5e528db3d70 |  | note | – – – – – – – – – – – – – – – – –
label | 85c9aa3b-bf2f-5b2a-a1be-ccbc75543fdf |  | note | METHOD: Document Review, Visual
label | 57e12a23-76ce-594d-a3a1-72ec8a214ec0 |  | note | – – – – – – – – – – – – – – – – –
label | 9d3763d5-cc7d-57d8-99dd-211e88d2e6d0 |  | note | FREQUENCY: Each Delivery
label | e315e624-7f2c-59f1-afde-488e4795e1f1 |  | note | – – – – – – – – – – – – – – – – –
label | 14293330-5a76-59ae-8305-a6741db3f332 |  | note | CATEGORY: IP
label | c57e86bd-db96-5493-b9fe-fe5fad2514bb |  | note | – – – – – – – – – – – – – – – – –
label | 9217fd8b-702f-5b68-83e8-7bdb3c972778 |  | note | RESPONSIBILITY: PE/SE
label | 7f59edbb-e9b0-5d96-a495-d7571ce7cb2c |  | note | – – – – – – – – – – – – – – – – –
label | 7d6de392-f002-5c0e-bd69-1509d3ac14d6 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 1050a98b-8ea9-5c07-99a5-52a1e471c386 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4. Packaging Inspection-Birth Certificate
label | 705d64bc-8a2a-5c19-825f-5b238a17e7ee |  | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
label | 463c923e-b01a-558e-9b00-29c8ad825f12 |  | note | ○ Precast components are to be marked on the birth certificate.
label | 6ea1bb33-5afb-5513-b882-e562ae55ae3a |  | note | ○ Cast date and lot are to be marked on the birth certificate.
label | 41e510b0-46c9-551e-8b6f-ab2bb4c6a7a8 |  | note | – – – – – – – – – – – – – – – – –
label | 3459da4a-9b41-5364-ad58-b45b34265f64 |  | note | METHOD: Document Review
label | 4ee071c0-e2af-5b5a-acf9-50c4ce514214 |  | note | – – – – – – – – – – – – – – – – –
label | 822672ef-d73a-5e72-bbb6-71b4454d2298 |  | note | FREQUENCY: Each Delivery
label | f47f9eb6-5c4a-5d13-91eb-f856fbb2ab12 |  | note | – – – – – – – – – – – – – – – – –
label | d7c6659c-ac8d-5959-884a-d6ce8ccb5c2b |  | note | CATEGORY: IP
label | 0c125d05-b82e-538a-9c49-6900b428bb01 |  | note | – – – – – – – – – – – – – – – – –
label | d2106352-718a-5737-b0bd-f28d8d002de9 |  | note | RESPONSIBILITY: PE/SE
label | f975fd62-b801-5deb-a170-1110bdf2b0fc |  | note | – – – – – – – – – – – – – – – – –
label | 2eed8395-1a3f-5474-b2bb-2ef9248d3fb5 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 184e5cb8-f2ab-5553-b8e0-a699b860df71 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5. Packaging Inspection-Transport
label | d2302e38-6544-526b-a013-e4c6e0292d52 |  | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
label | 42fc1186-0691-59fa-b1d6-d80d3515fd27 |  | note | ○ Precast items are protected from damage during the transport
label | c5b47e72-95aa-5fc9-a7b8-56af505b5d64 |  | note | – – – – – – – – – – – – – – – – –
label | b3f11370-d279-528c-ac61-c59a10b74a2c |  | note | METHOD: Visual
label | b30d4c73-e228-51e5-9b56-1002806725f5 |  | note | – – – – – – – – – – – – – – – – –
label | 428e8df7-be4f-5a7c-bd99-167652280f5c |  | note | FREQUENCY: Each Delivery
label | 738f3b95-49a2-55d0-9f8f-8938f78429f7 |  | note | – – – – – – – – – – – – – – – – –
label | a9d571c7-cc5c-5381-a4bb-f62b1c2ce38d |  | note | CATEGORY: IP
label | a3d633c2-49b8-5c6a-8f87-90cf884823c5 |  | note | – – – – – – – – – – – – – – – – –
label | fb308de7-0289-5d55-999b-97519b1337ab |  | note | RESPONSIBILITY: PE/SE
label | dd342786-c509-52b2-9dcf-ec5eb69c0f4c |  | note | – – – – – – – – – – – – – – – – –
label | aab64e02-da9d-565c-825e-fbdbd9d6f348 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 25f42070-5c3e-5023-818c-bd2e91973dd7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6. Fault IDs:
label | c4235f2e-3c74-5d81-93eb-19a79087f02c |  | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
label | f51da19b-68eb-5ec7-a8e8-82ed557e1de5 |  | note | 1 - Identification markings match the Precast type
label | e985a98d-11b0-56b6-9540-733676275696 |  | note | 2 - Precast Pit fabricated as per drawings - inverts size.
label | d83c9ae6-6e6f-54f3-9497-f41406aa2467 |  | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
label | b13318fd-3772-5644-b285-5e4fae462ec9 |  | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
label | d762deea-1ea1-5f4d-a6b7-7f8d1445661f |  | note | 5 - Precast Pits- Inverts coliding.
label | d40fc15f-6931-5304-91d7-6c13a960f927 |  | note | 6 - Precast Pits a - Inspect for Cracks.
label | 049cd494-2255-572a-9a95-50e4377d5b23 |  | note | 7 - Precast Pits - Inspect for Spalling/Damage to concrete surface
label | 38cad2d9-c86e-56a4-8e2b-0da71012d3bc |  | note | 8 - Precast Pits - Inspect for Exposed Reinforcement.
label | c22c99c3-7c29-5b82-b82f-c40691700861 |  | note | 9 - Precast Pits - Inspect for correct Lifting mechanism.
label | 3740203b-908d-5b0e-b3e4-b9ee3fb52ef6 |  | note | 10 - HDPE pipes-Inspect rubber rings
label | 109d3cd8-924f-5b37-8778-ea3d6752c99b |  | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
label | c171ace1-0556-5249-9cf4-ec27def80bad |  | note | 12 - HDPE pipes - Inspect for any defaults/deformation in the pipe
label | e23a6b77-e0df-56b1-91a5-6344902bc2b0 |  | note | – – – – – – – – – – – – – – – – –
label | 0d13640a-1dfa-5d2c-a194-1a68aa9473d6 |  | note | METHOD: Visual, Measure
label | a053e48a-de2c-5529-9710-2a06eec23094 |  | note | – – – – – – – – – – – – – – – – –
label | a55bfed2-7b5d-53df-9aa7-3d305a773e59 |  | note | FREQUENCY: Each Delivery
label | c87d991d-413d-5659-b754-fc2440e81e75 |  | note | – – – – – – – – – – – – – – – – –
label | 2c5ae821-29fc-556c-b9e8-8e5ee52809a7 |  | note | CATEGORY: IP
label | 95c5593e-db6c-56cf-a3fe-7802e629eb1a |  | note | – – – – – – – – – – – – – – – – –
label | 18d238d8-0105-5811-893b-4c52a56b944e |  | note | RESPONSIBILITY: PE/SE
label | 86cda14b-7321-56cb-b891-e30261eee54e |  | note | – – – – – – – – – – – – – – – – –
label | 046e99ee-c99c-52e1-a64f-d6c8529b56cb |  | note | VERIFYING DOCUMENTS: This Checklist
date | 9bd33929-a2fc-508f-8110-8f0ad8fa0005 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Check for Faults - 1
label | 76600261-3134-577c-842c-30cbbad512a1 |  | note | REFERENCE: Item 6 on this Checklist
label | 3bae0ab5-e1f5-5524-8ebc-a3cfc7c44056 |  | note | – – – – – – – – – – – – – – – – –
label | b874b17c-eb99-5e40-84f7-8cc8c066a869 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 02b5923b-5c41-5955-a088-ec7e37962b38 |  | textbox | Enter: Pit Identification:
text | 9d7f28c0-4978-5a1b-8225-f1ba991f4f43 |  | textbox | Enter: Quantity:
text | 7f5fec29-e406-58f8-b8e3-07f66902247a |  | textbox | Enter: Fault ID if any:
label | 0ad78038-96e9-5ffa-bd7d-5ef5917801c8 |  | note | – – – – – – – – – – – – – – – – –
label | 07ffd7c0-a3c5-5539-b8bd-7f4b22b0fa8c |  | note | METHOD: Visual, Measure
label | 03898245-ed4c-56cd-8cb9-e36330a214cd |  | note | – – – – – – – – – – – – – – – – –
label | d9e504d2-4852-5cb3-8b57-75862bb2b6e0 |  | note | FREQUENCY: Each precast type delivered
label | 297f53ef-6c78-5a56-b43b-ca3efd6a3156 |  | note | – – – – – – – – – – – – – – – – –
label | da6f58f9-7d08-586e-9d2d-4915e8609fc1 |  | note | CATEGORY: IP
label | 85d85f9b-fbdd-55a5-9d7c-612f6c8c9f94 |  | note | – – – – – – – – – – – – – – – – –
label | 9bb8f437-5cde-5e32-9de1-5c50f017f93c |  | note | RESPONSIBILITY: PE/SE
label | 1480504b-0b48-5ef1-a29d-e97a156b7a5a |  | note | – – – – – – – – – – – – – – – – –
label | 30f98071-0816-533b-8b55-51d1c1d8fdea |  | note | VERIFYING DOCUMENTS: This Checklist
date | eb0f9639-c90b-507a-a1ca-b705ff1964d0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Check for Faults - 2
label | ee62fe60-d35d-514a-8b33-1bfecb1dbdbe |  | note | REFERENCE: Item 6 on this Checklist
label | ae45c303-41d2-5d63-8fe9-2454e00e130e |  | note | – – – – – – – – – – – – – – – – –
label | 07304b29-fc1f-5280-b9ad-1a9b2101baab |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 8d5826ae-5045-52eb-8e86-272fa12686bb |  | textbox | Enter: Pit Identification:
text | 47c8bdca-4999-5e1c-bb61-009b44e8863b |  | textbox | Enter: Quantity:
text | 79c7f98e-d4de-5795-a007-a40bc513cd50 |  | textbox | Enter: Fault ID if any:
label | fa157429-0ba5-5a7b-b1f6-bf1dfde104e4 |  | note | – – – – – – – – – – – – – – – – –
label | 2fa4c95b-23c9-58e7-9b4e-e19d1b12b573 |  | note | METHOD: Visual, Measure
label | 59ca28b1-53c8-5d76-a1f3-07df3d535aba |  | note | – – – – – – – – – – – – – – – – –
label | 49462a0d-afe8-5159-bd9b-1782a1f42fd5 |  | note | FREQUENCY: Each precast type delivered
label | 374603f3-4a66-5297-95f9-6dfb28d2702e |  | note | – – – – – – – – – – – – – – – – –
label | fe44dca7-a0cc-5cb0-870f-71ad4ee98ec1 |  | note | CATEGORY: IP
label | 12722d07-1117-5650-a276-a4465c9c0b14 |  | note | – – – – – – – – – – – – – – – – –
label | 41440912-7389-5ae1-bbac-cdd34254c42c |  | note | RESPONSIBILITY: PE/SE
label | dcdc62ba-c501-57d7-9583-c4d473d665b2 |  | note | – – – – – – – – – – – – – – – – –
label | 0fb2aaae-59b3-50a0-a9cb-17e65dc81855 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 46aa7d7f-ffe1-5fce-8444-9d15a5e78826 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Check for Faults - 3
label | 7a8a2a26-77b4-5076-9975-347009e3cbcc |  | note | REFERENCE: Item 6 on this Checklist
label | 166f390c-4241-543c-9c9c-bb013a62c110 |  | note | – – – – – – – – – – – – – – – – –
label | 620478a0-1e41-59b2-b7cb-efacd7ab0249 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | e721c376-a058-593d-94fe-d206460f4177 |  | textbox | Enter: Pit Identification:
text | 39d66ac6-558f-5475-aed7-fbb590fabd25 |  | textbox | Enter: Quantity:
text | 8df4393b-362c-56c8-bf23-873c92f1bb76 |  | textbox | Enter: Fault ID if any:
label | 07706f36-b42f-5537-b638-0643b942cb81 |  | note | – – – – – – – – – – – – – – – – –
label | 8678740b-4383-5e55-9e22-0d39c20bc9c1 |  | note | METHOD: Visual, Measure
label | 4994ea99-475f-58a7-b566-93cf8a364e3b |  | note | – – – – – – – – – – – – – – – – –
label | 8ca202c4-20d0-523d-b585-97755d22576a |  | note | FREQUENCY: Each precast type delivered
label | 2a121cb0-7425-5332-9d53-3fcbbfe56300 |  | note | – – – – – – – – – – – – – – – – –
label | 9ec33d5b-6736-53f1-88eb-142ee650411e |  | note | CATEGORY: IP
label | c79fcead-2f43-5b9b-b80e-fbd20e5e727f |  | note | – – – – – – – – – – – – – – – – –
label | a62f0ae1-a80d-53e3-8f4b-2fd0d9ca012f |  | note | RESPONSIBILITY: PE/SE
label | 4556cea5-0fbd-5e33-8939-a44605fe6730 |  | note | – – – – – – – – – – – – – – – – –
label | 2636d0af-88f4-5f6a-b2de-bf89f9df556b |  | note | VERIFYING DOCUMENTS: This Checklist
date | 80bca0d8-7e42-51f0-a5db-c67179e1ed64 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Check for Faults - 4
label | 213d3c86-6a1b-5474-a7aa-c21b3d59db69 |  | note | REFERENCE: Item 6 on this Checklist
label | 0d0d8123-e03f-52a6-9ef1-3744169b3350 |  | note | – – – – – – – – – – – – – – – – –
label | 7f6c02fe-d847-59a1-bd74-dcff7a6727f4 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | f7beff20-23c2-53ff-8c40-1acac1912bd6 |  | textbox | Enter: Pit Identification:
text | 7966bf0a-8149-5196-8f3a-72df6b96671d |  | textbox | Enter: Quantity:
text | 6728a277-c9f3-5537-92c3-77ab9d921df6 |  | textbox | Enter: Fault ID if any:
label | a1c340d9-5665-5294-bed6-a467f5092ae3 |  | note | – – – – – – – – – – – – – – – – –
label | 0edea162-430a-5d8a-b637-9a6ac98da5b6 |  | note | METHOD: Visual, Measure
label | 05400f5b-ddf6-5268-85dd-e1c9ef79f424 |  | note | – – – – – – – – – – – – – – – – –
label | d6b33501-5cab-5d8f-bdaa-0f4d8d5247b8 |  | note | FREQUENCY: Each precast type delivered
label | ee6a320d-a631-53fc-869c-02fe2fc23f0b |  | note | – – – – – – – – – – – – – – – – –
label | 4773c645-b17e-5ffb-adef-2b597eb905ac |  | note | CATEGORY: IP
label | a1696cc2-78f5-5727-90fa-85f69158b4ce |  | note | – – – – – – – – – – – – – – – – –
label | 584fd335-d74e-502c-9c1e-17447915c4d7 |  | note | RESPONSIBILITY: PE/SE
label | a43710bc-3232-5049-b7ea-769df6382b2b |  | note | – – – – – – – – – – – – – – – – –
label | 9f1c5844-feac-5926-8ac5-d76be023e6a2 |  | note | VERIFYING DOCUMENTS: This Checklist
date | cf43c7ca-a82e-56f4-807b-0218c3ea67f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fc0d394f-b94f-5505-975d-3c070b424af1 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | dfcba24b-0b6b-5aa8-a057-3f871c15cb91 |  | textbox | Name:
text | 6d367d1a-6079-5d9e-9bd8-28c8f8924fc8 |  | textbox | Position:
date | 9126cc5c-9de6-5018-b636-cee8bd0a7648 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-012-CIV-SSB-RSS Walls-Precast Panel installation | itp |  |  |  | Yes | CHK-012-CIV-SSB-RSS Walls-Precast Panel installation Rev 0 | be43eaff-afb5-44dc-aa1f-9e226838b559
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 05bcb1af-b56b-5a71-974c-0e9a167df243 |  | note | Document Title: CHK-012-CIV-SSB-RSS Walls-Precast Panel installation
label | 314c22f4-f135-5814-88ae-4c7900a4ef17 |  | note | ITP Description: SSB RSS Walls - Panel installation
label | 5c2f25e1-bec6-5bc3-8ebf-976febb0364c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | b1bd4a56-30c2-50a1-9f2d-64a32c22a6ee |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | c3f7bb2c-323b-5293-9934-184a5643a0ca |  | note | Revision Number: 0
label | 504075f4-aad7-5718-a4c9-684c512078f4 |  | note | Revision Date: 18/3/2024
label | 03830593-2163-5b7a-a93f-252a255e0e79 |  | note | ITP created by: Victor Mira
label | 80b92985-8d18-5b39-8ccc-00f86f716053 |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1. Panels-survey set out-Tolerance
label | 35282311-353a-57e9-b5be-ee301c56cfcf |  | note | REFERENCE: IFC Drawings VR 682.20
label | f6492370-d092-5fdb-895e-385574f586de |  | note | – – – – – – – – – – – – – – – – –
label | e9a38788-f3a4-5565-bff5-2757dea2161d |  | note | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | 47d0d8e6-ca49-5718-a31f-2f58a68477c7 |  | note | – – – – – – – – – – – – – – – – –
label | e08e6458-9baa-5054-a2d4-d4a33ed61656 |  | note | METHOD: Measure
label | ff8df87d-c057-59a9-9677-810172a3d834 |  | note | – – – – – – – – – – – – – – – – –
label | 176add7d-1842-5f20-95b5-881f3063e2d3 |  | note | FREQUENCY: Base course panels
label | 6b8221e2-d952-5d08-bee0-b1482f11da2e |  | note | – – – – – – – – – – – – – – – – –
label | 2be475a5-d090-5c9a-b62a-064bf1cb8de8 |  | note | CATEGORY: IP
label | 5a8af662-2a86-509a-9f52-a86956312ba2 |  | note | – – – – – – – – – – – – – – – – –
label | d9549b38-ac6d-520d-80ea-d7d37ce9f071 |  | note | RESPONSIBILITY: Surveyor/PE
label | e15bdf03-5aa1-5c72-b968-ea75a8f8e318 |  | note | – – – – – – – – – – – – – – – – –
label | 3a5198eb-2991-5c13-bb01-1b5ec46797b4 |  | note | VERIFYING DOCUMENTS: This Checklist
date | ec636b6b-8700-5424-8209-1432b450dcf0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2. Mark-up panel for construction team
label | 82967d01-8a36-52d0-872e-1abdc76f0e85 |  | note | REFERENCE: Construction Manual
label | 05a6aa71-f7ff-5b22-bf11-1c490d10d9ca |  | note | – – – – – – – – – – – – – – – – –
label | 64e506c0-89f5-5882-bd0c-ada50e46e842 |  | note | ACCEPTANCE CRITERIA: Mark number of strips per row on the back of each panel.
label | 70d11210-dc50-5f75-8486-23407839b9d6 |  | note | ○ Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
label | 1ff03c31-16b4-5532-8a5a-d47028bec71d |  | note | – – – – – – – – – – – – – – – – –
label | 026a64de-dceb-5bbb-bebb-f838e67ee0aa |  | note | METHOD: Visual
label | f495f419-3f0a-51ff-b93f-708808de5cb0 |  | note | – – – – – – – – – – – – – – – – –
label | 0644de4e-1f60-5170-ab96-f168d1868fa0 |  | note | FREQUENCY: Each panel
label | 8ada8656-0ca2-5d19-b619-ce3fa3ae36a7 |  | note | – – – – – – – – – – – – – – – – –
label | 6607fc1f-c4f5-54cd-ab22-ca0d8ea07ad3 |  | note | CATEGORY: IP
label | 89a61a37-5af1-5f5c-a797-7b315d6c1574 |  | note | – – – – – – – – – – – – – – – – –
label | b3e0b1b9-29cf-57c1-95f2-db1ab46a7137 |  | note | RESPONSIBILITY: SE
label | ff598cea-0ee3-5be9-a666-386c0f1d821f |  | note | – – – – – – – – – – – – – – – – –
label | b650c1da-3680-564c-b87a-a510f5b2514d |  | note | VERIFYING DOCUMENTS: This Checklist
date | 7f53c1e7-feae-542e-9603-c3e747f2ae84 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3. Panel installation
label | 6308eeac-2092-5856-be52-e724bd2e2d37 |  | note | REFERENCE: IFC Drawing:, Schedules:
label | 2b485135-a82a-5c4e-bcbc-e075b4485aa3 |  | note | – – – – – – – – – – – – – – – – –
label | 42e49546-13da-5e3a-8719-dbadeb8feb93 |  | note | ACCEPTANCE CRITERIA: RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | 223e699c-eaa6-5ad9-b472-e355a4729396 |  | note | – Check for correct architectural pattern
label | 04c2d140-9dda-5036-ba0d-633ba13c8218 |  | note | – Check for Weephole Locations
label | 03f7e517-9a6b-5475-838a-f259f5ea895e |  | note | – Check the 19mm nominal gap to be maintained
label | 4189957a-ffbb-59cb-b122-dd4eed26245a |  | note | – Check the 1 in 40 slope is to be maintained
label | 2923a843-2326-5be5-9ae4-9351f931a6b2 |  | note | – – – – – – – – – – – – – – – – –
label | 553e63c9-fd9d-5102-ba4f-4c990745f2bb |  | note | METHOD: Visual, Measure
label | 0aed1d61-1c72-55fe-9e0c-c10f26f25583 |  | note | – – – – – – – – – – – – – – – – –
label | 21e44ef2-96b4-5606-9106-cc1cdaca1cd4 |  | note | FREQUENCY: Each panel
label | cd2f51d9-533f-56e1-bb46-dff722ba4104 |  | note | – – – – – – – – – – – – – – – – –
label | 86ee691e-8df7-5f87-8c18-07ea8a43cdf5 |  | note | CATEGORY: WP
label | 4eb0eb4a-92dd-5921-9d9a-e67343c0b37a |  | note | – – – – – – – – – – – – – – – – –
label | b4534345-0d56-5ab8-9b61-ff607a97dbe1 |  | note | RESPONSIBILITY: SE
label | e0042898-c33d-5ac8-81d6-a94154bd2169 |  | note | – – – – – – – – – – – – – – – – –
label | 225eeffc-7aca-5d3a-b234-46cab6f97881 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 6296a8bc-6ae4-52a1-a2c0-9ffd087f17c0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4. Panel installation-Abutment interfaces
label | 8a949ded-bb76-5203-bd4a-35883ecb7849 |  | note | REFERENCE: IFC Drawings
label | 225f727b-d35a-528c-94a6-dc5518c4ef72 |  | note | – – – – – – – – – – – – – – – – –
label | c2a8bdfe-8cab-5c4e-bc2f-5f1cc4d80e82 |  | note | ACCEPTANCE CRITERIA: 20mm nominal gap between panels and Abutment wall is to be maintained
label | e8261631-bd22-5fee-b080-90ecf4adfab2 |  | note | ○ Where nominated 125mm wide x 6mm thk hot dipped Galvanized plates fixed to abutment wall OR 250x6 Galvanised Folded Plate as per IFC drawings.
label | cf3ddf46-191b-57f9-b4f7-765d02209c52 |  | note | ○ 600mm wide BITAC tape installed on the joint
label | 0295b165-e60b-59ab-9e17-c75357dfd018 |  | note | ○ Galvanised Plate, installed with M16x75mm long Gr.4.6/S
label | 2a9765b8-b55d-56c5-8ada-8ccf18b3f719 |  | note | ○ For the slip joint location, spcing between panels to be min 25mm.
label | efe70b07-09fe-5d41-8cce-d9a1db71e413 |  | note | – – – – – – – – – – – – – – – – –
label | b04cd623-728c-58bc-99f8-f97fc0d3ee89 |  | note | METHOD: Measure
label | c8300c24-f320-51cb-a123-25a2795984e7 |  | note | – – – – – – – – – – – – – – – – –
label | 46c307f1-d065-506a-b8a6-65f3885bbf19 |  | note | FREQUENCY: Where applicable
label | af29307f-5093-52eb-8756-1d8790c383d4 |  | note | – – – – – – – – – – – – – – – – –
label | 7580e6db-4904-5397-b690-d2cff3241727 |  | note | CATEGORY: IP
label | 14678039-5602-5625-9591-800e06e8271e |  | note | – – – – – – – – – – – – – – – – –
label | 511c0a07-210d-5ee9-a594-f3d9f575d31f |  | note | RESPONSIBILITY: SE/PE
label | bd8b5a13-d0d7-5b98-a7b6-4e8694b25218 |  | note | – – – – – – – – – – – – – – – – –
label | dff3f0a9-58ec-5dd5-8cd7-0e3185b3b378 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 51bdbf5a-a892-51fa-8de5-f19b26955197 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5. Filter fabric -Installation
label | 30662360-8209-5ec4-81cb-f9e5f36c7dc9 |  | note | REFERENCE: IFC Drawings
label | c0b2b1b9-19ec-5989-826c-d7b514168a1b |  | note | – – – – – – – – – – – – – – – – –
label | da6ee7de-4164-538e-87b0-f62982010ca6 |  | note | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
label | fba659fc-2c12-5e7d-865d-bde0c58da3e6 |  | note | – – – – – – – – – – – – – – – – –
label | 780bc4fe-32b1-5f51-9847-783ea192ffdb |  | note | METHOD: Visual
label | e2fc4782-c4fd-5ce8-a949-03e3ac3cfa33 |  | note | – – – – – – – – – – – – – – – – –
label | 22d7ebb2-119e-5899-8b32-9dbf8a13ac87 |  | note | FREQUENCY: Each course of panel installation
label | b3aa2df6-0a60-57cb-90b2-e8ed0409fcc7 |  | note | – – – – – – – – – – – – – – – – –
label | 43a52030-61b5-51dd-b18f-3b67ede195c5 |  | note | CATEGORY: IP
label | a99a15b3-31b9-50bb-b0a8-35062e8ff4e2 |  | note | – – – – – – – – – – – – – – – – –
label | fabf06e5-211a-5fb9-b3fe-c66740c7c21a |  | note | RESPONSIBILITY: SE
label | 0ce1f0c7-cd99-51c3-a394-6a5b2a544b8c |  | note | – – – – – – – – – – – – – – – – –
label | ef0797b1-9247-552e-8316-7cc8484d0221 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 13c4b006-2f77-59c1-b1fd-9471dd35ebca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6. Drainage-Strip Drain
label | b427c354-075d-5abd-b105-b7e0ba91876b |  | note | REFERENCE: IFC Drawings
label | 58f5bbbd-fd06-5f18-b0e9-d132411f1d6a |  | note | – – – – – – – – – – – – – – – – –
label | 305a2908-9474-5065-b118-b1df5c726347 |  | note | ACCEPTANCE CRITERIA: Install 300mm wide vertical strip drain -at every vertical joint between panels in RSS wall.
label | b1a501fd-5309-55d8-a28d-70913255112d |  | note | ○ Ensure no gap is formed between strip drain and RSS panels.
label | d7f5e14f-a1fd-5c62-9a53-b5d6f56cd6fb |  | note | ○ Strip Drain to be encapsulated by non-woven geotextile with minimum width of 500mm in accordance with VR 682
label | b899bcd2-c8bd-5cff-a945-b9c377b0de7b |  | note | – – – – – – – – – – – – – – – – –
label | 89f1483d-ca60-5f9a-b4b8-091de81b127b |  | note | METHOD: Visual
label | 1ee32909-3623-507e-9845-ddabbce60750 |  | note | – – – – – – – – – – – – – – – – –
label | 25ec28b1-ca83-521b-a726-e87341ff0932 |  | note | FREQUENCY: Each course of panel installation
label | a90566f5-bb76-5023-b23e-73f777256e3c |  | note | – – – – – – – – – – – – – – – – –
label | b5c9645b-ee64-5380-988d-ac39ce327143 |  | note | CATEGORY: IP
label | a9087e9c-da9c-5899-bded-c19d19f90f92 |  | note | – – – – – – – – – – – – – – – – –
label | 21b6189f-9aaa-5bae-bcef-20f921ac0bbc |  | note | RESPONSIBILITY: SE
label | d0eaa692-76d7-5579-af99-47199724b3b0 |  | note | – – – – – – – – – – – – – – – – –
label | ef3f7b60-389b-5f83-86fc-a68910c85210 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 1b85873d-365c-5931-ba71-ffafa2456732 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Panel installation-Survey reference points
label | 499a73e5-93fd-53a5-9bf3-f0b905e4e820 |  | note | REFERENCE: VR 682.21
label | 384e5d43-7dd6-58dc-bf79-1da75f81e984 |  | note | – – – – – – – – – – – – – – – – –
label | fca123bf-92d9-5968-ba10-2386311a5319 |  | note | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | 8bc85f5d-c314-5468-96ae-3c987bcddd64 |  | note | – – – – – – – – – – – – – – – – –
label | 15041c87-691b-5bd2-90c7-b67909137405 |  | note | METHOD: Visual
label | 5430a93c-e1ef-5087-9b15-924ff6d42f4d |  | note | – – – – – – – – – – – – – – – – –
label | 7447a8ab-dd3c-5d87-957c-8f9e46313df2 |  | note | FREQUENCY: Each course of panel installation
label | d6a327ff-6070-5c66-b9eb-5069eae65306 |  | note | – – – – – – – – – – – – – – – – –
label | de66e3d1-1d06-5af2-b821-88638b1d5ab8 |  | note | CATEGORY: IP
label | 03c2743e-fb21-58b8-a746-7e8c0e861993 |  | note | – – – – – – – – – – – – – – – – –
label | adc8c9ed-3498-5a7f-9db3-505951fceee0 |  | note | RESPONSIBILITY: Surveyor/SE
label | 2fc68bde-115a-5d97-8b7f-d183a1614606 |  | note | – – – – – – – – – – – – – – – – –
label | b4bf84f0-12a7-57fa-8891-85027205cfa9 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 736f350f-ab19-535b-99fd-164239d5a544 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Traceability of precast units and records
label | 6941c21b-0c69-5d10-823b-9fbcc79c2f55 |  | note | REFERENCE: VR 620.09
label | 8187dd1d-bf2e-57f4-b410-9f169827cc52 |  | note | – – – – – – – – – – – – – – – – –
label | 10c47335-e6de-5567-af77-f4010ae2ee63 |  | note | ACCEPTANCE CRITERIA: Unique ID of precast panel is recorded.
label | 23774d0e-de82-57bb-8d24-e21130a22c33 |  | note | – ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | 69e1fd82-72a8-5659-93cc-242c9f3e73e0 |  | note | – – – – – – – – – – – – – – – – –
label | 1ac1d32b-0015-5cf6-8599-cc38a14fd0cb |  | note | METHOD: Visual
label | 73c2bf58-9129-566d-96f5-233840a8d4a8 |  | note | – – – – – – – – – – – – – – – – –
label | 3b9e4aad-6b94-5cf9-a4ca-f5dc0d802ba9 |  | note | FREQUENCY: Each panel
label | e4f14066-6a4f-5f52-9abd-d318b4f072bd |  | note | – – – – – – – – – – – – – – – – –
label | 444f3911-f2ad-542d-8a85-85c88d2f76ac |  | note | CATEGORY: IP
label | bb07e712-55e3-5fdc-b417-4b8b5a8c92f5 |  | note | – – – – – – – – – – – – – – – – –
label | ecacb9ed-6431-581c-aa69-435be6fac318 |  | note | RESPONSIBILITY: SE/PE
label | 27d90366-e1a6-554b-aa73-19d1c230790a |  | note | – – – – – – – – – – – – – – – – –
label | c6031028-01f3-5d1f-8d87-eb70106d1c52 |  | note | VERIFYING DOCUMENTS: Attached marked-up drawing or installation record
date | 7c03c2c9-ac90-5c44-b7f6-cf0bd7720312 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 9. Panels installation-Conformance Survey
label | 07b326e5-cbc5-5584-b294-1d4f55725be9 |  | note | REFERENCE: IFC Drawings VR 682.06, VR 682.17, VR 682.20
label | b3debc78-0a6a-5243-8ac8-fae0d5805ab5 |  | note | – – – – – – – – – – – – – – – – –
label | 2c2e2f2c-43a8-513b-a5cd-988a4854ce5d |  | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | 88a70efb-5b16-53af-9c93-9f4b544403b5 |  | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | b8dbe46a-c35a-5476-898e-278ade318d1a |  | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | 412b1942-f533-548b-a0c8-3250480811eb |  | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | e6323a32-47e2-587f-b5cf-b60741f7cfb9 |  | note | – The wall level shall not deviate from the specified level by more than ±20mm
label | f1145391-4016-5cb4-9ed8-3326855f4dc2 |  | note | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | bad53cca-a92f-53ca-9032-400cad48261c |  | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | 739a6de6-d9d5-5618-b662-f66b17c5c2bd |  | note | Attach: Survey Report
label | b5a5d1ea-7353-5d92-8b9c-1802796b8114 |  | note | – – – – – – – – – – – – – – – – –
label | ba45a3e1-7e7a-50c6-9569-21829fd03afc |  | note | METHOD: Survey, Measure
label | 0bf2a5c6-8e3c-55c0-92a4-6d8405738d50 |  | note | – – – – – – – – – – – – – – – – –
label | 3f399745-fb1a-5c01-84a6-fe6fd853ab8e |  | note | FREQUENCY: Each course of panel installation
label | e39d040f-970f-5891-a6d4-8ccd97da3d13 |  | note | – – – – – – – – – – – – – – – – –
label | 3d83ab46-937a-5e83-b257-54783ae28ae0 |  | note | CATEGORY: HP*
label | 3095caa4-5fc3-5154-99c5-5c77b9c29cb3 |  | note | – – – – – – – – – – – – – – – – –
label | 73786f00-c168-5cdb-85cb-34558fc193d3 |  | note | RESPONSIBILITY: Surveyor/PE
label | 486d5f38-96d2-5049-96e2-3bd515aa7ca0 |  | note | – – – – – – – – – – – – – – – – –
label | 4a054169-3638-554f-ba8e-6a4422a48f2c |  | note | VERIFYING DOCUMENTS: Survey Report
date | bfee1f38-af2f-5c80-9c8a-0df388cac163 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 18c3c798-d013-556a-9b6f-1fbfbb5f3512 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | eace2a7d-3544-5833-bd67-cb34a461e93b |  | textbox | Name:
text | 10b2739b-24fd-55e5-9806-e5b274b802e9 |  | textbox | Position:
date | 48639596-4cb4-5bda-badc-97d66c05219a |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-056-CIV-SSB-Subgrade Preparation - Road | itp |  |  |  | Yes | ITP-056-CIV-SSB-Subgrade Preparation - Road Rev 0 | c47369ae-e017-4a33-93e0-e81567b3736d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 43f1a6b4-521c-559b-8716-f46c9ba08ad4 |  | note | Document Title: ITP-CIV-SSB-Subgrade Preparation - Road
label | fd3dd5b3-7d7b-5f48-b032-e8f438be3fe4 |  | note | ITP Description: SSB-Subgrade Preparation - Road
label | 4d5aaeca-1881-5e6b-9463-7d44ffbbbfeb |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c21832a1-4fb4-5bf6-9b42-2247a076b161 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 273c51aa-23c8-54a0-9ca9-9d662907b064 |  | note | Revision Number: 0
label | c4f95be2-ffb3-5317-aec3-4311cd96b507 |  | note | Revision Date: 11/08/2023
label | df307c58-caf9-5e44-af0e-ab400354add8 |  | note | ITP approved for use by: Victor Mira
label | e3771424-2177-5951-8a50-765b9db83fd7 |  | note | 1.1 Non Dependent
label | 050dfb9d-9974-5f4b-861b-7fdc3755b27b |  | note | Reference: VicRoads Section 204
label | 54fec37a-c5ae-5cea-a2d2-d31c51433b9a |  | note | 1.2 Non Dependent
label | e5b25163-fbed-5585-82e1-8dfc3a7fd833 |  | note | Reference: VicRoads Section 173
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Material Approval
label | 72862695-1125-5a19-87e8-a3086266123e |  | note | REFERENCE: VR 204.04 (C)
label | f198a012-b50c-5b02-8bd2-0bcf5bdd43ac |  | note | – – – – – – – – – – – – – – – – –
label | 969b55b7-eeff-51b8-baa2-39a6267e1ff2 |  | note | ACCEPTANCE CRITERIA: Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
label | 74f5db17-7f5d-5510-ac53-0331d7c591db |  | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
text | 21c18480-bf8f-5b5d-bae6-2a8a6985e210 |  | textbox | Enter: Teambinder Material Approval number
label | 99073c38-e0bf-57db-97b7-2b7e28f304e7 |  | note | – – – – – – – – – – – – – – – – –
label | 69170ad1-8c52-522f-939a-f1fb7b5f095c |  | note | METHOD: Document Review
label | 360c2264-ad88-588c-89e9-b9d2d355a0d2 |  | note | – – – – – – – – – – – – – – – – –
label | c4fcfbe9-e148-5bda-935d-bd0ceae7255f |  | note | FREQUENCY: Once, for each mix material
label | 2e261e98-2b0f-5492-a21a-946ab3d31782 |  | note | – – – – – – – – – – – – – – – – –
label | a2d10b82-a27f-5b76-bed1-7708277f048d |  | note | CATEGORY: HP
label | 127a1708-9efe-579c-ba39-d9a8fd49a661 |  | note | – – – – – – – – – – – – – – – – –
label | e1e10970-820d-56ed-bf76-4bb02080ea11 |  | note | RESPONSIBILITY: Nominated Authority
label | 66c931c3-bc1c-56fd-a92c-4fce157acae9 |  | note | – – – – – – – – – – – – – – – – –
label | b6ed2c20-9b1f-564f-9ccf-e5a47bd9986f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 03106aa2-ea45-5ac6-9289-2c505d5288c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Non Dependent
label | 7fc23713-ec1c-56f5-b3d8-c82560876c5c |  | note | REFERENCE: N/A
label | a7807b01-e0d0-5390-9c01-76943f23be17 |  | note | – – – – – – – – – – – – – – – – –
label | 24a28126-4db6-51e3-9608-d750166eaf62 |  | note | ACCEPTANCE CRITERIA: N/A
label | c40c586b-83af-5800-a7ee-b722a002f587 |  | note | – – – – – – – – – – – – – – – – –
label | 7d42cecd-ac90-5ed0-a21c-20a9e9454e93 |  | note | METHOD: N/A
label | 5222a907-62ee-5708-ab99-678b69d4f1e8 |  | note | – – – – – – – – – – – – – – – – –
label | 36673688-a8fe-5f44-94b8-6ba7be9038bd |  | note | FREQUENCY: N/A
label | 791b7f6d-1f45-582a-b587-e62a40c54d19 |  | note | – – – – – – – – – – – – – – – – –
label | 90232f03-c94b-52f5-bc1c-103a5906271c |  | note | CATEGORY: N/A
label | 5f2b51cf-18ab-57c0-841f-3afded2abab2 |  | note | – – – – – – – – – – – – – – – – –
label | a43175ae-62fe-505b-b60f-897cb6a773dc |  | note | RESPONSIBILITY: N/A
label | b3d4c8bc-2115-5b67-9fc8-2ba7e6143b38 |  | note | – – – – – – – – – – – – – – – – –
label | 0a941dfb-53aa-5cf4-8a63-3d1d59f36021 |  | note | VERIFYING DOCUMENTS: N/A
label | 3602c07d-7085-5791-a9bc-cff0a09980dc |  | note | Date Completed: N/A
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-Out
label | ca3cb0a6-e33a-5102-9f88-58439fec3ad2 |  | note | REFERENCE: IFC Drawings
label | 9c124884-1468-5904-9a7a-f9ace9b8a736 |  | note | – – – – – – – – – – – – – – – – –
label | 3d24f37b-6574-5264-955f-8eb067f02cd4 |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | de6e43e0-395a-507a-9fea-f77fa852ce20 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | ec380872-4b3d-585f-9495-643285373ea8 |  | note | – – – – – – – – – – – – – – – – –
label | 17b002d8-2d9d-56b7-bc94-9d35c15f543b |  | note | METHOD: Verify
label | d2f2867c-c725-512e-8ec0-4603d0373de9 |  | note | – – – – – – – – – – – – – – – – –
label | b7e924df-e3ee-569c-9daf-9828694098ad |  | note | FREQUENCY: Prior to commencement of excavation
label | 4788bd36-9cc8-53c0-b954-5f61fcd2dd6e |  | note | – – – – – – – – – – – – – – – – –
label | 65cca9f7-fea9-5b6d-98e5-d07d7d2b5457 |  | note | CATEGORY: IP
label | 97cf5727-7833-556d-977d-2a0b6fda2265 |  | note | – – – – – – – – – – – – – – – – –
label | 65fe314d-7685-5321-a54e-36fa8794a140 |  | note | RESPONSIBILITY: SE/Surveyor
label | 976675df-2906-5be8-808d-2e0126fc27e7 |  | note | – – – – – – – – – – – – – – – – –
label | 9814210e-82df-53c1-8973-b828b0d2710a |  | note | VERIFYING DOCUMENTS: This ITP
text | e5274ee4-d38e-5efa-80e8-c59632623e0a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Inspection of Subgrade Material-Subgrade Material Properties
label | 9a7fb192-5f58-5baf-b993-32b2908b58a6 |  | note | REFERENCE: Section 204.06 (c), Section 204.06 (e) IFC Drawings
label | c4339e6c-ad67-573b-ac97-73935c402f87 |  | note | – – – – – – – – – – – – – – – – –
label | d12d64b4-4640-5eea-996b-893b7842669a |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | b51e5b02-6e5a-54c2-a776-912d81a88538 |  | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 2576035e-f803-5df4-816b-119461caa397 |  | note | ○ Assigned CBR ≥ 2.5%
label | b3918b64-014a-5b53-bb67-860de0577f60 |  | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | 77de24b1-24d7-556b-9618-e85388d35bd4 |  | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | d428b87a-62f0-5abc-bff4-12c5c705d25f |  | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | 9c3c3cdb-a2f1-5457-a2fd-878a49fbb6c4 |  | note | Attach: Laboratory testing Verification:
text | 9f88e21c-fde8-5859-b780-7c7ae86a66c8 |  | textbox | Enter: Type A fill Lot Number:
label | b845a033-d7c2-59ab-9b0c-7ccba176f38f |  | note | – – – – – – – – – – – – – – – – –
label | 4be2c54d-e431-5829-8075-3b1c4ed5a175 |  | note | METHOD: Verify-Document Review
label | b4bf38ba-dc97-534d-9258-356ea9020450 |  | note | – – – – – – – – – – – – – – – – –
label | a652ef41-06e5-5108-9f9c-1151d9f5f321 |  | note | FREQUENCY: Each lot
label | 2fe936a8-30d6-5281-bec6-78d2b59738fe |  | note | – – – – – – – – – – – – – – – – –
label | 4422d136-0e87-599e-8239-50f383c7e8fc |  | note | CATEGORY: HP
label | e3c54ca0-ce71-5c2a-bef6-7d18ef19ac38 |  | note | – – – – – – – – – – – – – – – – –
label | d444da0e-7d61-539e-8aad-f1af07b9a51c |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 429aa6b7-49ef-5f86-bb5e-3293de259e2d |  | note | – – – – – – – – – – – – – – – – –
label | be3fa3fd-dd88-5320-903c-48928607e25c |  | note | VERIFYING DOCUMENTS: This ITP/Test Report/Referenced Lot number
text | 98ffe92d-3d8b-5e46-8188-183f4cb8d0ea |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Material classified as silt
label | 21c0c27d-724a-58b4-b0a2-580c089a1773 |  | note | REFERENCE: Section 204.04 b)
label | 70dd408c-793b-5852-85d3-ac0fd2bce180 |  | note | – – – – – – – – – – – – – – – – –
label | 7628b37d-15c6-5e93-9e44-5bfabdba07e5 |  | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | 9f1f25ca-c335-50f3-94af-421fae5cd320 |  | note | – – – – – – – – – – – – – – – – –
label | 09f9440d-debe-52ea-9579-f171504e2225 |  | note | METHOD: Document Review
label | a69488af-9cd8-5659-a02b-a0690ef39056 |  | note | – – – – – – – – – – – – – – – – –
label | 5dd1ba1b-e446-536b-8a3f-9b7926f2c0d1 |  | note | FREQUENCY: Prior to commencing
label | 7b4fac0d-7135-5dec-9f76-9cbef350bcb7 |  | note | – – – – – – – – – – – – – – – – –
label | 4ec2fd2d-1401-551c-bca2-37e1ca2bf1df |  | note | CATEGORY: HP
label | d0cf831e-fbc8-5001-be13-191c08cb6b02 |  | note | – – – – – – – – – – – – – – – – –
label | ba6af5a2-c58d-5f25-b500-4c4d2527fe00 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 1e6676c4-65bb-5cbb-9b43-e40ba7fa2bed |  | note | – – – – – – – – – – – – – – – – –
label | a82bdc1d-5e8f-59cd-b799-017a7b915bf8 |  | note | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation, Signed ITP/ records
text | 6cbadbab-282e-55be-99f3-e64b78d1b860 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Acceptance of Rock Subgrade (where applicable)
label | f1b4ab8d-656a-5380-88e0-78c061e55fec |  | note | REFERENCE: Section 204.06 f)
label | e5dee5ea-ff0f-5b79-989a-d6b63c2b2fc3 |  | note | – – – – – – – – – – – – – – – – –
label | e5643806-96a8-50af-b396-c5492e8113db |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 9374921d-471b-55b4-a848-f0a556704c88 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | fc95fd9a-6bb5-578f-b2cd-50824bb644e6 |  | note | – – – – – – – – – – – – – – – – –
label | 3dee2f0f-b636-5d95-a0ce-dec007396cf4 |  | note | METHOD: Site Inspection/ Document Review
label | 754765f0-3b95-5cb4-8f56-1c4ccd9592fd |  | note | – – – – – – – – – – – – – – – – –
label | d61c5edb-d893-57ef-8323-5490d18bbc3e |  | note | FREQUENCY: Prior construction of the regulating layer
label | d2c562d1-2460-50c0-8a6b-052f44089179 |  | note | – – – – – – – – – – – – – – – – –
label | fffc0ae2-ae73-5d30-b06b-16a5857b4a5e |  | note | CATEGORY: HP
label | 4b0c2042-4483-5220-84b4-7d48d866db6e |  | note | – – – – – – – – – – – – – – – – –
label | 9ba87b82-10d3-52eb-b8c4-f4906cfc23be |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 52d51c3a-cfa4-5eb9-a9aa-cfcf79997bec |  | note | – – – – – – – – – – – – – – – – –
label | 475efa8e-0125-5129-8283-02fc54367e40 |  | note | VERIFYING DOCUMENTS: This ITP
text | a5304167-9904-5334-ad52-c0d7cfb22d30 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Unsuitable Material
label | 263648d1-3b90-5917-b80a-6f991e3ddd59 |  | note | REFERENCE: Section 204.07 d)
label | 0c81f2e8-f8c6-528e-bf33-0e5f92a35c28 |  | note | – – – – – – – – – – – – – – – – –
label | 40385ad7-4258-5a78-9b7a-9a00acf0cf39 |  | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | dfd4e832-54c2-56f7-8419-81374646c17e |  | note | – – – – – – – – – – – – – – – – –
label | b2c2ae2b-bad8-5a70-957f-6a77b6ba4489 |  | note | METHOD: Visual inspection
label | 882ef4bc-11b5-5566-bf65-61b1e45ccdcb |  | note | – – – – – – – – – – – – – – – – –
label | 906b7737-a966-50bf-bcd2-aa586a67c9e7 |  | note | FREQUENCY: Each lot
label | a4c86912-cbaa-5283-ae2f-2fbb65bc89ff |  | note | – – – – – – – – – – – – – – – – –
label | 525545d4-e116-5a2b-b09d-290beb6936f8 |  | note | CATEGORY: HP
label | 4b67f3b2-745c-5a2c-8fa3-2aed71d49c40 |  | note | – – – – – – – – – – – – – – – – –
label | 19260519-9ba4-5c81-a6ea-b0b75742cf29 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | d2e81e58-dd36-5fd6-818d-43296fc29bdc |  | note | – – – – – – – – – – – – – – – – –
label | b761b80f-92cf-59ce-a5af-29d10ad1f065 |  | note | VERIFYING DOCUMENTS: This ITP
text | ab19cf57-64d6-58d5-9e25-e2a0b9465a97 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Groundwater
label | 152e1013-f707-522a-8e78-3bca87fde8fc |  | note | REFERENCE: Section 204.06 h)
label | c0e3c65c-a7f0-520e-9dfb-122de4ccba16 |  | note | – – – – – – – – – – – – – – – – –
label | 5115ecd2-7d5a-5d4e-9566-b7386c86bd03 |  | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | b14fa0dc-c5b5-5dda-aada-d828d5beeb6b |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 30781549-88cc-5914-ab5c-7fce6afaaa64 |  | note | – – – – – – – – – – – – – – – – –
label | 3f39096c-6973-54b8-a3e8-a52c21e26ef3 |  | note | METHOD: Visual inspection
label | fdc3d21b-6fe0-51e2-9516-994f405a9234 |  | note | – – – – – – – – – – – – – – – – –
label | f35ba411-65fc-55eb-9f42-40e4982043c1 |  | note | FREQUENCY: Each lot
label | 9785ac06-6456-531a-9aab-0a0520fa9a51 |  | note | – – – – – – – – – – – – – – – – –
label | b6dc25d8-1ee3-532d-9d03-53f9259ed7e6 |  | note | CATEGORY: HP
label | baa9e1c5-baee-56d0-8e6a-47c4f062fbbd |  | note | – – – – – – – – – – – – – – – – –
label | 70e757e7-16f3-5b59-92c3-8feec91d9bb4 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 2f31140c-68be-592c-aa36-d667c6f2fc26 |  | note | – – – – – – – – – – – – – – – – –
label | bf5ae979-82d8-593f-82f3-cb4cace083b5 |  | note | VERIFYING DOCUMENTS: This ITP
text | def140bd-38db-596b-b360-d5ad09c3cdd4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Cut to Fill Zones
label | ddcfb788-d94c-5697-8841-4b16c2f4e110 |  | note | REFERENCE: Section 204.06 g)
label | d41763af-bcfe-5419-b6d0-af1359b11072 |  | note | – – – – – – – – – – – – – – – – –
label | 11e8e4d9-8fb9-506f-910b-777f5aa1a7fe |  | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | 618026d6-1010-55e0-98e6-ca612b7f222b |  | note | – – – – – – – – – – – – – – – – –
label | 919d220f-7780-54bf-a21f-91700f16d9d2 |  | note | METHOD: Site Inspection
label | c5583104-8770-5120-8367-0862de976328 |  | note | – – – – – – – – – – – – – – – – –
label | 33b7f408-5ba3-55eb-8c48-edc7e1ad3283 |  | note | FREQUENCY: Each lot
label | bfc7900f-7e5f-5945-a6a2-50e88d3ef1de |  | note | – – – – – – – – – – – – – – – – –
label | 143e6b06-f90f-55d9-8356-ed6308e3aa04 |  | note | CATEGORY: IP
label | ba9ba640-a25b-5233-974b-efe22267ade0 |  | note | – – – – – – – – – – – – – – – – –
label | bb198729-6790-515a-aa5a-9ed17feaac4d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8d6e5b43-6c6e-5a86-8719-2bd4ce1a69da |  | note | – – – – – – – – – – – – – – – – –
label | cb56ef4a-5908-501e-8634-13c3a7442a41 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | d023d1c0-fc18-5b02-b1de-d87f9425b1d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Proof Roll
label | 3b50f972-5138-52bc-b19a-002be202d65d |  | note | REFERENCE: Section 173
label | a96d8080-d2e6-5c46-8d4d-26a6d2575db3 |  | note | – – – – – – – – – – – – – – – – –
label | 1f6fe37a-7e89-5bb4-a631-e60a007e3e21 |  | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 446745fb-0847-5585-a3d2-c30bff017d95 |  | note | – – – – – – – – – – – – – – – – –
label | a63518ff-0ae2-5e2c-ace4-257438c13126 |  | note | METHOD: Visual inspection
label | bcf1accc-0e7a-50e1-bd32-0ca79736d882 |  | note | – – – – – – – – – – – – – – – – –
label | 8785a5d3-750d-539a-bcb9-8cad567a38d4 |  | note | FREQUENCY: Each lot
label | 9d3546ac-2f88-5c6e-a588-601c9a41f6e7 |  | note | – – – – – – – – – – – – – – – – –
label | 90dc1a5f-9ed3-57de-8a78-8373f7821cfd |  | note | CATEGORY: HP
label | ecf82675-f1c4-51d5-8608-fee86ea5a2da |  | note | – – – – – – – – – – – – – – – – –
label | 787ba668-dfef-5b8a-82b4-abc9294bb95f |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 920f8aff-c366-5870-92f9-0ca2f5fec438 |  | note | – – – – – – – – – – – – – – – – –
label | 72d3af76-fc09-50ee-8dfc-55eeb0191980 |  | note | VERIFYING DOCUMENTS: This ITP
text | fef5ca9d-5bc5-5d0f-8d19-dee01bcbfd8d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Compaction Testing
label | d261768c-41b4-5a41-a790-056ff1c9fd93 |  | note | REFERENCE: Table 204.131
label | 98aeec87-3f3b-5025-9423-d41767d4618a |  | note | – – – – – – – – – – – – – – – – –
label | bb15fd21-45f7-5628-b3f2-355fa70e11aa |  | note | ACCEPTANCE CRITERIA: All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | f4d00e56-a660-5218-857c-c709aa90b1b9 |  | note | ○ Ripped and re-compacted material below Cut Floor Level
label | b495fe56-ee36-5ab1-8b3b-4f66fa351187 |  | note | ○ Scale A: Characteristic Density Ratio 99%.
label | 043dbcdc-ed9d-5643-9946-2a16b439d8aa |  | note | ○ Scale B: Characteristic Density Ratio 98%.
label | d01b9687-ceb4-5dc5-80b5-125220127a1f |  | note | ○ Scale C: Mean Value of Density Ratio: 100%
label | e48f4bb7-b774-5ddd-8eec-b2d836924a17 |  | note | Attach: Compaction Test Result:
label | c4602536-8e26-591b-bf8d-cf1a8693bb49 |  | note | – – – – – – – – – – – – – – – – –
label | 218b1e14-8250-5d0e-987d-d3140bc04821 |  | note | METHOD: Document Review
label | d0550e8d-8474-575c-a1d9-ebb9763cd94c |  | note | – – – – – – – – – – – – – – – – –
label | 7a1f6b90-cbd5-59ce-8e88-c92697e54a87 |  | note | FREQUENCY: Each lot
label | 88ebffb2-6f51-5c01-8227-db0026f0d2d3 |  | note | – – – – – – – – – – – – – – – – –
label | 9fbfcd89-40b7-5d87-837a-29dec83ee075 |  | note | CATEGORY: IP
label | 5c40642a-91ec-554a-b3cb-95823373a4c0 |  | note | – – – – – – – – – – – – – – – – –
label | bb09f10f-88d5-5ccd-8c57-d6fc4a0ec15a |  | note | RESPONSIBILITY: PE/SE
label | ad57c6f2-d44d-5196-aef7-cf5cb4a1b5cd |  | note | – – – – – – – – – – – – – – – – –
label | 4163a074-01dc-5407-b9ac-88620c8d2f9f |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report
text | 439a0e88-8eca-551d-8fb3-b59c57f5ecc1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Post Compaction Material Property Testing
label | ac99a703-9313-5218-9bbd-45ad5139e52d |  | note | REFERENCE: Section 204.04 (c), Section 204.14 (a) and Table 204.141 For Scal A Section 204.14 (b) for Scale B IFC Drawings
label | ba418250-5f19-5fba-80c7-93ab9deb293c |  | note | – – – – – – – – – – – – – – – – –
label | c119b231-a987-5fe2-9419-6cd1db143982 |  | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
label | 6a1aafb4-6e09-5fe9-a4d6-362182d574c0 |  | note | Scale A:
label | b5389c87-068e-57ff-b21a-140c04da34ec |  | note | CBR and Swell as per IFC for design packge:
label | f3052f6a-97f5-5412-91c6-b96ee9c23fab |  | note | ○ MRP-DPK-087-00-CDR-0002-0
label | bb34619d-c722-5c44-b5ae-37650617d181 |  | note | ○ as per table VR 204.141
label | 432a4400-ac83-5ca7-8b7f-4b4293f743ff |  | note | Scale B:
label | 196ff042-b0cd-5744-846f-fe2a1bf261de |  | note | CBR and Swell as per IFC for design packge:
label | fd83fb0c-22fe-5fff-8987-93d82143141c |  | note | ○ MRP-DPK-087-00-CDR-0002-0
label | 0a9e69ae-0987-5b67-a59c-a41c2254a4ca |  | note | ○ First Lot for Max Particle Dimension:
label | ba62fdf4-6fc3-57e0-9e1a-621c4be40955 |  | note | ○ After compaction Type B material shall have a maximum particle dimension of not more than:
label | ef4d0d6e-e46a-534d-b8dc-a217094dde62 |  | note | – 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
label | 5d5ecdd7-d0d5-55f7-aac4-33cb17cd0d51 |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 84f66be1-7eda-58f5-b23f-d3c7b7c08195 |  | note | Attach: Post compaction test results:
label | 45e3424b-4fce-5d69-901b-10180ec151da |  | note | – – – – – – – – – – – – – – – – –
label | 539fafb4-685b-5f4d-8d2e-a7332447d0e3 |  | note | METHOD: Review Document
label | ee861b40-acfa-5d56-92ae-e668359e97bb |  | note | – – – – – – – – – – – – – – – – –
label | b2f834a2-d9e8-5441-8bf6-a540d1fb17c8 |  | note | FREQUENCY: Refer to Section 204
label | 14d394ad-0fa4-5e45-8268-05cce7ef1c2d |  | note | – – – – – – – – – – – – – – – – –
label | e15d7c65-92c6-5df9-a5f3-7004293083f3 |  | note | CATEGORY: IP
label | 57a9fa61-a0e6-5fd4-a3e2-e2a3c86d2d22 |  | note | – – – – – – – – – – – – – – – – –
label | e92f37d2-72f8-56ad-9c01-7670a63f6220 |  | note | RESPONSIBILITY: PE/SE
label | ccc79817-abe0-54a0-8357-d5c3ebfa678e |  | note | – – – – – – – – – – – – – – – – –
label | f71c1277-2d6e-58dc-adc4-846fc004ab88 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
text | 44471867-362e-531c-b2a0-51f81fe2b6dc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Survey Conformance
label | 08321b5e-67c1-5368-80c8-592b2e102b26 |  | note | REFERENCE: VicRoads 204.03f,g and h
label | 9bc124d4-d01a-5328-8f1b-1fda15bf1fcd |  | note | – – – – – – – – – – – – – – – – –
label | 6b78f629-e7fd-55dd-b2e5-6a566f62d724 |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | c272b85b-6b8f-50df-af67-981fee50fc7e |  | note | Level tolerances (Scale A):
label | ffd60f9c-54df-5f24-8224-09343a499d1f |  | note | ○ Range x = +5, -15mm
label | d649d53d-0c6e-5844-9335-bc99447f2884 |  | note | ○ Max S = 12 mm
label | 66d9d045-8aed-52a1-973e-79a88210fa64 |  | note | ○ 80 measurements per lot
label | 13836022-acde-534d-82b5-d00288961110 |  | note | Level tolerances (Scale B):
label | c96be512-c037-5db1-9816-65f2971d5509 |  | note | ○ Range x = +5, -25mm
label | b68d04c4-5b2d-54b1-89a7-7389bd1256c9 |  | note | ○ Max S = 15 mm
label | 237c2e45-0de3-520e-94d1-3cd07e25331f |  | note | ○ 40 measurements per lot
label | f8f7ea42-f4ac-5946-956f-65272f3b7b77 |  | note | Level tolerances (Scale C):
label | b0205a51-7117-5688-b6f0-8abc8c07f63c |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 8a9ec1ac-ae9d-5e88-9d6d-1613af00f74e |  | note | – – – – – – – – – – – – – – – – –
label | f8fbeb2e-2d28-5bdd-8bfe-ceba3e509969 |  | note | METHOD: Review Document
label | ca3cbdbb-ef47-5329-916b-8892b6eab40c |  | note | – – – – – – – – – – – – – – – – –
label | df4eb765-a079-5692-8b0c-41c8f651b230 |  | note | FREQUENCY: Each lot
label | 20f347f0-3b05-5764-a09b-25100f76d129 |  | note | – – – – – – – – – – – – – – – – –
label | 97d41209-01db-5be6-82ec-8f53bbc8eab9 |  | note | CATEGORY: SCP
label | ed2b9122-9072-5c85-b7cf-b18fb3b4add8 |  | note | – – – – – – – – – – – – – – – – –
label | c59a9788-cb66-5a05-a73f-964b0b58ddf3 |  | note | RESPONSIBILITY: SE/Surveyor
label | 82aa7d03-47e9-5542-8cae-1a746deb6b4c |  | note | – – – – – – – – – – – – – – – – –
label | c8bbeafd-7197-5c2f-a975-70a10f780ca8 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Survey Report
text | 742513f2-d118-510b-8b49-efe6b50d9b07 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c05c783b-5b0f-519a-88f6-b1daaa6d8cca |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2f7954a7-3d9c-537a-a150-28fb0564b9d6 |  | textbox | Name:
text | 278a50b3-e91e-5274-9bcd-7533476aae5f |  | textbox | Position:
text | b33132bd-0368-52c3-8914-c4c21fa16718 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-013-CIV-SSB-RSS Walls-Fill Placement | itp |  |  |  | Yes | CHK-013-CIV-SSB-RSS Walls-Fill Placement Rev 2 | cda7bc59-5f3c-45bd-945d-15d1241d5fc0
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 8334ad17-b4fe-5a39-8933-6e2232e47c6f |  | note | Document Title: CHK-013-CIV-SSB-RSS Walls-Fill Placement
label | 192ab00b-cfcc-51e2-a101-f1f3d4962e75 |  | note | ITP Description: SSB RSS Walls-Fill Placement
label | 15bf60e5-f731-50e0-94a0-4204a54618a0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | d761d5da-7a1d-5858-95fb-ef8281bd6adb |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 23ccd149-92c4-500d-b7a4-6ea6a84f0460 |  | note | Revision Number: 2
label | 9776ccb6-7134-5562-88c3-73c40565baf1 |  | note | Revision Date: 18/3/2024
label | c0959d49-e4c7-5c75-845f-9b897816cb40 |  | note | ITP created by: Victor Mira
label | d3f4310c-a9b6-5ce4-a53c-b86d46191493 |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1. Soil reinforcement-Straps
label | 1971b550-2524-53c3-a8c3-205ecf6a1118 |  | note | REFERENCE: 682.08
label | 1720aa8f-2986-5c24-94b2-70972467b300 |  | note | – – – – – – – – – – – – – – – – –
label | aae46a44-873e-5d09-91e0-1802bfc46827 |  | note | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | 9c32d158-5a79-5f82-8d65-34e5885e346b |  | note | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | b395dcc8-852a-510b-b857-2791a32860af |  | note | – – – – – – – – – – – – – – – – –
label | 1319f167-ea43-577f-9594-80d4e4badfed |  | note | METHOD: Visual
label | 3c4e9bd6-a8c0-5303-82fc-c7591cb4adcd |  | note | – – – – – – – – – – – – – – – – –
label | 01f6e0b4-d558-5cc6-8ae2-81a3a832fb31 |  | note | FREQUENCY: Each strap
label | 3e678fd7-057f-59c7-bd95-c8dd16810592 |  | note | – – – – – – – – – – – – – – – – –
label | 5332a9c1-829d-5f05-a18b-18477c7b7bd3 |  | note | CATEGORY: IP
label | 3aae7819-e406-5d3d-90f7-5f38c8ac94c0 |  | note | – – – – – – – – – – – – – – – – –
label | e0743194-4b2b-5f6a-a9f6-746c0ea936c3 |  | note | RESPONSIBILITY: SE/PE
label | eadfc9f0-98d7-5694-a715-1e002f20dda1 |  | note | – – – – – – – – – – – – – – – – –
label | 1c945a30-f6b3-5c14-9e58-e2a120aa94a8 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 13933cdc-8d3d-5e81-897e-c7cee194652b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2. Soil reinforcement-Straps
label | 09114d5f-052f-52f7-880c-9cce84df5bb3 |  | note | REFERENCE: Installation manual
label | 36de66df-c4ca-55be-8d72-5e9fe1ad9c63 |  | note | – – – – – – – – – – – – – – – – –
label | 6fafeadd-798a-5073-add6-6f02170758fd |  | note | ACCEPTANCE CRITERIA: Correct number of reinforcing element shall be attached to each panel
label | ec68a1f1-ceb1-5857-8a43-b61ccf732fd7 |  | note | – – – – – – – – – – – – – – – – –
label | c40b65cd-9da7-5b63-8c47-15f11e572f67 |  | note | METHOD: Visual
label | 2cd4cd8c-15ea-54e4-9e03-20760bf2ecbb |  | note | – – – – – – – – – – – – – – – – –
label | 4f410dcd-8790-5a56-b251-f2b1b496fc97 |  | note | FREQUENCY: Each panel
label | 86899828-a9b5-50ee-b315-1b6e942b9490 |  | note | – – – – – – – – – – – – – – – – –
label | d7e13b8e-197e-5191-98de-973bb4d15b5c |  | note | CATEGORY: IP
label | 49f3f0cc-5fcf-519e-b5a7-0dd210176f98 |  | note | – – – – – – – – – – – – – – – – –
label | adc3cc69-19a6-5adc-9c01-cc838d34430e |  | note | RESPONSIBILITY: SE/PE
label | 7f2a8fbd-5bf2-51a9-899a-ac742707a782 |  | note | – – – – – – – – – – – – – – – – –
label | 085e1d42-6bf6-5edf-9836-ca74cda70925 |  | note | VERIFYING DOCUMENTS: This Checklist
date | b372d29a-a1bc-5491-b2df-5c8e6d7b88ed |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3. Soil reinforcements-Connections
label | 345ea69a-6aad-520c-bcaa-c560a10c2c0a |  | note | REFERENCE: IFC Drawings, Schedule of lenghts
label | b1f1a86b-5ef2-58b4-919e-e0762eb9c124 |  | note | – – – – – – – – – – – – – – – – –
label | 9d24d19e-6a25-5396-ba49-02ec6f53e2e3 |  | note | ACCEPTANCE CRITERIA: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | fc756f05-1d29-59bd-960c-76f4ef2e38ad |  | note | ○ Bolts are to be snug tight.
label | 6043db55-2229-5c88-9502-925dd5f7cce2 |  | note | – – – – – – – – – – – – – – – – –
label | 88d0e03c-ef39-5799-b844-17ff8ef95a6a |  | note | METHOD: Visual
label | f908145f-4e3e-543a-a376-693f58905eac |  | note | – – – – – – – – – – – – – – – – –
label | 537cbc9b-8fed-513b-9e0f-e20f3d0c5bb3 |  | note | FREQUENCY: Each Fill Layer
label | f19c25d7-d6f5-5f5a-bf0f-0af5fabeda7b |  | note | – – – – – – – – – – – – – – – – –
label | e3ee187c-f162-56fb-880c-b439616d6df9 |  | note | CATEGORY: IP
label | 66f5f8a0-a8fe-5c1a-be9f-b6f13b63f95e |  | note | – – – – – – – – – – – – – – – – –
label | 332937f0-0030-5892-a127-5076a7d30f1e |  | note | RESPONSIBILITY: SE/PE
label | e4f2e383-cacf-54a6-a4f8-dc2919723bc2 |  | note | – – – – – – – – – – – – – – – – –
label | 35e250f2-b9ec-5f27-bd44-5e7ea21310df |  | note | VERIFYING DOCUMENTS: This Checklist
date | 5b13cb25-724f-5da7-8451-faaa17c21e58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4. Soil reinforcements-Plan arrangement
label | 0475f369-266a-5525-a412-398859c4c8cd |  | note | REFERENCE: IFC Drawings Arrangements: VR682.06
label | 6ff97acd-5cf7-5aa1-a513-7fdd934e1eda |  | note | – – – – – – – – – – – – – – – – –
label | 7e64ca49-ac34-554b-a0d9-bc1727496a71 |  | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | 068c875b-41a3-589d-ad56-e983cd4ae8aa |  | note | ○ Grid Strips shall not overlapped
label | b0792032-df35-52f1-99b6-82a1243c7d3e |  | note | – – – – – – – – – – – – – – – – –
label | cbea7ff1-d573-5c4c-a8e3-f863910b1ec4 |  | note | METHOD: Visual
label | b65a0374-fa3b-5db9-b40f-49fc03a2adc1 |  | note | – – – – – – – – – – – – – – – – –
label | fe7657b0-dc53-5971-a987-a39ffb0f2ed2 |  | note | FREQUENCY: Each fill layer
label | 5ca42f04-e02e-5082-a733-74af66739e4d |  | note | – – – – – – – – – – – – – – – – –
label | 2ebf0c5b-7426-56b9-aaa2-196ce37f434b |  | note | CATEGORY: IP
label | d48a02ac-76c5-538c-9caa-7d88cd7faf73 |  | note | – – – – – – – – – – – – – – – – –
label | 1b0c7db8-92ac-5176-8b3f-48c104e8b2a5 |  | note | RESPONSIBILITY: SE/PE
label | ff8ff4a8-1fc4-50f8-bdda-ef5957330ffb |  | note | – – – – – – – – – – – – – – – – –
label | d8c315fd-ff90-53e5-ac76-c210dd6cc097 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 13548385-bf90-5c78-ba1a-5d6f24aa9d8e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5. Soil reinforcements-Plan arrangement
label | f388bf7d-f388-5c97-ad42-130f75aa2370 |  | note | REFERENCE: IFC Drawings Arrangements: VR682.06
label | 467ec53c-849a-5c39-a01f-1eb88a2d9c71 |  | note | – – – – – – – – – – – – – – – – –
label | f399f7c0-28af-56ba-ac0c-c89602095b60 |  | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | d9d482ae-2d1b-5d4b-bc7d-3b81ae78e321 |  | note | ○ RSS used in conjunction with a bridge abutment shall be independent of the bridge structure (i.e. Straps shall not cross pile cap boundary unless noted in IFC)
label | 2b2973d4-d9e2-56c6-abb9-22d2a66ddbea |  | note | – – – – – – – – – – – – – – – – –
label | 7d6e65ff-04fe-524f-a1d2-d66713140a6f |  | note | METHOD: Visual
label | 7e9a4d66-886e-5192-960d-e5386ccc0fc6 |  | note | – – – – – – – – – – – – – – – – –
label | 41898d6f-38f4-586c-9d14-f54112ffc8f7 |  | note | FREQUENCY: Where applicable
label | fc222203-8654-59ba-b830-ab795b0865ee |  | note | – – – – – – – – – – – – – – – – –
label | f7d90e39-5a4c-5d80-b62c-16bdcd237928 |  | note | CATEGORY: IP
label | 2323e64d-ae9c-5184-8570-4fda9318ceb1 |  | note | – – – – – – – – – – – – – – – – –
label | 29389113-36f3-535a-b162-6bb73f284654 |  | note | RESPONSIBILITY: SE/PE
label | 03b0a87d-2530-5471-95a3-281eb8f1cf61 |  | note | – – – – – – – – – – – – – – – – –
label | 0af6822b-3f00-5338-bebf-790fc4318ec5 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 2c27872b-2d59-53ad-b5ed-3c8d9b8cf11e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6. Soil reinforcements-vertical deviation
label | c75cecab-fe77-50ce-ae13-f20bac2997cc |  | note | REFERENCE: IFC Drawings
label | ee09c3a9-2fa9-5a0e-86c6-1dd657cc6892 |  | note | – – – – – – – – – – – – – – – – –
label | bb4fac1c-932e-531c-a843-395b239d462f |  | note | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height.
label | cba87e6a-f4f8-52e2-bc0a-7552fb1f6092 |  | note | ○ Avoid clash with drainage as directed in IFC Drawings.
label | a73e4a4a-5563-5c5f-b97f-14b615805567 |  | note | – – – – – – – – – – – – – – – – –
label | 73ec3bf6-274c-52b0-8671-92763662edfc |  | note | METHOD: Measure, Survey
label | 6e730456-f58c-5539-a5c4-eef922f62ae8 |  | note | – – – – – – – – – – – – – – – – –
label | b8fa5c4f-d98a-58b0-b57d-5cb29e473711 |  | note | FREQUENCY: Each fill Layer
label | 3bad7a8d-4f0e-513a-90f7-524362c61296 |  | note | – – – – – – – – – – – – – – – – –
label | 11af4add-ffc5-5f2e-8e65-9f6c8d5d9a5f |  | note | CATEGORY: IP
label | 981671b7-aec1-5955-ab3a-f4990a61cb47 |  | note | – – – – – – – – – – – – – – – – –
label | a7e6317a-856a-54b5-987f-a9db1a3c622a |  | note | RESPONSIBILITY: Surveyor/SE
label | 12f0e907-3aff-5da0-b4a4-95d7375cfea2 |  | note | – – – – – – – – – – – – – – – – –
label | 2c9f5679-a91d-504b-afb8-fa9e4d27a72b |  | note | VERIFYING DOCUMENTS: This Checklist
date | 99caa4dd-45ce-523c-9ba3-f997f3af0d79 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Fill placement-Protection of Straps
label | c04dc4ac-84b2-589f-b658-9cfb8757dc2f |  | note | REFERENCE: IFC Drawings
label | 9e68b99f-6e61-5ec2-9bc6-f04d8b4a05b3 |  | note | – – – – – – – – – – – – – – – – –
label | 3ec5546d-f43d-5eee-8832-bbf3be74f8a6 |  | note | ACCEPTANCE CRITERIA: A minimum of 200mm select fill required to protect reinforcement elements before tracked machines or vehicles are permitted access over soil reinforcement as per dtp specification 682 and ensure stability of the top layer of reinforcement.
label | 2626ce50-c742-5a7b-a852-8b142cc7a7d8 |  | note | – – – – – – – – – – – – – – – – –
label | d422a546-bdde-59c7-b4a7-f1e73fbe9e28 |  | note | METHOD: Measure
label | 238b197a-915f-5d19-9fd9-2ca5672def65 |  | note | – – – – – – – – – – – – – – – – –
label | 1c54369c-f6dc-5380-8033-3cc5e93de575 |  | note | FREQUENCY: When applicable
label | b00dd57f-8be6-5209-b662-6fcedffddc15 |  | note | – – – – – – – – – – – – – – – – –
label | 79a997fe-796c-5f82-8c81-435916761c6e |  | note | CATEGORY: IP
label | 69d9a8bb-6b5a-5754-9183-0dd6d2c8f240 |  | note | – – – – – – – – – – – – – – – – –
label | f31a1e4f-1e86-54a4-aa22-8d0734476663 |  | note | RESPONSIBILITY: SE/PE
label | ce21fafb-02f8-5000-b43c-d65593459795 |  | note | – – – – – – – – – – – – – – – – –
label | c05644b9-c828-5173-965d-57ef54075d60 |  | note | VERIFYING DOCUMENTS: This Checklist
date | b9a02604-6ec7-5072-887f-d0fa5ece5cad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Fill-Pacement
label | ed550cd7-0ccf-555b-87af-6147dc731d0f |  | note | REFERENCE: 204.10
label | a4e99d81-2a54-570c-9145-b75ed8ce9ae0 |  | note | – – – – – – – – – – – – – – – – –
label | a2cbfe6f-ac2f-5e36-a057-b343f55e77cc |  | note | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
label | 2f1cab84-2977-5504-bc10-c2390476e304 |  | note | ○ All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
label | e1d43eee-ab4d-5abd-a410-d45e66940879 |  | note | – – – – – – – – – – – – – – – – –
label | ebe0e150-f199-522a-b1b8-083a9e69896f |  | note | METHOD: Measure, Visual
label | 1f92fcf1-2a18-50fd-9ac6-dd4ebc786e31 |  | note | – – – – – – – – – – – – – – – – –
label | 03117531-9c9e-5a76-9e42-2fd25a4d0794 |  | note | FREQUENCY: Each fill layer
label | 1376e580-a4af-569a-8742-a851429bf309 |  | note | – – – – – – – – – – – – – – – – –
label | 492d9a9f-1cd4-5007-a088-71ee47e59329 |  | note | CATEGORY: IP
label | dd4e710a-5805-5f95-bb6e-a2e7ee5a3727 |  | note | – – – – – – – – – – – – – – – – –
label | b5780d96-9707-5cb9-9a11-1a3d045c2394 |  | note | RESPONSIBILITY: PE/SE
label | d56d417b-4568-5aa4-8b7e-a51192b5ac7c |  | note | – – – – – – – – – – – – – – – – –
label | 5f235724-9736-52c0-83eb-0107bb148d3e |  | note | VERIFYING DOCUMENTS: This Checklist
date | d8ca780c-0825-52e6-8d1a-802fb47b0764 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 9. Select backfill-moisture content
label | 34132710-9e7b-5394-b2db-e7f8ab5c7aa2 |  | note | REFERENCE: IFC Drawings
label | 0308d2b2-f716-5fa3-bf1a-d14b4f9ef2df |  | note | – – – – – – – – – – – – – – – – –
label | 6d2ec039-45de-57fd-bac8-7abb049002a6 |  | note | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
label | fe0f3e4b-1005-54cb-bba2-0ca52da98cdb |  | note | – – – – – – – – – – – – – – – – –
label | ffebdb8f-62f6-5d53-8b4c-31fb022cc7c4 |  | note | METHOD: Measure
label | ce62cae5-acba-5f16-ad7f-b8e2c257895c |  | note | – – – – – – – – – – – – – – – – –
label | 89b84252-7d27-58ee-b715-140588b0a024 |  | note | FREQUENCY: Each Fill Layer
label | 0afec9a6-7e0f-5a04-a312-93d48f11d870 |  | note | – – – – – – – – – – – – – – – – –
label | 0a18604c-7118-55bb-903f-039a8e71e477 |  | note | CATEGORY: IP
label | 5ef67f78-4114-5ed5-97f2-a4757aeda1c3 |  | note | – – – – – – – – – – – – – – – – –
label | 56790dab-bdb6-52c1-b853-dd65c1f6d5ac |  | note | RESPONSIBILITY: PE/SE
label | 6a07e3d3-d21e-58d7-a5a5-bd16b359204d |  | note | – – – – – – – – – – – – – – – – –
label | 1213574a-167a-56c8-83de-c6758af58ae2 |  | note | VERIFYING DOCUMENTS: Attached Test Results
date | 38a2cbea-2da7-599a-8708-002a3a368a65 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 10. Select backfil - placement
label | 60c9b8ac-7d6b-573d-b81d-02d6767d714b |  | note | REFERENCE: IFC Drawings
label | 8519e808-1672-5207-9df5-de0ef7628259 |  | note | – – – – – – – – – – – – – – – – –
label | c101e411-70e7-56fd-922a-a41bf51a3916 |  | note | ACCEPTANCE CRITERIA: select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
label | 267e5a9b-6d0a-5c16-9e87-e3a47a5573e5 |  | note | ○ Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
label | e2b7fedf-a74f-54e8-a754-bae0a927603b |  | note | – – – – – – – – – – – – – – – – –
label | 42556010-77d1-5a75-88bb-0a49d71cf924 |  | note | METHOD: Measure
label | 10d59bef-21a2-574d-9a64-72450f329065 |  | note | – – – – – – – – – – – – – – – – –
label | d895951f-ec4d-52dc-87c4-df9d5b6e66ba |  | note | FREQUENCY: Each Fill Layer
label | 98647c6d-14b9-57f0-865d-4574d86f2446 |  | note | – – – – – – – – – – – – – – – – –
label | 077dde33-4cd6-5e23-9f8a-56a5d50cbd1f |  | note | CATEGORY: HP*
label | 7bf34389-c6bc-54fc-8c68-836effe111d5 |  | note | – – – – – – – – – – – – – – – – –
label | 9ea9baed-3bda-55c9-b9e0-28966f221c4c |  | note | RESPONSIBILITY: PE/SE
label | b58ae4ad-62d2-5546-a877-30a14518ffb7 |  | note | – – – – – – – – – – – – – – – – –
label | 9848d274-8261-5fb4-96c0-16dfcc37981f |  | note | VERIFYING DOCUMENTS: This Checklist
date | 442c68ea-a2e3-5378-af63-b9013ed4a59e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 11. Select back fill-reduced frequency
label | f06467d6-3222-5c3a-9c41-8b2fba43af33 |  | note | ACCEPTANCE CRITERIA: After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
text | 81acc552-06a8-56cb-a093-bdff1446bfb9 |  | textbox | Three Consecutive Lots tested to satisfy this requirement.
label | 5cdde263-04df-59fd-809c-27667f2cdd8d |  | note | – – – – – – – – – – – – – – – – –
label | 0cef5afc-e833-556b-bb57-4c47bb0c3d6c |  | note | METHOD: Document review
label | d81f36ff-9705-5996-87c4-2533ba6e798c |  | note | – – – – – – – – – – – – – – – – –
label | 5414ac65-f988-5112-860b-3d8802406628 |  | note | FREQUENCY: Each Fill Layer
label | 25c9a63d-5377-59c1-821a-9952f7bd40e7 |  | note | – – – – – – – – – – – – – – – – –
label | 54541b95-14b8-5eb0-961b-fea51b9ae51b |  | note | CATEGORY: IP
label | 1b220a2b-54af-527b-b403-a8b2f2fef022 |  | note | – – – – – – – – – – – – – – – – –
label | 091ec4d1-5842-56af-9538-02b43506f56e |  | note | RESPONSIBILITY: Nominated Authority/PE
label | a2fda2df-ccb8-5b91-a859-22f1048070c7 |  | note | – – – – – – – – – – – – – – – – –
label | aa105454-aa30-5a3e-b455-cd69dc220824 |  | note | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
date | fcaf36f4-ed8c-593d-812a-96c963ef3b5b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 12. Select Backfill-Testing frequency-acceptance
label | ba49a6ef-3a73-58ba-a6bc-13e8af6fe6cc |  | note | REFERENCE: IFC Drawings VR 204.14, VR 682.16
label | 721c3690-ced7-559a-a54f-d650f16bc1e3 |  | note | – – – – – – – – – – – – – – – – –
label | 974980ed-3889-589b-90fc-21b0db2dd7f3 |  | note | ACCEPTANCE CRITERIA: Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | ce11f76f-5aa9-52b1-be44-d77632e95543 |  | note | ○ The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
label | 3e9d37b2-4039-5928-a46a-fc99edc4e0d9 |  | note | Attach: Compaction test results
label | 9af2c3b4-612e-582a-9a57-fa12a5359eb7 |  | note | – – – – – – – – – – – – – – – – –
label | cc53f70b-7bbd-523a-91b2-3c6838f2563e |  | note | METHOD: Measure
label | e054b0cc-dae6-5e60-976f-7113edb5f3aa |  | note | – – – – – – – – – – – – – – – – –
label | b4ff6d72-cc4c-57c2-ac04-e9ef6853a3e4 |  | note | FREQUENCY: Each Fill Layer or every second layer as agreed
label | 205ef72a-2564-5d02-bbf0-4a7eb419835f |  | note | – – – – – – – – – – – – – – – – –
label | 4402e821-21c0-5216-ad81-4e3cc100cd78 |  | note | CATEGORY: HP
label | 001b0b10-4a2e-59f4-a408-f79df209a97e |  | note | – – – – – – – – – – – – – – – – –
label | 57bcdcaa-e255-5e0a-a020-742f9b1df43b |  | note | RESPONSIBILITY: Nominated Authority
label | 10105200-e48c-505c-9faf-5ede191ad4ef |  | note | – – – – – – – – – – – – – – – – –
label | 9fa4c3b9-d993-567f-b222-d82bf324aaf7 |  | note | VERIFYING DOCUMENTS: Attached Test Results
date | d9adce36-86fd-587d-a6c6-27f1262029ae |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13. Select backfill - acceptance
label | 79951b2c-477b-5b31-b956-1448f0c1eb1d |  | note | REFERENCE: VR 204.12
label | 1f6a1623-62d2-5f0a-beab-eae18e3650ee |  | note | – – – – – – – – – – – – – – – – –
label | 4d32da82-2dd0-546e-b393-d886fd523e7b |  | note | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | 82c118ed-ba95-5f08-9826-94a78c4f171e |  | note | – – – – – – – – – – – – – – – – –
label | c8800936-04ac-509c-b899-04cfc6c441c0 |  | note | METHOD: Visual
label | abb91a2a-9ae9-56f5-9bc9-89ae177e0eb0 |  | note | – – – – – – – – – – – – – – – – –
label | 43050042-1f0f-5623-ae91-67c02be27816 |  | note | FREQUENCY: Every Fill Layer
label | 913c6ef8-34cf-5f2c-b735-27b13765a1e1 |  | note | – – – – – – – – – – – – – – – – –
label | 324fdd87-83ec-5a14-8ed9-97f19790dcc0 |  | note | CATEGORY: HP
label | 5e3e9063-f25b-58f7-930c-d5d4e5175c71 |  | note | – – – – – – – – – – – – – – – – –
label | cb21dde2-09c3-58bf-8b1a-db922b004e02 |  | note | RESPONSIBILITY: Nominated Authority
label | 8d675e83-acb9-5c35-97c7-7b935007f4e2 |  | note | – – – – – – – – – – – – – – – – –
label | 152dbcb4-0903-531f-bfed-a93fd76473f1 |  | note | VERIFYING DOCUMENTS: This Checklist
date | cfb245c5-6004-5d99-afd8-b5279d4678d8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 89d0475f-2e25-5602-9a04-d0c2cc159253 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8349daf8-32fe-538f-a62a-9ea90d1fa4ae |  | textbox | Name:
text | 4417d222-abad-5f70-837d-102689fee9a3 |  | textbox | Position:
date | 4ce82da6-0b9e-5c3f-b09e-078658f3322f |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-088-STR-SSB-CFA Piling | itp |  |  |  | Yes | ITP-088-STR-SSB-CFA Piling Rev 1 | d3e61578-6c22-4a6f-87fd-2ba278163233
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ce37ef73-4e8a-5b31-84a7-13ab05eaa17d |  | note | Document Title: ITP-088-STR-SSB-CFA Piling
label | f9f382c9-466a-5a6f-9409-97ff3ccc83bb |  | note | ITP Description: CFA Piling
label | 0383d153-fa28-53aa-9e5f-91e59483d9d6 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 9fa81cf5-bb44-5721-a5a7-482a97868bb5 |  | note | Discipline (e.g. CIV/STR/RAIL): 088-STR-SSB
label | 9931dbc4-0014-5a03-9a37-5fbb4a3b02b7 |  | note | Revision Number: 1
label | 739096e2-4ddb-5a55-8aa0-77f07df7064f |  | note | Revision Date: 6/10/2023
label | 5d7314c8-b206-5b95-8e75-3141ad10dd07 |  | note | ITP created by: Victor Mira
label | f0b87ae0-6173-5c9c-9a68-0414afc22e13 |  | note | ITP approved for use by: Victor Mira
label | e00f86c9-68dd-589b-9d54-6550d8f69b31 |  | note | 1.1 Non Dependent
label | deec25ad-cb5e-589d-83fd-7a5b873573f6 |  | note | Reference: VicRoads Section 607 March 2015
label | e01c462f-cfbd-5b14-9c9b-3e7749f4d91a |  | note | 1.2 Non Dependent
label | b53992ca-f875-5cea-92cd-e2abf3cb9aca |  | note | Reference: VicRoads Section 610 February 2020
label | 38e74d20-fa1f-5879-93ac-78ffcb87392e |  | note | 1.3 Non Dependent
label | 52103ce4-e79d-5546-a511-1c39558ba210 |  | note | Reference: VicRoads Section 611 November 2018
label | 1fc603d5-7899-507b-b1d0-51f008ea79e0 |  | note | 1.4 Non Dependent
label | 6ec2342c-d4ab-59b3-aa36-102d20ee1284 |  | note | Reference: AS2159-2009
label | f0425074-4384-529a-9f6f-344b7e0b59fc |  | note | 1.5 Non Dependent
label | 4bf407fb-36e9-586e-9060-5104ce71bb47 |  | note | Reference: AS3810.1-2015
label | 3ab0aeb3-be95-56fb-8fb6-d3bf680c7457 |  | note | 1.6 Non Dependent
label | 8f54073a-225a-59e0-ba49-08a372349636 |  | note | Reference: AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 78255ff4-0c25-58f1-a03f-0556f2ba7a83 |  | note | REFERENCE: 610.07 Table 610.071
label | 79add433-0035-5554-aaef-cb2fcf9dbab5 |  | note | – – – – – – – – – – – – – – – – –
label | 49608451-a0a0-5d86-ae15-e2e6bf9e43e1 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 83a3f782-c89d-59d7-b884-8cd20b8d97e2 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | ff5e37ca-f19a-5884-92ab-6aabdbc9e980 |  | textbox | Enter: Teambinder Material Approval number
label | 9d700b82-0ebc-566c-aa9d-4ae207706787 |  | note | – – – – – – – – – – – – – – – – –
label | 5b3ac936-2b6c-5207-9020-231462a052b9 |  | note | METHOD: Document Review
label | 486c39a3-65c4-527d-acdb-a42ac38a8757 |  | note | – – – – – – – – – – – – – – – – –
label | eb3ef777-f8b3-51fe-bb88-c6b87bf06dff |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 8b484514-4c86-5fcf-b2b8-641df1d548b2 |  | note | – – – – – – – – – – – – – – – – –
label | 7648f3e7-a414-5d58-81ba-616546d8f6eb |  | note | CATEGORY: HP
label | 93502526-a0d0-58dc-9a3c-1d19a1410430 |  | note | – – – – – – – – – – – – – – – – –
label | ad0f964e-dd17-54a6-ba7c-15ee5b4734c2 |  | note | RESPONSIBILITY: Nominated Authority
label | 9bfab37f-8f47-5792-a649-c4684d0205c4 |  | note | – – – – – – – – – – – – – – – – –
label | 2beaecf4-7fae-53e9-93d4-7a25b9cee91c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 0ded282d-791d-558f-b40a-3e0f85f9a91d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 7bd65bad-5e0c-5e52-a595-469296e9342c |  | note | REFERENCE: 611.05 (a)
label | 82b0ef7f-6589-5cb1-bc3a-0a55724cb63c |  | note | – – – – – – – – – – – – – – – – –
label | 8abe62d7-91d7-5d40-986e-fd26aca0f862 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | ed127fc3-b5c9-5b5b-b9e5-1984ba60c947 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | c6b4da98-b01b-5815-a0a2-8cea3b45c243 |  | textbox | Enter: Teambinder Material Approval number
label | 6285d169-9a52-5016-91aa-ad3ab385531a |  | note | – – – – – – – – – – – – – – – – –
label | af94afb6-508d-5346-9979-52c34f0340f4 |  | note | METHOD: Document Review
label | 2808050f-ec43-597d-84fb-1e5a6c09a11f |  | note | – – – – – – – – – – – – – – – – –
label | 50b81989-76cf-5ef8-a15e-e140989dad9b |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | d1f2c93e-5676-59ce-8544-88560a29aa84 |  | note | – – – – – – – – – – – – – – – – –
label | 46447890-728a-5914-a0a4-22de4ff66040 |  | note | CATEGORY: HP
label | d12ad430-999d-5bd4-b6ce-6dca3472632e |  | note | – – – – – – – – – – – – – – – – –
label | 34ec5b8b-2b05-5b68-a45e-400a62266726 |  | note | RESPONSIBILITY: Nominated Authority
label | e8cab6b5-b4cc-5c03-bada-cfb9b0ae25bd |  | note | – – – – – – – – – – – – – – – – –
label | bcfaf1f4-103b-58dc-86d0-dfd7e001a4e0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 96b31571-04ee-594f-856a-414c85f6d9da |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 2daf3003-daec-532d-9895-fcc702b5115d |  | note | REFERENCE: 610.26 (a)
label | bfcc2a23-4d6e-5e0d-9812-c91ddb47d474 |  | note | – – – – – – – – – – – – – – – – –
label | c16abb5e-9ee8-53e5-8cf0-4df0ab34f4f9 |  | note | ACCEPTANCE CRITERIA: Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
text | 8d89fcc0-3fd0-58a3-acb0-79cdcd75ba41 |  | textbox | Enter: Teambinder Material Approval number
label | 0f90ab9f-052d-5552-8c52-4d557cbe99d3 |  | note | – – – – – – – – – – – – – – – – –
label | 041625c5-b487-5e57-907a-e0efd71f7773 |  | note | METHOD: Document Review
label | 10086686-6d63-50c8-bf5f-c51d0cd25793 |  | note | – – – – – – – – – – – – – – – – –
label | efed78c9-fbbc-590c-9f48-1178ac288cf8 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 9f37edd0-fef6-51ce-9ec8-6af861eaf651 |  | note | – – – – – – – – – – – – – – – – –
label | 0258d279-2d27-54c6-b532-850b976908b1 |  | note | CATEGORY: HP
label | a1c57d98-c8fe-50ce-88d3-b8a8d5692df4 |  | note | – – – – – – – – – – – – – – – – –
label | 2122adb4-e5bc-5aeb-88c6-a74855a7485f |  | note | RESPONSIBILITY: Nominated Authority
label | 94f9d6d1-402f-5077-8447-87b88388732b |  | note | – – – – – – – – – – – – – – – – –
label | 818f3d70-901c-52a3-9de2-15f951c4f9b5 |  | note | VERIFYING DOCUMENTS: This ITP
date | b04159f0-e229-5c9d-af9c-b09a1d08a58f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | 367852f8-e2d9-55fd-a572-878baebd9965 |  | note | REFERENCE: Piling platform design
label | b4a86204-665b-5df5-9661-a4cf5aada2ce |  | note | – – – – – – – – – – – – – – – – –
label | 88774f8a-9d68-502d-9681-3120e6dd8f0b |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement.
label | 385be268-61d9-5194-a3aa-e8af6e241eba |  | note | ATTACH: Piiling Platform Certificate
label | d6c82414-a00f-5335-a484-b3838ee9e33e |  | note | – – – – – – – – – – – – – – – – –
label | 31662025-e223-5b00-8042-1afdc178d2ff |  | note | METHOD: Document Review
label | 6cec18db-1edf-5ade-ae2f-86d272ccd71b |  | note | – – – – – – – – – – – – – – – – –
label | 6b52529c-3d39-5ace-884f-f6bf8f97264a |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | a712c1d3-4732-5263-a232-6899e4c732e5 |  | note | – – – – – – – – – – – – – – – – –
label | ebf0fab2-a1a1-5b82-9555-a89c53b2152d |  | note | CATEGORY: HP
label | 34b2d6b0-5d3c-5205-b06f-51c36ac131c9 |  | note | – – – – – – – – – – – – – – – – –
label | 23356866-44ce-560a-b547-c47a7f231145 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | a0af1c07-83f1-5e83-81d3-8f3e5aa2d464 |  | note | – – – – – – – – – – – – – – – – –
label | 3026f215-2e42-549d-b1ca-58cdbc986d99 |  | note | VERIFYING DOCUMENTS: This ITP, Platform Certification
date | ba4c118c-057d-558e-939d-004883e32896 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete CFA Pile Design
label | 6a1ae8bd-7739-585b-994f-a082666ae9a2 |  | note | REFERENCE: 607.01 IFC Drawings
label | ea2471da-3230-5f14-9432-d0b93fd5b606 |  | note | – – – – – – – – – – – – – – – – –
label | 08499d74-8acf-5b3f-9da0-9b9d79887e39 |  | note | ACCEPTANCE CRITERIA: Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
text | 239f8a1e-1686-5eb9-9071-d7aaaa6d98f1 |  | textbox | Enter: Teambinder Approval number
label | 6e07dc0b-9200-5f27-8e8e-a74ff9c17099 |  | note | – – – – – – – – – – – – – – – – –
label | 6612fbe4-d193-5ee5-b9ac-fc330093212d |  | note | METHOD: Document Review
label | 367fe31c-3497-5ead-a778-c3642a96d389 |  | note | – – – – – – – – – – – – – – – – –
label | 9e3da163-8e60-537b-a17a-1d7e2c4095a4 |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
label | 9c39b601-8a7a-5ad8-a1d7-931d7bb44dbe |  | note | – – – – – – – – – – – – – – – – –
label | bd91fbb7-2464-5b57-94db-82a838c986a3 |  | note | CATEGORY: HP
label | 868d0a67-3ca2-51ee-8a6f-a98d9c7bfea8 |  | note | – – – – – – – – – – – – – – – – –
label | 3b985391-e031-5e3d-b335-1cae722aef19 |  | note | RESPONSIBILITY: Nominated Authority
label | 175ed209-27a3-5dd1-9400-0c9decd2418e |  | note | – – – – – – – – – – – – – – – – –
label | 16d360a0-5cea-5da1-92d6-0831308077ac |  | note | VERIFYING DOCUMENTS: This ITP
date | 1cbebf6f-807c-54c2-be0d-cc55b184f1d0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Piling Operations Work Procedure
label | 4e9060c1-e956-570e-9341-57bdee8a820f |  | note | REFERENCE: 606.03 (a)
label | 1815493b-8184-515d-8b4d-091d9eb42e18 |  | note | – – – – – – – – – – – – – – – – –
label | 9a2bcfd5-25d9-56d7-8f61-2261fc82f8cf |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | e0380fd9-53c0-5272-b9c6-45611a4ec6b3 |  | textbox | Enter: Teambinder Approval number
label | 67071498-e961-56a5-8179-35f0eb260b63 |  | note | – – – – – – – – – – – – – – – – –
label | a985af60-e19f-5c14-8a46-a01c4be2980c |  | note | METHOD: Document Review
label | 0f5925b3-2ac5-5bf8-b41a-2b9ac0c7f322 |  | note | – – – – – – – – – – – – – – – – –
label | bd0c6efa-fbba-5824-a18d-a1927ca34628 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 105bf3a1-a7f9-56bf-990b-eff503151a53 |  | note | – – – – – – – – – – – – – – – – –
label | 044c55dd-30f6-59db-8078-2ff265910f2c |  | note | CATEGORY: HP
label | 1d593e2f-6a06-5429-978a-cddd1ab4dd05 |  | note | – – – – – – – – – – – – – – – – –
label | 110c4cd2-ab5f-5b15-935f-50d645e6122a |  | note | RESPONSIBILITY: Nominated Authority
label | 1df8b480-9afb-55f4-a215-c1ea4e31cd31 |  | note | – – – – – – – – – – – – – – – – –
label | 08a36ffa-bf42-5841-ad23-b66363dccb6f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 28200b30-098a-5e7a-b473-047836185049 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 61c6daee-2dfd-542e-ba20-7a382a762019 |  | note | REFERENCE: 607.04
label | 732075ee-d818-5b61-ba47-8a8cea223545 |  | note | – – – – – – – – – – – – – – – – –
label | 7359427f-8b64-5ddf-9e73-8e1dc534b47e |  | note | ACCEPTANCE CRITERIA: Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
text | 6d26025e-5fa1-545d-9576-2d13bb15b743 |  | textbox | Enter: Teambinder Approval number
label | 5772f720-0d9d-5668-8563-234ae2f84ddb |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 75705bd9-1748-5735-ac89-fcc4c804b5bb |  | note | – – – – – – – – – – – – – – – – –
label | b13baa63-5db8-5511-b723-fb29b5e48bf7 |  | note | METHOD: Document Review
label | 83fe223d-d974-5345-bf63-d8b3f5b0ea98 |  | note | – – – – – – – – – – – – – – – – –
label | 9bd8a5b2-d9aa-5be7-86db-22fc6f76af59 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 7d703e67-ce49-58b8-8560-377822191af0 |  | note | – – – – – – – – – – – – – – – – –
label | bc898154-95dc-553d-a8d0-b4c4093f1012 |  | note | CATEGORY: HP
label | 9ba45203-95a2-5611-905f-4c299f602146 |  | note | – – – – – – – – – – – – – – – – –
label | c0ea5c15-3753-5a43-8627-3ea1463a86d2 |  | note | RESPONSIBILITY: Nominated Authority
label | 527d26ad-6af4-5581-8531-909f49287ae2 |  | note | – – – – – – – – – – – – – – – – –
label | 45994e4e-06e8-56d3-a3b2-9b6f50d5cfc5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9ad12ddf-f9bb-5d61-a416-06a3fff46d58 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Dynamic Pile Testing Procedure
label | ffbc2438-a24c-5aaf-abe0-e96995acebd7 |  | note | REFERENCE: 607.07
label | cc626ac1-f783-513a-9326-3773161be8de |  | note | – – – – – – – – – – – – – – – – –
label | 448c4288-106f-5a85-8ee5-d0e54ebcbfb8 |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 38200a75-af1c-5890-864a-92607af6a430 |  | textbox | Enter: Teambinder Approval number
label | 6f4ca88f-c509-544b-9b7a-438c1486c034 |  | note | – – – – – – – – – – – – – – – – –
label | c8a080bd-74cd-5482-9ab4-881d20e394ce |  | note | METHOD: Document Review
label | 2d0a399a-3075-50d8-a0f4-411134a6c229 |  | note | – – – – – – – – – – – – – – – – –
label | 60a3ef58-eeda-59d4-a487-c3fed8551f89 |  | note | FREQUENCY: Once, prior to testing
label | d6639a63-232f-52ec-b829-19392a252f08 |  | note | – – – – – – – – – – – – – – – – –
label | 9a1b1b8f-9d69-53f8-8276-4f77308e167a |  | note | CATEGORY: HP
label | e336f652-0b5a-57fd-be5f-f87fb6e7dad4 |  | note | – – – – – – – – – – – – – – – – –
label | f77fda92-1e5e-5c95-a910-014bcfe48dfa |  | note | RESPONSIBILITY: Nominated Authority
label | 385b0d33-65a5-5617-b1bc-b77c1c24ef7f |  | note | – – – – – – – – – – – – – – – – –
label | a9471b2e-5392-5083-926f-209c5e9203f0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 799fd910-5af3-5dc7-8130-bdace764deb0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Pre-qualified Pile Testing Consultant
label | aea3b065-ecfa-509e-ad67-f58a74a05f9f |  | note | REFERENCE: 607.07
label | 26e59fc1-c23e-50a3-993c-d4ee119fe105 |  | note | – – – – – – – – – – – – – – – – –
label | 980c931e-9f8d-5083-88b5-d89e65375227 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | af911ab6-56b2-5002-975b-230482aa69b0 |  | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
text | 7aafb37d-c3c7-5915-8b77-5a0614f3458d |  | textbox | Enter: Teambinder Approval number
label | 433b83b8-7984-51c4-887e-e4273dc66512 |  | note | – – – – – – – – – – – – – – – – –
label | 45d062f3-37b4-51f8-b65c-b242646abc8b |  | note | METHOD: Document Review
label | 93686288-f15f-5d5b-8ae2-8166b339c4e9 |  | note | – – – – – – – – – – – – – – – – –
label | c20a8953-c93e-5977-8f1b-9293862272ed |  | note | FREQUENCY: Once, 2 weeks prior to testing
label | 665d0c32-a94b-51a0-8312-b4a0f440d8b1 |  | note | – – – – – – – – – – – – – – – – –
label | f7329050-acd4-5f1a-aee4-5606858f7624 |  | note | CATEGORY: HP
label | 9fc8f1f1-1f4b-532d-9d58-5d5b8a3caffb |  | note | – – – – – – – – – – – – – – – – –
label | 6306dc3f-b31e-5f42-8ab7-7bad4ec4188c |  | note | RESPONSIBILITY: Nominated Authority
label | 6f4abe53-3a91-5182-8797-d274f5d7c203 |  | note | – – – – – – – – – – – – – – – – –
label | 9aabeca8-225c-5e5b-838b-19e598ffd57c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | fde87147-16e2-5fc0-8f13-958226288d4e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
label | f86c6f37-dc0b-5fee-8a67-89596071360a |  | note | REFERENCE: 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
label | fd321fdf-40db-573c-b5c1-150b903f00e0 |  | note | – – – – – – – – – – – – – – – – –
label | ffcb4a38-4167-5ff8-9a0f-490c169a4a41 |  | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | 68649927-7992-5402-9726-70f78e634cfa |  | textbox | Enter: Teambinder Approval number
label | 36a0d57e-a136-56b4-889d-56a7387b1629 |  | note | – – – – – – – – – – – – – – – – –
label | bac90f7b-8be7-53ea-8742-7a271e56b52f |  | note | METHOD: Document Review
label | 16eb88e2-7cab-5c80-bfe6-1d73c7779d15 |  | note | – – – – – – – – – – – – – – – – –
label | 0c1a48d6-d11a-5abb-8a72-c390c556b383 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 573f0454-941a-5740-a880-cfb408872c05 |  | note | – – – – – – – – – – – – – – – – –
label | 758d975e-ddee-516e-9f9a-6388557e7464 |  | note | CATEGORY: HP
label | 9860dcbf-b240-5fef-9ec3-3cf4ecc6f49c |  | note | – – – – – – – – – – – – – – – – –
label | 7e16a135-3f28-53ce-88b3-b191b19190e9 |  | note | RESPONSIBILITY: Nominated Authority
label | a79b98d0-a868-5d3b-ac15-ceb08002e833 |  | note | – – – – – – – – – – – – – – – – –
label | d8aadd38-de18-5ecb-aa34-dc7c230e5816 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 512142dc-8906-580a-9c32-f4f02f293d2b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 6cbe3aae-92d8-51f0-8845-604710e27cd8 |  | note | REFERENCE: MRPA Quality Management Plan
label | ebfb51e5-91ce-5dcf-811b-dc3d591ef3d1 |  | note | – – – – – – – – – – – – – – – – –
label | 82e81376-0688-5064-be8b-acad138af265 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 9122d00a-1d11-5a21-b2e9-1d96c64cb806 |  | note | – – – – – – – – – – – – – – – – –
label | afbac224-561a-5c9e-862f-4d57a235a5e1 |  | note | METHOD: Document Review
label | 0f4a4015-b958-581e-96d5-2a158842fa02 |  | note | – – – – – – – – – – – – – – – – –
label | 59ba392d-cf90-542a-980a-3f03719d0550 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 3e666726-00ec-50d5-83e5-88559b42792f |  | note | – – – – – – – – – – – – – – – – –
label | bf84d808-9eba-5e07-bdb4-d55505a08f3e |  | note | CATEGORY: HP*
label | 4a1bbf32-16a7-5c76-8c76-5e7474ae63d3 |  | note | – – – – – – – – – – – – – – – – –
label | b3f7f45e-14d7-5d81-929f-66d6c8222b16 |  | note | RESPONSIBILITY: All
label | 933cd9cf-8a78-5463-bbed-bf89a2b73705 |  | note | – – – – – – – – – – – – – – – – –
label | 47a216ce-26d1-5d63-92f4-11683a576d8c |  | note | VERIFYING DOCUMENTS: This ITP
date | f19e295c-68e2-5c9e-8d88-28cd4148f625 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 085b8400-2040-5134-ba2f-a24f9966b1a9 |  | note | REFERENCE: IFC Drawings 607.06 (a)
label | f03974ef-0c9d-5c87-bc73-27e827fbbe5a |  | note | – – – – – – – – – – – – – – – – –
label | 0476ec99-803e-5efe-9e42-b013665ffef4 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 7fe4dda2-415d-5f9f-9003-7fcfb20c42df |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 5aed1df6-3574-5002-8295-e51428599242 |  | note | – – – – – – – – – – – – – – – – –
label | 89239d70-d462-52ae-9094-4f4cee8b8b0d |  | note | METHOD: Measure, Visual
label | 55ff35a3-cee0-5225-8a7b-c61c8fdbd408 |  | note | – – – – – – – – – – – – – – – – –
label | a4216ab5-fa9f-5b09-b2ea-1e00e71d4123 |  | note | FREQUENCY: Each pile
label | df8d1009-271f-531c-93a3-45c95c6ba806 |  | note | – – – – – – – – – – – – – – – – –
label | 24d23c7b-e3f6-5d92-ac90-3274164ecdd0 |  | note | CATEGORY: IP
label | 1fd1cdd1-d51f-5028-867c-73eebaad3a21 |  | note | – – – – – – – – – – – – – – – – –
label | 701cac65-b38e-55a4-aa4a-9e5e8cdaefb5 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 7dd9f119-3419-52b8-91e1-acb7587b87dc |  | note | – – – – – – – – – – – – – – – – –
label | 0a68846e-15c2-53d2-b958-c77eb6c3951b |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f0ba86f-61f3-5019-9415-69503bc28317 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 83a11a23-115a-584e-b542-ab42ff3c9dac |  | note | REFERENCE: 607.05
label | ee671884-afe6-50ed-a0e8-517e7b9dcc0c |  | note | – – – – – – – – – – – – – – – – –
label | a87901c2-2de8-5129-8953-b68a64f99518 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
label | 9d4b6070-e384-566e-be52-5e9fefcf0c9f |  | note | ○ Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 Mpa
label | befb2217-100d-58d0-abee-c9750e1856cd |  | note | – – – – – – – – – – – – – – – – –
label | 40a3b7d7-c56f-5a78-ac7c-e199a855e79f |  | note | METHOD: Measure, Visual
label | 6251b6e4-6aca-5eba-a549-823b9b838526 |  | note | – – – – – – – – – – – – – – – – –
label | 1e91fba9-653f-50e1-8d58-42fc28f5f63b |  | note | FREQUENCY: Each pile
label | 08cc4f44-7195-507c-b063-06e923565db9 |  | note | – – – – – – – – – – – – – – – – –
label | 910d7c5d-1f09-5cff-8997-c7ec7a84e6b9 |  | note | CATEGORY: HP*
label | 1952dc61-d804-5e02-a661-80751bf7eee8 |  | note | – – – – – – – – – – – – – – – – –
label | cd6da1fb-d060-5b9a-a9e9-c87c6d8e2496 |  | note | RESPONSIBILITY: SPE/PE
label | 930e2a14-b424-56cd-86c9-62f4088530f9 |  | note | – – – – – – – – – – – – – – – – –
label | 139ea829-398d-5aa3-b58d-e92c6260d418 |  | note | VERIFYING DOCUMENTS: This ITP
date | 92d17f58-1c4c-56db-8aac-fbfc7ca8d5d1 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement - Inspection
label | 71cc85e3-7300-5cfb-8936-e20c7c67077d |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | e58173aa-50b6-5d06-bbb6-e15606408ab5 |  | note | – – – – – – – – – – – – – – – – –
label | 5518a310-8609-5aa2-a835-c0d8cc5fb2e6 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | b88a9b05-ba65-5565-9227-5dcaa6b87907 |  | note | ○ Projecting reinforcement is the correct length and location.
label | dc9d9f1f-7f8b-5e8a-a5b7-8910bbf0dfbf |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ce182849-d444-5f4e-8003-aaf3505784d8 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | d42bacb0-8798-58b4-b94d-1668cc2a844e |  | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | da3edd89-0d34-55aa-a760-ce9dce75edee |  | note | ○ The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
label | fc2857d5-e576-5df6-8d78-2585664e8820 |  | note | – – – – – – – – – – – – – – – – –
label | 26dc6085-4b4e-520c-a1e0-6a21f864a0aa |  | note | METHOD: Measure, Visual
label | 36247318-cebe-5a0d-8dd4-534f7067f1bb |  | note | – – – – – – – – – – – – – – – – –
label | c43ea7f4-8ca9-5b73-b68f-d9ee171a7770 |  | note | FREQUENCY: Each pile
label | ef69c6fa-944f-5da6-b657-27bd6ad43e0b |  | note | – – – – – – – – – – – – – – – – –
label | feb23be9-aa79-5350-899e-e98c85e01a19 |  | note | CATEGORY: IP
label | c78be086-dbda-52b6-be44-0e49bebdb27c |  | note | – – – – – – – – – – – – – – – – –
label | d2ecb7ac-4eca-56e1-86e8-62bc31f9ddae |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 3eb1a448-5ff7-5e1c-9d91-d0d7aadaa20c |  | note | – – – – – – – – – – – – – – – – –
label | a58eb6c6-03c7-5a1d-878a-104ad0d6495e |  | note | VERIFYING DOCUMENTS: This ITP
date | 724e3aaf-c0f8-5fb2-b28d-90f1a38858cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Reinforcement - Electrical Continuity
label | e493912b-5be9-504a-97b2-77b2802918b8 |  | note | REFERENCE: IFC Drawings 610.29 (d), 610.43
label | 18212ef2-6e35-599a-99a5-e81ca9f2a683 |  | note | – – – – – – – – – – – – – – – – –
label | e63f36d4-104f-5b35-ba43-14fc199f93b6 |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | a81895c3-230b-5073-a92d-d614bd861764 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 59736c91-d7f5-56ad-8e18-818280ce819c |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 4d59e3a1-84ed-5489-b655-0b57330abb23 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 1886bacc-4579-5203-a636-2a6d764ea664 |  | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 928b2f18-5aa7-5f8a-90e4-f281ce4b7e75 |  | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 2a9b0ce5-04bb-5a76-acce-8721d97ab70a |  | note | – – – – – – – – – – – – – – – – –
label | 37cfdd2f-50b9-57c3-bbe1-7ea3db67d7cd |  | note | METHOD: Measure, Visual
label | fcc56d71-c530-5b3c-a101-896e55fadc9a |  | note | – – – – – – – – – – – – – – – – –
label | b525e2eb-2ba7-5bf5-a972-507da7fce95c |  | note | FREQUENCY: Where applicable, each pile
label | a0767561-74ba-58ca-802c-f5d20b925127 |  | note | – – – – – – – – – – – – – – – – –
label | 200684bf-df27-5f34-84dc-391a1c03d10e |  | note | CATEGORY: IP
label | 3a00e492-fb52-5eaf-9a3c-bc3d6727e7dd |  | note | – – – – – – – – – – – – – – – – –
label | 76ca7d32-99e3-5fd3-a6b4-45e7a94ef191 |  | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
label | 98c53ee7-e27d-5173-86fe-3a06072c86b6 |  | note | – – – – – – – – – – – – – – – – –
label | 3a63c3a0-51f2-571b-a125-38839cee3ee6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 240ef8bb-746c-5c39-99ef-cdbb5ed773bc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Augering Operations
label | fcdbaca9-0c23-59c6-b09b-402638ebcc2a |  | note | REFERENCE: IFC Drawings 607.04
label | cf151e9e-e445-58c9-9153-d90ab2f777e1 |  | note | – – – – – – – – – – – – – – – – –
label | 109cf183-117e-58b2-83df-f85682f856b2 |  | note | ACCEPTANCE CRITERIA: Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | caeb467f-a0a4-5cb1-a8d2-d22914f82857 |  | note | ○ The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
label | 09765511-eac2-5413-ac31-c7c77227e361 |  | note | ○ Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
label | 28094a3f-7062-5b57-ac64-cbfd69413d53 |  | note | – – – – – – – – – – – – – – – – –
label | 2e852797-d569-5375-a94c-afadac9b6d1c |  | note | METHOD: Measure, Visual
label | 29639528-a711-59f5-9e6c-db4abf11fc21 |  | note | – – – – – – – – – – – – – – – – –
label | 6dfbeb58-690a-52bf-a5f0-e2ea9b346b8d |  | note | FREQUENCY: Each pile
label | 164c5f35-af5b-5edc-aa98-b45a4f8bd4a3 |  | note | – – – – – – – – – – – – – – – – –
label | 4fbc5f7a-c8b7-5141-9801-b69ad10d557a |  | note | CATEGORY: IP
label | 4532ee6b-0d83-55e6-bcd8-31238bfbe361 |  | note | – – – – – – – – – – – – – – – – –
label | be7c161f-5943-5735-9bec-790915c6c5de |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | dddea390-4f3b-50dc-b3a0-f8ffd4ca0ee5 |  | note | – – – – – – – – – – – – – – – – –
label | 838d3a92-b172-5fa8-8a2b-6c7a57558294 |  | note | VERIFYING DOCUMENTS: This ITP
date | e935d3db-5a0d-5de5-a917-2c40cd25f302 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Inspection of Excavated Material
label | 71fc95cd-b548-53e2-9396-d70a9ce5e50a |  | note | REFERENCE: 607.04
label | d6d4b4d3-3874-5e17-b2f0-2fc87aaa52cd |  | note | – – – – – – – – – – – – – – – – –
label | b39e7e9b-0032-5a6e-b7ce-672a4b703fea |  | note | ACCEPTANCE CRITERIA: Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 49693156-86da-5c5a-8b7f-25a8d873afbd |  | note | Attach: Geotechnical Field Sheet or Report
label | f2db6836-bea0-5541-8e0b-db43d020fd89 |  | note | – – – – – – – – – – – – – – – – –
label | b3cf4ed2-a78f-52d8-beb7-cbef2a13b07d |  | note | METHOD: Measure, Visual
label | 76a1363d-1f72-5283-80b9-5478c2423490 |  | note | – – – – – – – – – – – – – – – – –
label | 87f60046-488f-59d0-aea2-7b816f4b4c5e |  | note | FREQUENCY: Each pile
label | 33bf5ec6-ef34-54ca-a98d-1cb37f021970 |  | note | – – – – – – – – – – – – – – – – –
label | 36626423-dce4-5bbf-8c8e-d74931b30bb2 |  | note | CATEGORY: HP
label | 51e603d8-78fd-5f09-a5db-9410414acfea |  | note | – – – – – – – – – – – – – – – – –
label | 69493d29-491a-5be9-98ba-d413598738fb |  | note | RESPONSIBILITY: Geotechnical Engineer
label | c99bece1-b435-576b-a1b7-ac994c9a970d |  | note | – – – – – – – – – – – – – – – – –
label | 05a0bd0f-9efe-5650-a3b3-65aeddfd2c5d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 239684ae-3c8b-57c9-89cc-8591b24d84da |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Increase in Depth Beyond Design
label | f9124dcd-63e7-5c3e-9779-ccc927a48077 |  | note | REFERENCE: 607.04 (a - d) Piling Operations Work Procedure
label | 49365e61-4848-5e66-951b-ca5e73d15d73 |  | note | – – – – – – – – – – – – – – – – –
label | f2915281-9ba8-538f-9837-cebb72d20b0d |  | note | ACCEPTANCE CRITERIA: Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
label | 63f98458-887a-5fbe-9860-cbab85de43f7 |  | note | ○ A full account of the changes shall be submitted for approval to the Nominated Authority:
label | 0d1142f5-4490-596f-9823-24f22d5545cf |  | note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
label | 4b42d1dd-27e7-5643-be42-a7d6554682ea |  | note | – – – – – – – – – – – – – – – – –
label | bccd2a1a-d64d-5579-9215-62e461e035e0 |  | note | METHOD: Measure, Document Review
label | 4769f511-22d4-5cd0-8d47-0f37f2f6cc12 |  | note | – – – – – – – – – – – – – – – – –
label | 1676d798-c39f-50a2-bd3e-92405436ab65 |  | note | FREQUENCY: Where applicable
label | c2c17470-925c-54f5-acdc-d1b5f7ae5256 |  | note | – – – – – – – – – – – – – – – – –
label | 2b64afbe-4aa4-5cfe-88e5-838f4da72b43 |  | note | CATEGORY: HP
label | 5ed44b24-af6f-5c4b-a437-ddc09662b651 |  | note | – – – – – – – – – – – – – – – – –
label | bc398501-5918-5a72-8693-07ea401d856b |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 8af1d52c-929f-53f3-872b-171abb89e0ba |  | note | – – – – – – – – – – – – – – – – –
label | 1704fbfe-5448-5674-927a-5f792aec80d9 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f9664053-79b4-5daa-8273-e7385a13f601 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Weather Conditions & Evaporation Limits
label | 6c4354bb-d852-52c0-8018-8944342ef096 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | 5a1df9d5-edc6-5c55-a509-a5894a1ca898 |  | note | – – – – – – – – – – – – – – – – –
label | 2bfbf3ac-1c99-52c4-8445-372dc54e38d3 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 3ea0d18b-60a5-5514-8e8f-ac6ba200ea6e |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ebdc9e67-5ffb-53aa-ac9a-fb22f6e21162 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 628a5fb2-e53c-555d-bd25-908615bb9017 |  | note | Record: Required information on the Concrete Pour Record.
label | 0207048a-9d59-5e53-95c2-5b4b3a7a8aeb |  | note | – – – – – – – – – – – – – – – – –
label | 579bdd69-d9e1-58fa-8803-43eb36e30b06 |  | note | METHOD: Measure, Visual
label | 6b83db97-ad3d-5e29-b0c0-7119bda0bf93 |  | note | – – – – – – – – – – – – – – – – –
label | a5ae7fd0-cfe3-5061-9a9b-9e39b467e608 |  | note | FREQUENCY: Each pile
label | e25d8e69-2d97-50bf-81cd-4f27f0782d75 |  | note | – – – – – – – – – – – – – – – – –
label | 3147301b-9326-5ea8-81ea-6d4430876e89 |  | note | CATEGORY: IP
label | 4a2ac6ef-6741-53af-a100-b88bc4480934 |  | note | – – – – – – – – – – – – – – – – –
label | 052e952e-0171-5b7d-8d30-476a74cd23cf |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fb436669-b701-5d6f-b8f9-3b723421700b |  | note | – – – – – – – – – – – – – – – – –
label | beb40417-efb0-5041-8030-9420435e2143 |  | note | VERIFYING DOCUMENTS: This ITP
date | 10b82ba4-839f-5762-91f1-036142b6c433 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Sampling Frequency
label | ac7d0bb7-39ad-55ba-8f77-67607991cf8f |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | 1d85bd2c-cc53-5148-8ffd-f98dee8a74fc |  | note | – – – – – – – – – – – – – – – – –
label | 7578848b-3589-5dfb-8d00-b4dcdb3c6803 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 6628801e-91d8-58e2-a0b6-719d28c7fef7 |  | note | 0m³ to 10m³ = 1 sample
label | 9fbeb11c-1230-53c7-a0f7-b308753c661d |  | note | 10m³ to 25m³ = 2 samples
label | b70783f5-c31f-574a-8d5d-cb0a10ff5584 |  | note | 25m³ to 50m³ = 3 samples
label | 024ffec2-ac2b-547d-9dbc-ef13bac034ce |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 3cbbbc94-49a5-5ff3-b5ff-8c25a3fa1671 |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 0ae47074-e043-52ec-9887-7f59ed77406c |  | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | db5197d1-6aa5-5641-91eb-781087e3629d |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 3bd648e9-23e9-52db-9aef-78c988e5d58f |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | a4f19947-3038-55f9-9e55-ffa5b75ce72e |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 457ddedb-2a49-512d-96a5-d7e476beef5d |  | note | Record: Required information on the Concrete Pour Record.
label | de9bb299-49f2-53f0-908b-8d56b1431b47 |  | note | – – – – – – – – – – – – – – – – –
label | b84a4e04-b62f-51c8-a4db-9e8786dce195 |  | note | METHOD: Test
label | 51a1e4aa-1327-5602-8024-9e980ddef260 |  | note | – – – – – – – – – – – – – – – – –
label | 23c9c9a3-d9b6-56c2-bfd3-18eb3eaa3d6d |  | note | FREQUENCY: Each pile
label | 7b8d6229-4dca-5a60-b159-5809154295d4 |  | note | – – – – – – – – – – – – – – – – –
label | 2575d3f3-3cba-5829-a767-f396132298af |  | note | CATEGORY: IP
label | 993dcf6c-e699-5dae-a508-ad7d7a61d1ca |  | note | – – – – – – – – – – – – – – – – –
label | c213cdca-a3dc-5d87-a0e0-0d1641ced218 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | e4f8abde-6567-5383-97a2-a0a0ce9abf96 |  | note | – – – – – – – – – – – – – – – – –
label | db32c4f0-e06d-59c8-9921-bce02f9c181c |  | note | VERIFYING DOCUMENTS: This ITP
date | e67c3525-aa9e-5f30-ac14-379b30be2b72 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
label | 5e2dc623-9b53-5eb8-bf78-96e775507633 |  | note | REFERENCE: 610.13 (b)
label | 15c863ac-ddb1-574d-80e2-9732a509e952 |  | note | – – – – – – – – – – – – – – – – –
label | 8f8d3f22-a83a-562e-9381-1438e1dc0160 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 800mm
label | 593674fa-5430-5247-bc7c-9e088e404520 |  | note | ○ T500 = 1 seconds to 5 seconds (to reach a spread of 500mm)
label | d11a385b-dd49-52d9-8b5b-0229f24830fc |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | 10ac6740-46da-5c60-99ae-ad8854cfb615 |  | note | Record: Required information on the Concrete Pour Record.
label | 99ab5fd4-ae66-55e1-a373-9d47039b29d0 |  | note | – – – – – – – – – – – – – – – – –
label | d171d348-0130-5000-9041-ffae8ac654bf |  | note | METHOD: Test
label | d6855e56-8457-5ac6-a0d9-1a6490046304 |  | note | – – – – – – – – – – – – – – – – –
label | 13a47615-5744-5507-be00-be23d3d27046 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 62946e57-a8bd-5589-bd6b-34223c6ac4fd |  | note | – – – – – – – – – – – – – – – – –
label | 8ea9b865-7623-5eb4-8355-592f159f1463 |  | note | CATEGORY: IP
label | cbfec71b-d19f-58c6-9f40-32793a855397 |  | note | – – – – – – – – – – – – – – – – –
label | 60d1bfc2-ca9c-5372-b823-a77fc5b31473 |  | note | RESPONSIBILITY: Concrete Tester
label | 4ed410e5-f63a-5133-93ac-4778a23a2be5 |  | note | – – – – – – – – – – – – – – – – –
label | 215c2bb6-63b9-53e9-9a97-049ef3220173 |  | note | VERIFYING DOCUMENTS: This ITP
date | 545b0136-5480-56f0-9ef7-9e7eb392b03c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
label | f0c78711-6bd0-539e-9b2a-a4be8c971b7d |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | b00e08a6-63db-5373-a89c-2df8daca0a58 |  | note | – – – – – – – – – – – – – – – – –
label | b60dfe3e-5f6d-579c-9a86-dcb60433d71a |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 653d7941-1dcd-53bc-9a60-8017ecf8d9f9 |  | note | Record: Required information on the Concrete Pour Record.
label | d45f1c54-a644-5c80-ab55-5974a7d62f38 |  | note | – – – – – – – – – – – – – – – – –
label | fc711092-c709-597d-b116-1bab7c7084e6 |  | note | METHOD: Test
label | bf2fdc4e-a54d-5a61-b5a0-df9badb87d3e |  | note | – – – – – – – – – – – – – – – – –
label | 99972190-acba-5c92-9c8d-16b38acc7faa |  | note | FREQUENCY: Each sample
label | 5e3d3585-6b65-505a-8ed5-c7d8bd3d22f3 |  | note | – – – – – – – – – – – – – – – – –
label | ae043bf1-f888-5c23-801d-3bb2533fa8b2 |  | note | CATEGORY: IP
label | 41a1d36c-1f20-5521-95db-7b5b6ec23946 |  | note | – – – – – – – – – – – – – – – – –
label | 462db342-c01c-5e80-a0bf-81220451a24b |  | note | RESPONSIBILITY: Concrete Tester
label | 536b87da-3a19-5812-97d7-62e347f2b879 |  | note | – – – – – – – – – – – – – – – – –
label | 0d0e7f0e-d6c7-5208-a04c-0de8f0baefd4 |  | note | VERIFYING DOCUMENTS: This ITP
date | ee3e51c0-0365-5570-8877-530506af4145 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Placement & Compaction
label | d9f51a49-e7c6-502f-8b17-43993afc5966 |  | note | REFERENCE: Piling Operations Work Procedure 610.18 (a) & (b), 610.18 (d) (i), 607.04
label | e937d999-b1f3-52d5-bb9e-067a32c67af3 |  | note | – – – – – – – – – – – – – – – – –
label | 4997cf07-aee7-54f8-968c-892665635212 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 898f8009-0403-565e-8ca6-8444d2fd0bb9 |  | note | ○ The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
label | eb25a466-1e4a-5c09-8296-dfca6fb34bb4 |  | note | ○ The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
label | 85e8b27b-040e-56b6-8b4c-519c20ee1d7a |  | note | ○ Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
label | 9e1d5c24-5cf8-54c4-8734-38426d72da6c |  | note | ○ Concrete shall not be dropped freely from a height exceeding two metres
label | 670d0627-dcd1-5901-9d38-20f53c8ffe98 |  | note | Record: Required information on the Concrete Pour Record.
label | 7744503c-a0b2-5291-a263-0358dd4d0452 |  | note | Attach: Concrete Pour Record
label | 0e01ed58-de64-5079-b6c4-e669f4984f5a |  | note | Attach: Concrete Dockets
label | 7abf77d8-ae91-591b-9d91-c9563353b184 |  | note | – – – – – – – – – – – – – – – – –
label | a8ddd601-10b4-5e03-8930-bc363af5f085 |  | note | METHOD: Visual
label | 53c10c88-dd04-5097-8a81-f74955a76599 |  | note | – – – – – – – – – – – – – – – – –
label | 09f5c2e3-eb34-5ccb-bbaf-2333e127c394 |  | note | FREQUENCY: Each load
label | 4e3d870d-0b2f-5ed3-8b39-6dd9ba167ed2 |  | note | – – – – – – – – – – – – – – – – –
label | 4342c1f0-02c0-5715-b503-4bfabb32d49f |  | note | CATEGORY: SP
label | 7bdc4771-f26d-569b-90cc-b8165e24a9a4 |  | note | – – – – – – – – – – – – – – – – –
label | 3592eed4-3302-58ac-bc33-06cc9b83c45c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
date | 02946fac-f1d3-578d-9c79-d67446ec4d4a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Reinforcement - Placement
label | ce0991c5-0a13-5d92-95ca-195a23c75154 |  | note | REFERENCE: IFC Drawings 607.04
label | 00190cb7-0a0c-59a6-b53b-d097004f58b8 |  | note | – – – – – – – – – – – – – – – – –
label | ccc2c1e2-d28e-5939-a435-ec3ea83daf2d |  | note | ACCEPTANCE CRITERIA: The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
label | 18df4be8-bbc1-5f0d-9e38-f6ae8771192d |  | note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
label | 75d2d33e-da21-5de2-a0b6-fa19c8ec8368 |  | note | ○ If the cage cannot be positioned into its final level, the pile shall be rejected.
label | 8f29b8c7-7f7e-56d6-9de5-80fa7912fc4d |  | note | – – – – – – – – – – – – – – – – –
label | c0befef7-6255-5147-b38d-cf35b1d29f6d |  | note | METHOD: Measure, Visual
label | 91eab24d-cf54-517a-9f6f-6875e4df196e |  | note | – – – – – – – – – – – – – – – – –
label | 9a5e0784-501b-58a9-8996-6b7c17295266 |  | note | FREQUENCY: Each pile
label | 684ce3a6-dcc3-52c4-a735-b357586a4e03 |  | note | – – – – – – – – – – – – – – – – –
label | 1047a014-24ec-520a-b124-1af0c6f34096 |  | note | CATEGORY: IP
label | f32ab5a1-d42a-59ae-b98f-3a105ff1a55f |  | note | – – – – – – – – – – – – – – – – –
label | 437ee4ef-b999-56de-819b-0f6ea5baa849 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e08b014a-0c31-5bef-9bae-2cd63c8c5dfe |  | note | – – – – – – – – – – – – – – – – –
label | a115dfc8-d804-5457-a76e-d0f2087daf03 |  | note | VERIFYING DOCUMENTS: This ITP
date | 126dff5e-b0b4-523c-a0d6-9cfaf502da77 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Cast-in Items
label | 3c2c83f6-59c0-526b-958d-327a27e7ca5f |  | note | REFERENCE: IFC Drawings 610.46 (a) Table 610.462 (November 2018)
label | 1fd6a4f7-5a4f-56be-8c74-ca4f5d5a5a9a |  | note | ○ 610.47 (a) Table 610.472 (March/June 2019)
label | c2ac5438-cf98-5fb4-bf12-099f42937442 |  | note | ○ AS3810.1 Table 3.3.6.2
label | cc9b041e-8bc7-5f41-bf7d-e0d51c37dc61 |  | note | – – – – – – – – – – – – – – – – –
label | 8d88710e-467d-53d4-ac96-50487bbf7154 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
label | f0771329-3e57-57b7-95c8-f480267ea620 |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 44c4a07b-63e1-5c9e-b23d-26ba54ba16b1 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 3cf8b8bf-bdee-598c-bd4a-cf963b0941d2 |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 436738de-4698-565c-9fd9-3dbff70dcea7 |  | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | f5c8d27e-e6a9-57e6-bb39-84112e3b5ac0 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | bf197ad8-db8c-5859-8db0-c44599022e4d |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 79572661-e04f-561f-9f43-432238085da3 |  | note | iii. Ducts and conduit location = ±12mm
label | 51718b28-3504-5559-946a-a9690c8e4050 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | d6be6812-4bc6-54a0-a12a-85358fc349e1 |  | note | – – – – – – – – – – – – – – – – –
label | 540f38bf-0cff-52b2-836a-bfc3302671b7 |  | note | METHOD: Measure, Visual
label | 6b7eaf0b-711f-5e4b-a255-bd6072e46aed |  | note | – – – – – – – – – – – – – – – – –
label | 683dd1be-521a-5cda-be3f-7171bf7e8e78 |  | note | FREQUENCY: Where applicable, each pile
label | dea35585-b472-5680-aeb3-ecbbfcd8074e |  | note | – – – – – – – – – – – – – – – – –
label | 5aa0bdb0-398d-5677-b045-f75639d5ae22 |  | note | CATEGORY: IP
label | 435c6e37-cee7-58cd-8947-fe6c7049a62a |  | note | – – – – – – – – – – – – – – – – –
label | da010cf0-96ea-5f56-a499-f09bf4ce8de4 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 9a2d4287-4483-503d-82c0-05c05fde6027 |  | note | – – – – – – – – – – – – – – – – –
label | 6cd847fc-5829-5e44-bdd1-62e49a37deed |  | note | VERIFYING DOCUMENTS: This ITP
date | e64249c7-058f-5017-9cf3-40962fc29968 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 7bef164d-ae2c-52a8-a450-1975892f6034 |  | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 607.04
label | f02a7fa5-809d-5e61-a112-06e0852936b4 |  | note | – – – – – – – – – – – – – – – – –
label | f9205aae-9e43-5266-815a-112b2ed5ae01 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | 5b30e2da-9ebb-5bb7-bade-4296dae3596d |  | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 817fe356-09fb-57b8-906b-3aa32c63f1bf |  | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
label | 01c2a79b-2e7b-5b47-8948-3dfe9e789ffd |  | note | – – – – – – – – – – – – – – – – –
label | 3db81e58-01a0-5d24-b189-0bd81669f348 |  | note | METHOD: Measure, Visual
label | 605d81ed-2cea-575f-8bca-0f5912f3de0c |  | note | – – – – – – – – – – – – – – – – –
label | 5cff535d-afa9-5d85-bdfb-0eeb79c1ee2c |  | note | FREQUENCY: Where applicable, each pile
label | cb317560-1340-5e7f-befd-be021f1c42f8 |  | note | – – – – – – – – – – – – – – – – –
label | 1f6a7455-dfb8-5216-8a92-a2e8209c1f75 |  | note | CATEGORY: IP
label | 0359b341-c601-5b14-8fcb-bda69fbffd5d |  | note | – – – – – – – – – – – – – – – – –
label | fbbfed90-f65e-565b-bf17-3612acc9b6c8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 26bf46fb-07f5-58b4-9a9f-c085ab1f9e21 |  | note | – – – – – – – – – – – – – – – – –
label | 8075161e-b72e-54af-8af7-105380acd7e5 |  | note | VERIFYING DOCUMENTS: This ITP
date | a7af3056-0950-516c-a842-8e1c38e37cc8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 9d39fd02-4ce9-5030-b1e3-37d86a0062b1 |  | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
label | f84c1f03-2de4-5b40-a2be-395cb5adcc73 |  | note | – – – – – – – – – – – – – – – – –
label | c005c0f0-2a0e-5690-b970-072be1196d57 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 562d5435-97d8-55de-aff1-04b3f0aaffcf |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | d2e5098f-66e8-5ce8-8f69-a54e053537d4 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 75d2af20-8ad1-5831-918a-decbffd2db8b |  | note | Attach: Compressive Strength Test Results
label | 04e96597-eaf3-5d6c-9894-3e62b417553d |  | note | – – – – – – – – – – – – – – – – –
label | f9bca2ad-3692-5231-b577-7b504c1d0b1e |  | note | METHOD: Document Review
label | fcaa88e1-2538-552c-9df7-4e1a213795c5 |  | note | – – – – – – – – – – – – – – – – –
label | 809383ad-a030-56a1-af48-3bb593563136 |  | note | FREQUENCY: Each cylinder
label | 9c891015-39a0-5ad5-be4f-b1f8610bbee0 |  | note | – – – – – – – – – – – – – – – – –
label | 2a60605a-484b-5f41-b935-03213d203ee5 |  | note | CATEGORY: IP
label | 2a5253aa-311e-58d9-bced-5f6b0092aae1 |  | note | – – – – – – – – – – – – – – – – –
label | 536e328d-d62b-5618-9d28-697c107c0074 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 674ce256-2596-5a15-9f2d-66bc22a4fb94 |  | note | – – – – – – – – – – – – – – – – –
label | 15f64e95-e718-5866-9570-39856bdefbed |  | note | VERIFYING DOCUMENTS: This ITP
date | 702beb48-3fa1-5036-b8a7-694ba4e5aa9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 00864ccf-c2e7-549a-9070-7d3ec5d62cc0 |  | note | REFERENCE: 607.07 AS2159 Clause 8.8
label | 2a6d7b7e-f0fa-5503-a58d-b02db6b1840e |  | note | – – – – – – – – – – – – – – – – –
label | 450bc72a-1aa1-5afd-a47d-0cccbd4aeb61 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | adcb6431-ded1-5d5c-bafd-8a0ddf9b9db5 |  | note | ○ Cross-sectional area = ≥90%
label | 7ec9b674-f4ab-5a05-a5b8-70936e1cf458 |  | note | Attach: Pile Integrity Test Report
label | b4d80fdc-990c-5d90-a291-86657f9cb086 |  | note | – – – – – – – – – – – – – – – – –
label | 2e2d9e09-ac8c-57c5-a67f-de3dadc516d7 |  | note | METHOD: Document Review
label | 81f187cb-fac3-5a26-b2d9-ae45fcde2ec6 |  | note | – – – – – – – – – – – – – – – – –
label | 92adc1e3-4234-5db4-88c5-696bb3c03e52 |  | note | FREQUENCY: Each pile
label | a1bb3602-fd55-52a8-9e06-e802936d31f8 |  | note | – – – – – – – – – – – – – – – – –
label | 85743e41-d18c-5136-a007-415402d3c804 |  | note | CATEGORY: IP
label | 153eeceb-31a2-5174-a085-9497fa59fa04 |  | note | – – – – – – – – – – – – – – – – –
label | ae9f86f8-2d9b-5738-a234-c094a7397a26 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 4ab01659-9478-561d-9ff0-d50e2c1fd4fa |  | note | – – – – – – – – – – – – – – – – –
label | 94ca1e02-3e64-5d78-b672-423957c5390a |  | note | VERIFYING DOCUMENTS: This ITP
date | 133c7689-a2ea-5b50-9f71-ef45888ed198 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Dynamic Pile Testing
label | d3164511-61e9-5ec3-b8ba-b0c361e47b5c |  | note | REFERENCE: 607.07 (b) AS2159 Clause 8.7
label | 3f0a954b-937c-5c3a-b70d-e1f1dd54b7d0 |  | note | – – – – – – – – – – – – – – – – –
label | f14a479a-f0cb-524c-b9dc-18f9e04595f0 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | ffd457e9-b484-557a-b0fb-ec4a976d801c |  | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
label | 2be4bac9-b885-5a19-a0d3-4dde2aef5fbd |  | note | Attach: Dynamic Pile Test Report
label | 2f30e772-6a75-5017-9c29-ecfe64d7a57d |  | note | – – – – – – – – – – – – – – – – –
label | 54aeccb8-890a-5c24-ad56-df4671745119 |  | note | METHOD: Document Review
label | 658f8039-ce16-5b03-9b70-39ff428082d6 |  | note | – – – – – – – – – – – – – – – – –
label | 87120cf2-08b3-5a19-b82e-2c72da7acec0 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | caa3c493-22ff-504d-894e-510c444eb0c9 |  | note | – – – – – – – – – – – – – – – – –
label | 871fdcc6-fe67-5a45-9ba2-9d579c91ab88 |  | note | CATEGORY: IP
label | 0a706749-7b70-5906-a0d3-1bbfb0cb1819 |  | note | – – – – – – – – – – – – – – – – –
label | e14dabb8-89c8-5e13-9576-6ce6c491c892 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 0c6f4e71-2bce-51e6-b4e4-c591e5accaf3 |  | note | – – – – – – – – – – – – – – – – –
label | f38b6867-345f-52fc-8653-47ffb6b6c568 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3b2beda6-c96a-5c42-9a8d-e2cac5a28756 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 As-built Survey
label | c281510d-156a-51ca-8472-2fa6f48bdcdf |  | note | REFERENCE: IFC Drawings 607.06 (a & b) AS 2159 Clause 7.2.1 and 7.2.2
label | 3bd64545-9446-5526-8816-dca9bb04e8fb |  | note | – – – – – – – – – – – – – – – – –
label | 2fd3fdd2-4271-584a-bda6-051c9408c122 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 1dab2f0a-1665-5ce4-8473-88abd27a7be5 |  | note | i. Centre of pile head plan location = ±75mm
label | da5d8ec4-9376-5cc3-9407-bc34928aa3c6 |  | note | ii. Variance from vertical or rake = 1:50
label | 521ebe53-c830-5157-9929-2319a93e56c8 |  | note | iii. Irregularities in straightness = 1:100
label | 6f60fece-aaf0-5d31-8027-074d482e3130 |  | note | iv. RL = ±25mm
label | 5787ac3d-cbe8-5322-999f-2f813aa50804 |  | note | Attach: Survey As-builts / Survey Report
label | 83c76d28-3b69-5a72-a849-a63f4abc9ae2 |  | note | – – – – – – – – – – – – – – – – –
label | fa5dd911-cfa3-583d-a396-6cc61d7fb344 |  | note | METHOD: Document Review
label | 4ee4401f-6495-583e-b437-0422317cdb92 |  | note | – – – – – – – – – – – – – – – – –
label | b1e72821-4a70-5e7e-9107-4813674a239d |  | note | FREQUENCY: Each pile
label | 7479e714-053c-53d5-aec5-4a5c397c4c72 |  | note | – – – – – – – – – – – – – – – – –
label | 423180c8-be90-576d-a392-75f63db5a613 |  | note | CATEGORY: IP
label | c24047d4-86af-5723-a73d-16611789e6d4 |  | note | – – – – – – – – – – – – – – – – –
label | f69743a7-f5e8-52cc-87af-6564201dc56b |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 4c752cba-4c6b-51c9-a757-6cc3624be485 |  | note | – – – – – – – – – – – – – – – – –
label | da537542-7966-5e7e-b41f-cc9073ca8ec9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3a13f2cf-e496-59c5-823c-a00fea1e2153 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 285d42de-6e77-5ef4-bade-ffd58e6f0853 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8da411c2-cd18-596a-8e4e-cc0a1ab80b07 |  | note | – – – – – – – – – – – – – – – – –
label | ec613088-7a1e-505a-8ecc-fa70bfe0bdc4 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1813bfaf-cd76-5917-a6dc-ba56e0ff075b |  | note | – – – – – – – – – – – – – – – – –
label | 35ba151b-82b1-5a88-ac5b-26601cf3e8ef |  | note | METHOD: Document Review
label | 18220dbb-0d0e-59df-9e52-6f99c30882f6 |  | note | – – – – – – – – – – – – – – – – –
label | 89a38244-6f50-57f0-ab49-79080c4cfc1b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | f8b4a8c5-2110-5357-8f7d-6b43669fcff4 |  | note | – – – – – – – – – – – – – – – – –
label | f87fc22e-aa4b-5582-a3b2-c9a4733300a1 |  | note | CATEGORY: HP*
label | bbb8baf0-c02c-5b1b-835f-36c3c989d792 |  | note | – – – – – – – – – – – – – – – – –
label | ca721224-81c7-5244-8c0e-2704fd3b053d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4aa76577-c2bf-5d24-af70-311964defd83 |  | note | – – – – – – – – – – – – – – – – –
label | 8fdb0309-bc25-565a-af81-8d7bec21f06c |  | note | VERIFYING DOCUMENTS: This ITP
date | ea549437-e0d5-5974-a552-041cf88789be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ade42c8e-cc3e-52cc-9d3b-e95f1725a8fb |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b71565bd-6a4d-522d-ae58-f0a2c6755796 |  | textbox | Name:
text | 38993dc6-6259-5e1b-bd29-18691443d425 |  | textbox | Position:
date | 38459256-5491-5501-b890-cb0b4417df56 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp |  |  |  | Yes | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | df1b0790-d11a-44ae-aaf5-24e136b391f5
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Reference Documentation
label | 6d4675ab-d88e-5714-8fa6-4fdff71aac86 |  | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
label | b541da8f-ec87-5d69-b686-206cd3c6b470 |  | note | ITP Description:Concrete Coatings (Protective &/or Decorative)
label | 9f51500c-0f2d-5ca1-9bfc-e558927202f1 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 8ffb0368-d968-5575-b29b-fefb08b51fba |  | note | Revision Number: 2
label | bbb04446-cfa8-5f95-8bdd-7bd537a31f63 |  | note | Revision Date: 11/12/23
label | 0cc18cf2-8dc8-5a5b-ba70-735460e906d2 |  | note | ITP created by: Mike Freeman
label | 53449ce0-3165-5820-b59a-9fd4db8f03d7 |  | note | ITP approved for use by: Mike Freeman
label | 42470bf6-7387-56f7-b789-c7e61e2d3be6 |  | note | 1.1 VicRoads Section 685 November 2018
label | 2595fe17-a24f-5ca3-ae1e-09167da3fe57 |  | note | 1.2 VicRoads Section 686 November 2018
checkpoint-group |  |  | section | 2 - Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Anti-graffiti System Selection
label | 0f949bc6-e731-5ea0-a72b-34b753600861 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
label | 6fdcbe77-0afa-5a8e-8e78-2bc3b04e2b8f |  | note | – – – – – – – – – – – – – – – – –
label | 2d6ba170-bb1d-58aa-8cfd-11fa20b11174 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 98d23cea-5429-5046-a2fd-f54af705a6ab |  | note | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
text | 1e354bc6-fb9e-547a-8894-238f23d91a18 |  | textbox | Enter: Teambinder Material Approval number
label | 58729775-5b81-5bd2-8452-ca9d8636dda3 |  | note | – – – – – – – – – – – – – – – – –
label | 580b046b-418f-5b0c-b350-23c0a6ca2db4 |  | note | METHOD - Document Review
label | 2f089821-a06b-5407-b15d-655c70317f5b |  | note | – – – – – – – – – – – – – – – – –
label | 3a61e1f7-ced3-5852-a1fc-924938ee7c8f |  | note | FREQUENCY - Once, for each coating system, 14 days prior to application
label | d59ee688-f686-5964-9d1a-158d74de895a |  | note | – – – – – – – – – – – – – – – – –
label | 311f8f95-d75c-54e8-a867-f615a6a03542 |  | note | CATEGORY - HP
label | 688fb48f-c6bb-592b-ab98-a8b2888e83d9 |  | note | – – – – – – – – – – – – – – – – –
label | b71d7735-3849-5547-a312-4509c7d0d0ce |  | note | RESPONSIBILITY - Nominated Authority
label | 0b619de2-cda9-5224-9c45-d342a34cd052 |  | note | – – – – – – – – – – – – – – – – –
label | 350f4d6b-8b86-5d9e-8d5f-96b5cb0364a2 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | ffd1deaa-4378-570b-a865-c852f3cd1d1e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
label | 87f53de2-4ed0-5aa0-94c0-d1912fa66ad8 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
label | 4b11c74c-af03-51c4-b398-e23cc9a11a22 |  | note | – – – – – – – – – – – – – – – – –
label | b03609f6-c13e-5703-9373-2d040da217a5 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | 16995d71-70b6-5d67-8c58-e663f8f8a48e |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
text | 18d2b163-5d65-5cab-b04c-1511385e9770 |  | textbox | Enter: Teambinder Material Approval number
label | 60691b7d-a891-59a4-a5e8-8fc991703ca7 |  | note | – – – – – – – – – – – – – – – – –
label | c5f95fdf-5f4b-598a-8df8-a953de087178 |  | note | METHOD - Document Review
label | e3611eca-ba9a-5722-afbb-07aff3fc53b5 |  | note | – – – – – – – – – – – – – – – – –
label | 2689a03b-94d7-5776-9ce4-2731cadfaae7 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | ec8fd45b-d79e-5b93-bf91-0b53feba2d69 |  | note | – – – – – – – – – – – – – – – – –
label | ebafb50c-236b-5f17-8256-a5e76fbd6225 |  | note | CATEGORY - HP
label | 55ca036e-7465-5961-a463-b731e9e98c35 |  | note | – – – – – – – – – – – – – – – – –
label | 56d79b77-b739-5fc2-96de-1b74a179052a |  | note | RESPONSIBILITY - Nominated Authority
label | a7cd8852-b9e4-5e8d-aa37-5bbb692ef4aa |  | note | – – – – – – – – – – – – – – – – –
label | 34bf93b7-e65e-58f9-b96b-920a0b1090e2 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | eadf3a0b-a5d2-5af5-a8c6-88d9a148d9a4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
label | 3b5b5683-fc4a-58b7-9b9c-919662227e44 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
label | e6b85902-0622-5f3a-adb3-03bad19724cf |  | note | – – – – – – – – – – – – – – – – –
label | 4f7581cc-9dcd-5b8b-b45b-f10cf34a5a7c |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | bc9f0600-db1a-58ff-9165-3bd45e2727cb |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
text | 216135f6-ce72-51fd-a4cc-16caed19cc73 |  | textbox | Enter: Teambinder Material Approval number
label | 28d8091f-9be6-55ab-b69d-42ce45560548 |  | note | – – – – – – – – – – – – – – – – –
label | 9afc8648-19f7-5e62-82cb-1ce3f8a59a73 |  | note | METHOD - Document Review
label | ac62028a-7f7b-54b0-a4a3-81502aa840ce |  | note | – – – – – – – – – – – – – – – – –
label | 8983baea-f114-51e2-9083-3a3058242b50 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 8612cde3-81d0-5a86-af56-bc01f41a13ce |  | note | – – – – – – – – – – – – – – – – –
label | 827239be-56fb-5614-805f-bb50912cca71 |  | note | CATEGORY - HP
label | e2839f30-9f43-5207-83d3-fad947a809ef |  | note | – – – – – – – – – – – – – – – – –
label | 0dc292e9-eeaf-5ae7-9852-eb4db1a88423 |  | note | RESPONSIBILITY - Nominated Authority
label | 46413889-5243-5aa1-a70e-b29c0cc288b9 |  | note | – – – – – – – – – – – – – – – – –
label | 142b7f5d-2260-52f4-a863-429c8e70dcd2 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 2c0b3645-8a9a-599b-8df6-aab5079eb386 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
label | 909fb6e5-1055-5a7b-8f0c-b281a0885601 |  | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
label | 1fd1868f-5605-516d-b739-84e123aab6c1 |  | note | – – – – – – – – – – – – – – – – –
label | a268ccf8-41d3-5fd0-92b6-14b55772ba52 |  | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
label | fcd0624c-9bbe-5727-b860-1d0301b09621 |  | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
text | fb2ca039-137a-5e38-bf6a-2f9d5a8a56f0 |  | textbox | Enter: Teambinder Material Approval number:
label | ce496800-f39d-599c-9a22-746a58f09a04 |  | note | – – – – – – – – – – – – – – – – –
label | ef221d62-2de8-5919-b4f7-70217e80d599 |  | note | METHOD - Document Review
label | 3d7729e7-03af-5779-970f-bcd7a8f5cc96 |  | note | – – – – – – – – – – – – – – – – –
label | 4a5c873a-94bf-53d9-bd1e-f31c758b5492 |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 8361444e-9a7d-5397-8ded-3f6b7d558722 |  | note | – – – – – – – – – – – – – – – – –
label | a4634a42-7d24-5653-a08e-518ed916ce00 |  | note | CATEGORY - HP
label | 899d51f1-dae8-5aff-af90-c58429864602 |  | note | – – – – – – – – – – – – – – – – –
label | 9b92e548-f3ee-5a73-b8e4-9dc9d786d59b |  | note | RESPONSIBILITY - Nominated Authority
label | 0a29cfe9-588c-5b3e-b1ae-0d83131b5917 |  | note | – – – – – – – – – – – – – – – – –
label | bd68ac4c-060f-5186-bebb-b56a0b356578 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 1f60d6d1-4844-529d-b844-b419fb5b39dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Quality Documentation
label | 553b4af1-19da-57f6-a670-d0b2d7e8f084 |  | note | REFERENCE - 685.05 686.04
label | ebc73fe7-f3e8-5249-a8bb-911d61052413 |  | note | – – – – – – – – – – – – – – – – –
label | 32bcb69b-50bb-5883-9e76-f8073ac449f6 |  | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
text | b42e5005-a611-58a5-aef6-ade832bd6e4c |  | textbox | Enter: Teambinder Hold Point number
label | 6eea7c98-f6ab-59c2-a27a-ab6a9d6a2cf2 |  | note | – – – – – – – – – – – – – – – – –
label | 9adbd7fb-4d9c-5433-a103-d428fd791ea9 |  | note | METHOD - Document Review
label | d7ac7456-2d55-56c0-acdb-6d7565a9ee29 |  | note | – – – – – – – – – – – – – – – – –
label | 5fbc3542-5540-5238-b930-4d1e2c0123ae |  | note | FREQUENCY - Once, for each coating system, 21 days prior to application
label | 4359368f-49a4-5ce3-9bfa-1dbf92fb8c39 |  | note | – – – – – – – – – – – – – – – – –
label | 3ffda72c-5bcf-5da6-853f-3c1fedd400a5 |  | note | CATEGORY - HP
label | 40010cc3-f242-5598-a96b-ce3e5eabaa8c |  | note | – – – – – – – – – – – – – – – – –
label | 27f3e7da-442b-504f-aed4-5516ddf46703 |  | note | RESPONSIBILITY - Nominated Authority
label | 961b8434-bea2-5383-ad1b-bd49a363c414 |  | note | – – – – – – – – – – – – – – – – –
label | b43ab333-754a-5749-85ad-7076730cca72 |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 71100b96-31b4-5257-95fb-d5a2a180b669 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Coating Personnel & Equipment
label | b037c35d-bb25-5a6d-9875-314482cac723 |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
label | d8adb728-e56c-56ab-a579-1de3fb18da76 |  | note | – – – – – – – – – – – – – – – – –
label | 2f56f074-1e5d-5e8f-9526-958d6bb8f668 |  | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | 4de1b36f-b757-55af-89c4-551ccc0b0a74 |  | note | – – – – – – – – – – – – – – – – –
label | 5ca7f56b-f021-5fae-99fa-e4dd56b3fc46 |  | note | METHOD - Document Review
label | 41c7753e-466b-5216-a2e9-4e824f02edd7 |  | note | – – – – – – – – – – – – – – – – –
label | f142cee1-f244-51fa-8ac1-928a453ea662 |  | note | FREQUENCY - Once, prior to application.
label | 804c30e9-24d2-5200-9a23-da17027ae457 |  | note | – – – – – – – – – – – – – – – – –
label | d04a5dd8-c74a-5b3f-986b-7c665e70dcd9 |  | note | CATEGORY - IP
label | df68eca1-6797-5c24-bbd7-852014ebf7ad |  | note | – – – – – – – – – – – – – – – – –
label | 55bc128b-ec96-5417-927e-7fceb1ab1db6 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 425b04ed-cb30-537e-b731-bc285d03dff9 |  | note | – – – – – – – – – – – – – – – – –
label | df3a04e8-46c9-5e70-ac53-a8841989864d |  | note | VERIFYING DOCUMENTS - This ITP
text | b3282d02-e420-5cde-a2c6-8131b258388b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Protection of Adjacent Works & Property
label | 0c4f106f-2a0e-58fa-a69f-ac78570fbd82 |  | note | REFERENCE - 685.17 686.10
label | fd3dd1c5-a369-5a69-9d74-c0d117844baf |  | note | – – – – – – – – – – – – – – – – –
label | f1724b42-4349-5534-b68a-6817907b4dcf |  | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | 3a65ab1d-7e25-5a9b-b902-718981b624cd |  | note | – – – – – – – – – – – – – – – – –
label | f9071711-7232-599c-9037-b82f4edad10e |  | note | METHOD - Visual Document Review
label | c0f4ef38-f762-5272-8fd7-b5d2c8f0915d |  | note | – – – – – – – – – – – – – – – – –
label | 47480554-38da-5eb6-b49c-3e010ead5c14 |  | note | FREQUENCY - Where applicable, 2 days prior to application.
label | f7d690c1-bf4e-531f-b0f3-5f977e8cd1a6 |  | note | – – – – – – – – – – – – – – – – –
label | f7b48262-052d-5d17-ade8-3ed103037dbf |  | note | CATEGORY - HP
label | 6c7384d5-71ee-58f0-910a-386fde33489f |  | note | – – – – – – – – – – – – – – – – –
label | c9db20e8-81cf-565a-a30f-e6abe6f9545e |  | note | RESPONSIBILITY - Nominated Authority
label | 637d703c-9b12-5f9e-9751-634bb8296e7a |  | note | – – – – – – – – – – – – – – – – –
label | 5a2dd8ff-9c14-5df2-8824-987e5c9cc03f |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | 4b23cedd-6af0-59b0-bc6f-616941c72da4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Minimum Concrete Curing Period
label | bd92d7f4-5f89-5bef-8c87-818046bc63ba |  | note | REFERENCE - 685.08 686.16
label | b52cbf3d-6417-5476-8eaa-12b583498c8f |  | note | – – – – – – – – – – – – – – – – –
label | fdd95f05-deca-5267-9d0b-7cdcb8999c5d |  | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | 2642feeb-2aff-5cea-b882-ca2463f18609 |  | note | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
label | 720175d8-c723-57c8-8040-18d1a886ae40 |  | note | – – – – – – – – – – – – – – – – –
label | 5d6ae32a-5da9-54cd-831f-1d12f58797cd |  | note | METHOD - Visual Document Review
label | 89eb59a3-4495-55e8-85c3-d6fa34092dc6 |  | note | – – – – – – – – – – – – – – – – –
label | 35305b24-5fbd-597e-ad33-bbce5e0067f2 |  | note | FREQUENCY - Once, prior to application.
label | 4290101f-0abb-5cf9-aa03-ed1eff8507a0 |  | note | – – – – – – – – – – – – – – – – –
label | 33578b1f-0de8-5aac-97fa-8b28ebc8f9ff |  | note | CATEGORY - IP
label | 124f7212-2926-58d4-98f2-17aa0c0d8f43 |  | note | – – – – – – – – – – – – – – – – –
label | ae69c80e-7a10-5fcb-9db4-8032653537bf |  | note | RESPONSIBILITY - SE/PE/SPE
label | 385a50f5-c033-5bd9-97b2-46d2f4a704c8 |  | note | – – – – – – – – – – – – – – – – –
label | 01978cd2-83db-574a-adff-6ca504271782 |  | note | VERIFYING DOCUMENTS - This ITP
text | 4ee6fdf7-70da-5675-8602-4df7275ea99b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
label | 3bbede8b-3288-56e1-b804-39241229eaaa |  | note | REFERENCE - 685.11 686.13
label | 4a6bbcdc-b901-52ac-9bae-2b36286c636e |  | note | – – – – – – – – – – – – – – – – –
label | 29046c8e-438e-5350-b1ac-a183e785dbd9 |  | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | 26df53a4-2d7e-5f5a-8509-4da724f5ced5 |  | note | Attach: Inspection Photographs OR
text | 71abb8ca-d7ea-572b-8129-40710c4e7c3e |  | textbox | Enter: Teambinder Hold Point number
label | 04ec3a58-8f89-5683-81f2-55eb6ac5b8b7 |  | note | – – – – – – – – – – – – – – – – –
label | e5043226-5750-5c03-b201-660f45e2a824 |  | note | METHOD - Document Review
label | 594ac971-acdf-57a6-a0f3-ae05b6470eaf |  | note | – – – – – – – – – – – – – – – – –
label | f291e3ce-71dc-5e2e-aae4-785014bfa30e |  | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
label | 7ce9dda0-087d-5103-ac66-8cd6a3b8e3f6 |  | note | – – – – – – – – – – – – – – – – –
label | 230cf319-f840-5d85-8891-14328c8969ca |  | note | CATEGORY - HP
label | 03f53e49-226c-5bc9-b8db-5152d8af7732 |  | note | – – – – – – – – – – – – – – – – –
label | 7e85ba6d-1fe4-5104-8cd5-e09c108ca76d |  | note | RESPONSIBILITY - Nominated Authority
label | df812984-7720-578f-9545-795108628169 |  | note | – – – – – – – – – – – – – – – – –
label | 0ea75d2d-09e9-599b-8c9d-3c2bcea7e8ec |  | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
text | c7503ab3-eef0-55eb-8e94-f53e5e2f5363 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Pre-application Activities
checkpoint-status |  |  | checkpoint | 3.1 - Material Records
label | c8e0e6b8-c51f-56c5-a71c-cfd0d8b9568b |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
label | d0eb2b36-4e7d-52ab-abd9-acba2fdf36f6 |  | note | – – – – – – – – – – – – – – – – –
label | 23f79383-3122-54cf-a9f8-728d7182fed2 |  | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
label | 6c03152a-9fe4-5b23-99cf-a8abe085ef7f |  | note | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
label | 6987770f-7c02-5e5c-b3f4-5f64885ec211 |  | note | – – – – – – – – – – – – – – – – –
label | 0538df22-5124-59a7-aee2-af39b487401c |  | note | METHOD - Visual
label | 79a0ff21-746e-597a-8938-78a9bca4a135 |  | note | – – – – – – – – – – – – – – – – –
label | 6829c902-f673-55f7-86bc-7cd500b43577 |  | note | FREQUENCY - Prior to application
label | fd3b030d-b6dd-519c-afa5-c4ea78c144e2 |  | note | – – – – – – – – – – – – – – – – –
label | 2a3ac776-8456-57ec-bfe1-3b8276be3a76 |  | note | CATEGORY - IP
label | d04da30a-8238-5157-a501-5a6e031813f8 |  | note | – – – – – – – – – – – – – – – – –
label | 70b23c23-ee63-5d15-98dd-7d34f8498923 |  | note | RESPONSIBILITY - SE/PE/SPE
label | ded2b8b3-5755-5258-804a-a4eb4b7a0827 |  | note | – – – – – – – – – – – – – – – – –
label | 21cdd6af-37f2-5be4-b0eb-2163ad7cd8c7 |  | note | VERIFYING DOCUMENTS - This ITP
text | 437fff6f-e0e1-56ee-ad54-6cf6cf5f7bdb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Weather Conditions
label | 0d806c1a-5c50-5a24-84d7-6827088c30fc |  | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
label | 8d889ee5-521b-52ab-a91e-14640a17451a |  | note | – – – – – – – – – – – – – – – – –
label | 1c711db8-b195-5849-b58c-936912bd2f1e |  | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
label | d01e1f86-d1c3-559d-8cfa-7b754dcf4877 |  | note | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | 0fc5f6ed-b712-5bb8-9b83-0b5f20f7df72 |  | note | Weather conditions are to be recorded.
label | e809766e-d308-51bc-bdf9-d1bd53ef3b07 |  | note | – – – – – – – – – – – – – – – – –
label | 2bad80dc-c31f-5c8a-9311-508859624c28 |  | note | METHOD - Visual Measure
label | 92b075f9-1c0d-5e74-bdf1-50322c2fda6a |  | note | – – – – – – – – – – – – – – – – –
label | bdf0650f-cdc2-58bd-b688-fc4993cd63ee |  | note | FREQUENCY - Prior to application and every 4 hours per shift
label | 257cb3ee-6052-54e5-a9f3-65bb65b6da22 |  | note | – – – – – – – – – – – – – – – – –
label | b6fe9d5f-576f-5a91-87e5-3d71bb5f0c6b |  | note | CATEGORY - IP
label | 0d77c98b-acf1-5df6-b3ec-4368fa37d60b |  | note | – – – – – – – – – – – – – – – – –
label | 2b99fe02-db09-5243-9bca-a76c605ef715 |  | note | RESPONSIBILITY - SE/PE/SPE
label | ba362a12-3b9c-5297-9fdf-9e05b9d3f17c |  | note | – – – – – – – – – – – – – – – – –
label | af799b65-70b9-5989-93d7-04b0986fd4b8 |  | note | VERIFYING DOCUMENTS - This ITP
text | 190c156a-8c5f-503c-9614-cb532cb78c62 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | 4f8cc284-b926-5df6-b957-7ce248236f41 |  | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
label | db8b7cf9-a012-54bc-8305-2dabacb1f72c |  | note | – – – – – – – – – – – – – – – – –
label | 32939c0c-cbb8-57c4-b3b2-fc289fcbbdd9 |  | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | 660da809-d65f-5b58-bb6f-98475fba8bf8 |  | note | – – – – – – – – – – – – – – – – –
label | 7b467fe4-e507-56de-bf42-ddc83de55368 |  | note | METHOD - Visual
label | 4a41d0f9-8be8-587c-bff1-5e2ab90f265f |  | note | – – – – – – – – – – – – – – – – –
label | b86c03ea-9eef-5fa0-b630-b265b22e1c70 |  | note | FREQUENCY - Once, prior to application.
label | 83cdabbd-0fe0-5e00-8c3c-a6ac6ea260a9 |  | note | – – – – – – – – – – – – – – – – –
label | b5d26318-f151-5803-87f7-f277635b78eb |  | note | CATEGORY - IP
label | 515702db-f7ed-5adb-a95a-4b794c29f185 |  | note | – – – – – – – – – – – – – – – – –
label | 13f9f8c6-3aa1-5067-89c9-82d26758519a |  | note | RESPONSIBILITY - SE/PE/SPE
label | b5eee343-b608-5695-b5c9-662b5aa41492 |  | note | – – – – – – – – – – – – – – – – –
label | 8d5be1d5-6c28-5828-be5f-0e6a2f4f6e5b |  | note | VERIFYING DOCUMENTS - This ITP
text | b030126d-6752-5e36-a0e9-7355360f0779 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 - Surface Moisture Testing
label | c7824685-c947-557e-aa26-a00045f93281 |  | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
label | 518f6249-63fe-516b-affe-f72306916a58 |  | note | – – – – – – – – – – – – – – – – –
label | a5744b53-0438-513f-820e-259cf67bb153 |  | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
label | ca4bba93-0654-50f4-a7e1-b028ff8be256 |  | note | – – – – – – – – – – – – – – – – –
label | f9da52f8-b527-5630-9bf5-52b51819bd79 |  | note | METHOD - Test
label | 62a48b4b-a169-55cf-ad98-93694c91b61f |  | note | – – – – – – – – – – – – – – – – –
label | 84ae067f-6c40-5b0f-9185-50f5c9ed4c71 |  | note | FREQUENCY - Immediately prior to application, test 1m²
label | 46548bb2-69ac-55f6-9d2e-9bd41ff6d37c |  | note | – – – – – – – – – – – – – – – – –
label | 41429650-e3a9-54ba-91be-bc201490833b |  | note | CATEGORY - IP
label | 5520f87f-e046-597b-81df-ed1826726b54 |  | note | – – – – – – – – – – – – – – – – –
label | 978833fe-c15d-5e0e-aea6-8e0a9257582c |  | note | RESPONSIBILITY - SE/PE/SPE
label | e9be829a-fcb7-51d5-92fe-2305509829ee |  | note | – – – – – – – – – – – – – – – – –
label | f47163db-60f7-5cdc-b017-5a6dde1c5373 |  | note | VERIFYING DOCUMENTS - This ITP
text | 4c0d1ecc-c981-5463-88e1-79a08ccff2ca |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Application Activities
checkpoint-status |  |  | checkpoint | 4.1 - Method of Application
label | 655720ad-d82e-54e4-a0cc-d7fd5a31743e |  | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
label | af121610-bb68-55a4-8eb2-2176e6e90107 |  | note | – – – – – – – – – – – – – – – – –
label | 69bc8ae9-c0d1-5723-afdf-095789d6ac31 |  | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | c1adaa0a-4d3a-5f6e-98b5-389677687e32 |  | note | Attach: Coating Application Record
label | 3033d845-deb4-5a72-9b83-79a99479d523 |  | note | – – – – – – – – – – – – – – – – –
label | f3a55f24-f00c-5c07-82f4-a18235f4b8b8 |  | note | METHOD - Visual Measure
label | fc096312-ac29-5d35-8a92-7f67d9118f58 |  | note | – – – – – – – – – – – – – – – – –
label | 2e91c6e6-099c-5fcb-94ab-df0836d14a49 |  | note | FREQUENCY - Each coat
label | 86e151e6-84ef-56fd-a6f4-1a1a1c1cc298 |  | note | – – – – – – – – – – – – – – – – –
label | 641c5595-8814-5e62-9558-4d62eef0edce |  | note | CATEGORY - IP
label | c6b5b327-afb4-5e75-bc89-d8e4233a69f5 |  | note | – – – – – – – – – – – – – – – – –
label | 38641917-a54a-5aa1-8e15-c4ab76ce48eb |  | note | RESPONSIBILITY - SE/PE/SPE
label | 0ad6481b-102a-5e40-9224-5add89afa529 |  | note | – – – – – – – – – – – – – – – – –
label | df63b177-5557-5219-946e-55a46ead8aae |  | note | VERIFYING DOCUMENTS - This ITP
text | 7432d4ef-cff9-5807-94af-5bee581c61e9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
label | 708a7795-5704-5a6c-8b9a-095cc8b0ce3a |  | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
label | 53960aeb-4658-5381-bed9-9a9bf50066af |  | note | – – – – – – – – – – – – – – – – –
label | a0dfcbf5-7bfb-561f-a3aa-24d1cf6e9edd |  | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | eec0a537-7881-525c-bfff-378ef4f98166 |  | note | Attach: WFT Test Results
label | f36e0fd0-0427-5961-9d65-8711b44a1848 |  | note | – – – – – – – – – – – – – – – – –
label | 46030ed1-1509-59d3-afd0-ac7f9019869b |  | note | METHOD - Test
label | 0461134c-4a19-5ff8-b1c2-5b20feb0e126 |  | note | – – – – – – – – – – – – – – – – –
label | 8244e37e-5af2-5355-95bc-a0505002eef9 |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | ad4bf1ca-f788-5bf2-98e6-a13871fb3194 |  | note | – – – – – – – – – – – – – – – – –
label | dcd32a9a-95bf-51ad-917a-ecad462b0cfa |  | note | CATEGORY - IP
label | 685bc9ea-6186-514c-8cb8-af54ff36ca1d |  | note | – – – – – – – – – – – – – – – – –
label | 0029a2f8-01e1-5523-9ecd-63ec8313fd99 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 724ab3ab-9857-5ab3-9023-f17a6dff81b2 |  | note | – – – – – – – – – – – – – – – – –
label | 4b564209-3f79-5030-819d-b2d3f8536809 |  | note | VERIFYING DOCUMENTS - This ITP
text | 3559d0be-f72e-5786-9d90-1f8ef8750942 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Inspection & Defect Identification
label | 5bc8e40b-388a-5cc2-b5d5-673573b089d1 |  | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
label | 5d5ddc9c-cd8f-5fe6-845c-35bbab177a51 |  | note | – – – – – – – – – – – – – – – – –
label | 96c21147-64d4-5bb1-a4f1-363d2c4cc603 |  | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | 42fe5049-6fe4-5fea-a31d-64dad81401de |  | note | – – – – – – – – – – – – – – – – –
label | 583d2564-8a31-5c59-9be2-7b87d59b8329 |  | note | METHOD - Visual
label | 204c8799-d0bb-5b3e-a9d5-9d4774a0deb2 |  | note | – – – – – – – – – – – – – – – – –
label | 16028530-22ad-5112-9028-c81bfbe5e1a9 |  | note | FREQUENCY - After each coat
label | fca1ec1c-10bd-5d16-86fa-43c6294a42b9 |  | note | – – – – – – – – – – – – – – – – –
label | f8f3e756-18fb-5949-a50b-484d415e97af |  | note | CATEGORY - IP
label | 811b2f10-f475-51e4-992d-19b5e873659e |  | note | – – – – – – – – – – – – – – – – –
label | b516472f-e389-5b74-ac4f-28044370f69f |  | note | RESPONSIBILITY - SE/PE/SPE
label | 307e9447-0404-5099-acf7-ac132d98763c |  | note | – – – – – – – – – – – – – – – – –
label | b57faf58-2427-5a44-b053-edef5d919948 |  | note | VERIFYING DOCUMENTS - This ITP
text | 5f85318f-17db-582f-b424-f34d5281ea0c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Drying and Curing
label | 392ead22-baaf-5dd4-bc84-1b2ae7c402cc |  | note | REFERENCE - Coating System TDS 685.17 686.09
label | b9d95df1-b463-545b-a1aa-6cd4f39527be |  | note | – – – – – – – – – – – – – – – – –
label | 1f7b3cda-ecdc-51b2-9c9a-2fe7a5637bfa |  | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | 36854694-25da-5335-becd-c67534cdb264 |  | note | – – – – – – – – – – – – – – – – –
label | 8b0362f7-94af-5b83-9757-e67efb125f55 |  | note | METHOD - Visual
label | 2af83e2f-f831-55fb-b092-1b0a651fa439 |  | note | – – – – – – – – – – – – – – – – –
label | a625602b-3f0a-5394-ae17-4a39ce62fc09 |  | note | FREQUENCY - After each coat
label | 41fb79d4-a155-5a7c-917a-1d57777dd541 |  | note | – – – – – – – – – – – – – – – – –
label | 64e7b141-cc82-56ab-90e7-dc5db9c30212 |  | note | CATEGORY - IP
label | 78db3937-8902-50b7-934c-550ab7130230 |  | note | – – – – – – – – – – – – – – – – –
label | fe9ecb23-665a-5ebf-8485-67dcc2dad435 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 831ed0c2-9bf2-5fb6-bd58-c8a624f8402e |  | note | – – – – – – – – – – – – – – – – –
label | c669c9f7-76b9-53c1-a174-ab28d4f82afe |  | note | VERIFYING DOCUMENTS - This ITP
text | 18e2dee1-7a57-5763-9f56-fdddc385234d |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Post-application Activities
checkpoint-status |  |  | checkpoint | 5.1 - Clean-up & Waste Disposal
label | c6002fa7-a387-5f0f-8755-7d6bcbc41caa |  | note | REFERENCE - 685.09 (c) 686.10
label | e443cb22-8578-5a41-8d57-79b1b4245d40 |  | note | – – – – – – – – – – – – – – – – –
label | 3f84001f-00d0-5e74-8d1e-34c094238f2b |  | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | 9dd349aa-1a5a-562c-a584-001e084cb427 |  | note | – – – – – – – – – – – – – – – – –
label | 554fa485-50c4-52a7-a130-e550d1085df9 |  | note | METHOD - Visual
label | bdc7227d-f077-5d8a-a3bb-b9c90f2cdfc8 |  | note | – – – – – – – – – – – – – – – – –
label | b8fd0e18-05ba-577a-bbd0-d187859da305 |  | note | FREQUENCY - At completion of Works
label | 1d3c129b-ecb7-5e50-95fc-76e57db4001c |  | note | – – – – – – – – – – – – – – – – –
label | 06783472-e872-580d-b3f0-6f96b7199b99 |  | note | CATEGORY - IP
label | 8cc1bc23-f9ae-5a5e-9355-022c3167bad4 |  | note | – – – – – – – – – – – – – – – – –
label | a77ca6ba-e48f-55fa-b5ae-493fb7daa7a5 |  | note | RESPONSIBILITY - SE/PE/SPE
label | a4abd4f9-caf2-5783-81a8-803e079dbccf |  | note | – – – – – – – – – – – – – – – – –
label | dc93b825-4cd5-5e8b-83b5-ed50673e1d4c |  | note | VERIFYING DOCUMENTS - This ITP
text | e8aea563-2d40-5c6b-a0c9-e8026333ff07 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
label | be4e403d-2640-5d45-bdbd-9fc3f8b524da |  | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
label | b5f88c05-5bc5-597b-9fd0-5c2287f2bb9c |  | note | – – – – – – – – – – – – – – – – –
label | deb87bea-1816-56bd-bfd2-34453ae894a5 |  | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
label | 4ec336cc-4890-5b87-821f-750b8044503e |  | note | No more than 15% of the readings shall be less than 90% of the required thickness.
label | e42b0b17-b2b1-543f-b905-114f18619c38 |  | note | Attach: DFT Test Results
label | 88143cf4-7f48-5d57-9819-3305f9a9c926 |  | note | – – – – – – – – – – – – – – – – –
label | 6d961fd0-7e47-5a96-8e6e-a2886a131eaa |  | note | METHOD - Test
label | b3a2ae24-4859-5e3c-9491-b1be2fe43e82 |  | note | – – – – – – – – – – – – – – – – –
label | 0cdb4d2e-bc0d-56fa-8a7c-746a396d14d6 |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | cc13de75-1e34-58f8-bdd3-7880e357c922 |  | note | – – – – – – – – – – – – – – – – –
label | 6f780589-51eb-5b58-8a73-3b247d052dfc |  | note | CATEGORY - IP
label | cb495448-85ef-5c87-90be-a3a78338d70f |  | note | – – – – – – – – – – – – – – – – –
label | 6c4e2a7a-e486-500d-b0cf-64f5b82a0f92 |  | note | RESPONSIBILITY - SE/PE/SPE
label | b8d8a558-3b3d-574c-9ef2-7fda0496c000 |  | note | – – – – – – – – – – – – – – – – –
label | 235a3374-4abb-58dd-9d10-1cb65b9073de |  | note | VERIFYING DOCUMENTS - This ITP
text | 15107dfd-6152-5881-b3fa-3965ad0c70d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Adhesion Bond Strength Testing
label | cc100967-76d9-5c22-9b68-14083be16bb5 |  | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
label | fff70190-e1c5-56a0-ba0d-10e9c9c40915 |  | note | – – – – – – – – – – – – – – – – –
label | 3f433876-7787-5b27-a836-d5fcf2d1b1d3 |  | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
label | e3b349d1-ef1d-507f-8195-a44cbf4f1bbb |  | note | Attach: Adhesive Bond Strength Testing Results
label | d79a3afa-c2ce-5d8a-908e-8e80b88c3531 |  | note | – – – – – – – – – – – – – – – – –
label | fbac51f5-9798-53f5-86ee-a4ef9408d189 |  | note | METHOD - Test
label | 846f7ee0-9457-536b-a0e1-4703ddd8229f |  | note | – – – – – – – – – – – – – – – – –
label | 9dde5978-e0b2-51a4-84dd-1f6321f1caed |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | f8ab95a6-ece1-5cad-bba4-109e65d8ead5 |  | note | – – – – – – – – – – – – – – – – –
label | b1030132-dfa6-559d-a7f2-5bedf80588dc |  | note | CATEGORY - IP
label | 036f6f00-79d2-5a7e-900b-15adb7e6a912 |  | note | – – – – – – – – – – – – – – – – –
label | 310a958f-6a25-5909-b33a-4f7c00633728 |  | note | RESPONSIBILITY - SE/PE/SPE
label | b843a549-d745-5b72-af6c-465bc457877f |  | note | – – – – – – – – – – – – – – – – –
label | 6881c750-5def-50f1-8b35-118100edbd61 |  | note | VERIFYING DOCUMENTS - This ITP
text | 6664a0e4-b320-5926-950a-8db0d8abf545 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Penetration Depth Testing
label | acbe54ad-56eb-593e-88cc-fe23b708bb5c |  | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
label | 45db9d31-41bb-5259-b76c-e81c462a0f73 |  | note | – – – – – – – – – – – – – – – – –
label | 4e2d59c5-98e0-54e1-b4eb-dee95edda7d5 |  | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
label | 5fd4fb10-3f03-5c65-b145-c8c6c08e0061 |  | note | Attach: Penetration Depth Testing Results
label | 8c358ab4-dd4e-55d4-9a3c-6a32485f6e7a |  | note | – – – – – – – – – – – – – – – – –
label | de28b52c-0bfb-5342-b318-474c7bc62b50 |  | note | METHOD - Test
label | ab2a8965-693b-560b-bcfc-6c741c198c83 |  | note | – – – – – – – – – – – – – – – – –
label | abeae67d-4a78-5f3a-934f-b2026efb123e |  | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
label | 2c50dcbf-bb17-5402-bc35-4205d157d346 |  | note | – – – – – – – – – – – – – – – – –
label | caf9fd23-0065-5f31-a61c-05e3e36e73c4 |  | note | CATEGORY - IP
label | 389dedca-0d40-5f49-a045-9bc3c98dca6a |  | note | – – – – – – – – – – – – – – – – –
label | bdd0c5de-2aa5-5b1c-a613-79ee0dcd00cc |  | note | RESPONSIBILITY - SE/PE/SPE
label | 0e809e38-8361-5a40-83a0-83642bd0f0e3 |  | note | – – – – – – – – – – – – – – – – –
label | 0bc49c4e-9366-5701-b7f1-12bf85f237c8 |  | note | VERIFYING DOCUMENTS - This ITP
text | 1bce364b-a644-5376-ad48-c5cb2646c06a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Non-conforming Coatings
label | 9c65e037-dc63-5c3f-a3d9-59ce9a4e0a59 |  | note | REFERENCE - 685.14 686.17
label | 6b2f3141-60c1-5fa9-8c7c-2e867dd61ca0 |  | note | – – – – – – – – – – – – – – – – –
label | 9888dc17-0a1f-5393-8ca7-fa8350a08c93 |  | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | 900833be-990b-53eb-b85e-e46124b3616a |  | note | – – – – – – – – – – – – – – – – –
label | 01fc1c91-8d77-5fed-af84-d2dac2fdce16 |  | note | METHOD - Visual
label | be1b1b83-db62-5c80-83e6-72eb188e0ba6 |  | note | – – – – – – – – – – – – – – – – –
label | 5da2174c-595a-50de-8fdc-5456ff853cd6 |  | note | FREQUENCY - Where required
label | 3a9f7d94-8cc6-5c13-b279-f2c90a14a9f6 |  | note | – – – – – – – – – – – – – – – – –
label | 172ee638-2228-5923-ae94-91c51107e68f |  | note | CATEGORY - IP
label | 32fe57c7-f194-5edd-95be-74c9016c9a5b |  | note | – – – – – – – – – – – – – – – – –
label | 3301536c-ce1e-51ba-9f7d-21009824cbcf |  | note | RESPONSIBILITY - SE/PE/SPE
label | fe603225-34c9-5628-b4d8-8788c62e71ce |  | note | – – – – – – – – – – – – – – – – –
label | e2b0cc1c-7311-5454-b90c-ad6ef431e882 |  | note | VERIFYING DOCUMENTS - This ITP
text | d1a43ad9-3bdc-5e42-8984-3f8a122de493 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Coating Application Guarantee
label | 3fe5b8bb-7878-5fc3-8333-15cc698b5961 |  | note | REFERENCE - 685.06 (b) 686.05 (a)
label | 03c3e7c4-8424-5016-87fa-1ce6aa778786 |  | note | – – – – – – – – – – – – – – – – –
label | 88e959ac-50a8-55b4-a1d7-824e593c8f11 |  | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | 33c00d73-fadc-578a-bd45-a751f761096d |  | note | Attach: Coating Application Guarantee
label | 2d4fc0b6-a7e9-56c1-b10a-94247cfbd283 |  | note | – – – – – – – – – – – – – – – – –
label | 806db9e1-1a88-53a1-8404-8e7bdabbe13d |  | note | METHOD - Document Review
label | c9ed8533-c6b2-5d31-b8a6-9a150ff744d7 |  | note | – – – – – – – – – – – – – – – – –
label | a98fe3bb-9efc-5821-8f09-029955bf69c5 |  | note | FREQUENCY - At completion of Works
label | f9e4ab0a-47c6-5b41-9463-2c820d4dc8b5 |  | note | – – – – – – – – – – – – – – – – –
label | ada7e861-b51e-500d-8630-a05f73b88abc |  | note | CATEGORY - SP
label | c0c831d7-0e6a-5bf7-b58e-bec0b44cc9a0 |  | note | – – – – – – – – – – – – – – – – –
label | 4b1a485e-cdca-500c-b3f5-25b538b9e034 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 08aeef1f-5a2d-5cff-8704-c5603a1bc9d4 |  | note | – – – – – – – – – – – – – – – – –
label | 5e779657-ffa0-516c-bfed-074ca33a7f2f |  | note | VERIFYING DOCUMENTS - This ITP
text | 2d4d9431-7bd9-5ba0-9bf5-f9e1fa032eb1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Repair to Damaged Coating
label | 180b6c84-2811-5fc6-b57b-a6916ff4f64b |  | note | REFERENCE - 686.17
label | 98d2513a-4131-540d-9ae8-883494a1c8cd |  | note | – – – – – – – – – – – – – – – – –
label | 14bce53e-2ee5-58b3-8d7e-96b05922d708 |  | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | 2873c5f3-d146-5836-9707-0882950645b7 |  | note | – – – – – – – – – – – – – – – – –
label | f3a6d425-1c36-590c-b2be-855de5e5f477 |  | note | METHOD - Visual
label | 18ffdec1-b2a4-5073-8217-a0216c5ac7d2 |  | note | – – – – – – – – – – – – – – – – –
label | 3ee96ce2-5c48-55b9-981b-0a4c3441284a |  | note | FREQUENCY - Where required
label | 6f1e03dd-da28-530b-8135-db346c8b62fe |  | note | – – – – – – – – – – – – – – – – –
label | d5348f04-d4b1-5a46-adc4-f172988d6b82 |  | note | CATEGORY - IP
label | b50d1ed4-9753-55f1-999f-579a1d64ff09 |  | note | – – – – – – – – – – – – – – – – –
label | 1e92013e-cae1-5540-adf3-da2b0f1c5a36 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 50973968-a9dc-5262-b9ef-aebee2cade1a |  | note | – – – – – – – – – – – – – – – – –
label | e271e26f-7287-57c5-b631-8d11515d6ffe |  | note | VERIFYING DOCUMENTS - This ITP
text | 112cf0f9-3cc6-569f-b2dc-473744572672 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Non-conformance Report (NCR) Closure
label | e4f1475e-9b1f-5d6b-8dbd-c2ea03ebf8d2 |  | note | REFERENCE - MRPA Quality Management Plan
label | ef38f786-9da7-504b-a772-1160ab1196c0 |  | note | – – – – – – – – – – – – – – – – –
label | a15d6906-45f3-59cd-9200-c0b90b496def |  | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 2ba6d1e5-66f1-5b08-9932-6c45b6adc43d |  | note | – – – – – – – – – – – – – – – – –
label | c63b6447-b969-55bd-9b08-68bf16d883f0 |  | note | METHOD - Document Review
label | e88b7b01-22d7-58dc-9209-910aa490c1cc |  | note | – – – – – – – – – – – – – – – – –
label | 3b9be799-59fc-561f-af02-7d8acdda258f |  | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
label | 01b11717-4eb7-53c3-984c-34920a04138e |  | note | – – – – – – – – – – – – – – – – –
label | c5c066c7-6b9b-5e6c-a0de-76ee09d427b7 |  | note | CATEGORY - HP*
label | 7b0024c8-2b9d-5f15-9654-e42ed01aece0 |  | note | – – – – – – – – – – – – – – – – –
label | 83fa62fe-bf6b-530e-8228-c271eac74777 |  | note | RESPONSIBILITY - SE/PE/SPE
label | 6226290c-42e6-53aa-bd18-395dfffeef0e |  | note | – – – – – – – – – – – – – – – – –
label | a892a54d-ae9f-5780-8d6a-a1dc61278210 |  | note | VERIFYING DOCUMENTS - This ITP
text | 0d409500-2de3-577a-a3df-2d7663fbe01a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5330004f-ca7b-5538-9b2c-054d5fe4eb8b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | f79e6845-cc61-589b-b2c2-6a49c1e124ee |  | textbox | Name:
text | b44f7681-4ea5-5ce5-86d6-03e57cd78467 |  | textbox | Position:
date | 38b344b0-e14c-582f-ae1a-0ab118b8c05b |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-053-STR-SSB-Bored Piling |  |  |  |  | Yes | ITP-053-STR-SSB-Bored Piling Rev 0 | e03702b7-ddba-496a-9339-005e25b3359b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 3e779f93-32eb-5df1-b569-0f4831f664d5 |  | note | Document Title: ITP-053-STR-Bored Piling
label | 926b15c6-16aa-5b9f-a782-48a7b5b905eb |  | note | ITP Description: Bored Piling
label | 246c3cdd-bb27-51dd-9632-64a715de6bc3 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 62c3eb0e-6fa8-5458-970a-85bfd4e240ef |  | note | Discipline (e.g. CIV/STR/RAIL): 053-STR
label | b2dc183a-025e-5a17-a1e0-d00df2ecde5f |  | note | Revision Number: 0
label | df936f2f-e7dc-5a9c-960c-afa4089f4cef |  | note | Revision Date: 11/10/2022
label | e633e78a-1d17-559f-bc6d-2d62a86916bc |  | note | ITP approved for use by: Victor Mira
label | 6e168bc7-9e17-560c-98b4-dd88846e4413 |  | note | 1.1 Non Dependent
label | 34bbfe00-602f-55d9-af5d-35fbf67b2b2c |  | note | Reference: VicRoads Section 606 July 2017
label | f16c8176-5569-50e1-a510-ec23258c0fa1 |  | note | 1.2 Non Dependent
label | 36c9023a-e270-533d-80c1-a7d5f1eebced |  | note | Reference: VicRoads Section 610 Feb 2020
label | 41955c0a-9961-5acd-a606-c92c9cd23c4b |  | note | 1.3 Non Dependent
label | 8d765d58-e0e9-5679-a32b-870ee1bfcea2 |  | note | Reference: VicRoads Section 611 November 2018
label | 8d3a2ec4-c31b-5acd-a538-6299d33894b0 |  | note | 1.4 Non Dependent
label | 7530dd1c-4b4e-5966-a9ef-12a7561e3b44 |  | note | Reference: AS2159-2009
label | c95fbb58-9376-5bce-9661-92b600315b00 |  | note | 1.5 Non Dependent
label | 51a73135-0f58-546b-9b8c-3a688fe88950 |  | note | Reference: AS3810.1 2018
label | 1ba23957-c205-5d23-b529-4c5cabd36ffb |  | note | 1.6 Non Dependent
label | a5934898-51d0-5304-b82e-c943773d48f8 |  | note | Reference: AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 941a16cc-2c20-5675-9cd1-6c2b5ea0c3db |  | note | REFERENCE: 610.07 Table 610.071
label | eb6ebe6e-360f-528a-ab87-391658604bad |  | note | – – – – – – – – – – – – – – – – –
label | fe177f23-b430-5866-af71-091a459e816b |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 2b1675e8-9f6b-5529-aeca-172c298a1d62 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 270b3928-c341-5a17-8fe6-280e6b59a19b |  | textbox | Enter: Teambinder Material Approval number
label | 1540c9f4-056f-5a70-9803-cb23cfeddff0 |  | note | – – – – – – – – – – – – – – – – –
label | 8a80406a-b036-5279-8a00-8c2c1de0c7f9 |  | note | METHOD: Document Review
label | fb963b6b-1f76-50db-8b50-45b8da7faefc |  | note | – – – – – – – – – – – – – – – – –
label | 0cc9a842-e533-5e07-8332-34854cc086ee |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 6236d37b-62c2-5d2b-bb98-0bbb50691d94 |  | note | – – – – – – – – – – – – – – – – –
label | 74900eda-3024-56ff-9785-9afcfc542cba |  | note | CATEGORY: HP
label | 53273832-94bd-5ddc-9bb2-b254d5194dab |  | note | – – – – – – – – – – – – – – – – –
label | 5abffe1a-306d-50f0-8caf-f66e6fb3e6fd |  | note | RESPONSIBILITY: Nominated Authority
label | 7c6156c7-b0cf-5de6-98bc-692b081b2a51 |  | note | – – – – – – – – – – – – – – – – –
label | f1d52cf6-2e84-51dc-8c07-2e728058842d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ac45fbf5-53f5-5002-8ec4-e4c660fd91b4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 2a0e4ed0-55f7-5ab1-972d-a4e2d82574c3 |  | note | REFERENCE: 611.05 (a)
label | c46fb620-dd8f-5fc4-a25f-811c5c7a143d |  | note | – – – – – – – – – – – – – – – – –
label | c346f5a2-391e-55a9-bd30-1d45278891ad |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | e6b0fa22-9de5-5920-b86e-d679017bc688 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | ec099a58-c8e8-5dac-a326-085c754fd691 |  | textbox | Enter: Teambinder Material Approval number
label | f8d90997-0f27-5b3e-b6ec-75963d24cebb |  | note | – – – – – – – – – – – – – – – – –
label | e3fc1327-8d16-51a5-8d85-cea7199c12b1 |  | note | METHOD: Document Review
label | 69f11c12-bb4d-580b-af24-a884c5356680 |  | note | – – – – – – – – – – – – – – – – –
label | b98fc91c-cb9c-5e7b-b9c0-bc948d370f15 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | f0175d6c-050c-5abb-a8bd-7913c57fe6c7 |  | note | – – – – – – – – – – – – – – – – –
label | 4dce3071-58dc-598f-a46f-5dc19df80a64 |  | note | CATEGORY: HP
label | 3515bc0f-d6b2-542f-9845-e124609fdb20 |  | note | – – – – – – – – – – – – – – – – –
label | e5e42af5-19cb-5c06-895d-69bc3f0f0cba |  | note | RESPONSIBILITY: Nominated Authority
label | 55f1ec4c-b392-53bd-b6ad-c55c133e3eab |  | note | – – – – – – – – – – – – – – – – –
label | 10dd8e46-15b7-5b78-908c-20ed53abd465 |  | note | VERIFYING DOCUMENTS: This ITP
text | a5ce4ff8-bec6-5617-9b67-b39238395bb7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
label | cecbdc14-156a-564e-a126-e241ce1abd4f |  | note | REFERENCE: 610.26 (a)
label | b6deab1b-51c3-5cde-8924-7d006a3dad18 |  | note | – – – – – – – – – – – – – – – – –
label | 8afe296d-ef4c-5c15-b1e8-e8e097c9d419 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | 653a0315-69e5-5ef5-a6e4-877150236b8d |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 85770361-1a80-5e82-aa56-b4fe1383107a |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 5a1bddc7-bfcb-5609-b7c6-19b357b20f63 |  | textbox | Enter: Teambinder Material Approval number
label | 68047fbd-3706-50ad-b41d-ee570452626c |  | note | – – – – – – – – – – – – – – – – –
label | d218b103-1fe1-5f02-beb6-944685d9473d |  | note | METHOD: Document Review
label | 1a4519e2-04ed-5aa7-9980-98f08fdd86c2 |  | note | – – – – – – – – – – – – – – – – –
label | 25f51cd2-b2bb-59b7-8461-d88aee9c1fe8 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 79176b08-8de4-5572-b3e3-d4f7f3867dd6 |  | note | – – – – – – – – – – – – – – – – –
label | 53ccb156-3b1a-57ed-ae90-ac316e7d076d |  | note | CATEGORY: HP
label | 9ed3d253-f53c-5863-b83e-b42ddb0f03df |  | note | – – – – – – – – – – – – – – – – –
label | cc3c4db3-2c18-5301-b840-85984bc9e97d |  | note | RESPONSIBILITY: Nominated Authority
label | e6547f30-7265-55a8-8e55-33121e36d6d0 |  | note | – – – – – – – – – – – – – – – – –
label | 986b7eb8-275f-5555-96aa-1be3b57b0e0b |  | note | VERIFYING DOCUMENTS: This ITP
text | cbcabe1e-c48f-5487-9fe7-10bddb067556 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | 872bdc04-7e18-5b26-9e86-75a27cfc23a0 |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
label | 435f6fda-2095-5c98-935f-604e3ec66c7d |  | note | – – – – – – – – – – – – – – – – –
label | 872a1ef1-e5d5-5a8f-92f7-f4c96e5ec457 |  | note | METHOD: Document Review
label | 649c27ee-8b50-5220-b7ae-1a8baa4639c9 |  | note | – – – – – – – – – – – – – – – – –
label | 42094b59-ea9b-5638-b522-5c64f2180aee |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 8a7bee26-0442-5512-9c4d-86c07aa5afa5 |  | note | – – – – – – – – – – – – – – – – –
label | d0ea6ac6-e3e0-5984-9b55-4e7808069c42 |  | note | CATEGORY: HP
label | 2c38b223-e49d-5d38-96a7-97ad35424700 |  | note | – – – – – – – – – – – – – – – – –
label | f8b62633-fae8-5887-8b12-99574f148d64 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | 3a5ad411-682c-5939-abce-fbc63c85fa9a |  | note | – – – – – – – – – – – – – – – – –
label | 2c32a45f-a95b-5a97-85ea-02ceacb783dc |  | note | VERIFYING DOCUMENTS: This ITP
text | 2d6b02d9-0807-5d7e-a870-0538fc79e877 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Piling Operations Work Procedure
label | c22ecb84-e503-5c28-a513-7a327cae13d0 |  | note | REFERENCE: 606.03 (a)
label | 0f3e6c41-60bf-596a-ad95-131c13c5b37b |  | note | – – – – – – – – – – – – – – – – –
label | 8bb9b383-e8ca-5bcc-b919-cc60bfce44c2 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 2760059d-2513-5c4a-b1a6-efdbcf7761f6 |  | textbox | Enter: Teambinder Approval number
label | 2fed6c2c-5e85-5809-a49d-feda9cf50054 |  | note | – – – – – – – – – – – – – – – – –
label | 4950638a-a6c4-5e8a-adae-f6233d696718 |  | note | METHOD: Document Review
label | b529d8aa-ab1c-509c-abe5-728b65424e4c |  | note | – – – – – – – – – – – – – – – – –
label | 235ed496-6711-58d4-8776-b1e6a806bf28 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 41d1e063-6dfc-50e4-9ef5-362cf70b7d24 |  | note | – – – – – – – – – – – – – – – – –
label | 40b62bcd-918c-5a33-a513-faac791da619 |  | note | CATEGORY: HP
label | a0ff54a5-961b-5378-9465-ba7aeb6f01f6 |  | note | – – – – – – – – – – – – – – – – –
label | 1c6a8d2d-7418-50af-bd1d-da5461450989 |  | note | RESPONSIBILITY: Nominated Authority
label | 787485fa-edf1-5789-934a-3944f7d53bb3 |  | note | – – – – – – – – – – – – – – – – –
label | 34656c9f-8bb7-5e40-9a8d-62902b0a397c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 231fa042-d1cc-5075-b450-a94c1f61f7be |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Temporary Steel Casings
label | 2ff5c3fb-5189-590c-b5f8-5ed1b25adb70 |  | note | REFERENCE: 606.03 (b)
label | c4832d7e-d7ce-5d43-ac5b-ab4f207fbbf4 |  | note | – – – – – – – – – – – – – – – – –
label | 2118a8f6-684e-5e74-bfb7-741e2dccb146 |  | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | b43144bd-d661-5f36-9848-6321d9621695 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 3d234586-1f4f-5ee1-8436-876961b300aa |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | 4ca75c62-1649-5f77-80cf-24be51a66d4c |  | textbox | Enter: Teambinder Approval number
label | 0092f992-dc99-5ea7-9fdb-534a1531152d |  | note | – – – – – – – – – – – – – – – – –
label | 76a53576-5611-5f1f-9152-16bbbed0ac3e |  | note | METHOD: Document Review
label | 89c1455f-dbe6-5caf-b115-32536de61b48 |  | note | – – – – – – – – – – – – – – – – –
label | 1ff73abd-0fa3-51d3-a52c-ff8afa719d32 |  | note | FREQUENCY: Where applicable, once, prior to use
label | 99d30d8e-594d-59bb-8571-645f376774d8 |  | note | – – – – – – – – – – – – – – – – –
label | 36a7d277-6630-5560-9d6d-a5c96eef8cc8 |  | note | CATEGORY: HP
label | 3a86384e-aa95-5663-8b33-8f174b445293 |  | note | – – – – – – – – – – – – – – – – –
label | cac74c9f-74c2-5362-b71a-bc5153b82f76 |  | note | RESPONSIBILITY: Nominated Authority
label | e88d6fd0-4583-5a03-bbd6-ca666be43ac1 |  | note | – – – – – – – – – – – – – – – – –
label | 1ebcbab7-6060-57c2-b911-e5549f72454e |  | note | VERIFYING DOCUMENTS: This ITP
text | 7c779421-b18b-5574-bddf-1d5fae86b4dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 3add7cec-31ef-5b4c-9ed9-ca56a7e64828 |  | note | REFERENCE: 606.06 (a)
label | 5e44ed80-5997-51f4-9fb6-252d30dcc7c7 |  | note | – – – – – – – – – – – – – – – – –
label | e75bf48a-ade5-579a-b8aa-cc5a57f655ff |  | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | cfb1a414-1e8c-582e-98d9-b7e54273eddc |  | textbox | Enter: Teambinder Approval number
label | ec55a1ec-4d29-5e66-808f-e385b408532c |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 474aff2d-781b-5af3-bfa4-b3a73b827a49 |  | note | – – – – – – – – – – – – – – – – –
label | 7f3884ee-ebde-5792-9675-6de1b4bb6fc0 |  | note | METHOD: Document Review
label | 6921638d-083f-5dc5-9f75-633aea20aa46 |  | note | – – – – – – – – – – – – – – – – –
label | ad8ef4bf-650c-5c18-a557-166d005fe30b |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | f722ca60-262b-55e3-9834-19dcd2888941 |  | note | – – – – – – – – – – – – – – – – –
label | 98e8e834-3aeb-5833-9db9-9e51159e8854 |  | note | CATEGORY: HP
label | 0b06d24d-125a-5546-b853-15b0b7ad8885 |  | note | – – – – – – – – – – – – – – – – –
label | f2d13015-311c-5b2f-869f-a2b48407c730 |  | note | RESPONSIBILITY: Nominated Authority
label | 8439a7fa-a23b-5d80-8bc1-eeef2cb94247 |  | note | – – – – – – – – – – – – – – – – –
label | 28b73fef-624a-52c0-b20b-3f8063ace0b2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 104682bd-891e-5000-a7aa-4b833ab3710b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
label | 8d07e610-041f-575d-8990-56c974b7f07a |  | note | REFERENCE: 606.03 (c)
label | d94e036b-ff4f-595b-88b2-a561e69fcdd2 |  | note | – – – – – – – – – – – – – – – – –
label | 2a842f17-519f-55ad-a810-93f31b58e407 |  | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 09f1670b-31ea-5933-89af-95e7a56bc201 |  | textbox | Enter: Teambinder Approval number
label | 53df5c46-16de-5027-812f-b2d61e34d349 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | cecbd039-797d-5f4e-950f-24137eb21ebc |  | note | – – – – – – – – – – – – – – – – –
label | dec48c30-86c2-5eae-b9ed-3274ad98a855 |  | note | METHOD: Document Review
label | c6498d35-2cc7-5856-8dd2-a7eac9ca963d |  | note | – – – – – – – – – – – – – – – – –
label | 4a9fd476-9417-5376-9428-8a2f3f0eb298 |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | 8481ac1a-6061-5b45-846a-3058cd85777f |  | note | – – – – – – – – – – – – – – – – –
label | db3a796f-822c-500e-91ac-3963d71cf3a3 |  | note | CATEGORY: HP
label | 6d4cae52-18a5-56fe-8a11-32dab24e598a |  | note | – – – – – – – – – – – – – – – – –
label | f66ecd06-33cb-58a4-811c-a99d80d579d4 |  | note | RESPONSIBILITY: Nominated Authority
label | c32dd49c-6f0a-52b3-8839-7c51be75053e |  | note | – – – – – – – – – – – – – – – – –
label | 32e409c5-1af4-55a1-bca9-e0239345f3fe |  | note | VERIFYING DOCUMENTS: This ITP
text | 4167edba-29e5-5de9-a4a0-4868fefdac08 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Dynamic Pile Testing Procedure
label | 3bb4982c-602e-52ce-a88b-97a8d564aaef |  | note | REFERENCE: 606.07 (c)
label | 123c5eed-fd7c-5336-8cbe-72922422653a |  | note | – – – – – – – – – – – – – – – – –
label | 57881b7c-677b-5607-b308-ad5a6057ae7e |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 407fc805-c775-5191-8797-82601d9283d9 |  | textbox | Enter: Teambinder Approval number
label | 899ebcb8-5cdf-5834-af40-45d69c9d764e |  | note | – – – – – – – – – – – – – – – – –
label | 359a32c7-5e55-5fb7-9d0c-fc22409588a1 |  | note | METHOD: Document Review
label | e9700d91-47b1-52e7-8cbe-2842f92baec6 |  | note | – – – – – – – – – – – – – – – – –
label | 34626023-76ab-5c9c-866d-e39395603733 |  | note | FREQUENCY: Once, prior to testing
label | 8f552ce8-d801-5106-a624-d6b6ededb984 |  | note | – – – – – – – – – – – – – – – – –
label | 42aa0cf7-ff09-5165-a0ed-eeedcd062e77 |  | note | CATEGORY: HP
label | 084a2391-f420-53b5-b048-5912fe69cee4 |  | note | – – – – – – – – – – – – – – – – –
label | e67936dc-6163-5f4d-83bc-671b46aaec56 |  | note | RESPONSIBILITY: Nominated Authority
label | 6b234cf5-d5a5-5fe6-acc7-8b0adad81d74 |  | note | – – – – – – – – – – – – – – – – –
label | 7f5b9ab1-4a57-5ee4-9ae7-92e90361ab09 |  | note | VERIFYING DOCUMENTS: This ITP
text | d8cdc248-cabf-59fd-9f5f-590b65a0ceee |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Pre-qualified Pile Testing Consultant
label | 6efc42f9-e241-5ef6-b14f-5d789e38d53b |  | note | REFERENCE: 606.07
label | 1ed10013-8050-548f-a055-c26a45f01538 |  | note | – – – – – – – – – – – – – – – – –
label | aeede161-5ba7-57cf-b7ca-e5207f5d3e56 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | 4cb61ecc-ee89-5e5f-9cbf-a376b291eda4 |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 87dc1559-080d-5a9e-ab15-c33ea14822f6 |  | textbox | Enter: Teambinder Approval number
label | 25afd119-23ec-52ec-a89f-f91e37ab364d |  | note | – – – – – – – – – – – – – – – – –
label | b0facab6-d8d6-511d-a728-a8943aca7d73 |  | note | METHOD: Document Review
label | 531ef812-0f39-5bd1-9030-f053cdd65b2b |  | note | – – – – – – – – – – – – – – – – –
label | ec8996d5-6d24-5253-a527-b9454c59a85d |  | note | FREQUENCY: Once, two weeks prior to testing
label | baf0c402-2316-519a-b337-f33621a94a41 |  | note | – – – – – – – – – – – – – – – – –
label | ec6d7407-8b92-5e02-b093-6ac7820e1846 |  | note | CATEGORY: HP
label | 0ad84e3e-f78c-5a77-a479-6c6ff9289df3 |  | note | – – – – – – – – – – – – – – – – –
label | 4c1a8182-f38d-5f3b-b081-5ca8efa6df34 |  | note | RESPONSIBILITY: Nominated Authority
label | d615a409-be1f-5695-8a85-9342fc99c8cd |  | note | – – – – – – – – – – – – – – – – –
label | 2af67ebd-aa4e-5c4a-9e9b-63327fcd37ef |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 50f7b956-52ff-5a77-a93a-a374893dcb52 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
label | f86d384a-9893-549b-8847-ec66867c7a95 |  | note | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | 7ceb68dd-1f8f-5843-9f1a-66fb243daf4e |  | note | – – – – – – – – – – – – – – – – –
label | 65bffa2e-8ef7-5790-8b9d-71d913b283db |  | note | ACCEPTANCE CRITERIA: Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | 217a172c-321c-5e79-82ce-fe2788519571 |  | textbox | Enter: Teambinder Approval number
label | 808f6cdc-48c9-57c3-80ca-b0f275d1c943 |  | note | – – – – – – – – – – – – – – – – –
label | 287f9101-b01a-569c-a0a7-4703b2e15526 |  | note | METHOD: Document Review
label | b8d40a8d-09d8-5123-8b94-552b180231c2 |  | note | – – – – – – – – – – – – – – – – –
label | 7d296d59-0ecf-5b17-93dc-128d1d97d651 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | d1445881-73ef-50c0-8ff8-76f6d9b52e0e |  | note | – – – – – – – – – – – – – – – – –
label | 51691f4c-fc5e-5054-874e-20605ca4da30 |  | note | CATEGORY: HP
label | daa394fd-fddf-5a81-872c-817bd3fdaf1a |  | note | – – – – – – – – – – – – – – – – –
label | 0745ddc9-2672-5948-9e8f-a81bae671354 |  | note | RESPONSIBILITY: Nominated Authority
label | 5880147f-25e4-5f48-ad84-218797e22930 |  | note | – – – – – – – – – – – – – – – – –
label | 60030d64-b85c-596b-be1f-3ee84bf41772 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3a1b2054-aa52-563f-a95c-5a7e62a2e162 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | f8568de4-33dc-5acf-b4b3-3be955513578 |  | note | REFERENCE: MRPA Quality Management Plan
label | a757bcee-03d8-5aba-ac0e-c75ed79524fa |  | note | – – – – – – – – – – – – – – – – –
label | a35e22a4-f9c6-5b3d-9f60-97c33ca345fa |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 7ad5ec8c-4a18-594c-a607-1ea1c524fefc |  | note | – – – – – – – – – – – – – – – – –
label | 43fb9970-1d9a-5163-9495-ea59bc2cb351 |  | note | METHOD: Document Review
label | 8f298032-d17c-5fa7-a608-9e3579e815a1 |  | note | – – – – – – – – – – – – – – – – –
label | 43f985ab-0e27-58ea-a433-b651ccb1fc77 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | b01b922f-fed3-5da0-8140-ed05637f5178 |  | note | – – – – – – – – – – – – – – – – –
label | ae693699-e51c-5838-8898-a6aa04fd7ee2 |  | note | CATEGORY: HP*
label | 99d3fc18-5419-5ad5-9cb1-204a10be0659 |  | note | – – – – – – – – – – – – – – – – –
label | 8a5e2df6-f933-536c-8f78-37d867aa6ddb |  | note | RESPONSIBILITY: All
label | 6327f7ed-24eb-52df-957f-39c58a2d400f |  | note | – – – – – – – – – – – – – – – – –
label | c56f7766-6c34-5c72-96d9-77b8f03ef125 |  | note | VERIFYING DOCUMENTS: This ITP
text | d0d1b552-7a62-5268-88a9-d2e1da9af9b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | c0050535-ec00-5b1a-aed5-ec72d873fbc4 |  | note | REFERENCE: IFC Drawings 606.08 (a - c)
label | 98e7112a-ed83-5f01-8a4f-139118f71734 |  | note | – – – – – – – – – – – – – – – – –
label | a82dd41d-15a7-57db-a709-acbffbc7ca0f |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 92361831-ee7c-51ef-89f6-78a2b89fc5be |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | ac77cde7-fbcc-574a-be9d-600fdf1d07bc |  | note | – – – – – – – – – – – – – – – – –
label | 7bc3350f-c562-51be-b215-a4742d6f88ac |  | note | METHOD: Measure, Visual
label | 6d963c03-a853-5fb1-9a5e-4594d8bc0659 |  | note | – – – – – – – – – – – – – – – – –
label | a50bfb06-25ee-5f60-bc31-1201abe3c9bb |  | note | FREQUENCY: Each pile
label | ec91d7e7-22d1-5f12-bf1e-a358ee1434e8 |  | note | – – – – – – – – – – – – – – – – –
label | 4b49669b-90ca-5d3f-ba64-d8e7b67fba40 |  | note | CATEGORY: IP
label | 685d3381-389d-5f1d-b3b0-fd9e1f28e674 |  | note | – – – – – – – – – – – – – – – – –
label | 2e6f8126-08ef-5d15-9c80-6fea6cc6632d |  | note | RESPONSIBILITY: Surveyor, SE
label | 48a620fe-b633-5939-9038-4e6b01f49411 |  | note | – – – – – – – – – – – – – – – – –
label | d07f1bd7-c951-5bc2-b4f7-d3201dba3e6f |  | note | VERIFYING DOCUMENTS: This ITP
text | 02791c64-ae11-54c0-8e7a-bcfe8fd02b75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | d268d5fb-5097-56c4-b908-f586c498005f |  | note | REFERENCE: 606.04
label | 571e442f-3d6a-5aad-9575-0eae5b115d24 |  | note | – – – – – – – – – – – – – – – – –
label | 4c8b2fd0-68b2-5323-a1ce-2722eca9a224 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not:
label | 7fc0db62-bc25-5343-8a63-c4196ff7f14e |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 4eeb74c7-b16f-550f-a03b-098cef8c1159 |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 98a09c19-0110-5ddc-91b0-59740ee11559 |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 553b4560-a503-5c91-99a3-a8171cf23a5c |  | note | – – – – – – – – – – – – – – – – –
label | 3d32afa8-5609-5e40-854f-08a023abaf99 |  | note | METHOD: Measure, Visual
label | 7ce2e205-0153-52c6-b00c-2740ec6096b6 |  | note | – – – – – – – – – – – – – – – – –
label | 7d64f9fe-2f17-5bc5-b9c8-ff5ab10b2933 |  | note | FREQUENCY: Each pile
label | f2ddce00-b4f3-5368-b17b-0b45606c6d7f |  | note | – – – – – – – – – – – – – – – – –
label | 86900af8-18fd-5b92-adc6-5383a728e080 |  | note | CATEGORY: HP*
label | 4748d0f8-36ec-5ad3-94d5-66445aa839ad |  | note | – – – – – – – – – – – – – – – – –
label | 6706da26-824e-5eb5-891e-5079423a5068 |  | note | RESPONSIBILITY: SPE/PE
label | 412f6dce-e0f7-5062-874d-84d398e1d5d9 |  | note | – – – – – – – – – – – – – – – – –
label | 454c7326-e444-5ae5-8bad-008dc2b5e428 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3c8612d8-9b44-522c-bdb6-3f80f7e2de50 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | ddfbdc17-e048-52a7-8ffd-d3a0c70b9b9d |  | note | REFERENCE: IFC Drawings 606.03 (a)
label | ad1c4225-4618-52de-86c4-3a826bf30b66 |  | note | – – – – – – – – – – – – – – – – –
label | b252f0a4-383e-5921-b883-f15c6265f7ba |  | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | e0142377-e723-5b22-b058-d79cd5796946 |  | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 3b06e9e2-29d5-558e-b955-097dbb41f202 |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | 12884335-7fe4-5d76-8ed1-d47f7b888a3a |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 41399950-3bc7-5b24-86d2-4f7004ef6144 |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | 8e563f03-27cd-5300-a279-095b1abec5bd |  | note | – – – – – – – – – – – – – – – – –
label | b8126d90-f1e2-59b1-b626-f825540d3b91 |  | note | METHOD: Measure, Visual
label | 0531cd92-2d3a-59ef-9804-3655ee88db0b |  | note | – – – – – – – – – – – – – – – – –
label | 546861cf-fbf7-56d8-8a2f-346612be24d5 |  | note | FREQUENCY: Each pile
label | df3d3f5e-0e48-58e1-803c-b18ceaa23a98 |  | note | – – – – – – – – – – – – – – – – –
label | 47182788-35d7-5e6b-ac5b-18112a9c4b16 |  | note | CATEGORY: IP
label | 60da6cb7-621c-514a-af1d-2a34fc09471c |  | note | – – – – – – – – – – – – – – – – –
label | 6d719055-9a75-5265-9831-c554fc27761b |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 095e60ad-40c7-53d3-92cd-307198adeecb |  | note | – – – – – – – – – – – – – – – – –
label | 0a41ffdb-01e0-5c4d-9844-c1c14f841796 |  | note | VERIFYING DOCUMENTS: This ITP
text | b08b2cc7-c376-5d95-ad39-a9f4a114f53d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | cf657713-a524-544c-941e-cf911f50f08d |  | note | REFERENCE: IFC Drawings
label | 66fca597-ea68-5b6a-8030-d8834b4b99de |  | note | – – – – – – – – – – – – – – – – –
label | 0ce51d4e-bd03-51dd-bd51-50f15a8899f5 |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | b2d09a53-f373-5524-afde-98b49d550c2d |  | note | – – – – – – – – – – – – – – – – –
label | b6a97393-9c16-551d-8ad8-2188622d4f1e |  | note | METHOD: Measure, Visual
label | b52c29ef-0f70-5859-b011-b0f3941a95d2 |  | note | – – – – – – – – – – – – – – – – –
label | 74879c65-1c33-5166-b547-df7d9d31c4c9 |  | note | FREQUENCY: Where applicable, each pile
label | 84a86778-85cd-5671-b8d8-ef4eb57022a3 |  | note | – – – – – – – – – – – – – – – – –
label | a32adf1f-4e37-54c5-92ad-10e4330e8d87 |  | note | CATEGORY: IP
label | 00eaf6f1-bfef-556d-9e37-c13611efa98b |  | note | – – – – – – – – – – – – – – – – –
label | 11972a2e-dcbc-5981-a31c-6eae13ef1b7f |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 0af9fdaa-c7a8-5dd6-8949-58e1813599c6 |  | note | – – – – – – – – – – – – – – – – –
label | e77a1b0e-c539-5152-bf95-8f8df6b34149 |  | note | VERIFYING DOCUMENTS: This ITP
text | 20d840ce-c9f5-5e0e-8ee6-c9bce2a065dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 6dbee983-e29a-5188-bfb9-abd633b29ccf |  | note | REFERENCE: 606.05
label | 67bfba29-62d1-531b-9535-da02c5a464c6 |  | note | – – – – – – – – – – – – – – – – –
label | 750bf1ad-a350-5b15-992b-c0fe9beec670 |  | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 51971968-23c7-5fbb-8783-883551559693 |  | note | Attach: Geotechnical Field Sheet or Report
label | 6345365a-8694-5b4a-bfd5-6e8c17f17a0d |  | note | – – – – – – – – – – – – – – – – –
label | 05b2f277-c42e-51f5-8fcd-273893fe9381 |  | note | METHOD: Measure, Visual
label | f1f32f37-844a-5bd0-b395-7efd3b4bea37 |  | note | – – – – – – – – – – – – – – – – –
label | 9ba9b66c-0ad9-529b-9c01-279fbf61593c |  | note | FREQUENCY: Each pile
label | 3656e087-8bfa-59cb-8f8b-6feee3fcb66c |  | note | – – – – – – – – – – – – – – – – –
label | 84ee6a5a-ab60-5e3f-b19d-a8dcb87a5faf |  | note | CATEGORY: HP
label | 1b3786f1-402d-5dbc-8e98-f9b93ebcafc7 |  | note | – – – – – – – – – – – – – – – – –
label | 2b2baabd-21be-5b34-bdeb-779b3a854c42 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 0dce1279-ae5c-54d3-940a-7fd81d69f5ca |  | note | – – – – – – – – – – – – – – – – –
label | 63a37005-e686-557b-b164-190fad11197a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 7bb331bc-292a-55e4-9cbc-f3d9aca501f2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | 0ab0f5a8-aaee-5be3-ba12-560b0ddbd0e2 |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
label | dd9c59c3-50e5-5468-bdcd-66a722329938 |  | note | – – – – – – – – – – – – – – – – –
label | 0e9a0b04-b067-5c8d-9f89-8f0adb5e562b |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 141197e7-8f37-51b0-be3c-381d818beccc |  | note | • Projecting reinforcement is the correct length and location.
label | 7fc9d350-14fc-5d49-94d6-4be62d38cf8c |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 99588dff-00b0-5a93-afd1-0f76e1871a7e |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | 3437824c-990b-5b1b-98c2-f4a7a3511d2b |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 3ead3e77-7b50-5769-8e95-42cabfa497e6 |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 28c5157a-052e-5316-bfc6-b9255bd1510b |  | note | – – – – – – – – – – – – – – – – –
label | bd28504f-0ab7-53e3-9711-859f37913666 |  | note | METHOD: Measure, Visual
label | 8e5ee3ab-50da-5e3b-8608-aa2423ba43d0 |  | note | – – – – – – – – – – – – – – – – –
label | 869c9bf7-b589-53c1-9b91-bb85200ab0d4 |  | note | FREQUENCY: Each pile
label | 5c3e44e8-c5a9-5115-8091-c2518317cdfe |  | note | – – – – – – – – – – – – – – – – –
label | b0c1b315-3eeb-5935-ae3b-24acd7cff46f |  | note | CATEGORY: IP
label | cfe1fff1-6274-5fdf-892d-1e2aa1653267 |  | note | – – – – – – – – – – – – – – – – –
label | 13e17386-5a99-5cc8-99ee-19c690c197d2 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 52411d72-955a-581f-b5f7-7f138979e7a9 |  | note | – – – – – – – – – – – – – – – – –
label | a749c53d-fc97-51f6-9494-0ec665766e3a |  | note | VERIFYING DOCUMENTS: This ITP
text | 08d69192-bb1d-5915-b610-4364acf7a9d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | c5779768-0bfb-5af6-a14e-8d2d686004d7 |  | note | REFERENCE: IFC Drawings 610.29 (d) 610.43
label | d7951f6d-7482-5152-9592-f71676c01278 |  | note | – – – – – – – – – – – – – – – – –
label | d2f8bc86-0aba-57bb-8d31-a127f6017adc |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | 0bb10d21-26e0-5a58-abba-8014734a6265 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 244cb006-bf98-500c-9fca-372415297748 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | cba62678-1573-5054-917d-f43be26d9f60 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 3df695e3-7d19-5959-99bf-2e2cbb190815 |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 523b4fec-2261-586e-a8c2-a65123a7c6a2 |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 18e9fb04-050e-5d8a-bba3-99a3c66e3cdb |  | note | – – – – – – – – – – – – – – – – –
label | 2b0e1af0-8ca3-57cd-ad63-c045f45cfb7c |  | note | METHOD: Measure, Visual
label | 5f017c6c-a12e-5146-ab2d-ab04e7c94428 |  | note | – – – – – – – – – – – – – – – – –
label | 61da597f-a19a-50b6-8be2-5c1b21a05dcb |  | note | FREQUENCY: Where applicable, each pile
label | 5fe55377-3845-5b67-b125-53c41c0abf8a |  | note | – – – – – – – – – – – – – – – – –
label | 8b136fc9-97f8-57b3-b295-2b0df59cdf38 |  | note | CATEGORY: IP
label | 7dc54f45-eb91-583e-8c4d-362e61bf0c4b |  | note | – – – – – – – – – – – – – – – – –
label | 9633d664-0703-58fc-805d-c6b474e2e958 |  | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
label | 86e9fd64-bc66-5f06-8aab-4ee29506f0bc |  | note | – – – – – – – – – – – – – – – – –
label | 6f70eb62-3221-5250-8168-530cbb0cb14b |  | note | VERIFYING DOCUMENTS: This ITP
text | 5e0eb8f0-c31b-50c6-b156-34a8c198336c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | fe32844f-4bed-55e0-87cf-e7cb17409e22 |  | note | REFERENCE: IFC Drawings 610.46 (a), Table 610.462 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 4d2c3489-5331-558e-bdc6-1d2bf5e62bc2 |  | note | – – – – – – – – – – – – – – – – –
label | e032a61f-3f57-511f-bb29-a7929637f2c8 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | a4af778c-08cc-5f1b-83a3-38e4feb1c672 |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 8791efca-b106-5985-805b-2298ef735362 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f8ddc543-0771-588b-b901-5ab9d855fc54 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | ced37e0c-99c1-5a73-94e8-c6b75b6bee7c |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 6db3b2bb-f514-5542-9c96-0b9202448e63 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | afd4bd31-e7e2-5c7d-ab56-8275222948d6 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | c2c1d39b-34b2-5513-9ae7-a4fa16b98a92 |  | note | iii. Ducts and conduit location = ±12mm
label | 54a9490c-1b24-5454-905c-2a20e75706a5 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | b05ae382-697f-5352-b3fb-b11a5b9c0bc6 |  | note | – – – – – – – – – – – – – – – – –
label | 0c6f25b3-2cb2-540d-9d97-198707e3809f |  | note | METHOD: Measure, Visual
label | 15668efe-f910-50fb-a36f-5d8c620f564b |  | note | – – – – – – – – – – – – – – – – –
label | e84711d0-10af-57e5-b9c5-cc7eb28e8034 |  | note | FREQUENCY: Where applicable, each pile
label | 477c2d6f-1c9b-583d-9396-ed05174002d9 |  | note | – – – – – – – – – – – – – – – – –
label | 02b2790d-a331-577b-bf95-2b27fe1b614f |  | note | CATEGORY: IP
label | a8b17f3a-8c64-5a9c-bfc5-9919dd1bb724 |  | note | – – – – – – – – – – – – – – – – –
label | 6d7651e8-5b95-5a4e-8ab5-f3a40bce44aa |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 0e737688-2fc5-591f-a941-0c790646661f |  | note | – – – – – – – – – – – – – – – – –
label | 379c9419-b6e3-5ff7-b569-ca53e90eff8f |  | note | VERIFYING DOCUMENTS: This ITP
text | 239bb120-5ea8-570e-877f-cd2bfb59b6e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | aec9448c-3f49-58c8-bffb-3a4219c400d4 |  | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
label | ed988ccf-811a-560c-be58-60f53ddb3184 |  | note | – – – – – – – – – – – – – – – – –
label | b5810a87-fc5c-557a-87b5-c47d7befa6b3 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 94986449-34b9-5484-8350-1a5883aac0a3 |  | note | • All foreign material has been completely removed from the excavation.
label | 0e650d7d-f573-56c7-97cd-1b1dcf3fbbd0 |  | note | – – – – – – – – – – – – – – – – –
label | a3ac4ca8-db97-514a-a453-9f98481b48b4 |  | note | METHOD: Measure, Visual
label | b0df3c99-abaa-55e0-bf4c-ef61faf87b02 |  | note | – – – – – – – – – – – – – – – – –
label | 21da78f0-9f39-5d3a-aaae-1d5c88466403 |  | note | FREQUENCY: Each pile
label | 3c464046-7cc3-51ea-998e-e5f833c3b05d |  | note | – – – – – – – – – – – – – – – – –
label | 6de6c2e9-0279-5f14-a158-305ee55b4073 |  | note | CATEGORY: HP
label | 309529c8-e0e1-5bb5-9be1-f7f0499627b1 |  | note | – – – – – – – – – – – – – – – – –
label | 352601b7-dbbd-59fd-8d1e-73fd317a72c7 |  | note | RESPONSIBILITY: Nominated Authority
label | f23c90b0-44da-5ad1-9672-6a1dfd515d10 |  | note | – – – – – – – – – – – – – – – – –
label | 01c46415-9c3d-5cf3-8049-5f0298b5f95b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9c6c2fc3-4d35-5f59-8921-75dc4c0ffcef |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | d51e64b2-ef2d-5730-a772-bfec68cffe09 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
label | 319b32b5-1d58-5d7e-b37c-5384f8438cb6 |  | note | – – – – – – – – – – – – – – – – –
label | 7c9dbdc0-4eba-5338-940f-bce9881b2b45 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | d5e7ee18-b6cc-56ab-9975-2ed604898c79 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 8fcb5a9b-cea2-57c0-bd7e-0d4e0c13d791 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 5fff7795-c309-5d25-8e6b-cd3e33510455 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | b0ad208f-d5a3-5ace-b5d3-8de30a760eb7 |  | note | Record: Required information on the Concrete Pour Record.
label | d6a37cc1-7b59-5abd-8566-b292ac639743 |  | note | – – – – – – – – – – – – – – – – –
label | 8324f3d9-174b-5dd6-828c-8238e52aea1b |  | note | METHOD: Measure, Visual
label | c5f60aed-5ffc-500d-aad6-99c1b3982e28 |  | note | – – – – – – – – – – – – – – – – –
label | 0832c559-a854-5126-971a-cc498240a507 |  | note | FREQUENCY: Each pile
label | bd66fdfd-68b4-5271-81df-01d38cdfe3b2 |  | note | – – – – – – – – – – – – – – – – –
label | c7650907-4e7b-59cc-9cbe-6795931a94b9 |  | note | CATEGORY: IP
label | 69469389-66d9-5317-8ce9-9385f4c7ef1a |  | note | – – – – – – – – – – – – – – – – –
label | d9bd4ae7-f39b-53b3-8dae-4e91aee3bd54 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b16389f0-80a9-5f55-968e-52823da89b61 |  | note | – – – – – – – – – – – – – – – – –
label | 6ae4b127-8c1e-54ae-afe6-1c73b1341962 |  | note | VERIFYING DOCUMENTS: This ITP
text | e37f9c59-f83c-58d6-ad3e-af5e32f04eb1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | 0ef40f34-b5ed-5d5d-a23f-178817e3973f |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | 3368c2d4-4171-51f9-b83c-b917c878e801 |  | note | – – – – – – – – – – – – – – – – –
label | 581f63df-edcc-5e79-9824-269bb8b1abb9 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 9478d5f6-8a35-5977-9233-b9a10dc4b386 |  | note | 0m³ to 10m³ = 1 sample
label | a3058852-f2dd-5154-9bc7-aa46886b8f50 |  | note | 10m³ to 25m³ = 2 samples
label | b290fa30-ffbe-5c96-805e-fbf08c88768b |  | note | 25m³ to 50m³ = 3 samples
label | b83379f7-39d9-588d-825c-e3b511bd75d7 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 9c4a0b1d-77d4-50bb-8070-a25450b24bcb |  | note | • For each additional 50m³ and additional sample shall be taken.
label | 657565dd-0505-5d12-88f9-eaa2af1d3708 |  | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | f5f0cb20-92a1-51c2-88d0-9ba4defb3643 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | df01f0cc-2fb3-51ab-85df-628bc60caf88 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 58e04722-0197-50e5-81c8-e0bd8af2ecab |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 93e87183-bd10-560d-a240-75405d6ecfe9 |  | note | Record: Required information on the Concrete Pour Record.
label | 1a3153f5-2685-5673-bca4-c1b7b23c169b |  | note | – – – – – – – – – – – – – – – – –
label | b75ff32b-f7e5-5f3d-a700-91b68b8f12cc |  | note | METHOD: Test
label | 2a46e046-7c2f-5d7c-acb3-53af6aca59b0 |  | note | – – – – – – – – – – – – – – – – –
label | 09dcf212-2eea-54f8-8bce-867d8284310f |  | note | FREQUENCY: Each pile
label | a5d26ecb-3f95-5764-aca6-1d47880a490d |  | note | – – – – – – – – – – – – – – – – –
label | 7fce780d-c539-5db5-bedb-d40f239c86f2 |  | note | CATEGORY: IP
label | a8155d83-b433-5765-bee0-9581329ec0f1 |  | note | – – – – – – – – – – – – – – – – –
label | 467ee8d8-9706-5da7-9225-922fdd08796a |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | d741dd6f-78c0-5bd6-9be8-1766d93ff6e5 |  | note | – – – – – – – – – – – – – – – – –
label | 39599ccb-2f02-5337-a845-5cdb88f89563 |  | note | VERIFYING DOCUMENTS: This ITP
text | c8b5c515-5071-59a2-953b-1bdfd14dee43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | 25bbde4a-27e8-5f06-8ffe-c666bdd11432 |  | note | REFERENCE: 610.13 (b)
label | 3a867ef0-afd2-5109-8478-0307137bff8a |  | note | – – – – – – – – – – – – – – – – –
label | cf175af7-9264-558e-94d7-ece78e8eb7fc |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | e77f4ca5-fb45-51a5-910f-3a4a1f09385d |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | c88d8a8f-7267-5280-9d8b-e37fb1da6c35 |  | note | • Passability = ≤10mm (aggregate height differential)
label | f456b928-de8a-5cd7-b592-a220995b51ca |  | note | Record: Required information on the Concrete Pour Record.
label | 495ca548-6d06-56d1-aad5-ee9a4ac423e6 |  | note | – – – – – – – – – – – – – – – – –
label | 0a5d52e6-0afa-5c47-baf3-c908305e649d |  | note | METHOD: Test
label | 8b2f5cdf-9280-5ea4-a0ab-3483165c99bb |  | note | – – – – – – – – – – – – – – – – –
label | a2b81406-8741-521e-9977-79cca9bab06d |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 06773d12-04c7-5177-ab9a-8de4a4badebe |  | note | – – – – – – – – – – – – – – – – –
label | af6cd45d-fc3a-5467-bf9d-3aea4a6a9522 |  | note | CATEGORY: IP
label | f520da25-40d7-5331-9196-7708c3e02245 |  | note | – – – – – – – – – – – – – – – – –
label | ed539f99-0f7f-5b89-b59c-661c25ea7605 |  | note | RESPONSIBILITY: Concrete Tester
label | 07852a82-f4bb-554b-93af-757056703b57 |  | note | – – – – – – – – – – – – – – – – –
label | f86da9c0-d9c5-51aa-8743-2f32f4c56c83 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8cd8bec6-9b72-578f-881d-bed59d5985e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | ec3883bc-1524-5e8c-a068-9f50027d69e0 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | 8c5ca500-29b4-5572-b071-644d66f15c5e |  | note | – – – – – – – – – – – – – – – – –
label | b47b01eb-dc35-5f39-a706-521bf36df788 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 5732e763-0a7e-5994-ae6a-5efc979fc742 |  | note | Record: Required information on the Concrete Pour Record.
label | 0511a59d-6f53-5dfb-b872-0c3344ed2a3d |  | note | – – – – – – – – – – – – – – – – –
label | b057c8cb-2d9d-581f-a4a3-02c3f47caa51 |  | note | METHOD: Test
label | 7b69b9fc-136e-5634-9e4d-5d8d8dc239d9 |  | note | – – – – – – – – – – – – – – – – –
label | cc2b989e-5ffc-5dab-b723-21e802716874 |  | note | FREQUENCY: Each sample
label | 6376fbf1-ce83-5bb4-9fe6-398e22384188 |  | note | – – – – – – – – – – – – – – – – –
label | 41347a79-8f67-5761-ac04-5aba9ef0e146 |  | note | CATEGORY: IP
label | 93681792-12c8-5d65-be91-b6b312805c36 |  | note | – – – – – – – – – – – – – – – – –
label | 54ec6182-351e-5836-ad13-383542bb19ec |  | note | RESPONSIBILITY: Concrete Tester
label | 2ff109be-33af-5319-a5ee-e21b085bb453 |  | note | – – – – – – – – – – – – – – – – –
label | 37904152-5e0a-5334-b6f1-bd8c37538714 |  | note | VERIFYING DOCUMENTS: This ITP
text | ed174a8d-ff8b-55d7-81ac-66f53e977b0d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | fd6e180f-8007-53f0-bdcf-6a97d5e9d73a |  | note | REFERENCE: Piling Quality Procedure 610.18 (a) & (b) 610.18 (d) (i) 606.06 (a & b)
label | bbc87a57-c5fe-56e9-a85c-dbe1a23e34ab |  | note | – – – – – – – – – – – – – – – – –
label | 771d951b-bcf8-5651-9061-4b9c7f6e719c |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | 6f802b8a-f987-5cd9-b3b9-f52ce1e4bc58 |  | note | • All concrete batches are traceable.
label | b3d38e5a-954f-5b57-b98e-e7e87ef1a313 |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 05fbd8bd-c6d8-5496-adc8-9e2307037a12 |  | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | b72ebfab-a267-5400-8e0b-d69c9f6a538a |  | note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 8e66b6f0-c8e1-5f04-8f04-4aac13054ceb |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 0e12994a-020c-5c1a-a3f9-dc855a78f7e7 |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 87424df1-f47c-5407-9cc8-842db2a10c50 |  | note | Record: Required information on the Concrete Pour Record.
label | 3adc00fc-7bee-52d1-a2fa-9f484d106a01 |  | note | Attach: Concrete Pour Record
label | d678cdeb-b317-5dde-a439-babdf3565ef0 |  | note | Attach: Concrete Dockets
label | d1336547-d67d-5ed0-8c62-8f5debac8da5 |  | note | – – – – – – – – – – – – – – – – –
label | 072d8bdb-377d-5b27-911b-b59b9310ff7f |  | note | METHOD: Visual
label | 2420f2f0-487a-5f15-a208-f63f3355b4a1 |  | note | – – – – – – – – – – – – – – – – –
label | 13fb2b26-c3b2-5978-8332-bff69aa56ffa |  | note | FREQUENCY: Each load
label | a3bcd20e-0bba-59ad-98a1-efef0725106d |  | note | – – – – – – – – – – – – – – – – –
label | c06c43bf-d9b3-55f5-a516-0f674b721ef0 |  | note | CATEGORY: SP
label | 61b5f67e-e191-56c5-ac06-95e1b3d44a5d |  | note | – – – – – – – – – – – – – – – – –
label | b5ba36d7-f8fa-5d33-9086-dfda1d801eab |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
text | 7733b376-bb14-5234-8a9d-0c534d2d352b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 0d761eb8-99e8-537d-8ad4-0ef5e6de13f5 |  | note | REFERENCE: IFC Drawings 610.31 610.20
label | 86f9a53c-f7e5-599f-9b10-80ed8c26f8bb |  | note | – – – – – – – – – – – – – – – – –
label | 4eeca337-ac4b-57fe-87c8-caf8cd910704 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 26309abb-2110-589a-9a3e-c0a6a4f8b363 |  | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 76aab080-d2b1-5fb8-a282-683b26fc2d93 |  | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | d3a46d65-70de-52e2-a13e-a93ab8f06f66 |  | note | – – – – – – – – – – – – – – – – –
label | d750caee-e2a6-5b80-8c4f-5b38ad4a55b3 |  | note | METHOD: Visual
label | 51b94231-81b6-5463-9099-ed7eb314bf19 |  | note | – – – – – – – – – – – – – – – – –
label | 1588c1b5-5f7f-5ffc-960b-5d4a24bd61d4 |  | note | FREQUENCY: Each pile
label | 1d70ea6b-af60-53ea-bd1f-10beb17c7803 |  | note | – – – – – – – – – – – – – – – – –
label | 15b9284e-d5dc-58a0-a0bb-10b02103a68a |  | note | CATEGORY: IP
label | 22017291-535f-5e32-ae9f-2066e07abefc |  | note | – – – – – – – – – – – – – – – – –
label | 13168a56-48a5-5a4f-a149-ad11c0c36cda |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 27718c8f-0d48-5c27-a946-698c58dadf62 |  | note | – – – – – – – – – – – – – – – – –
label | 93afa108-21d6-5e4f-80b7-580c29c64554 |  | note | VERIFYING DOCUMENTS: This ITP
text | f49d177e-84bb-5c1d-ac83-f1287885f725 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | a35a1395-5ba0-51c8-bd80-b3a6f555dc26 |  | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 606.06 (a & b)
label | 06baa5f0-cb05-58b2-8e4a-cb9440e19e62 |  | note | – – – – – – – – – – – – – – – – –
label | 497334a1-4237-589a-a972-8165d7bafa99 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | e81c681e-a3fc-5f71-86c7-f3425b1c51c4 |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 2cdf6ad6-0df0-53b9-9c73-d1b91b13ab1b |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | d513c63d-65ef-5340-bed2-1ffa52547244 |  | note | – – – – – – – – – – – – – – – – –
label | a7531f63-444f-531f-806e-a81a928260d7 |  | note | METHOD: Measure, Visual
label | 39f0b93e-8c5d-5b18-8e1e-59c79845a93a |  | note | – – – – – – – – – – – – – – – – –
label | 5feef4a9-1091-5c67-94e9-5d010a457afb |  | note | FREQUENCY: Where applicable, each pile
label | ddd7e43d-2a0b-5ef5-84c8-a1a1e0fc8ec9 |  | note | – – – – – – – – – – – – – – – – –
label | ce078fa7-2f28-5199-8383-1d70ec2df69d |  | note | CATEGORY: IP
label | cd75d82e-f6b6-599c-ab4b-1c434e1c2edf |  | note | – – – – – – – – – – – – – – – – –
label | 06554806-b026-5685-975c-23597c73dc6f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3f47f00e-d1e5-5b4b-992b-13d6a5ca1a31 |  | note | – – – – – – – – – – – – – – – – –
label | 0af724d2-a189-54e9-b86a-502aee1e18f0 |  | note | VERIFYING DOCUMENTS: This ITP
text | ae5c577a-8921-55a2-8779-78b8a2391b57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | cbed9ec4-f4ae-52a1-8106-f5675e36d5bc |  | note | REFERENCE: IFC Drawings Table 610.05.051 610.16 (g)
label | 74d36346-f5f4-52df-a6e8-267398569422 |  | note | – – – – – – – – – – – – – – – – –
label | 92b3a5fb-9e3c-5489-9ba8-ec26dda0e2c5 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 3d5ca9bc-a78d-516d-8e51-fc6496310dae |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0786d6dc-f624-509d-b9fa-313d5ad01395 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 92710a56-c23b-5c8b-8445-ba43eae0db35 |  | note | Attach: Compressive Strength Test Results
label | 877146d2-d4a8-5707-a08d-1781031ef103 |  | note | – – – – – – – – – – – – – – – – –
label | a230532e-e713-5813-9b21-26d22d717a3a |  | note | METHOD: Document Review
label | 1ece919b-c936-5c15-ae74-e4b92ae0e677 |  | note | – – – – – – – – – – – – – – – – –
label | 6eb7b19a-30ec-597b-8fc4-f3fc6eb4c2c6 |  | note | FREQUENCY: Each cylinder
label | dd8c695b-8228-59e4-9258-d570130e9781 |  | note | – – – – – – – – – – – – – – – – –
label | 065d8868-3c0d-5d17-bd53-be2eb5d82658 |  | note | CATEGORY: IP
label | 850e472e-f900-5d9b-9fbb-6575e05ba867 |  | note | – – – – – – – – – – – – – – – – –
label | 7a921fc4-c414-5450-bd8f-1b3ea7fd4ef7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0e02434f-d120-5f0f-8304-420d50949645 |  | note | – – – – – – – – – – – – – – – – –
label | 31acc580-13b8-5820-9214-101680427fcc |  | note | VERIFYING DOCUMENTS: This ITP
text | 5c71fd28-65fe-509b-ac3b-f707ea5e7aa7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 34489083-0cf4-5377-97ab-0d15981aacaa |  | note | REFERENCE: 606.07 (a, d & e) AS2159 Clause 8.8
label | 59def6eb-33aa-50b2-8e51-1463eec49314 |  | note | – – – – – – – – – – – – – – – – –
label | 8db43e17-e389-5145-9ce2-c6f492b845c0 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 54229314-3721-5d37-b80a-5a2aa0e10959 |  | note | • Cross-sectional area = ≥95%
label | 50ae2fe2-74d5-55fe-8aa9-08a78e612210 |  | note | • If any test fails, all piles shall be tested.
label | 99ec655a-b15c-58e8-8176-969310710dea |  | note | Attach: Pile Integrity Test Report
label | 4adbd8d8-6e3a-56ea-9bae-6af78e57405f |  | note | – – – – – – – – – – – – – – – – –
label | 51abb88c-445c-5751-a0bb-5cc4028dfe1d |  | note | METHOD: Document Review
label | b7cc1458-3376-5a3b-8a8f-5b8a41df340b |  | note | – – – – – – – – – – – – – – – – –
label | d0a0e821-2b79-526a-9c21-3782962857db |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | ee931a78-9eba-5e18-a25a-c072e186eb47 |  | note | – – – – – – – – – – – – – – – – –
label | 09ad1d2e-13ad-57cf-9b9c-5bbd6d659b8b |  | note | CATEGORY: IP
label | 51bdf18d-1686-55cf-b37d-22feb688436e |  | note | – – – – – – – – – – – – – – – – –
label | a3910dca-276b-5d77-a924-5f36adce41d2 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 9366cf7c-322b-5fdd-9231-ed9fa2cf273f |  | note | – – – – – – – – – – – – – – – – –
label | b66620c3-af5b-59e7-9d11-4937f54f6e9b |  | note | VERIFYING DOCUMENTS: This ITP
text | a15dcd91-c44e-54aa-8af0-42d0df8c67e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | 8fa2952e-8b3e-59f4-b359-82d49947a468 |  | note | REFERENCE: IFC Drawings 606.07 (b, d & e) AS2159 Clause 8.4
label | e9dc46dd-2d19-5ab5-9d22-aae75122cf27 |  | note | – – – – – – – – – – – – – – – – –
label | c2fd5d9a-fc19-56e9-8779-0f9a2def5daa |  | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | 4f3f9445-9bfd-5a92-8c8a-eb40e8adb94c |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | c394a371-4136-5028-9344-98db2690a5f5 |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 19f78f32-62e1-5468-895a-96279e815cb0 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | b7bb2580-b435-54a5-9898-af8885b8539c |  | note | Attach: Static Load Test Report
label | ea3dee8c-d330-540e-85f5-7b6d5f557b28 |  | note | – – – – – – – – – – – – – – – – –
label | 0daf8d6a-cc14-5be6-a6ba-0905bbfc7031 |  | note | METHOD: Document Review
label | b0278f04-8320-5699-8a79-dcaa0370cde1 |  | note | – – – – – – – – – – – – – – – – –
label | 2b652acb-90e4-5b7f-8e0c-a74f64c9013a |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | 2d3c8ed2-c3a4-5aa9-9475-742de5364346 |  | note | – – – – – – – – – – – – – – – – –
label | a6fc1eb1-134b-5821-afb3-db8383cb5b4f |  | note | CATEGORY: IP
label | 00f2776d-6123-5d4e-afe6-f5da4c8072c5 |  | note | – – – – – – – – – – – – – – – – –
label | 56c915af-b3cb-52bf-a581-3d605671969d |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 4f50c1c3-4fc7-5546-8a3a-3f23c0639312 |  | note | – – – – – – – – – – – – – – – – –
label | 2140f516-eafa-5763-8434-d48236e86a42 |  | note | VERIFYING DOCUMENTS: This ITP
text | ad2bff45-5e0c-53cd-aa59-fdc3ca05f92c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | e0fd7af3-817f-5270-b7d8-8c633360d1ad |  | note | REFERENCE: 606.07 (c, d & e) AS2159 Clause 8.7
label | 9c879cfa-edfa-5ed2-aa08-f5f58d03ea97 |  | note | – – – – – – – – – – – – – – – – –
label | fdd57f8c-18cb-5766-97d4-c12615cc1b45 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 27ac50c3-e764-5f31-8e4c-989092073278 |  | note | Measured Ultimate capacity = ≥ values on IFC drawings
label | d0b64a48-a830-5062-ac5d-eaaa82318678 |  | note | Attach: Dynamic Pile Test Report
label | b0d61f88-759c-54de-9d79-1cfd499fdfa4 |  | note | – – – – – – – – – – – – – – – – –
label | efe95a01-36b4-5bda-a01b-c81d41a6a453 |  | note | METHOD: Document Review
label | 450f7055-9924-5519-aa1c-14a07c49d788 |  | note | – – – – – – – – – – – – – – – – –
label | c96ebc1f-99ff-5132-a1b6-0f5b190e2e9c |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | b1448f93-6028-59c9-b9b5-015a2c8c96f2 |  | note | – – – – – – – – – – – – – – – – –
label | 3b642563-d674-546c-8271-5a4ecc08a50b |  | note | CATEGORY: IP
label | eeea3685-4d92-51da-9f97-d01af1d938cd |  | note | – – – – – – – – – – – – – – – – –
label | 2d8dc730-bb04-5726-8fe4-23cdedab77f9 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 3e659148-5302-5418-a49e-239b159697fe |  | note | – – – – – – – – – – – – – – – – –
label | 7dc30864-caf3-5530-9bc6-6e37bed712c3 |  | note | VERIFYING DOCUMENTS: This ITP
text | bc3543a7-8f57-52b4-8603-505a0f07e92c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | 2f4d8cdf-1906-5a27-9e25-0ed3d4ed5d69 |  | note | REFERENCE: IFC Drawings 606.08 (a - c) AS2159 Clause 7.2.2
label | 3f15c219-1392-5583-92f8-86205a15170c |  | note | – – – – – – – – – – – – – – – – –
label | 00f6530a-f988-5c07-ac83-6f968004df49 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 77a5082d-a0a6-514d-ab94-4a4a210b0145 |  | note | i. Pile head plan location = ±75mm
label | f5028a51-e933-5fb7-9437-6af72aa60347 |  | note | ii. Variance from vertical or rake = 1:100
label | c45fa42f-4160-579f-9044-b7231f441978 |  | note | iii. Irregularities in straightness = 1:100
label | 4d4212b0-c828-5ad0-be18-03c397270f50 |  | note | iv. RL = ±25mm
label | 8990839e-1bfb-50e3-af96-a01d70faf6ab |  | note | Attach: Survey As-builts / Survey Report
label | 41bfeafd-395e-5454-96af-a96f7624af3e |  | note | – – – – – – – – – – – – – – – – –
label | e5a33d2e-693d-51c4-bc44-da65dc3d326d |  | note | METHOD: Document Review
label | 4b1500b9-2771-504f-b4f6-2f9e74d09783 |  | note | – – – – – – – – – – – – – – – – –
label | 64c02500-df77-5cbf-bbfb-c0add0c7dc5e |  | note | FREQUENCY: Each pile
label | fc5a0f51-7c3f-5480-b5e4-30aea4e99ca0 |  | note | – – – – – – – – – – – – – – – – –
label | f9ef3e50-e7b4-53f7-84d2-3eece36860c9 |  | note | CATEGORY: IP
label | c3c40ace-4d7d-5968-aab9-c7b0ae847e8e |  | note | – – – – – – – – – – – – – – – – –
label | 2114f26c-5cef-5159-bb49-5de60d42e9db |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 16154ae5-3aee-5865-9126-9d79c7be197c |  | note | – – – – – – – – – – – – – – – – –
label | 608bc0fc-1634-58a6-a334-c8092b899aa6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 12204703-9300-5cce-ac1b-17cef2b718cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | cafe9266-53b6-5392-9679-b1a071be7b2c |  | note | REFERENCE: MRPA Quality Management Plan
label | 88332635-95a9-5973-bf34-9d4bc34e76eb |  | note | – – – – – – – – – – – – – – – – –
label | 3711deab-c05e-5df2-9f2c-d51836593294 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 00ef86c3-ef4f-5dcc-b629-ae514f6ee85e |  | note | – – – – – – – – – – – – – – – – –
label | 8c9c699d-8f01-5ba8-9a33-e8e2a89b6e62 |  | note | METHOD: Document Review
label | 502988e0-7ceb-588f-a899-216454e5346f |  | note | – – – – – – – – – – – – – – – – –
label | ad983036-4157-5f5a-baa1-496b1070e4ff |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b8c11c63-386d-51bf-bad1-97ba8d92b27d |  | note | – – – – – – – – – – – – – – – – –
label | b1800cd7-0f2d-585d-b1b1-a816ddf80826 |  | note | CATEGORY: HP*
label | b18c3f9b-5d8a-5a1c-b034-1fcf5105fa9e |  | note | – – – – – – – – – – – – – – – – –
label | 340dadef-d945-50c5-bd59-2768337d1174 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b9788f93-bb61-5a88-826d-02f157a65662 |  | note | – – – – – – – – – – – – – – – – –
label | fd10df2a-a440-5349-be4c-50b125be4617 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9c689bc4-dd86-58f8-8914-d38923729003 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 600c0e73-1d0b-5d6d-8436-164f25379f77 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 34953e20-dec5-504c-9fde-76bc5ee207ad |  | textbox | Name:
text | 3425c2e7-9c84-5a30-805b-afa9a69dd763 |  | textbox | Position:
text | beff82c2-e6aa-5ba5-91c5-15888ce25759 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-134-CIV-Stormwater drainage materials and CCTV | itp |  |  |  | Yes | ITP-134-CIV-Stormwater drainage materials and CCTV Rev 0 | eacfb1db-cb28-4a15-8ce0-317027c98af8
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b6df2066-a908-5df3-b475-a2f174ba945a |  | note | Document Title: ITP-134-CIV-SSB-Stormwater drainage materials and CCTV
label | 693f6f69-8b01-50cc-8411-21f0399154ed |  | note | ITP Description: SSB-Stormwater drainage materials and CCTV
label | 3f705841-b60b-5562-aea0-ea99960949c1 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ae6cd36a-f46b-529c-b5c7-57a3917087fe |  | note | Discipline (e.g. CIV/STR/RAIL): 134-CIV
label | ef784316-36f8-5884-b014-915e6d7da16f |  | note | Revision Number: 0
label | ea37f743-facb-5be7-b74a-f8cd575736bc |  | note | Revision Date: 30/01/2023
label | ee319ba6-8dac-5158-bef7-82a232516a89 |  | note | ITP created by: Hiruni Wickramarathne
label | 204e181c-9791-5f9b-aba2-e251a101ba16 |  | note | ITP approved for use by: Victor Mira
label | be926cc4-e8c1-5813-8783-f9bc218e72cd |  | note | 1.1 Non Dependent
label | 073d3d4a-5212-58b5-b5a0-d681b6d27a71 |  | note | Reference: VicRoads Section 701 (May 2020)
label | fcc1fa88-86ed-5271-a3c6-49c6c31dae91 |  | note | 1.2 Non Dependent
label | de119a66-7e73-5615-8444-2d22bf630f09 |  | note | Reference: VicRoads Section 705 (June 2021)
label | 1d9b205e-f8ab-5dbc-a391-f338aa59524b |  | note | 1.3 Non Dependent
label | b0c258d7-bd93-577d-9cd2-cbfd83d2cd3b |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.2 Drainage Flexible Pipes
label | 1560bf2d-896a-5752-94ad-fcd2696d367d |  | note | REFERENCE: Section 701.08
label | f0d5cb77-b35b-519c-9a4a-4e5b0f730bb8 |  | note | – – – – – – – – – – – – – – – – –
label | c5bf580c-6edd-5cc3-b8d3-f44a8720f4cb |  | note | ACCEPTANCE CRITERIA: Flexible pipes shall be supplied in accordance with 701.08
text | 6b4dadd6-15fc-5b5e-b045-d677d06e7c7f |  | textbox | Enter: Teambinder Material Approval number
label | 353b896c-c45f-552d-8d95-6cc282b23a74 |  | note | – – – – – – – – – – – – – – – – –
label | bff0030a-0859-5053-a94d-cfbbf367c87d |  | note | METHOD: Document Review
label | eec6e970-88b9-5eb3-8725-056a2375ea77 |  | note | – – – – – – – – – – – – – – – – –
label | 46fbfb08-eec8-5421-8f1f-fb7278020e4b |  | note | FREQUENCY: Each lot
label | 912c8b30-8ac2-5d6c-9278-70ac96828aa7 |  | note | – – – – – – – – – – – – – – – – –
label | 31f0afe7-ae58-5bea-9a32-004f2a4530e4 |  | note | CATEGORY: HP
label | 4de0794d-a82c-50d9-a527-363daf1d1bf2 |  | note | – – – – – – – – – – – – – – – – –
label | 6a9cf61c-a218-59a4-8314-4f452ae3b19f |  | note | RESPONSIBILITY: Nominated Authority
label | 6eb83c92-55a1-5204-b3e3-ad6c034b9433 |  | note | – – – – – – – – – – – – – – – – –
label | a083acdb-002c-5095-bb66-6826f3826609 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 2dc99c3b-0d71-5464-82ce-cc553412097b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Precast Drainage Pit
label | 99d482dd-5422-5019-839b-9559784d3ff8 |  | note | REFERENCE: Section 705.07, Section 705.04, Section 705.09
label | 16c01170-9231-52ec-a9c4-e9c2488406e9 |  | note | – – – – – – – – – – – – – – – – –
label | bfd20872-04e8-5932-91b4-5a3b6da9696e |  | note | ACCEPTANCE CRITERIA: Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | fcd66195-d803-52a4-8825-0004a99247c3 |  | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | 882147a3-bf3c-54e2-b532-cbdc1992e7d0 |  | textbox | Enter: Teambinder Material Approval number
label | db53b2cf-f4d6-5963-a098-d2ba09d6e5b4 |  | note | – – – – – – – – – – – – – – – – –
label | 655347ac-4312-5f4a-ae58-c82cade83363 |  | note | METHOD: Document Review
label | 540fc1e0-b882-5a69-80bc-204cd2fba020 |  | note | – – – – – – – – – – – – – – – – –
label | 5c9f802a-43a5-542b-b4fc-14ea5e536df1 |  | note | FREQUENCY: Each lot
label | 4e3f1473-3542-50a5-9bf1-8c334bcd800a |  | note | – – – – – – – – – – – – – – – – –
label | a1a9d853-8651-568f-8298-e4c1bca299cd |  | note | CATEGORY: HP
label | 7f07fcfb-1523-59a7-a884-974d397ea8c6 |  | note | – – – – – – – – – – – – – – – – –
label | 878566e0-558e-507f-b0ef-e76727806da4 |  | note | RESPONSIBILITY: Nominated Authority
label | 71cd9045-2d68-5fdb-a9ea-3589e0bd8f0c |  | note | – – – – – – – – – – – – – – – – –
label | c0d0c430-783f-56b0-85a4-d634c8bf3d29 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 81c29c8c-894c-55d1-b6de-051377a230fa |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Cast in Place Drainage Pit
label | 211fe53b-9865-582f-8f29-5bb0e8ff5514 |  | note | REFERENCE: Section 705.06 IFC Drawings
label | 86577d97-27f4-5fc4-8913-ccea2fb521c0 |  | note | – – – – – – – – – – – – – – – – –
label | d3e9d8ff-7dce-5d7a-855a-406aded55f6a |  | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | e928b4dc-8181-5627-bc2b-2f3360296938 |  | note | – – – – – – – – – – – – – – – – –
label | 6553d6a1-be04-5326-bf4d-2adc3910a6b2 |  | note | METHOD: Document Review
label | 6110e432-1a97-5b11-bd74-e3023546c579 |  | note | – – – – – – – – – – – – – – – – –
label | df05c318-70fe-57c3-9122-c26bd6ff2cd7 |  | note | FREQUENCY: Each lot
label | 28960e55-a7c4-5cf3-83bc-6d13ad603f6a |  | note | – – – – – – – – – – – – – – – – –
label | 055321bf-1dd6-5ed5-853f-1e6f2f3bd8a4 |  | note | CATEGORY: HP
label | 0e99e633-afc1-582e-9a57-3ba7f00120ec |  | note | – – – – – – – – – – – – – – – – –
label | c43722a7-eced-5808-9b0f-f1da7af2ac2c |  | note | RESPONSIBILITY: Nominated Authority
label | 3139d56c-2c87-593e-9bce-65637f84d15d |  | note | – – – – – – – – – – – – – – – – –
label | 2439740d-cb56-5cab-82f0-bfef82adf662 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 2d507439-d758-56cd-907b-2223798a97a8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Drainage Pit - Step Irons
label | 906387b2-a3b0-5120-bb16-5265217a61af |  | note | REFERENCE: Section 705.04, Section 705.12
label | 034935a3-7e68-5210-8eaa-5ce8c29d03bf |  | note | – – – – – – – – – – – – – – – – –
label | b69e7290-b9c0-5dfc-b345-2da5667c6cfc |  | note | ACCEPTANCE CRITERIA: Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | 81ac4805-4820-5b70-9932-4bcd687ff1de |  | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | 8fb918b5-211c-5fba-a92a-0b0b6149fbe7 |  | textbox | Enter: Teambinder Material Approval number
label | 36136f23-4fea-51c6-ae95-3a7d24fa645c |  | note | – – – – – – – – – – – – – – – – –
label | b57bc471-213b-5610-b3ec-bec9cb269e50 |  | note | METHOD: Document Review
label | e99aaede-b236-5748-82c0-4061f92be5dc |  | note | – – – – – – – – – – – – – – – – –
label | b403e655-7a2a-5a4d-8abc-22fd89dc854f |  | note | FREQUENCY: Each lot
label | 7b3a3c8c-95fc-541c-80b4-9f1755110c83 |  | note | – – – – – – – – – – – – – – – – –
label | e1407ee4-0c8e-5aee-86e3-0c17eb301c00 |  | note | CATEGORY: HP
label | 012d3a78-204b-5054-aff9-d9d03792ecce |  | note | – – – – – – – – – – – – – – – – –
label | 946c17f1-7458-59ac-a890-234cd4d936c5 |  | note | RESPONSIBILITY: Nominated Authority
label | 06c25003-c063-5a36-b9e9-a478a88ea46d |  | note | – – – – – – – – – – – – – – – – –
label | 665b7242-648d-5dcc-b522-a4ce5006ff37 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 4b0b38ee-54d8-52c4-8b48-34be576a433a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Drainage Bedding Material
label | 0a235c29-2911-5e84-9c76-a110a0b46f5c |  | note | REFERENCE: Section 701.09
label | 991f8991-2e80-58cb-94d9-548731a57c0d |  | note | – – – – – – – – – – – – – – – – –
label | cb86d183-37f3-5760-8237-e8aedf866c44 |  | note | ACCEPTANCE CRITERIA: Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | a24192ad-6261-57a1-8efe-656646965bae |  | textbox | Enter: Teambinder Material Approval number
label | aa173625-007d-57ef-a58c-a3c85e0e991d |  | note | – – – – – – – – – – – – – – – – –
label | 599ccef6-dd21-5eff-8c72-7192ff8de980 |  | note | METHOD: Document Review
label | b0b90333-9e98-5fb4-a5f8-3bcc93f544a9 |  | note | – – – – – – – – – – – – – – – – –
label | b27498d0-69b5-5e32-b26b-5643f0e5acc9 |  | note | FREQUENCY: Each lot
label | 51141b22-1d3a-5145-baa6-646481403beb |  | note | – – – – – – – – – – – – – – – – –
label | f8dc3c9d-ffe8-5b50-b7b8-49e0a1a257db |  | note | CATEGORY: HP
label | eaa62a6c-e912-54d7-9866-05dcbf64ca32 |  | note | – – – – – – – – – – – – – – – – –
label | 21dbc6f8-a636-5d9a-9366-d54ad051e517 |  | note | RESPONSIBILITY: Nominated Authority
label | 8eb3f777-983e-535c-a8fb-90ad4e64aabd |  | note | – – – – – – – – – – – – – – – – –
label | 4e5f5bb3-7e89-5305-997f-90668bdfa9e8 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | efd8a22e-1681-5ea5-aba4-52f1d886de50 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Drainage Backfill Material
label | a594a59f-ccba-57ea-87e9-80155dc6506f |  | note | REFERENCE: Section 701.09, Section 701.19
label | dfc36ac7-b92e-5d31-8025-6077ac56ecb3 |  | note | – – – – – – – – – – – – – – – – –
label | b9969b5e-a80a-5cfe-9e78-932f915315a3 |  | note | ACCEPTANCE CRITERIA: Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | 2efabe59-bd24-5c63-a4b4-8bd1d4403f36 |  | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | ae207015-41ce-51c4-bd0e-b109a9c092f4 |  | textbox | Enter: Teambinder Material Approval number
label | d3293c7f-cf9a-5e88-b7e7-d54b6a73cbc0 |  | note | – – – – – – – – – – – – – – – – –
label | 5f6abd62-7d2a-5798-88c9-f1dedc07e72d |  | note | METHOD: Document Review
label | 8cd5beb8-0e35-57b7-82c9-bf1ea244e028 |  | note | – – – – – – – – – – – – – – – – –
label | 0e94615d-883c-59cf-b4eb-ae151184bdba |  | note | FREQUENCY: Each lot
label | 58299da3-a96d-5fd0-8c28-b44f332f81b3 |  | note | – – – – – – – – – – – – – – – – –
label | 35cc81da-c841-5a7f-baa4-a0f2f1f99c30 |  | note | CATEGORY: HP
label | b1412ab3-c7ec-5cae-8855-bc098fa33701 |  | note | – – – – – – – – – – – – – – – – –
label | 9c64ecba-d94a-563c-889b-61c2549796de |  | note | RESPONSIBILITY: Nominated Authority
label | b037f207-7231-572b-b0bb-f3c242c10039 |  | note | – – – – – – – – – – – – – – – – –
label | afe21135-fbcc-5743-8f43-e3195f1e7226 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
date | 9b121048-8e18-569c-90b2-adb650cdad60 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Pits - installation
label | fbf26493-2be0-52ae-9094-baf75b455f17 |  | note | REFERENCE: IFC Drawings VR 701, VR 705
label | be082da4-ddb2-55da-8393-bec9e9ef8446 |  | note | – – – – – – – – – – – – – – – – –
label | 1c3226ef-6269-5908-86d0-687f1bcc0204 |  | note | ACCEPTANCE CRITERIA: All the pits for this separable package are installed and respecting Lots are closed
label | e9fd10e3-3d09-5966-abf2-13d7732c7b64 |  | note | – – – – – – – – – – – – – – – – –
label | a5d63093-149f-5859-806d-de93856a0c6c |  | note | METHOD: Document review
label | 09dd1c74-5474-5195-9dd7-4a8ada764d78 |  | note | – – – – – – – – – – – – – – – – –
label | 6ddeccf6-3f7c-5c52-ba57-aabf03916d28 |  | note | FREQUENCY: Each drainage separable package
label | 7c968c95-e0b1-5331-8434-27077154cdd9 |  | note | – – – – – – – – – – – – – – – – –
label | 4615c388-ee90-5ee4-ae1c-e92805739863 |  | note | CATEGORY: IP
label | 8e40b438-4520-5b8c-a83e-62684e8dd09f |  | note | – – – – – – – – – – – – – – – – –
label | b6ffadfe-b3c3-524b-8563-e9a0b9c5a966 |  | note | RESPONSIBILITY: PE
label | aab03cd7-b46c-57ff-acfe-aedd5446401f |  | note | – – – – – – – – – – – – – – – – –
label | f423e3e2-5c0d-5dd2-9e86-31962b38f06a |  | note | VERIFYING DOCUMENTS: This separable package Pit installation Lots
date | 4d401518-bac6-595a-8cb9-8b2075a0a0e1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Pipes - installation
label | f89147d9-659e-5ce7-936c-464e3364b246 |  | note | REFERENCE: IFC Drawings VR 701, VR 705
label | 8b4d53cd-d524-52ea-8a6c-e3481c5c9a95 |  | note | – – – – – – – – – – – – – – – – –
label | f0eb49cb-056b-5a11-9ac8-1b6c44223d30 |  | note | ACCEPTANCE CRITERIA: All the pipe runs for this separable package are installed and respecting Lots are closed
label | a93f3dc9-023a-5a50-8aad-4ba635bf86e4 |  | note | – – – – – – – – – – – – – – – – –
label | 66f20e8b-6620-52fe-9b3a-0ee2f7d1dc26 |  | note | METHOD: Document review
label | 246b30d4-6242-5690-a05d-39ef7fac2d05 |  | note | – – – – – – – – – – – – – – – – –
label | 2edf073d-9dd4-5035-a4b6-f3b09bc4306a |  | note | FREQUENCY: Each drainage separable package
label | 648f5186-d1f5-5fcf-87b9-f755bc55eb4c |  | note | – – – – – – – – – – – – – – – – –
label | 853c587b-0e5f-501d-bd12-c36625cf1ea7 |  | note | CATEGORY: IP
label | 641f36e7-8700-50da-b7f4-cd27decb8558 |  | note | – – – – – – – – – – – – – – – – –
label | 19fa22ea-70c4-5835-8b87-00de22a0fb2d |  | note | RESPONSIBILITY: PE
label | 8e9d7b94-42c8-544a-bc98-22fa43b76ef1 |  | note | – – – – – – – – – – – – – – – – –
label | c2e42f49-0418-58ec-8c5f-79389923bc1b |  | note | VERIFYING DOCUMENTS: This separable package Pipe installation Lots
date | 1a00d89b-9068-5e8f-b0d6-934cf041a6e2 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | 1b6ad945-a41a-5b48-ada9-8ad377ce88df |  | note | REFERENCE: Section 701.28, Section 701.30
label | 318b0ad6-cb2b-5fdb-a7e3-93ecdb2fc257 |  | note | – – – – – – – – – – – – – – – – –
label | 3a491b3a-7c10-58cd-9f1a-601398ba2450 |  | note | ACCEPTANCE CRITERIA: All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | cd8f5565-dd59-579d-bc44-15af2c3479b0 |  | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 6c8e4b71-2b1a-514e-ae98-1513ffa9d57d |  | note | – – – – – – – – – – – – – – – – –
label | 270bed7b-9f46-5ede-a066-7ec75ec2ac1e |  | note | METHOD: Record Review
label | 928e703a-5c66-56de-8fc9-a93f75a6b40b |  | note | – – – – – – – – – – – – – – – – –
label | 25b07617-9361-5278-a036-7c0422a1c13e |  | note | FREQUENCY: Each lot
label | ba8b2bf9-7c86-5f7a-9df2-cc0771c0e532 |  | note | – – – – – – – – – – – – – – – – –
label | 7e8e6595-b031-5f41-9ae0-23d43b3dfb12 |  | note | CATEGORY: HP
label | a58b2f62-8857-5003-a41a-746154efe5ed |  | note | – – – – – – – – – – – – – – – – –
label | 1476c701-f18e-5ef5-a013-9a7cf4551b9c |  | note | RESPONSIBILITY: Nominated Authority
label | 7a4b29b0-893d-553e-8817-7429c8eaad62 |  | note | – – – – – – – – – – – – – – – – –
label | 2efa0526-7b40-544c-84e5-2f352086e533 |  | note | VERIFYING DOCUMENTS: This ITP, CCTV Reports
date | b12a26b6-a181-5c44-8f95-c09665e93f71 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 As Built Survey
label | bd213bef-fc55-5b92-ade4-1f67d16a3a7f |  | note | REFERENCE: Section 701.10
label | cd6082bd-f164-50b8-94ce-9f70ecc9ce2e |  | note | – – – – – – – – – – – – – – – – –
label | b62150c6-3f68-5827-b19e-37ef7281c1ec |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | aa98b22a-8b51-5454-9174-8f1f48d12260 |  | note | – – – – – – – – – – – – – – – – –
label | de6e57a5-82fc-5c1b-a690-e5229fafc98a |  | note | METHOD: Document Review
label | 05085290-30ab-5d1a-9525-c3f849aa23bf |  | note | – – – – – – – – – – – – – – – – –
label | 1f91f13f-cd77-5510-831c-d256e1f907ba |  | note | FREQUENCY: Each lot
label | e8821cf2-2f50-51e4-9d47-07a8d61b341b |  | note | – – – – – – – – – – – – – – – – –
label | 462cf1ab-7750-5e00-8c2e-fd390b459ded |  | note | CATEGORY: IP
label | 3dde512c-3579-5237-ba16-03817597cb34 |  | note | – – – – – – – – – – – – – – – – –
label | c9f8933c-466c-531a-ab80-0ca2f63e3f0a |  | note | RESPONSIBILITY: SE
label | 30b430f1-7f61-5b39-80ab-64cb3acc9762 |  | note | – – – – – – – – – – – – – – – – –
label | 329f3b49-a3d8-5fd1-a3ab-070bb537bb9d |  | note | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
date | 545daaa6-39f1-5f85-ac02-9f3afb19f8c8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | f6e3e40e-399c-5a93-b266-b81e8d0fe6fd |  | note | REFERENCE: MRPA Quality Management Plan
label | 15d318c3-3651-5424-872c-c003ff90eeaf |  | note | – – – – – – – – – – – – – – – – –
label | 46a0955c-8cb5-5a29-8a28-90e064efc042 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 29fe7c1e-9b7c-5fdc-9449-edb0df709ebf |  | note | – – – – – – – – – – – – – – – – –
label | ce9fac5b-e223-5bd2-9c6a-32d8caf3c7c4 |  | note | METHOD: Document Review
label | c2f8073c-dbef-5ee9-a92a-701e1ccb4760 |  | note | – – – – – – – – – – – – – – – – –
label | 3abcd0ec-bfb9-5a7f-906f-d8c790e2420e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | cd59348f-85a9-53a7-896e-5466d716fb97 |  | note | – – – – – – – – – – – – – – – – –
label | cabfd1e2-1fe4-5e71-8955-3eadf4cd1a74 |  | note | CATEGORY: HP*
label | 8d253613-f7d0-51ac-9cec-5b44abd65571 |  | note | – – – – – – – – – – – – – – – – –
label | fe6c529a-5f94-5261-8b99-9e03beffacda |  | note | RESPONSIBILITY: PE
label | e226c724-6c3b-5a2f-bb0e-a05aa513241a |  | note | – – – – – – – – – – – – – – – – –
label | 0359a043-c611-5ac8-8da8-0b35d565f8d0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 01749e93-6fe2-5c53-88e4-1789a453f466 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Repairs to Damaged Pipes
label | 89cf432a-036a-5b68-935e-e2d5badb5d26 |  | note | REFERENCE: Section 701.31
label | 5b996d2c-e8a5-5605-bbeb-110e7a066bd9 |  | note | – – – – – – – – – – – – – – – – –
label | f40bd7bc-e39b-586a-b2ac-d87a0283ac0f |  | note | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | 2aa06115-82d7-56a2-b343-4a90349096c2 |  | note | ○ cracks wider than 0.5 mm
label | 986cd197-e8f6-5a1a-8bf0-fcca6db92d4f |  | note | ○ spalling of concrete
label | 3dd8cac0-368b-590a-94e9-3e8def388852 |  | note | ○ exposed reinforcement
label | dd1014d9-7e32-50d2-81c7-85689c60ef5d |  | note | ○ joints that are not fully engaged.
label | 880ff1f2-3b37-5ea3-b0c9-bfee9767e0ef |  | note | Any pipes with defects greater than the following limits shall be removed and replaced:
label | 04bb313f-1075-57c6-bb08-50c9c6e50403 |  | note | ○ longitudinal cracks greater than 2 mm
label | 8221aea6-876e-5adf-8d3a-52c8b7e57a14 |  | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | cab96df1-a09e-53dd-a352-c1c0170a5dc6 |  | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | e5e3ac21-5b46-568a-b3e0-75ecb3dc32bc |  | note | ○ penetrations with area greater than 400 mm2
label | 30a6c14c-2134-54f8-ba95-1cada10f6fc9 |  | note | ○ pipe joints that are separated.
label | 727ae7b0-3b45-54cc-abe7-42cf73f4f7c6 |  | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | 2028f1e8-22e6-55d6-8643-263514e87144 |  | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | c82ed60d-4417-5225-ba40-35844157e9d8 |  | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | 782d8c0f-c326-54e0-af09-9ae206b4f0e7 |  | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | cfd31a4f-aec2-51b4-9913-f09673fb79ea |  | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | e781f43f-dc88-5fc2-a274-155a32c4f720 |  | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 4ba8a41c-c5c0-54c5-9b68-1deb708b4c0d |  | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | 24ae10eb-a5f9-58cd-b7c4-b90666bf9368 |  | note | – – – – – – – – – – – – – – – – –
label | c8a68447-cecd-5c87-bbca-afa416a06647 |  | note | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | 22771e1b-b1c0-5270-884d-604e07c9fd4f |  | note | – – – – – – – – – – – – – – – – –
label | cce2e277-fe64-5c87-9abd-b84e42270cab |  | note | FREQUENCY: Each lot
label | 2ad05663-ee80-58fb-a4b8-cdd72dd9d3b7 |  | note | – – – – – – – – – – – – – – – – –
label | 7ad42deb-f3fb-5e8f-ab29-70d7b25787c1 |  | note | CATEGORY: HP
label | 7a55fe5b-42bc-59a5-bb25-bbcbe7fcb61e |  | note | – – – – – – – – – – – – – – – – –
label | 1a3c1bbd-29f9-5734-964b-b5b5a6ef0806 |  | note | RESPONSIBILITY: Nominated Authority
label | e250f340-c7c0-5ee6-857b-3c0823281ec3 |  | note | – – – – – – – – – – – – – – – – –
label | f5ba17e1-54d9-575e-bb2a-27e2a13edb20 |  | note | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | 9c22fa31-6549-529b-87f3-369941c5d75c |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | e319ba46-cf6c-5bd3-b09f-69050c010dd6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 72e643a2-d40e-5df9-a562-7ddaa7cb4403 |  | textbox | Name:
text | bad3487d-a8f4-5566-927e-839e739bb50b |  | textbox | Position:
date | 3214e678-a7f2-59ff-bd7d-22082e257665 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | CHK-014-CIV-SSB-Precast Material Inspection | itp |  |  |  | Yes | CHK-014-CIV-SSB-Precast Material Inspection Rev 1 | ec7a57c5-8c28-4e1f-970b-69932a9645a9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 92a805bb-368b-5734-ab7a-741b8b56c0c4 |  | note | Document Title: CHK-014-CIV-SSB-Precast Material Inspection
label | 0ec0c184-43a2-5ab4-b5f7-27980645788e |  | note | ITP Description: SSB -Precast Material Inspection
label | d4b43c5d-b498-50dc-a547-2ad74406bef6 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c741d6a1-3b5e-590b-a10c-0343d702a64a |  | note | Discipline (e.g. CIV/STR/RAIL): 014-CIV
label | cb66a994-ae78-5ead-8524-364e7cceb38b |  | note | Revision Number: 1
label | 31f24d4a-2547-5b1a-84ba-6de3ceae648f |  | note | Revision Date: 23/04/2024
label | c294256f-29e7-5a7a-8348-7cadcdede08a |  | note | ITP created by: Dan O'Brien
label | 799a8b44-3db4-5d14-af97-aa508adcd0a6 |  | note | ITP approved for use by: Victor Mira
checkpoint-status |  |  | checkpoint | 1. Delivery Details
label | a0982009-6d08-5a13-8d14-153751be74fb |  | note | ACCEPTANCE CRITERIA:
text | b164f3d6-5131-56d0-9ab8-c6c623af1d8f |  | textbox | Enter: Delivery Docket Number:
text | 586bbf8b-cabe-5a46-a8bd-e41d4e936fab |  | textbox | Enter: Delivery Date:
text | d14e9af6-16e9-5093-a4a8-44d7242b26cb |  | textbox | Enter:Element ID (s):
label | 61106c2f-a5cd-5ea8-b313-b67ec5fe920a |  | note | Attach: Delivery Docket and packaging Slip
label | 6f33cd9a-e3f7-5815-97c3-3fd0a94bdd6f |  | note | – – – – – – – – – – – – – – – – –
label | 72667d66-a31e-591e-bd7c-1dc85e0284a3 |  | note | METHOD: Document Review, Visual
label | 98b91db8-e8fe-576d-891e-7b1a52d73c5f |  | note | – – – – – – – – – – – – – – – – –
label | f584f39b-56e7-52b6-b7e4-a725976e165a |  | note | FREQUENCY: Each Delivery
label | 638fab0f-bf99-5c7b-b551-5522a930eb99 |  | note | – – – – – – – – – – – – – – – – –
label | d954e536-a88b-5fbb-a046-aa55d4d929b7 |  | note | CATEGORY: IP
label | 2b005d39-f251-5f47-8267-a055d3c93279 |  | note | – – – – – – – – – – – – – – – – –
label | 7ebd7dc5-385e-572c-ae4e-33ee17eb35c8 |  | note | RESPONSIBILITY: PE/SE
label | f25ef1a8-0ec9-5b60-bc9a-4ac8f223bcef |  | note | – – – – – – – – – – – – – – – – –
label | 6b94cef5-c02f-5169-9d1c-c6ef7e672c32 |  | note | VERIFYING DOCUMENTS: This Checklist
date | c210fa47-212e-5cf2-a699-61565e039392 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2. Packaging Inspection-Quantity
label | 73e5843a-5d10-5f8d-beb7-a93d49f38818 |  | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | cd2f29b5-497d-5ff3-87b8-352a0ce8a7e7 |  | note | – – – – – – – – – – – – – – – – –
label | c7026021-aa11-508e-b977-546be57d5b59 |  | note | METHOD: Visual
label | 974d1bf8-3428-5945-8ef8-f54240bc186b |  | note | – – – – – – – – – – – – – – – – –
label | 18544677-25cd-57b4-b8fa-4bc2d0f63767 |  | note | FREQUENCY: Each Delivery
label | e7f081bd-f9d9-52ea-b919-6bd467dd0691 |  | note | – – – – – – – – – – – – – – – – –
label | 9afdc1bc-bf15-5ef9-907e-ea89642ac97e |  | note | CATEGORY: IP
label | 52373539-89d0-5522-9eed-a9a59f580d3c |  | note | – – – – – – – – – – – – – – – – –
label | e3c5c16c-1764-5b79-875a-33c39bbe72f8 |  | note | RESPONSIBILITY: PE/SE
label | 2541c0f6-42ef-57d6-b936-0ef76f51c153 |  | note | – – – – – – – – – – – – – – – – –
label | 3e7b542c-fb75-5e53-bf11-a09c43faea62 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 7d476000-8cb4-5c51-b42f-4710443b532a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3. Packaging Inspection-Delivery Contents
label | 1c65cf4e-f97e-500f-98b6-ac019bf9c301 |  | note | ACCEPTANCE CRITERIA: Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
label | b064da43-3b9b-5842-b768-5af765fcb1ff |  | note | – – – – – – – – – – – – – – – – –
label | 38cb9493-c494-50fc-b818-c2da7155144f |  | note | METHOD: Document Review, Visual
label | 3d7eeb5e-0c81-5855-81ff-5f2e25f4e399 |  | note | – – – – – – – – – – – – – – – – –
label | a6467116-7865-5232-aacf-12deadc782bb |  | note | FREQUENCY: Each Delivery
label | 3cce4219-eb12-50c6-a5cc-62c92a05280c |  | note | – – – – – – – – – – – – – – – – –
label | d291b333-1c8f-53e4-a1fe-8ebdbe0463f3 |  | note | CATEGORY: IP
label | 27423cde-f42a-548c-bb2c-9e52d18c01b0 |  | note | – – – – – – – – – – – – – – – – –
label | 1d9df1c5-f6a3-5d9d-97a2-c0722fcbc776 |  | note | RESPONSIBILITY: PE/SE
label | 87842f4d-284c-5b1b-ba36-cedeb6890963 |  | note | – – – – – – – – – – – – – – – – –
label | ece48e5f-41a0-59ca-901a-7ad42fa4314d |  | note | VERIFYING DOCUMENTS: This Checklist
date | f03ffb02-bc10-5d1f-b834-ee37c9881a96 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4. Packaging Inspection-Birth Certificate
label | c16d5e0c-4346-5019-b1f1-7b627845b0da |  | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
label | 93e4b8e7-3702-5317-b763-2cf1a8f36425 |  | note | ○ Precast components are to be marked on the birth certificate.
label | 604fcfcd-7896-58e8-a6db-71ae4fd23e2b |  | note | ○ Cast date and lot are to be marked on the birth certificate.
label | bd9c80f8-3ec0-5fc9-98da-18bd398dcdcd |  | note | – – – – – – – – – – – – – – – – –
label | 0bae3046-f529-5f6f-94d6-c80928b2f541 |  | note | METHOD: Document Review
label | cf481477-bdeb-5e52-8608-a9a65659de15 |  | note | – – – – – – – – – – – – – – – – –
label | 1c36c791-1982-5ec6-a63d-0e60334de40e |  | note | FREQUENCY: Each Precast item
label | 49368e55-451a-5c0c-bc53-d80f6b7cfec4 |  | note | – – – – – – – – – – – – – – – – –
label | a6858150-286d-575b-b0e0-d3723124a518 |  | note | CATEGORY: IP
label | 962a0105-ef10-5d0e-878f-5b5452307c39 |  | note | – – – – – – – – – – – – – – – – –
label | 0fc923ed-daab-5a41-885b-090b2b96d97d |  | note | RESPONSIBILITY: PE/SE
label | c3241fc7-0ae6-5896-996f-464111b87dc9 |  | note | – – – – – – – – – – – – – – – – –
label | c2846f2f-1138-5716-8b86-30c4bfe55c12 |  | note | VERIFYING DOCUMENTS: This Checklist
date | eba88c58-6db4-56d9-b6c5-57b4c798967e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5. Packaging Inspection-Transport
label | 251531ed-38c7-5ed7-bd4a-07f8651ab4c3 |  | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
label | 06acdaa7-5d84-5998-8df4-44cff122a9b4 |  | note | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
label | c36b1db8-643a-5393-9ff7-3141e5934216 |  | note | – – – – – – – – – – – – – – – – –
label | 05375baf-07a8-56ec-82e4-dcd5a59680c5 |  | note | METHOD: Visual
label | 154c49a9-36e1-5615-865b-ed645e6ff07c |  | note | – – – – – – – – – – – – – – – – –
label | 4194a83e-7e32-5537-837b-b36f75d7849d |  | note | FREQUENCY: Each Precast item
label | b65e7bea-054f-527f-9e80-57e1ea5b2c3c |  | note | – – – – – – – – – – – – – – – – –
label | 67ed73f0-6881-549f-9a6e-39110ca4e67f |  | note | CATEGORY: IP
label | e437f135-2d14-5fad-99a9-f3539499e293 |  | note | – – – – – – – – – – – – – – – – –
label | 307167cc-48f3-5e51-aa9c-5a844a831487 |  | note | RESPONSIBILITY: PE/SE
label | c565a63b-7308-576f-915c-61650684728f |  | note | – – – – – – – – – – – – – – – – –
label | 8c47d16f-fb3b-5785-bfb9-9dfdafe95f3d |  | note | VERIFYING DOCUMENTS: This Checklist
date | 24e92d4b-debb-5d78-b55f-1fccf00b4185 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6. Pre-Lift Inspection-Transport
label | 0bcc6c9f-8152-54cc-8617-81d36ffef173 |  | note | ACCEPTANCE CRITERIA: Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
label | 63c7577d-fb6b-5b45-868c-946ecea9539a |  | note | – – – – – – – – – – – – – – – – –
label | 811eb581-4f3d-5911-9e53-a3b5906642e1 |  | note | METHOD: Visual
label | bf4ea95b-264e-5d74-a8bf-1b5308a98614 |  | note | – – – – – – – – – – – – – – – – –
label | 13b487f5-8f71-5575-813a-f540c1a16e7b |  | note | FREQUENCY: Each Precast item
label | 3ecc5b46-917a-5ad4-b62d-718cfcfa2e20 |  | note | – – – – – – – – – – – – – – – – –
label | f7acedff-9eb1-50ab-85e0-8e0df491777f |  | note | CATEGORY: IP
label | ea61a3d9-fff3-55af-b064-ca3fd0eca138 |  | note | – – – – – – – – – – – – – – – – –
label | 877d3d8e-5e94-5cf2-9c9c-3682131ad067 |  | note | RESPONSIBILITY: PE/SE
label | 2e6049f6-ef6c-5528-acc4-810862c5595d |  | note | – – – – – – – – – – – – – – – – –
label | 9e2bb213-64ad-50f7-8f46-455de4b0f80e |  | note | VERIFYING DOCUMENTS: This Checklist
date | 61575d96-3927-543b-8e2b-abdd996b5732 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 7. Fault IDs:
label | ba079847-8998-5e82-9ef5-543c1903fbfd |  | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
label | d53f67ba-d5b8-5390-87b9-7803309bb3b9 |  | note | 1 - Identification markings match the panel type
label | c81e3bb5-21e8-59a9-ab3a-154c16675836 |  | note | 2 - Panels fabricated as per drawings
label | 4cc44dce-2f0e-5cd3-9e2d-05de32f8c03d |  | note | 3 - Cracks
label | 3a236fcc-b3f3-51c1-9849-6c3676be1030 |  | note | 4 - Spalling/Damage to concrete surface
label | 5b7f7ea9-d3e4-5abe-acfc-fd7508335074 |  | note | 5 - Exposed Reinforcement
label | c0a1c3ee-fb8c-5d12-b666-8ae957340592 |  | note | 6 - Damage to Anti-Graffiti coating
label | 7422cfea-3e22-5662-9152-541790344940 |  | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
label | da11e5cf-8cbb-541f-a9ed-8ceb9f701303 |  | note | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
date | ea1884f3-9636-5b60-9769-3eb5cb506874 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Check for Faults - 1
label | d2397547-9e48-5646-a949-23e9d33712fa |  | note | REFERENCE: Item 7 on this Checklist
label | 57bae06c-bc20-5d92-b061-e6868b6da06d |  | note | – – – – – – – – – – – – – – – – –
label | 2cafbb79-a8ee-5376-a5b7-9b3e3644bb10 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 1f3a4068-6488-5c7e-a0dc-a26e71547c81 |  | textbox | Enter: Panel Identification:
text | 30283c25-d82d-591f-8427-f7a76c7a0c5a |  | textbox | Enter: Quantity:
text | a977b8d4-5016-537d-9f14-bb99f62a4109 |  | textbox | Enter: Fault ID if any:
label | 9a13a205-3325-5002-a7a2-f371c45f990d |  | note | – – – – – – – – – – – – – – – – –
label | 4b781d2e-ea5c-5f79-9dfe-2d3338fd62c4 |  | note | METHOD: Visual, Measure
label | f2ed32cf-a815-5b78-a882-12c57e2df343 |  | note | – – – – – – – – – – – – – – – – –
label | e3fbd2b0-c3ea-5327-9304-4e09348a5e57 |  | note | FREQUENCY: Each precast type delivered
label | 58e214da-5314-53b9-9ff8-0684c99cd77f |  | note | – – – – – – – – – – – – – – – – –
label | c7e3b3e1-2428-5f69-a2e5-515d2574d0c6 |  | note | CATEGORY: IP
label | ecfa34b8-e4fa-5754-8688-a08e557a55bc |  | note | – – – – – – – – – – – – – – – – –
label | da4844ab-7c1b-51d1-a80e-459ca4c0afb8 |  | note | RESPONSIBILITY: PE/SE
label | 2e8e6bea-3a3a-5bf0-93a9-90deaaff2d07 |  | note | – – – – – – – – – – – – – – – – –
label | 1de0f2cc-4fc8-5afe-8b53-a82350fc6920 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 6c5c9b75-fb7c-5ed2-9b9a-a9b708191ba8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Check for Faults - 2
label | 282331ee-abc7-53ee-b000-89580a2d436a |  | note | REFERENCE: Item 7 on this Checklist
label | c357c0ef-c532-50de-829c-ef85a82fda1e |  | note | – – – – – – – – – – – – – – – – –
label | 84086150-ebc0-5bb8-8e7a-d2a15529f515 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 3b1caca2-1cb6-5911-bc11-96df8bff205c |  | textbox | Enter: Identification:
text | 5bacf16f-af4e-564a-89f1-02980fffec6b |  | textbox | Enter: Quantity:
text | cbe721b1-2ba4-5b7b-b8a5-a4e2f22fdcfa |  | textbox | Enter: Fault ID if any:
label | b7c57bf1-e488-53ba-9918-a2fc1a9be53d |  | note | – – – – – – – – – – – – – – – – –
label | b40085b5-34cb-5d37-955d-6141727e3adb |  | note | METHOD: Visual, Measure
label | 4b27600f-e826-5cdc-b4d9-1e7647899b30 |  | note | – – – – – – – – – – – – – – – – –
label | a4f54e6c-ad88-5389-aaf6-f09770c5b64a |  | note | FREQUENCY: Each precast type delivered
label | e0a9c2fa-d385-5d55-84d4-4f787d2c434e |  | note | – – – – – – – – – – – – – – – – –
label | d115925b-d75f-5ac0-8f4a-44cba931b075 |  | note | CATEGORY: IP
label | bcb0e471-b040-57e0-a7b5-5347b6f15b44 |  | note | – – – – – – – – – – – – – – – – –
label | affdabe9-e2cd-5535-ad48-0d6ccb831a18 |  | note | RESPONSIBILITY: PE/SE
label | 2275d6c0-ffdb-568b-9945-cff6b358c7a9 |  | note | – – – – – – – – – – – – – – – – –
label | 15a6acb6-672a-5847-b362-7b69a7770321 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 19575ab6-ac46-5030-afd8-dacc611e5b44 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Check for Faults - 3
label | 48c1bc93-4f6a-51d4-a7f2-a1ebc19a8d60 |  | note | REFERENCE: Item 7 on this Checklist
label | 855f7b60-1c4e-543b-bc70-89d52c926d06 |  | note | – – – – – – – – – – – – – – – – –
label | 552163da-d5cc-53df-a1d4-373a4e8dfc33 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 3f02e9fb-28bd-5f3e-a9fc-8c5ea59bc5a7 |  | textbox | Enter: Identification:
text | 7b098a5b-b295-5ddd-9be2-cd4355679add |  | textbox | Enter: Quantity:
text | d5a7ee5c-f4e6-54bc-988a-febe17f16f1a |  | textbox | Enter: Fault ID if any:
label | 818d33e5-fc2b-575b-913a-01b265b2adb0 |  | note | – – – – – – – – – – – – – – – – –
label | 9fa3b8e7-9939-5fb4-9dbb-6c0c2158f821 |  | note | METHOD: Visual, Measure
label | 753663e7-b484-5a45-ab4e-82d1cd529070 |  | note | – – – – – – – – – – – – – – – – –
label | 19b41c01-f719-5f32-9292-b224ba3ac48b |  | note | FREQUENCY: Each precast type delivered
label | 42ddb35d-d282-5df3-a095-3def173d4858 |  | note | – – – – – – – – – – – – – – – – –
label | 8fb719ed-7bd8-5b2a-9814-646f2df3b38e |  | note | CATEGORY: IP
label | 7f8c65ef-ba3b-54e6-9eaf-b0474562be6e |  | note | – – – – – – – – – – – – – – – – –
label | b366b2f7-65fa-51f8-8dce-ff1489e5de54 |  | note | RESPONSIBILITY: PE/SE
label | ac03f430-ab00-5d7a-a296-fbd3ffae7e7a |  | note | – – – – – – – – – – – – – – – – –
label | 0d3a8f5b-2b21-5a73-8ce3-0bb3845e5b34 |  | note | VERIFYING DOCUMENTS: This Checklist
date | a6a05642-2f68-5f38-8fe8-88b3005329e2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Check for Faults - 4
label | 2e8e3baa-1740-539f-96f0-221055129bce |  | note | REFERENCE: Item 7 on this Checklist
label | 362a1279-8c4b-561f-b4c8-4c76393ffda1 |  | note | – – – – – – – – – – – – – – – – –
label | 221ea5be-3f88-5bfb-bbcd-2881fb9c1544 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 8b48bf88-bd64-5d77-ab94-c09d3237ae60 |  | textbox | Enter: Identification:
text | 4556840a-95ff-5718-b2e4-3bc2d0a678ed |  | textbox | Enter: Quantity:
text | b55a7f7e-45e3-5c3f-bacf-4fc4a7fae502 |  | textbox | Enter: Fault ID if any:
label | 65132cee-282e-5a47-ad37-9f03c1c8a2c1 |  | note | – – – – – – – – – – – – – – – – –
label | ee0a4063-f9ff-51e1-bab7-00c19923786c |  | note | METHOD: Visual, Measure
label | 68963492-5a72-55d5-88b0-0b144f242e94 |  | note | – – – – – – – – – – – – – – – – –
label | 07bc638c-13fe-55e9-a7a1-de34b0e4d4dc |  | note | FREQUENCY: Each precast type delivered
label | a29a75ed-c957-54a5-a133-80763fd1f98a |  | note | – – – – – – – – – – – – – – – – –
label | 6016b514-48f2-5fbb-9176-e9b76f87474b |  | note | CATEGORY: IP
label | f690b14a-bfb0-54ba-a0d5-f25cf80b4fb4 |  | note | – – – – – – – – – – – – – – – – –
label | 3e344112-2460-54cc-af45-817ca7a7f8a5 |  | note | RESPONSIBILITY: PE/SE
label | 48b8bb2e-69a9-5e6c-80a1-6c5557c7250d |  | note | – – – – – – – – – – – – – – – – –
label | c3599c0f-4cf0-517c-b208-fe55fe897b22 |  | note | VERIFYING DOCUMENTS: This Checklist
date | 4fe0c6ab-a6dc-54a9-9516-dd07670807f2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Check for Faults - 5
label | 0622a3db-8770-5393-af77-cc1280aa7391 |  | note | REFERENCE: Item 7 on this Checklist
label | 300215ea-c326-57b8-a3b8-02878f6bc929 |  | note | – – – – – – – – – – – – – – – – –
label | 6f6bc281-cb81-54b4-ab0d-76b6e3d00ae0 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | 8d9d5076-f53b-5bbd-ba16-b32f77a8b4a3 |  | textbox | Enter: Identification:
text | ee93b2fd-95bf-58c1-b0c1-3e2ca5444494 |  | textbox | Enter: Quantity:
text | 9a415e8d-84b7-58d3-8076-5284dc684b32 |  | textbox | Enter: Fault ID if any:
label | ca6c6904-f5a5-5139-8801-5b51567b21f4 |  | note | – – – – – – – – – – – – – – – – –
label | 09f48556-44c8-5f44-9c13-c0cff8b64d4a |  | note | METHOD: Visual, Measure
label | 263d1286-abcd-5a69-a9cf-a8bbc8ec6d37 |  | note | – – – – – – – – – – – – – – – – –
label | 81e59016-5c56-5869-887c-a16e8e47ba23 |  | note | FREQUENCY: Each precast type delivered
label | ee58e7a8-b433-5316-85ce-f478ab02b086 |  | note | – – – – – – – – – – – – – – – – –
label | 3987bb14-8bfb-5f11-a98c-501f2bcd809e |  | note | CATEGORY: IP
label | 4104254f-d22b-5b31-8027-07dd4669dfe4 |  | note | – – – – – – – – – – – – – – – – –
label | 30846f39-df45-5d02-a9c6-59b731bf1163 |  | note | RESPONSIBILITY: PE/SE
label | f9b2494d-ba68-5cb4-a69a-27d017fa7891 |  | note | – – – – – – – – – – – – – – – – –
label | 69285cff-9999-50db-9050-67395daf9e8f |  | note | VERIFYING DOCUMENTS: This Checklist
date | b49199d5-c08e-5e08-b6b0-fb02091a709e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 8. Check for Faults - 6
label | ceae903e-de4f-5c91-a626-8276764b0931 |  | note | REFERENCE: Item 7 on this Checklist
label | dcc9d65b-e255-5443-a0f3-0e19efd55746 |  | note | – – – – – – – – – – – – – – – – –
label | ac4ed648-c3b3-5724-8bb6-e9773b181747 |  | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
text | c1e79155-d00c-54f7-b08a-c3f466803715 |  | textbox | Enter: Identification:
text | 83e72d28-9ba8-5dec-a0ce-054fc364c19c |  | textbox | Enter: Quantity:
text | bae17b5d-bac3-5ed2-afad-71853e3ac6c3 |  | textbox | Enter: Fault ID if any:
label | 44159820-b083-5e8b-aaac-80afbb265080 |  | note | – – – – – – – – – – – – – – – – –
label | c10854c2-86be-5589-98a6-7bc9235f91dd |  | note | METHOD: Visual, Measure
label | 16927016-a11b-53de-a7e5-e4e65ddeb91f |  | note | – – – – – – – – – – – – – – – – –
label | fd0dfa1d-ffc5-5f2e-af12-5b67b66a709e |  | note | FREQUENCY: Each precast type delivered
label | c00ce30a-0a4e-5471-9aa1-6b4db3612861 |  | note | – – – – – – – – – – – – – – – – –
label | 6b11217d-bc58-5991-ada3-acc5def2d3cc |  | note | CATEGORY: IP
label | ca9af56e-c6a7-5e8e-822c-8689ba3c1ef1 |  | note | – – – – – – – – – – – – – – – – –
label | a8bac74d-7b74-52e0-8e2b-3c7291b693eb |  | note | RESPONSIBILITY: PE/SE
label | e054950b-bdc9-5c36-9d69-90b9cb774fdb |  | note | – – – – – – – – – – – – – – – – –
label | 23f7b486-c66c-57ae-b045-3425d408e11c |  | note | VERIFYING DOCUMENTS: This Checklist
date | 2f93e750-48d9-55b5-935f-52710cc57f3a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 749348ee-5917-584d-950b-dd3478501043 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | f9cc0039-4b1e-5002-915c-3a6243a33856 |  | textbox | Name:
text | 22766b4a-2016-5fb1-a95e-ae2a03dcd4cd |  | textbox | Position:
date | f1c7190c-34b3-5cd0-bbaf-26470fdf1105 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-108-CIV-SSB-Pile cap construction | itp |  |  |  | Yes | ITP-108-STR-SSB-PILE CAP CONSTRUCTION REV 0 | f914bbe2-ca9a-489c-8d3f-3a96a23a3107
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 75ad334e-f5c3-5ad1-b32b-f0f302a757e4 |  | note | Document Title: ITP-108-CIV-SSB-Pile cap construction
label | a1eac5be-aff0-58f1-9281-835d0cc99aab |  | note | ITP Description: SSB-Pile cap construction
label | 9d2e0ed2-e245-58f7-aff3-b1580222a1a8 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 00aff2f5-1113-5292-85ac-aa14ff967b6d |  | note | Discipline (e.g. CIV/STR/RAIL): 108-CIV
label | 1c8ff8d5-ea80-5c40-9149-d096cbfc89b8 |  | note | Revision Number: 0
label | 9a30eff1-213d-5dff-91ca-e9451a2ded1e |  | note | Revision Date: 22/11/2023
label | 9216fa02-b12c-5cff-9463-c3b1d37b3332 |  | note | ITP created by: Iyasu Enoro
label | 196569bb-798a-5e29-b6a0-de08145ff6ef |  | note | ITP approved for use by: Victor Mira
label | 57087e35-7009-5d0f-870c-f8d19158b348 |  | note | 1.1 Non Dependent
label | ce2b26eb-eb19-51dc-a655-08cc1e69b1dd |  | note | Reference: VicRoads Section 602 October 2007
label | dc213dbb-1b32-5e71-b1eb-79ef7f204477 |  | note | 1.2 Non Dependent
label | b628ffd8-1578-5914-9226-76ab775e48e5 |  | note | Reference: VicRoads Section 610 February 2020
label | 0f88d43e-8140-5f13-80ad-5819c1f5ee97 |  | note | 1.3 Non Dependent
label | 866312a1-af54-5b5d-ad84-91744cbd4311 |  | note | Reference: VicRoads Section 611 November 2018
label | 2ebfdc2e-174b-59f1-a8b1-5d42e831c6a9 |  | note | 1.4 Non Dependent
label | 774d0111-a0ea-56f2-9238-100730d47b06 |  | note | Reference: VicRoads Section 614 June 2017
label | e03e1a39-cf37-59c9-8541-1f0b62ff9a45 |  | note | 1.5 Non Dependent
label | 67c98bcc-dbf8-560f-aaa2-7bfb7fe23ae1 |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | eb13fda3-99f5-5119-8b41-cf565cc20114 |  | note | REFERENCE: 610.07 Table 610.071 IFC Drawings
label | 964aaaab-cab1-582b-8ccb-72a57df1e78a |  | note | – – – – – – – – – – – – – – – – –
label | bed43440-48ff-59f0-a0c0-1c627a2c4486 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 9fa546e5-9118-5d58-98ec-e7eb317e6c4f |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 5a93a7f1-66ab-588d-9db1-035d9628a9c8 |  | textbox | Enter: Teambinder Material Approval number
label | 9986f40d-2eb5-590b-bdc9-f2c868cc9c54 |  | note | – – – – – – – – – – – – – – – – –
label | c700d991-b989-56de-be58-4aa70808ee0e |  | note | METHOD: Document Review
label | c80eaef6-3362-5a66-bba5-39ed98380a6c |  | note | – – – – – – – – – – – – – – – – –
label | 6ae2976e-6ae9-5780-aa2d-a48ea37ed7f9 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 0e9ade17-cf8f-5eb7-b42d-5c50e0e28900 |  | note | – – – – – – – – – – – – – – – – –
label | c205df14-335a-5f8e-9415-b8ebf53e35fb |  | note | CATEGORY: HP
label | 8ddf48e5-bec2-5cfe-88d9-7ca413b23e85 |  | note | – – – – – – – – – – – – – – – – –
label | 897b8c64-bbd8-5f11-be70-8868347dbbfd |  | note | RESPONSIBILITY: Nominated Authority
label | 1dc6c592-1a52-58cf-bd88-d6870eb9cca2 |  | note | – – – – – – – – – – – – – – – – –
label | dbc4c161-6487-59ed-a6cd-f623633e1faf |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 82e75caf-44ee-575d-9265-8e177ab4430f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | a25203ed-bfa4-5833-9200-023b21f3baf4 |  | note | REFERENCE: 611.05 (a)
label | 99aca7ac-f54f-571e-b22c-ed6431a98da2 |  | note | – – – – – – – – – – – – – – – – –
label | 84eea4c7-c8f0-52ea-8c82-554e10efe740 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 12c50047-eac9-5598-bab8-56539fc79cc8 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 9e5b6d94-93be-55bf-8334-5492b19959d8 |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 3144bef0-71a5-56c0-9122-27562e8e0357 |  | note | – – – – – – – – – – – – – – – – –
label | 3a4f7328-46e9-5b54-8b81-cc89199f6333 |  | note | METHOD: Document Review
label | d5f86f8f-12e3-5a0a-87a0-18fc1da0c583 |  | note | – – – – – – – – – – – – – – – – –
label | 9eb5531f-4a51-5231-9523-974079f38b22 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 155dcc4f-f445-5004-9bb4-d15df36e2281 |  | note | – – – – – – – – – – – – – – – – –
label | 3352c9b5-0386-5f25-8257-3284ba19d283 |  | note | CATEGORY: HP
label | a5725e78-efc6-581c-872a-559cae352595 |  | note | – – – – – – – – – – – – – – – – –
label | 49f5d99b-9adc-5853-a4be-dd208bdcb75f |  | note | RESPONSIBILITY: Nominated Authority
label | cba70abf-a64b-52fc-8d7d-852ad6c6fe2e |  | note | – – – – – – – – – – – – – – – – –
label | c45c82af-0a1a-538a-b179-ff04a0d52a1d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5d38627a-8688-5610-84f5-38f15483354a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 6e3ce1d0-81c0-5f16-b4e3-03b737419a3f |  | note | REFERENCE: 610.26 (a)
label | e88a8d0e-a1bd-5b99-aa24-9d31cce29044 |  | note | – – – – – – – – – – – – – – – – –
label | de68321c-a2f4-57f3-a72c-e4c543be4e74 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
label | 4eb45076-e07f-5325-9b4a-b4d791179296 |  | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 997a73e2-d048-5eb2-abbe-3855fc5a26dd |  | note | ○ Concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12%. Bar chairs and spacers made of wood, metal, plastic coated metal and site made concrete shall not be used.
label | 00d4e383-283c-5fd4-a938-0a0854cd40d6 |  | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 33358328-f834-56c4-96ea-594d5dbbd08b |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 70c5ebe7-2ad4-57de-8270-8afcc575b9ec |  | note | – – – – – – – – – – – – – – – – –
label | 260debe8-4e30-5127-8908-4533e35c02a8 |  | note | METHOD: Document Review
label | 5a06cef4-03b2-54ed-94e9-b8c7f4e64ed8 |  | note | – – – – – – – – – – – – – – – – –
label | 1a5c9547-3c77-55e9-92c0-44d7c2a0287c |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | e39d93ab-8000-5ee4-abc7-36524ba5f89e |  | note | – – – – – – – – – – – – – – – – –
label | eac58f6b-88bb-5423-9d79-0dd47d357ffe |  | note | CATEGORY: HP
label | 8cde9566-e707-585b-987d-88c86c18193f |  | note | – – – – – – – – – – – – – – – – –
label | dc93c961-1d39-5622-90bf-772c02adc55f |  | note | RESPONSIBILITY: Nominated Authority
label | 65fe747d-f01f-52df-a807-4452b4e2be59 |  | note | – – – – – – – – – – – – – – – – –
label | 0e796ffc-091a-5027-a4c9-e95ac2325c50 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 1b0199d2-e5d6-5171-8071-8133ae221ec7 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 5b0f2d95-270d-5f91-ad94-1b834f5dca4e |  | note | REFERENCE: 610.17 (f)
label | bbb339dc-498a-50f8-b9f8-37f829c242aa |  | note | – – – – – – – – – – – – – – – – –
label | c9cd3752-b65c-562c-b818-eeb9dd2fafb6 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 10819e99-a1ff-5e1f-8347-6720a1fc21d6 |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 9a404f9c-3de8-58c4-87ad-42495af812d3 |  | note | – – – – – – – – – – – – – – – – –
label | 0eaabbf7-3c33-51ad-9e4a-27e3e15db7b6 |  | note | METHOD: Document Review
label | 40fd6056-789c-5cdb-8e8d-9aeaa1e1eee6 |  | note | – – – – – – – – – – – – – – – – –
label | c7a312df-41d0-554f-b4cf-bf35eef3c743 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | d9b56557-891a-5861-bc36-f47b641ac1b9 |  | note | – – – – – – – – – – – – – – – – –
label | 28ba91a0-f68d-5130-a1f3-27a12420224d |  | note | CATEGORY: HP
label | 60a57c11-7377-543b-8a25-2a892d4467d4 |  | note | – – – – – – – – – – – – – – – – –
label | 11e99c19-44ef-5436-ac14-8ac7f0a3c22d |  | note | RESPONSIBILITY: Nominated Authority
label | 3501cc85-5e11-5e11-9464-baa7d57adccf |  | note | – – – – – – – – – – – – – – – – –
label | 327d0001-d21b-5dbe-8189-f09823506f48 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 31bcef47-1bc1-540f-9325-2471ec9a77eb |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | dd443fb9-51e8-5ad5-839a-c5d0b9c7f12b |  | note | REFERENCE: 610.23 (d)
label | 054e1b58-60bc-557f-8b2e-495e0be6c9eb |  | note | – – – – – – – – – – – – – – – – –
label | ef1f9f1e-4b34-5e34-9779-8682d10cce4f |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | a69ae6cb-e467-5ba4-9244-c17a0d88145a |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 50d7dd80-b485-58ef-8a6b-2b59853501c4 |  | note | – – – – – – – – – – – – – – – – –
label | edd9f899-9ea3-5e42-ae54-ef6753b3a879 |  | note | METHOD: Document Review
label | b5053cfa-5d3e-50c4-a881-7a2b1ee69f6e |  | note | – – – – – – – – – – – – – – – – –
label | 85b1c2d4-1ddb-531b-b9f6-822710ec93e5 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | ee93496c-6067-5591-b83a-48a186ff4955 |  | note | – – – – – – – – – – – – – – – – –
label | 9a967ea1-5b6c-54b8-a1c7-962a256a3839 |  | note | CATEGORY: HP
label | ed617d64-f34e-5d5f-9cc1-7f254f49b0c7 |  | note | – – – – – – – – – – – – – – – – –
label | d378f76c-83ce-5f5d-b2f2-8ee2abcb0443 |  | note | RESPONSIBILITY: Nominated Authority
label | 7192da8c-e9a0-534b-a183-012ae759de55 |  | note | – – – – – – – – – – – – – – – – –
label | 932d0359-184a-5888-b658-2470fbe74618 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | c725cf19-f8b8-546d-af47-085c495582a2 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 3bb16a2e-3283-54da-a55e-b1af4f69b136 |  | note | REFERENCE: 610.18 (a) (i)
label | 7aa79323-b9c9-58b2-bfb9-9d9938eacfb3 |  | note | – – – – – – – – – – – – – – – – –
label | 9b761ed8-1ead-5513-9240-d668371734be |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | 6ed5a249-8c35-5aa2-8cdc-b647e59e0c24 |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 4f3ed4f8-b389-5d1c-a6d3-79d94feb46d1 |  | note | – – – – – – – – – – – – – – – – –
label | e6c8f141-d297-51d5-b157-929bb66d0c7e |  | note | METHOD: Document Review
label | 64b3edbe-7ea7-537d-9f70-69d050357fb9 |  | note | – – – – – – – – – – – – – – – – –
label | 9d83b6fc-20ea-5435-8b30-98d0254e722b |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 83cd0803-200f-5809-8364-ff91c754b0dd |  | note | – – – – – – – – – – – – – – – – –
label | 3ff17ddd-915f-5919-b9d7-9af5688d20c1 |  | note | CATEGORY: HP
label | 37d78bd9-4907-500c-8d2f-e361a15b28b7 |  | note | – – – – – – – – – – – – – – – – –
label | 47d50a06-8ccd-5d29-8100-f461c8bf1631 |  | note | RESPONSIBILITY: Nominated Authority
label | e056df59-a916-5b12-be6b-2b904be166a2 |  | note | – – – – – – – – – – – – – – – – –
label | 80194c35-5ca8-54e5-b756-fbb456f934f3 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | fc1f682e-cf3b-5202-9bf8-a4b0c3792010 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | 865c5113-1727-5a61-983b-328345115740 |  | note | REFERENCE: 610.18 (a) (v)
label | 8a3a6a12-8b48-5f44-adc2-5d2c66a6f151 |  | note | – – – – – – – – – – – – – – – – –
label | 07c6d53e-86f3-5518-bc1c-3a650172c22e |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | af93aaaa-d95e-5831-8459-278134198310 |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 39484936-53a6-58b6-a2e2-454a17a83c49 |  | note | – – – – – – – – – – – – – – – – –
label | cddd39a5-aa25-5e9b-84c7-738da78b147a |  | note | METHOD: Document Review
label | ce572a31-0014-5476-ac9e-f48d2624829e |  | note | – – – – – – – – – – – – – – – – –
label | 952c1ebe-0d17-5807-b0f4-4be86c7f8ab8 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 772d097e-3580-5d9d-a173-75c4a10a4b52 |  | note | – – – – – – – – – – – – – – – – –
label | dfba63ae-ce43-55ee-a71f-cea528607646 |  | note | CATEGORY: HP
label | 2fae6b30-e1df-535a-a48b-68a99e338da7 |  | note | – – – – – – – – – – – – – – – – –
label | 6dd2da4b-a598-53df-a9dd-9a5470a4156d |  | note | RESPONSIBILITY: Nominated Authority
label | 87d9e8f1-a467-5253-8b62-ef2704bd9fbf |  | note | – – – – – – – – – – – – – – – – –
label | 590330cf-cc82-57c2-a96f-4be873a76659 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 8f96fe99-fc6b-52df-895c-3dffd3b5b47a |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | 8dde537b-ef57-5efa-bc80-8a439a284af1 |  | note | REFERENCE: 610.18 (a) (iv)
label | e39dc8eb-3300-5158-a9fc-007f2babf77f |  | note | – – – – – – – – – – – – – – – – –
label | 976486a0-3a4d-5717-b931-3b7301231807 |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | 55c96f04-853c-56bb-aa4e-9eaa8dc7027f |  | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
text | 8e4397f6-8095-57cf-b6ec-843f6c7d1c9b |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 2cc0dd5f-c239-5d6b-be5f-1a6ef063cb2f |  | note | – – – – – – – – – – – – – – – – –
label | 608c38ba-f90f-5e72-af0d-a23948c2fa07 |  | note | METHOD: Document Review
label | a029c3f5-7d4b-52b7-a006-ee5c3b5d4485 |  | note | – – – – – – – – – – – – – – – – –
label | 3b3f445f-3c13-506e-8a98-3717eaa14f24 |  | note | FREQUENCY: Once, 1 week prior to placement of concrete
label | 87099105-0059-53dd-a11d-a02b404057a8 |  | note | – – – – – – – – – – – – – – – – –
label | 7f6b05f2-cef5-5973-b8e2-35344420a50c |  | note | CATEGORY: HP
label | 12aee24d-9bac-502c-9231-42d860777943 |  | note | – – – – – – – – – – – – – – – – –
label | 01f43475-4aee-56b8-8d10-0762228ff401 |  | note | RESPONSIBILITY: Nominated Authority
label | 2dbccacb-f0bd-537c-ac9c-b5b956ba9014 |  | note | – – – – – – – – – – – – – – – – –
label | cbe71a3e-5d7d-5e81-a099-e9cdb9a39611 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 58c3fca5-a207-5c5b-9b79-5cb51066c3bc |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 537adb6c-a6ec-5395-8a06-e905c592f41a |  | note | REFERENCE: 610.17 (a)
label | 17af61b4-8c37-5089-a0f3-0b0bae6e66bf |  | note | – – – – – – – – – – – – – – – – –
label | cf863cfb-f35d-5d09-bcf6-5922135a47f0 |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 5e48d6af-1505-5eda-85a0-b1e9c8aaaedf |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 9e2d4572-d55c-542c-a4cc-31e01d194fdb |  | note | – – – – – – – – – – – – – – – – –
label | 19439da4-7a55-519a-88bf-cefe0bd7f82e |  | note | METHOD: Document Review
label | f3c2ec95-93e7-565f-b659-100da54f062e |  | note | – – – – – – – – – – – – – – – – –
label | 93baec44-4e61-5144-b52c-7f8ad78793da |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | e33d1fa1-d161-53c8-bfe9-4af03ecae850 |  | note | – – – – – – – – – – – – – – – – –
label | c3b9a27e-f22c-5a9a-ac99-3f708f347599 |  | note | CATEGORY: HP
label | d85c0eed-0ed1-5580-82e0-6487b32c67b9 |  | note | – – – – – – – – – – – – – – – – –
label | 135ce26d-8920-5f74-bbf5-1120788cf82d |  | note | RESPONSIBILITY: Nominated Authority
label | b1a29fce-ad91-5ad0-b067-fb93732dfb7a |  | note | – – – – – – – – – – – – – – – – –
label | 4941cf49-9321-57c6-9eda-9749170e80e0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | cc75e4c6-753f-5038-8f06-f085fff979e1 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | 0059ee76-bd72-51a7-924b-9f449a3dbfc3 |  | note | REFERENCE: 610.23 (a)
label | db780c17-ae88-5bcb-a82f-8794d1736d0f |  | note | – – – – – – – – – – – – – – – – –
label | 4be02d95-1e9b-52b9-a1ad-9329237cb503 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 7590bc5f-625d-5327-9577-3cff46c85bc6 |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 734a2722-b346-5eb1-8d30-9bf3ee2f3a69 |  | note | – – – – – – – – – – – – – – – – –
label | 8557e966-c2d4-5c78-91da-0b0178d1ba0e |  | note | METHOD: Document Review
label | a48893c7-b6e1-51e8-8d58-3791c221650a |  | note | – – – – – – – – – – – – – – – – –
label | 921d376c-26ce-514f-a99b-916e3ebca288 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 5f5e91cf-2a6a-5b6e-b505-7e28bbafef63 |  | note | – – – – – – – – – – – – – – – – –
label | fab206d5-2be7-5c0b-a67c-8e4673eb20f1 |  | note | CATEGORY: HP
label | 32738457-53ab-5656-9be4-9d534d197725 |  | note | – – – – – – – – – – – – – – – – –
label | 0eef0e54-37af-5e05-a69e-27c40ed58b61 |  | note | RESPONSIBILITY: Nominated Authority
label | ec4f8989-9c49-511f-800d-78144aab0d1f |  | note | – – – – – – – – – – – – – – – – –
label | d597bf4a-f610-58e5-9a8f-c5e8b38c66c3 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | b5c0daa2-6456-5744-9abb-553b87d15ced |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Concrete Drilling Procedure
label | 4453b6b2-c52d-5f48-8fc3-794c796c8431 |  | note | REFERENCE: 610.46
label | 8d11747f-9d06-5f0b-93bd-c1305fb91273 |  | note | – – – – – – – – – – – – – – – – –
label | aa29123c-fea5-5ed5-98b0-792aa29a1e40 |  | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | ef620911-cea5-5121-9a82-dcaaaf1a6cb0 |  | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | 295f1dfe-12d6-556e-b98e-52b3cb21f483 |  | textbox | Enter: Teambinder Hold Point Ref Number
label | 58083a15-a415-5086-9c2a-df66269725ef |  | note | – – – – – – – – – – – – – – – – –
label | 3414c841-25c3-5fa3-b4c1-dda0b38acc84 |  | note | METHOD: Document Review
label | 12db835c-5e2d-592f-9be6-e426daba0342 |  | note | – – – – – – – – – – – – – – – – –
label | 99ac93ee-9668-5f50-89a0-89ed281a7e92 |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | 169c1787-3b49-57cd-ab45-ee369fa621d7 |  | note | – – – – – – – – – – – – – – – – –
label | 3e3ce1ba-fcd8-5d9c-8a25-a0e0e8f4039a |  | note | CATEGORY: HP
label | 6bc96472-74de-5c41-a382-23e52d51f5c3 |  | note | – – – – – – – – – – – – – – – – –
label | e4e113eb-57ec-56ff-afe2-be61a7614d47 |  | note | RESPONSIBILITY: Nominated Authority
label | 5badbbb2-d7fb-5ebe-b343-f255766b11fa |  | note | – – – – – – – – – – – – – – – – –
label | cd9a2c53-68bc-5048-b4c3-28308145b160 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f770757d-04da-5ee8-b843-c04f3fea85a8 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Temprature difference measuring-Calibration
label | fa36e064-e342-5941-9825-b9293bf391cd |  | note | REFERENCE: MRPA Quality Management Plan
label | fb44124d-e62c-515e-8668-f375b25cc3ee |  | note | – – – – – – – – – – – – – – – – –
label | 972a5cfa-b12c-515d-91f5-5948325f5416 |  | note | ACCEPTANCE CRITERIA: Calibration records for Themocouples are valid and up to date.
label | 68845afe-7e60-51e5-a87a-19e025aa7fe7 |  | note | Attach: Calibration certificate
label | 5c42b84b-85bc-5d31-a965-16c0739d7d85 |  | note | – – – – – – – – – – – – – – – – –
label | 1f3e4bbc-3da3-5bf3-a5b9-6d071bfee8ea |  | note | METHOD: Document review
label | d534e0cd-fc77-52be-88f2-4ee449536ac9 |  | note | – – – – – – – – – – – – – – – – –
label | 44ee315b-c39d-5ebd-8349-6aa781242240 |  | note | FREQUENCY: Where applicable
label | 5053a5cb-eb42-5835-8df9-5ee975f508c8 |  | note | – – – – – – – – – – – – – – – – –
label | 2433afce-8613-55c5-a58e-c600d3ea82dc |  | note | CATEGORY: HP*
label | e360394b-85f3-59fe-a343-f84f99e3b7c8 |  | note | – – – – – – – – – – – – – – – – –
label | 0b262405-a4fe-5e90-b5cc-050ffb736906 |  | note | RESPONSIBILITY: PE
label | 71b07c55-b4a6-55e2-a844-7ee68cdb6c19 |  | note | – – – – – – – – – – – – – – – – –
label | 001624e3-d9cd-595c-a428-e1a8dde588ec |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 58c963fb-2861-57c8-b55b-bc6d4e95545a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
label | 3e74be04-2cf9-5983-957e-527296f077c0 |  | note | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
label | ae06e9b1-43ad-5609-9a51-f86d1eaa5ce9 |  | note | – – – – – – – – – – – – – – – – –
label | c216e302-b1cb-5d55-a241-84a435a312cd |  | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
label | e213a39b-da34-54df-bb01-24fe0abec9b6 |  | note | – – – – – – – – – – – – – – – – –
label | e6a3b632-6f9b-5125-a042-a23612d9646e |  | note | METHOD: Document Review
label | c54451e7-1874-5f83-9d05-6e52213db480 |  | note | – – – – – – – – – – – – – – – – –
label | 357e33a9-73a6-594d-b63d-c9a377d0544c |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 2b309e67-7427-5434-983a-cbcfbfbf7d8e |  | note | – – – – – – – – – – – – – – – – –
label | 9f90c1c6-a5d3-5fd6-a45d-efce358f2ded |  | note | CATEGORY: HP
label | 958eb80c-68b4-567d-adfc-7d2a554754d5 |  | note | – – – – – – – – – – – – – – – – –
label | bd65da05-16cd-54f6-b21b-e05305f5e077 |  | note | RESPONSIBILITY: Nominated Authority
label | a4e5586f-2702-5414-b56f-44905599ae50 |  | note | – – – – – – – – – – – – – – – – –
label | 44705d6a-1488-5b87-a50f-9eb5ce7e47c4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 5c66912f-2104-5f13-8159-ec0d05271425 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 01c651bb-7a4f-5df0-9291-67dc5a934917 |  | note | REFERENCE: MRPA Quality Management Plan
label | d512fa7a-a63c-519a-af43-4548403e616f |  | note | – – – – – – – – – – – – – – – – –
label | 691e7aef-ec07-5cb9-8529-47a0f22c51c9 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 37bfb56b-baad-5de2-8f6c-d223d381aaa3 |  | note | – – – – – – – – – – – – – – – – –
label | 6067c163-75dd-5df4-884a-53c0c5a09147 |  | note | METHOD: Document Review
label | 6f39bdf1-4588-5243-828f-569be76b425c |  | note | – – – – – – – – – – – – – – – – –
label | f40ee8c3-86e2-5878-b594-9e4eb922aae9 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | f76b11c3-4b2c-534c-8add-fd4af6178e7c |  | note | – – – – – – – – – – – – – – – – –
label | 1468a1de-44e2-5baf-8361-e6f5a12854f5 |  | note | CATEGORY: HP*
label | b3b9eb62-06e6-5c97-bc97-be43c0f05ab6 |  | note | – – – – – – – – – – – – – – – – –
label | b4f482c2-dca8-5c4f-919a-a3da83ffb65e |  | note | RESPONSIBILITY: All
label | 5a5222c5-d058-5914-bde9-0950c36ff469 |  | note | – – – – – – – – – – – – – – – – –
label | fa1e8e43-eb75-5c78-aca6-99c85aba898b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 32fcae49-d134-5450-a13a-8a5e57592250 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | e9aa9197-1a50-5210-be0d-fe25935e81fe |  | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472
label | 7011ef0a-0ced-51f3-b6cd-f0f6146d783b |  | note | – – – – – – – – – – – – – – – – –
label | ac94741c-da42-5c70-af2d-07b163ff2b4f |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | 44d3be9a-19d3-5a97-aecd-45827864041e |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | f6f93a28-6684-5d74-a8bb-2cc38ceec0b3 |  | note | – – – – – – – – – – – – – – – – –
label | a4d1a88d-e45b-54fb-9172-83d5813b752b |  | note | METHOD: Measure, Visual
label | fcea2ecb-0642-5997-9955-8a108d25ac23 |  | note | – – – – – – – – – – – – – – – – –
label | 12751e15-ee2e-58a8-ac9f-703ff9dae24c |  | note | FREQUENCY: Each element
label | e8b79840-6e78-526b-9384-1388104c4d98 |  | note | – – – – – – – – – – – – – – – – –
label | cf082f96-0022-53a6-a0bc-f09eac262712 |  | note | CATEGORY: IP
label | d088766f-7503-5ef0-817c-e65fa19bf4bb |  | note | – – – – – – – – – – – – – – – – –
label | e752a94a-dbcc-5cb1-b9ca-e3723686e2fb |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | f6742a8e-5475-524c-b08e-851527c6fff5 |  | note | – – – – – – – – – – – – – – – – –
label | 1d422bc3-9a7b-5ae3-94e8-a2f4b340976f |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 61502484-0b0e-5f57-a49f-84a2bc018b14 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Piles - Completed Prior to Construction of Pile Caps
label | 5cff02df-3057-5e4c-9eae-e7882c637383 |  | note | REFERENCE: IFC Drawing
label | e0049fce-b933-5784-90de-88bd1c353347 |  | note | – – – – – – – – – – – – – – – – –
label | 3f403321-0f30-56d1-ba0e-228560d4367c |  | note | ACCEPTANCE CRITERIA: Related piling Lots are closed.
label | 61154a99-00b2-5457-9b32-ef0ecf08a4a0 |  | note | – Pile design strength is achieved
label | 37f4226c-ec38-567c-952a-174f68455921 |  | note | – Integrity and Dynamic tests performed and interpreted (if applicable)
label | 4a0cb65d-c3b4-5f37-a6a6-f26168e55512 |  | note | – Pile is broken back to the design level
label | 8ade11ab-00cc-55b3-90c9-f01becac527d |  | note | – As-Built Survey performed
label | 8cd6780f-6744-5fb9-8087-c37334fa140c |  | note | – Related piling NCMs are closed
text | 90dedd97-4e1d-5d1c-ac0d-ee4c7cdcddbd |  | textbox | Enter: Relevant Piling Lot Numbers:
label | 87717015-e93e-5a40-bbbb-0ef4c5ce78df |  | note | – – – – – – – – – – – – – – – – –
label | 956964aa-cdcd-55f2-b991-4f56691068e0 |  | note | METHOD: Document Check
label | 27abf0ee-487b-5449-9859-50beeb477bcf |  | note | – – – – – – – – – – – – – – – – –
label | feabe1fb-c47d-59ca-bac9-1eeac1426319 |  | note | FREQUENCY: Each Element
label | 4874a157-70bd-5f42-9101-1f19893e208f |  | note | – – – – – – – – – – – – – – – – –
label | 39914738-48a6-5624-9d95-f90dde0b4bdf |  | note | CATEGORY: HP*
label | 63521a8b-70dd-5d19-8a6c-e3073df765c2 |  | note | – – – – – – – – – – – – – – – – –
label | 99060254-d75d-5dc2-b4af-c0d381a43f4b |  | note | RESPONSIBILITY: PE
label | c4069790-616c-5d92-844a-ad9af7a1c045 |  | note | – – – – – – – – – – – – – – – – –
label | 674bf0b0-4264-5d4a-89c7-4220e00edf27 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Piling Lots Closed-Out
date | 969bb123-bce2-5a4f-b442-c7eee801dd29 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation support
label | bdd92dcf-8def-54e2-9f04-1fbeb578d4e8 |  | note | REFERENCE: 602.02
label | cb08bb6c-f43b-5962-a2ea-0154dd28d56d |  | note | – – – – – – – – – – – – – – – – –
label | 0b34f6a2-7566-5f5b-ac28-ca6fc9cb1e62 |  | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal. Where applicable, a PTDT approved for use.
text | 586da738-472f-5a86-9b3b-b11c3ba5733b |  | textbox | Enter: PTDT Ref No.
label | 8ef5cc89-90a9-5fd2-a9a4-a0994c6780d0 |  | note | – – – – – – – – – – – – – – – – –
label | 03f56ffd-2f26-5e22-adde-d89e89a06075 |  | note | METHOD: Document Review
label | ce9d9696-0299-5ca1-bd00-e75a4aabacf3 |  | note | – – – – – – – – – – – – – – – – –
label | d3b21cce-0cf8-5953-bf35-e2ac1087f78e |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | 732f533a-17e6-5b62-973d-949a66e9e76c |  | note | – – – – – – – – – – – – – – – – –
label | 19bad036-6825-599e-9034-03d3613a3a90 |  | note | CATEGORY: WP
label | 98b72a25-5782-5dbb-a63b-d4afc7df4b26 |  | note | – – – – – – – – – – – – – – – – –
label | edf81731-7d5a-5726-9739-edb459a1c2d2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | fcd6f22f-3a73-5c93-a21b-81ea25c521d5 |  | note | – – – – – – – – – – – – – – – – –
label | 703a12cd-1f5e-5791-b882-5391ea9d34aa |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 394972e5-c783-5b17-b963-71e2998460c2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Excavation Inspection
label | 709527a8-3e92-5425-a790-a0719c74cb99 |  | note | REFERENCE: 602.03
label | 92589bcf-81d7-5630-955c-e26cf7dfd5e8 |  | note | – – – – – – – – – – – – – – – – –
label | 88425b6b-20ba-5d6b-8a6e-be1c2d018377 |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | bbe5b5d5-6160-5708-bc3e-ac847d97f255 |  | note | – – – – – – – – – – – – – – – – –
label | 6494bbb0-f6c0-533e-aae3-50219f417793 |  | note | METHOD: Visual
label | 99d80111-0a82-5676-8768-ce197b5cc335 |  | note | – – – – – – – – – – – – – – – – –
label | 31bd2386-02ce-503a-8f11-6fec6be6612d |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | f5cf7f0c-ab5f-520e-ac7a-dfd7ce674a25 |  | note | – – – – – – – – – – – – – – – – –
label | d9c4da3c-6691-5cb9-8aed-7fc11a29e1d8 |  | note | CATEGORY: HP
label | 51947593-96fb-5511-bac5-275e18b8b57c |  | note | – – – – – – – – – – – – – – – – –
label | a343a525-889f-5905-9298-05a9e5307033 |  | note | RESPONSIBILITY: Nominated Authority
label | bc53246f-eeb4-517f-98fe-09f511db3e84 |  | note | – – – – – – – – – – – – – – – – –
label | 8d022393-53b6-57e4-bc5d-e3fef6dff509 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 8675b58f-d5e5-5345-abb4-d983031f8c12 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | 4b0c3059-3e2b-59ea-93cc-5a1aab6ffd7e |  | note | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
label | b4282e1f-0312-5a76-85bd-06ec2ba51e11 |  | note | – – – – – – – – – – – – – – – – –
label | dd4a3b57-f0b1-59a4-a48c-a814ee4c7060 |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | e942c15d-71cc-5671-a76c-9e2504f7b782 |  | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | 2b26b8dc-e473-559d-acd0-88a38ba83b6d |  | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 5f9782b1-99d6-50ec-beaf-c05166d06c5c |  | note | – – – – – – – – – – – – – – – – –
label | b527e63d-e6c6-54c3-8dfa-2919ba835290 |  | note | METHOD: Document Review, Visual, Measure
label | ae76910d-9818-56aa-a52c-da4e8bfb53ff |  | note | – – – – – – – – – – – – – – – – –
label | 710c142d-1f89-5f32-b28c-63ba0ccccc4a |  | note | FREQUENCY: Each type of element
label | 45fcc732-cc27-53f4-82d1-8d512963d34c |  | note | – – – – – – – – – – – – – – – – –
label | 607d5c23-eb97-5431-a3ae-05beca1a90ae |  | note | CATEGORY: IP
label | 051cffb6-66b4-580c-aba0-ccb04970aa52 |  | note | – – – – – – – – – – – – – – – – –
label | 1a766206-c166-5cf1-8287-f39bf297eee7 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | be91c0e9-36f6-5a17-89c3-550f8216513f |  | note | – – – – – – – – – – – – – – – – –
label | 8f7f487f-0f0b-5e03-b9e6-092fca2eeaaf |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 540250b8-4169-5c7f-bdc4-8fe6b61083a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | 15d673eb-c71c-5de5-9530-f2ffe2321e1c |  | note | REFERENCE: 614.08
label | 25295e0b-5aa3-5321-908c-9ff9e92b9f17 |  | note | – – – – – – – – – – – – – – – – –
label | f22fc474-65f3-5539-b2b8-ab1a9f393e76 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | da3a45d5-410f-52c5-ade4-05068997d5de |  | note | ○ Pile caps with heights greater than 2.0 metres
label | 7423e30a-f039-5056-bc1c-f65159ff837f |  | note | ○ Any member for which self-compacting concrete is proposed.
label | e6224a45-4cd8-5a82-ad44-b037c11d3296 |  | note | Attach: Attachment A
label | a337c332-fa4d-5a11-ad3d-2db97026de0e |  | note | Attach: Attachment B
label | 147d0441-c604-5b07-b2cc-31b0197a52a9 |  | note | – – – – – – – – – – – – – – – – –
label | b8aeaa42-4fbf-5558-910f-10e7726897cb |  | note | METHOD: Document Review, Visual, Measure
label | 86eb0fda-4195-5a28-82d1-7fed7235eca2 |  | note | – – – – – – – – – – – – – – – – –
label | a9da7a77-85d6-52d0-b4d0-d5b42bf6b2a6 |  | note | FREQUENCY: Each element (where greater than 2m)
label | a74d7a3f-0c18-5ea7-a849-92e4b4a95737 |  | note | – – – – – – – – – – – – – – – – –
label | a58c27a6-76b8-5625-b0dd-671541074f8d |  | note | CATEGORY: HP
label | 9642a304-485d-595e-990b-429c2658bbf1 |  | note | – – – – – – – – – – – – – – – – –
label | 7f88f279-ee7d-5160-91cf-2cf4e4e6bdf9 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 29dd9c67-fb84-5c0d-a88a-529d5897b535 |  | note | – – – – – – – – – – – – – – – – –
label | 6d1f6888-7df4-5f5b-890e-c6623986b2ec |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 2e9da57b-8a7c-5605-b03e-6225c7a7564e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | bc3b7a42-8f16-5a89-b080-f988c4ee8cfa |  | note | REFERENCE: 614.08
label | f0909d00-de42-50c2-90d6-bb424526e4de |  | note | – – – – – – – – – – – – – – – – –
label | 2031dcb9-3272-5d90-b6d9-f965e33c86c2 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | c924bf7c-8b77-5cae-bfca-074567470bfc |  | note | ○ Pile caps,with heights less than 2.0 metres
label | 29c79e9e-5d46-5e0f-bcf9-518b817c06d4 |  | note | Attach: Attachment C
label | 904afa4f-0a07-59e4-976d-bd92dfaedf0f |  | note | – – – – – – – – – – – – – – – – –
label | c544a07d-0789-585f-89bd-d021365d8675 |  | note | METHOD: Document Review, Visual, Measure
label | 3512b01c-7ae9-563e-b136-ffa382a00d26 |  | note | – – – – – – – – – – – – – – – – –
label | 766d1fec-73a0-539c-a3fb-41aeb035d565 |  | note | FREQUENCY: Each element (where 2m or less)
label | ca0f643f-056a-5bb4-bb88-47d1f5d009a6 |  | note | – – – – – – – – – – – – – – – – –
label | 58f72beb-2989-560b-938e-954fc43a2e36 |  | note | CATEGORY: HP
label | 046e5053-758b-52dd-b6ba-27ab387e2fe4 |  | note | – – – – – – – – – – – – – – – – –
label | 08ae2bec-d976-568b-86d2-8912a3e03919 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 51449e44-6417-57b0-9b7d-9fdeef388d07 |  | note | – – – – – – – – – – – – – – – – –
label | d515e061-1a75-5b23-a54a-086d3901a56c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 27c34810-88ba-57ed-a971-20c5a4dc2651 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | a1c9e217-fcdf-5f3e-96af-0d04e076777d |  | note | REFERENCE: 610.47 (a) Table 610.472
label | 01d19e9a-f8f1-57cb-af0c-98152eefdab3 |  | note | – – – – – – – – – – – – – – – – –
label | 79e76956-1a5f-586d-952d-3f1bf89d5486 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | 65dcaea6-71fa-5b7a-a323-8c0109489a84 |  | note | – – – – – – – – – – – – – – – – –
label | 13f0fcb8-04b7-5127-b937-f1df89ff7c94 |  | note | METHOD: Measure, Visual
label | 3b65670f-d2e7-573f-ae36-dbc6db6d9ecd |  | note | – – – – – – – – – – – – – – – – –
label | b492de2d-783a-5c37-974f-a039e96074bc |  | note | FREQUENCY: Each element
label | e5743eef-9405-583c-bb53-c81bf69b53f7 |  | note | – – – – – – – – – – – – – – – – –
label | a53c95e2-cf16-510a-afc0-361661b0980d |  | note | CATEGORY: HP*
label | 299b2931-84c5-5420-adfd-90c178918a20 |  | note | – – – – – – – – – – – – – – – – –
label | 12237a6e-8537-52d0-99b9-10d88e57dc9b |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 654ad862-ff2c-5c01-8606-7e12c95be8b9 |  | note | – – – – – – – – – – – – – – – – –
label | afd8e860-9686-5563-9bd3-7574f8bbe77c |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 5c9d1497-71be-5a6c-bde7-4e16505e5c83 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | 169fb114-13ad-5bcb-ae68-0834c7ecccfd |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | e88e116a-c435-555e-ba8e-909ed165c166 |  | note | – – – – – – – – – – – – – – – – –
label | 0fe3ee6d-6fe6-57c4-9c1c-5be2260ac9aa |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 97e3dc98-bb0e-585e-bfbd-d1aca42b2801 |  | note | ○ Projecting reinforcement is the correct length and location.
label | de39ccba-f4d4-5f6b-8b18-8764f492deab |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | 468ae188-91f9-5735-88f4-7b188f185379 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | c0117e44-0dfe-5763-a8b3-70de3614904d |  | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 8aa8b212-7d84-5dc5-9aed-a6a0063d8ae5 |  | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | fd2ddf52-0b0c-5c1c-85de-536f34a74c47 |  | note | – – – – – – – – – – – – – – – – –
label | 413c1ab8-46e8-52e5-83e7-fb851a33252f |  | note | METHOD: Measure, Visual
label | 7fda199e-08d4-56f6-bf22-5454bc764d01 |  | note | – – – – – – – – – – – – – – – – –
label | 7484138c-b161-582c-843a-e43c0db6b8f6 |  | note | FREQUENCY: Each element
label | cdf2fe43-b86f-572a-9c62-108a6a36ba3a |  | note | – – – – – – – – – – – – – – – – –
label | ca26b1ab-2bce-5cf1-8c1c-906c517d2557 |  | note | CATEGORY: IP
label | f556660e-9116-5910-b717-593c96eb3c99 |  | note | – – – – – – – – – – – – – – – – –
label | 8875fca1-bec4-54a1-8380-23ca52f20ecf |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 83898f7e-88db-5f7c-883a-8ec8ce243c65 |  | note | – – – – – – – – – – – – – – – – –
label | e6fc4aa6-b8e5-5e77-80ff-432e0260ea6d |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 4e4b75a5-138d-5854-b44c-c5a255d829f7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | 38ce53fa-d016-5295-9316-03d13b7c05bd |  | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
label | 11847715-3429-51b9-a0eb-58bb3238392f |  | note | – – – – – – – – – – – – – – – – –
label | e387c32c-807c-5d01-846a-ba4b507b52e3 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 34feb54c-5a97-5333-83ad-e6a1e4983f38 |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 3b60fa78-5d39-5198-b1de-c2a4218634b5 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 9aa24af1-1e36-544c-b9af-027bb3484130 |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | e354e949-f117-59ee-b4b0-597bac763004 |  | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 99df53b0-b4e1-5e65-8789-83b6ed03147b |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 6b652b88-9025-53f1-8bcd-79e60e3e5b09 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 8773037c-4795-533a-a7d6-8dde12466f26 |  | note | iii. Ducts and conduit location = ±12mm
label | e9dd2fd4-1333-5a32-b691-40b0907aee6d |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 529e2556-6d13-5600-a15c-1197e7b5d4ea |  | note | – – – – – – – – – – – – – – – – –
label | 2b780473-3798-5a8b-940f-66f47a87adbb |  | note | METHOD: Measure, Visual
label | de75a17b-00b6-5e4c-bfa7-c9530b37c9de |  | note | – – – – – – – – – – – – – – – – –
label | 2296dfb6-08ca-546e-8cf8-076ac9200b97 |  | note | FREQUENCY: Where applicable, each element
label | 303a149c-e7db-548a-8302-0055faad6aad |  | note | – – – – – – – – – – – – – – – – –
label | 53b66f2c-b8f4-5009-bb42-ed343261fc2f |  | note | CATEGORY: IP
label | 88020e01-1594-5e95-afa7-cca79881a4b1 |  | note | – – – – – – – – – – – – – – – – –
label | 97094c75-3f55-59ce-a02f-99fe0321dfdb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | bfd28305-3ca2-59d3-8017-15efccac04dc |  | note | – – – – – – – – – – – – – – – – –
label | 21780c99-9361-514d-ad0f-01922991080e |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 27fe1c14-2b45-575e-986b-817263572836 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Thermal Differential Monitoring
label | 295e9482-be82-577b-8a79-f0b12f7a6966 |  | note | REFERENCE: 610.22
label | ba8a2640-c1f1-5374-a8ab-6172995e9657 |  | note | – – – – – – – – – – – – – – – – –
label | c0a2708a-7f0d-5858-8c23-54d0fecdcce7 |  | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
label | b4f6544a-6bd8-5bff-bdb5-e8943fac60f3 |  | note | Only applicable if the element has:
label | ad5ca6b1-c671-50f6-8ac7-a7871a07dc8a |  | note | i. the smallest sectional dimension exceeding 500mm
label | 2479051c-c75d-5b45-bb18-ab279e383c0e |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 8bb50839-9d4a-59a8-942f-288b98bf787e |  | note | – – – – – – – – – – – – – – – – –
label | 3e5f2325-e4ab-51e7-8b8a-be0ccfcf0722 |  | note | METHOD: Measure
label | a51c64ad-521e-5088-8996-2af3e47749d7 |  | note | – – – – – – – – – – – – – – – – –
label | 08ab76e1-6d9b-5b96-9304-8f11fba28bf1 |  | note | FREQUENCY: Where applicable, each element
label | 350548e9-5a92-5d30-a1c5-ce44606902f1 |  | note | – – – – – – – – – – – – – – – – –
label | 536cb6a3-2ec2-5a2c-9c22-28a2a49c323e |  | note | CATEGORY: IP
label | 0dcf4dbf-565a-59f3-bed7-d00f97595b48 |  | note | – – – – – – – – – – – – – – – – –
label | 14cfad9d-ff00-5a8a-9b87-5641a2ab0b10 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 5cab74ff-bd86-583e-aecf-a2b993176795 |  | note | – – – – – – – – – – – – – – – – –
label | 0d364ff7-c4e9-5aed-98b6-62e93021097f |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | d1ce9eca-ee09-5f1b-8c58-9f09082c76a3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-pour Inspection
label | 490c2fc4-5d76-58b7-b165-002865ecb29a |  | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
label | bcf16635-3cdc-5e01-8f7a-af0bca7a7dc8 |  | note | – – – – – – – – – – – – – – – – –
label | da4e69da-5735-5b50-8b5a-7397095a40b4 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 798d9bca-195e-5868-95d6-448ff694ad99 |  | note | ○ All foreign material has been completely removed from the forms.
label | 2b445b25-c667-5b1e-b3b3-8d884391e123 |  | note | – – – – – – – – – – – – – – – – –
label | ce73a211-b8e2-5d54-8305-a9a7fa45597c |  | note | METHOD: Measure, Visual
label | 7019365b-ed2f-53bc-bca4-ffbc4af1e24c |  | note | – – – – – – – – – – – – – – – – –
label | 27f8e618-7842-5e1e-a910-cdf75bd49073 |  | note | FREQUENCY: Each element
label | c4d6394a-720c-5221-b838-7df34121bcd9 |  | note | – – – – – – – – – – – – – – – – –
label | 2521b607-5337-55b8-8ed2-190611a17335 |  | note | CATEGORY: HP
label | 4f6c39eb-f276-5548-91ee-abf32780a79a |  | note | – – – – – – – – – – – – – – – – –
label | 9513cf9a-3184-5b3d-bd3d-6ac94000836f |  | note | RESPONSIBILITY: Nominated Authority
label | b2671d5a-7265-5486-98f8-6fda664649c4 |  | note | – – – – – – – – – – – – – – – – –
label | cbce3166-15f8-5302-92ff-53aa0df46dd4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | c36c8511-3b19-5ff7-a794-9ff46be37d36 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions & Evaporation Limits
label | 8d891a01-650a-53ed-bafd-a4dfac85d544 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | 53b0ad40-21b3-575b-aa3e-255c1ebc2f0c |  | note | – – – – – – – – – – – – – – – – –
label | 755a9b6e-9fa9-5cfd-bb50-939f609381a3 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 493e0dd1-94ab-5bf1-9de0-1fd3aa8f2bf4 |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 8591c6cd-b3e4-5017-9eb3-cd80e999043d |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 133e241d-92c2-5fe1-ab9c-fd130f693edd |  | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | bc639595-7260-559e-8843-e8f1d4c032af |  | note | Record: Required information on the Concrete Pour Record.
label | 3d481ab8-6017-54e7-9930-7f4eb4fd435f |  | note | – – – – – – – – – – – – – – – – –
label | 6acb1fdc-5d48-5d6a-8719-05a6f2277363 |  | note | METHOD: Measure, Visual
label | 99f5970b-9a63-51de-ab76-ea8fb8836ade |  | note | – – – – – – – – – – – – – – – – –
label | b1a08e07-34f8-5d85-8bb0-a8de3326a7d6 |  | note | FREQUENCY: Each element
label | ce7a9ae2-d1f9-54bb-aac9-64cb778f200c |  | note | – – – – – – – – – – – – – – – – –
label | 36f710e3-4ca7-5dc2-9d1d-f641cc8904dd |  | note | CATEGORY: IP
label | 291f43d4-6601-5e2a-8b44-54047c2f1734 |  | note | – – – – – – – – – – – – – – – – –
label | 11d26f07-0e3a-5b31-a47a-4afe4cf50557 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 73ecb994-1225-588b-b1a1-0a5740920af7 |  | note | – – – – – – – – – – – – – – – – –
label | 8bfdbe64-8ce0-535e-9e62-0ba889074d3b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 51219050-18bb-5ea3-9e12-0a5fb58cd41e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Sampling Frequency
label | e47a285c-4d4b-5342-a3c3-b9fb83322695 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | 8fec8d57-b327-5767-bbd3-c241775ee222 |  | note | – – – – – – – – – – – – – – – – –
label | 673daaad-f361-540d-a7d4-6d16624e616c |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | b8be0292-fe73-5518-9627-0b648ae0239a |  | note | 0m³ to 10m³ = 1 sample
label | 245b8276-e1c0-5131-ab3f-27abc3737c29 |  | note | 10m³ to 25m³ = 2 samples
label | e71a7c76-f380-5433-965f-bcc404e17e6e |  | note | 25m³ to 50m³ = 3 samples
label | 89fcb291-9ef6-5a9a-b41e-db4f6f11a7dc |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 3957b494-8a8a-5554-8f6d-8dadcfcf6872 |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | b0f227a0-4e80-546f-974d-574023eab261 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 6fbb32d6-eb10-5042-b2a9-7867094851dd |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | e8df9fda-fdee-5c29-9f93-6d1170faf9a5 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 5d53382a-5f96-5b50-92f4-2b48e7e00a85 |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 1f593956-73f1-552c-b6fe-7e2b0b31b002 |  | note | Record: Required information on the Concrete Pour Record.
label | 8f2117b7-8730-5baa-badc-e12aea994010 |  | note | – – – – – – – – – – – – – – – – –
label | 1f95fefa-ce1e-589b-94a6-7919596665b6 |  | note | METHOD: Test
label | 3eb92c4c-b358-580b-ba5f-899c0b7b6edb |  | note | – – – – – – – – – – – – – – – – –
label | 0cca850f-001a-5d73-8203-f642d2087a5f |  | note | FREQUENCY: Each element
label | cb4aad9a-3ded-5f07-b8f1-08a18b19b3b7 |  | note | – – – – – – – – – – – – – – – – –
label | b8621594-6a08-530d-ac68-160226f1b992 |  | note | CATEGORY: IP
label | 6392e9ac-7674-5ad9-bd43-f6215bccd3fa |  | note | – – – – – – – – – – – – – – – – –
label | e04dedd4-e368-5f39-91ec-e8ae8f36f794 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | ac2a10d2-8b5d-5dec-b342-2755113513da |  | note | – – – – – – – – – – – – – – – – –
label | d9cfe656-c092-5e1a-8e68-6c37bfeb9b1b |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 9340b217-5d17-55f5-996e-14d4bbad33f3 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Slump
label | 95f7e703-c0a1-515e-94a3-d8aec9bcf888 |  | note | REFERENCE: 610.16 (c)
label | 939c21dc-10a1-5ea7-b816-41865a7adc4e |  | note | – – – – – – – – – – – – – – – – –
label | 2ea8807b-77ca-5860-9578-2c1168c117ec |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | 9113e36a-1caf-5e16-9520-15dbec0e9bbf |  | note | <60mm = ±10mm
label | 057e2e59-8a02-5127-8ae5-30256ea937ea |  | note | ≥60mm to ≤80mm = ±15mm
label | 4ef62e6c-e57f-5c20-8ac2-1fcba00164ef |  | note | >80mm to ≤110mm = ±20mm
label | 463245dd-39d8-53dc-ba2e-ee79373bf385 |  | note | >110mm to ≤150mm = ±30mm
label | 5517c4bf-c628-5243-9cec-76568fd6b415 |  | note | >150mm = ±40mm
label | a9350005-c4fc-5d6f-a129-a23619c4d475 |  | note | Record: Required information on the Concrete Pour Record.
label | 424036ec-91b6-5e5a-97a4-ae720d576b90 |  | note | – – – – – – – – – – – – – – – – –
label | d3c6f689-5304-50b4-b39c-90a9f2e1385a |  | note | METHOD: Test
label | fcca32ca-d338-5fc8-8aa4-a9bb8ca08637 |  | note | – – – – – – – – – – – – – – – – –
label | 4d320755-8e01-5562-9fb5-3237d9379ca7 |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | f9a75554-4093-51f6-a692-cb53dc0e8d47 |  | note | – – – – – – – – – – – – – – – – –
label | 5a3f3dd5-99b6-57ff-996a-dc4ac69a8f73 |  | note | CATEGORY: IP
label | 11adf8e2-1cbd-5801-847d-eab9ed8cf151 |  | note | – – – – – – – – – – – – – – – – –
label | 678a01f4-b8e0-5033-bf51-cf1515020ed5 |  | note | RESPONSIBILITY: Concrete Tester
label | 9a76ca9e-9657-59bc-93a0-d01cc7b21b1f |  | note | – – – – – – – – – – – – – – – – –
label | 49242aba-0ecf-5800-a094-b1bd5e962d83 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 3d17259b-de22-5dc9-b12b-708b8f5bd3a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
label | 2bc6852b-96b2-5efe-9cf0-3d808b34657a |  | note | REFERENCE: 610.13 (b)
label | 4ec471b2-b4a0-5242-8530-2f631c6a6a7f |  | note | – – – – – – – – – – – – – – – – –
label | 78a7d2dd-0522-5204-99cd-c8f6a13117bd |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 696a5ffe-fbf1-5929-a2fd-b2f4d81e1dff |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | a6fd2e28-edd6-56c1-87eb-2e5fb81be7ae |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | f611ece4-431f-581d-b902-b5a24ffe3190 |  | note | Record: Required information on the Concrete Pour Record.
label | 6eec8e5e-2177-5b59-a7ea-c8678c33d986 |  | note | – – – – – – – – – – – – – – – – –
label | 0bae0e43-0a19-59ae-86c3-366fb43183c6 |  | note | METHOD: Test
label | c3ad13a8-fc2e-52bd-8560-934f8bdad40a |  | note | – – – – – – – – – – – – – – – – –
label | 00800c62-92e3-59ee-acca-a0e3f19481fe |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 394369e1-8d2d-504d-851f-e00a41ec7523 |  | note | – – – – – – – – – – – – – – – – –
label | 9549e3f3-6bd0-5377-affe-84316eca9afc |  | note | CATEGORY: IP
label | ba08f6d7-e40f-577a-b0a1-56f12da31faf |  | note | – – – – – – – – – – – – – – – – –
label | 14a1c3ff-19eb-5a46-9b9e-75314ad668e6 |  | note | RESPONSIBILITY: Concrete Tester
label | 23c80ff1-e056-5515-a01e-9e7ac005fd42 |  | note | – – – – – – – – – – – – – – – – –
label | df258501-3653-52e4-a02b-131d4308d7bc |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 920db69b-6a1a-50bb-bc71-ee069b6ed87a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
label | fcb36d3f-0809-5dd0-a138-2cd4eeb4b77e |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 90e43887-87cf-56a8-830a-f037db3a1f59 |  | note | – – – – – – – – – – – – – – – – –
label | d63e0724-e06a-5085-ba75-3800a60e3dda |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 594745a7-399e-5120-8a3c-b0a6ebfbdd2b |  | note | Record: Required information on the Concrete Pour Record.
label | 5c28a684-f84c-5196-b352-580727ba9f1c |  | note | – – – – – – – – – – – – – – – – –
label | 820fda40-b7a8-5bf4-9e08-c9553bca913a |  | note | METHOD: Test
label | 7385d12e-54af-5240-ba2f-a424724c6198 |  | note | – – – – – – – – – – – – – – – – –
label | 6aa07a05-8cb5-5b1a-9512-fbc4bd272982 |  | note | FREQUENCY: Each sample
label | 174f43d3-bbe8-5058-93dc-8ee2f07f223a |  | note | – – – – – – – – – – – – – – – – –
label | 77cdb8c7-6481-5374-bc9a-164d430c3176 |  | note | CATEGORY: IP
label | b9243425-cc7a-5cf9-a4b6-8b889f4a1ccc |  | note | – – – – – – – – – – – – – – – – –
label | 6b5e4ba6-81a8-546d-b837-4f8fdaedcfea |  | note | RESPONSIBILITY: Concrete Tester
label | d1a5d4f7-fcf7-5004-93f1-1e69870967a5 |  | note | – – – – – – – – – – – – – – – – –
label | 688fb8a0-242e-5100-8be9-70e35e38f121 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 6f5dc458-4953-5ea4-b23c-cfeccf1780f9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Supply & Discharge Rates
label | 0ae15405-76ae-569e-aaaa-26dc757eb9d4 |  | note | REFERENCE: 610.13 (a) & (f)
label | 77141fd7-fa61-575a-9ee0-b5e75f35be2c |  | note | – – – – – – – – – – – – – – – – –
label | 611c5833-7e0b-5ee2-bae6-63f8b935a344 |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 5fd8e20a-67e0-5537-acb5-1ecddd767563 |  | note | ○ No water is to be added once discharge commences.
label | 22bf9342-6a42-5223-a54a-ad44c04478af |  | note | ○ Maximum time between batching trucks is 25 minutes.
label | 49eba8d8-12a5-5f7f-af4e-b7499c009178 |  | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | bb93a7b4-a4a8-54b7-861e-e01573756b85 |  | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 80c3ad78-72b5-5f9f-9c24-d94e1b54277d |  | note | Record: Required information on the Concrete Pour Record.
label | 51d75ad5-e7b9-5d57-ba67-56a7f07fee43 |  | note | – – – – – – – – – – – – – – – – –
label | 312628cb-3f69-572e-a602-6a43098ba5f3 |  | note | METHOD: Measure, Visual
label | 0dce991d-0aaf-521c-9379-9c10b8d0e50d |  | note | – – – – – – – – – – – – – – – – –
label | 6c2116f9-05e8-58b2-a900-1a458d35d31a |  | note | FREQUENCY: Each load
label | 5c2a574f-50cc-56f7-9e72-b834bff7573a |  | note | – – – – – – – – – – – – – – – – –
label | 72ae9ae8-17c2-546c-b200-1a5bf0f654ac |  | note | CATEGORY: IP
label | cfe39ef6-0535-5fcf-932e-b08c8c287c4d |  | note | – – – – – – – – – – – – – – – – –
label | 69f3820f-a79e-5148-90a1-3d32644913c6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b324308b-3210-57ca-907b-8563ee0f2995 |  | note | – – – – – – – – – – – – – – – – –
label | 542e6b55-b030-5933-9900-91ee944cc465 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 509a4c13-60d6-5a7e-ad7f-2a341c796c4c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Placement & Compaction
label | 9af40069-8407-5b72-966e-c011973c1f34 |  | note | REFERENCE: Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | ba1ef2ab-1a7f-5475-9325-77e4e5e468b3 |  | note | – – – – – – – – – – – – – – – – –
label | 60c3bd9d-0365-50ab-b0f8-da2b600acd8b |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 885534e6-8ba5-5a9a-a0cb-dbc76b156651 |  | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 59fb8e0b-cc8e-5ba0-8c58-e0449cc9feb1 |  | note | ○ Concrete is not dropped freely from a height exceeding 2m.
label | af289af5-1c12-5af6-a170-bb908e3967a4 |  | note | ○ Concrete is not moved horizontally by use of vibrators.
label | 1d8984cb-29d5-5628-8c5a-e753c378cb5a |  | note | ○ Adequate compaction is ensured
label | c7a3154e-1130-59a1-b7a6-8ad6f0058dde |  | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 8aeca3e1-9a4f-50c1-9650-0aa3659d3140 |  | note | ○ Concrete layers are not more than 350mm
label | 21e803e6-079b-5b15-8858-39cc59926420 |  | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | a4f63cd8-2bb0-50d7-8ac6-d375d9aad529 |  | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 7aaa5a02-f128-57f1-9496-d1fac33f1908 |  | note | Record: Required information on the Concrete Pour Record.
label | 5346b63c-4345-5db1-9d97-38bbe8b22221 |  | note | Attach: Concrete Pour Record
label | 660dab67-3202-541e-9d66-b3f79e1cd8b1 |  | note | Attach: Concrete Dockets
label | 25ba33f6-bda3-561f-8b48-af7bc78f5c1e |  | note | – – – – – – – – – – – – – – – – –
label | 619cfceb-8afb-56f3-9ae3-0943c232a215 |  | note | METHOD: Visual
label | f8518f5e-4bec-5cc7-ac2f-68be706a76bf |  | note | – – – – – – – – – – – – – – – – –
label | 04e320e5-d72b-5ed4-8d92-805ac45f2733 |  | note | FREQUENCY: Each load
label | acc3908d-504e-5be9-9932-20c63a415fad |  | note | – – – – – – – – – – – – – – – – –
label | c1a6c9e7-c2f1-510b-b40a-049060695812 |  | note | CATEGORY: SP
label | e4c73b7a-2297-5bda-879b-a6ef5817cb23 |  | note | – – – – – – – – – – – – – – – – –
label | 63deefc5-d771-5892-aa47-3dc31bea077d |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 938e45d8-2572-5472-b7f0-c04db6666b2d |  | note | – – – – – – – – – – – – – – – – –
label | 8e7e304b-2746-534a-9890-452c40d4290f |  | note | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | 0a6a436d-c7b7-5722-8b60-567ab4134a60 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Surface Finishes
label | 20546c31-6aec-5fdc-96b4-a9b913a7cca1 |  | note | REFERENCE: IFC Drawings 610.31, 610.20
label | f471be65-7abb-51e4-90e4-7a92170b05aa |  | note | – – – – – – – – – – – – – – – – –
label | f38ba466-d487-5bf0-a423-c05bded050a7 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 0d14777b-f8ba-5c35-9a1e-72790269890e |  | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | d18bf5a0-898c-51a8-80e5-de6f31f0d8a2 |  | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 9c63c4f9-48bc-56e1-9232-2a11b2035b7b |  | note | – – – – – – – – – – – – – – – – –
label | 7cea8ae9-7d2e-59ae-8a54-b6bd0481bb61 |  | note | METHOD: Visual
label | 8ba6c378-03f3-52d9-baea-1f1c00a79b38 |  | note | – – – – – – – – – – – – – – – – –
label | 7140403d-508d-5cd1-9e6f-535ccda5a6fd |  | note | FREQUENCY: Each element
label | e9d02230-6ae3-5711-9562-d822d6a47d5d |  | note | – – – – – – – – – – – – – – – – –
label | e0cf4962-c45c-5d24-974e-9765ef196621 |  | note | CATEGORY: IP
label | 890a6699-6bf0-582e-a1ff-677072abf58b |  | note | – – – – – – – – – – – – – – – – –
label | 856c4d5d-eab0-56d9-9736-26933aadd8a0 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 70b3b7d0-0111-52a7-a8aa-8bee704426b7 |  | note | – – – – – – – – – – – – – – – – –
label | 8d610d2e-074c-5c73-a362-2a44a47cebc7 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | b6e175fb-e5fd-5cab-8418-99a04495a000 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Curing-Top Surface
label | b7aaa924-896d-5160-a873-7972fb585b63 |  | note | REFERENCE: IFC Drawings
label | 8b1dfcef-668c-5630-b39a-82500427f7f9 |  | note | – – – – – – – – – – – – – – – – –
label | acaa58fa-e1ae-53c6-8bc7-dff6eae9b01b |  | note | ACCEPTANCE CRITERIA: Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | d9098656-005c-5173-b798-1aef16461bf3 |  | note | – – – – – – – – – – – – – – – – –
label | fc01384d-0348-530d-a3f7-506bab97e625 |  | note | METHOD: Visual
label | 79a7c41a-4ebf-5b1e-a0c2-6a2c094a790d |  | note | – – – – – – – – – – – – – – – – –
label | b34640d8-c2fd-5b83-99e0-4ba0ef224fcc |  | note | FREQUENCY: Each element
label | c06f85b6-3f21-5ee4-80ee-8d2d12e173a0 |  | note | – – – – – – – – – – – – – – – – –
label | afc3754d-0159-5a5d-845d-1c65453646c3 |  | note | CATEGORY: IP
label | 994aced1-93f1-5fc0-b79e-78ecd934885f |  | note | – – – – – – – – – – – – – – – – –
label | 3f843df2-55e5-5f1e-bfad-473b9100b659 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 9acbc8d9-b3a0-5a94-bb73-b0dd7911bf4a |  | note | – – – – – – – – – – – – – – – – –
label | 1dbcb2f0-bb77-5c9c-9bb0-85d185b6af47 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 69cdcae8-9d91-5fc2-9133-2432218a4a50 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Curing after formwork removal
label | 9abea23f-b0b8-59a6-84bf-235149c59955 |  | note | REFERENCE: IFC Drawings
label | 8d2e421b-841c-5bc9-9540-ef6756e668aa |  | note | – – – – – – – – – – – – – – – – –
label | f005b622-f39b-5501-bc3f-6f51afbb9779 |  | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 89a29cfa-70d7-5961-993f-aad041fb8b88 |  | note | – – – – – – – – – – – – – – – – –
label | 77d0eada-b1af-578d-9377-326bf6031def |  | note | METHOD: Visual
label | 9753428f-2660-58b2-ab9f-182239541a3a |  | note | – – – – – – – – – – – – – – – – –
label | 1adb7283-e28d-5110-8f08-00e09703ccdb |  | note | FREQUENCY: Each element
label | ab2aad19-3f07-57db-91ef-9e85dcd2bdee |  | note | – – – – – – – – – – – – – – – – –
label | b7dd3568-bd91-520a-b61c-cfc5d5d379c3 |  | note | CATEGORY: IP
label | c139a828-dde3-5756-87f3-1eb386c65e85 |  | note | – – – – – – – – – – – – – – – – –
label | fcc4ed7f-ec0b-5200-b19e-047a92e28b1f |  | note | RESPONSIBILITY: SE
label | 93ab68bd-ea1b-506e-a23e-afd9b6fabf6a |  | note | – – – – – – – – – – – – – – – – –
label | d947dfd8-f9e8-5369-a768-101b15d4a1c4 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 1de77906-7a15-53ff-8f6a-62f4621cff94 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | df951459-210b-5114-b0bb-e6287156b14f |  | note | REFERENCE: 610.22
label | 363b99f8-bb9d-5a54-bb56-7e41a20fa245 |  | note | – – – – – – – – – – – – – – – – –
label | afb0e797-8218-5af9-bb43-98e0fca93c2f |  | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 976f957c-1246-5634-a613-87ef1cd481cd |  | note | Only applicable if the element has:
label | 9417a764-b314-50e4-8962-062619445c06 |  | note | i. the smallest sectional dimension exceeding 500mm
label | a7693dee-e6a8-5ea6-a12b-349c7a0ab4a9 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | 170e1ea3-e648-5b82-bd25-4da6b8225641 |  | note | Attach: Thermal Monitoring Report
label | 089d72f0-f3b7-5314-b5dc-4efd984547a7 |  | note | – – – – – – – – – – – – – – – – –
label | bb87a86c-0c4c-5d4c-9456-14e1105b7408 |  | note | METHOD: Document Review
label | 0adefe46-e8e5-5b20-8b38-471c8ae6b6eb |  | note | – – – – – – – – – – – – – – – – –
label | 245aaaa7-01f2-513c-a66d-5f157accc9d7 |  | note | FREQUENCY: Where applicable, each element
label | d90ee354-db3f-59b5-9522-4f9ecca53edc |  | note | – – – – – – – – – – – – – – – – –
label | 0410da2e-fe96-5223-a846-798beae23842 |  | note | CATEGORY: IP
label | 4082d6ca-7cee-5bfb-8121-1100016d9985 |  | note | – – – – – – – – – – – – – – – – –
label | f2e23410-be41-5143-9d99-4e5a5a583451 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | ee318345-f1ce-5dcb-a115-4b9b377013cf |  | note | – – – – – – – – – – – – – – – – –
label | c0252605-0c09-58ad-a2f2-cef5f8546efc |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | d43782f7-0775-58d2-9cda-dd35f17392c7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
label | 5805f5e6-06b2-54e9-a32c-41b45cf2c50d |  | note | REFERENCE: IFC Drawings
label | e5ef1535-b14d-5c64-b378-8e4f4a144572 |  | note | – – – – – – – – – – – – – – – – –
label | 0f0a90ea-907b-5600-b174-2ec8ddcd9cf8 |  | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | f8880ad7-9699-59d8-ab15-2df03bcd6b18 |  | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 4e782f81-267f-5c34-ab26-c1bb6a2f3524 |  | note | – – – – – – – – – – – – – – – – –
label | 16c29ea9-dd18-554e-b866-3c41c1029139 |  | note | METHOD: Document Review
label | b93210d2-02b8-5798-b817-3f46c4aa520d |  | note | – – – – – – – – – – – – – – – – –
label | 791d4fb8-5eeb-5d08-ad0d-1ce7fb54cf60 |  | note | FREQUENCY: Where applicable, each element
label | ecd3c28d-0f35-5cf7-a768-3db13a8f5401 |  | note | – – – – – – – – – – – – – – – – –
label | 90079d0b-fdc5-5342-bb36-5028efff23ce |  | note | CATEGORY: IP
label | 3aec0bdf-6672-5b03-bedc-f8775aaa6546 |  | note | – – – – – – – – – – – – – – – – –
label | 87d8c41c-dbb7-5df2-8703-22535209efbb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | ea522cb7-5227-5ae4-a8e8-e1931e91d44c |  | note | – – – – – – – – – – – – – – – – –
label | edaf6c99-6e7e-5868-8945-256b2688c41c |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 2cadc7ee-73e4-50b8-945f-b4975e845251 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection - Cracks
label | 22e64788-71da-5167-ad8e-137fcb9353fc |  | note | REFERENCE: 610.24
label | ac1dc02b-f0ac-515c-84fc-5e08855fb724 |  | note | – – – – – – – – – – – – – – – – –
label | 59293335-9d1b-5b11-a255-e9c41644511c |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1). If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 596181b3-1e2d-5a57-8469-4eecb19ee0c0 |  | note | – – – – – – – – – – – – – – – – –
label | 643ea348-1100-5734-869e-2421720e1f26 |  | note | METHOD: Visual, Measure
label | 1c900044-f1d9-5be0-babc-cc60da84c1ea |  | note | – – – – – – – – – – – – – – – – –
label | fdae024e-869b-5366-89d2-016a15ccf117 |  | note | FREQUENCY: Each element
label | 0a5b7fc5-dbf3-51cd-8348-14240b0b40d0 |  | note | – – – – – – – – – – – – – – – – –
label | e1ca5cf0-7508-578e-af86-afc9dbac1fde |  | note | CATEGORY: IP
label | 058c6d4b-ce0d-5ca2-b4f6-94652ccc9b0f |  | note | – – – – – – – – – – – – – – – – –
label | 76806fce-c3a7-5551-952b-4cc2e04dcff0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cfe9a5a2-1cad-5640-903d-b6c2fd9d0c40 |  | note | – – – – – – – – – – – – – – – – –
label | 7320dbca-26b3-527e-8ee5-9356e851cfbe |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 0e22ac14-99f2-5ce8-9b85-9e2c67be9bfb |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Surface Finish
label | 9a64021c-2666-574a-859c-1e0d47e6b231 |  | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
label | 718cded4-e028-5856-88c7-c7ad3f3551db |  | note | – – – – – – – – – – – – – – – – –
label | fc4f527b-8508-5712-9a64-829357de8dbf |  | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | ce785974-e512-5f0e-92fd-8b08d5bf076c |  | note | – – – – – – – – – – – – – – – – –
label | 02bcd21a-937a-5d3e-a872-8a1ce5e9c56d |  | note | METHOD: Visual
label | af41fc44-e02c-530c-8312-24cba703066b |  | note | – – – – – – – – – – – – – – – – –
label | 46af4362-0087-5c59-aa18-a31f8d9650b5 |  | note | FREQUENCY: Each element
label | f0efe838-5cd1-58f2-b768-f7ac07899441 |  | note | – – – – – – – – – – – – – – – – –
label | 38c44a43-4848-5171-a0e4-525afde4cfbb |  | note | CATEGORY: IP
label | 8c210766-8e44-53a9-8146-f3b8974cc4ea |  | note | – – – – – – – – – – – – – – – – –
label | fdb996c7-73e1-5662-af9c-71572028b35a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8065ad4f-a7f1-5db1-bacf-dcc772631b41 |  | note | – – – – – – – – – – – – – – – – –
label | 40a5334a-6711-5c25-9e1e-42be4fa96f10 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 4838401b-7afb-5fba-b63c-c93f86570e1b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Measurement of Concrete Cover
label | f1912451-a285-52e1-ba61-b8a616feb133 |  | note | REFERENCE: 610.34
label | 11b43a97-fecc-5522-b6b1-2775d9ce3007 |  | note | – – – – – – – – – – – – – – – – –
label | 260ad736-08d3-5456-b86c-50cd499359ee |  | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 954b855b-8c28-5478-98e7-6846d6294b2e |  | note | ○ Minimum 10 no. measurements recorded in each area.
label | 0a7aae5c-601e-59ec-a828-7f18385e2a8b |  | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | c410cf41-0cde-502d-b9bc-faddbdced9d3 |  | note | Attach: Covermeter Check Record
label | cbc487a2-e517-5e89-95c5-cfd4480082e9 |  | note | – – – – – – – – – – – – – – – – –
label | 2493ccb0-cf95-51cb-bed0-389bb0c8212a |  | note | METHOD: Measure
label | a654085d-d41f-555e-8b43-5da7e857f67e |  | note | – – – – – – – – – – – – – – – – –
label | 3649b612-e1de-5ccc-9d04-52cd0126ca42 |  | note | FREQUENCY: Each element
label | 2021626d-8bdf-52cf-af0d-b9419f90d2c4 |  | note | – – – – – – – – – – – – – – – – –
label | 3056604c-50fa-57a4-9205-6462196637cd |  | note | CATEGORY: IP
label | 7bef27d9-f1ba-5e05-88ab-9fdb5563c570 |  | note | – – – – – – – – – – – – – – – – –
label | d6ec20af-872f-59e9-b6fa-6e9654508c85 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b311e8b9-7381-5ea7-8ea9-35328d161e84 |  | note | – – – – – – – – – – – – – – – – –
label | 1845b2fd-4f6a-513b-b1c4-90e9680695f2 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | d16ce1f3-90a1-5daf-989f-7131d20a5958 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 84713a49-5f7d-5da2-a125-683653f7bedb |  | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | 1a691f44-1539-5689-9567-00be224050a2 |  | note | – – – – – – – – – – – – – – – – –
label | 424d66e5-4702-54d8-8dc6-a564dc65f751 |  | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
label | f3243b66-27d4-5fe7-919a-dac9abe7ba12 |  | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | d8cf0ba9-3074-5e11-afd4-31839ec4ae26 |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 47ac9658-e1d0-54d2-94b0-d47bbcf53362 |  | note | – – – – – – – – – – – – – – – – –
label | 7bbcaec6-7aa9-53a0-bca5-cfd3aa474547 |  | note | METHOD: Document Review
label | c8791c55-eb9d-5212-9c8a-8de1112e883f |  | note | – – – – – – – – – – – – – – – – –
label | ea799b1d-010c-59e0-aae7-de486cd93f9c |  | note | FREQUENCY: Where applicable, each substructure element
label | 3a11ac0b-8dd6-5bc8-ba32-1a593b2e6f2e |  | note | – – – – – – – – – – – – – – – – –
label | 57516961-a5a5-5ea7-b30b-58b9af781f37 |  | note | CATEGORY: SP
label | ae00a234-8b99-54fd-be6b-8a623c043b95 |  | note | – – – – – – – – – – – – – – – – –
label | 6d5fc2da-a242-5914-bd77-c0a624397894 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 834551b2-5ecb-5a78-bc7e-13b16c58c2b1 |  | note | – – – – – – – – – – – – – – – – –
label | 7de058de-5ddc-5e7c-a29e-37f1c7cfd371 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 9bd73a25-fc18-5c04-98da-c05c08c69729 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | f3f6d7c1-7bd5-5dea-ad18-779cdca21242 |  | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
label | 82ca1944-b066-5ec7-bd69-f189f5673ad8 |  | note | – – – – – – – – – – – – – – – – –
label | e8ec5a7b-8150-592c-a2d2-14ee69d2d253 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | c2cfa570-4796-57a4-92ca-9adcf5e96321 |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | b63ed3e6-dbc2-5e57-82ce-07254754d060 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 60c7e6e4-74b7-59c9-b6bf-81522501d5be |  | note | Attach: Compressive Strength Test Results
label | 6c1bc01d-9c95-51e4-bc79-f7a645c70162 |  | note | – – – – – – – – – – – – – – – – –
label | 0bd5333c-bfaa-5e53-8fbe-c064b3c8339e |  | note | METHOD: Document Review
label | 4ab8158f-98ce-5dd5-9bad-62cd22e16d5b |  | note | – – – – – – – – – – – – – – – – –
label | f6ad73fd-dfcf-56f2-8343-c5a3cad70d97 |  | note | FREQUENCY: Each cylinder
label | 41ab39f9-7543-5f9e-aa61-17d086c88af4 |  | note | – – – – – – – – – – – – – – – – –
label | 4744a4b0-71be-56fe-b960-c9e2e1958994 |  | note | CATEGORY: IP
label | 2e0045e3-8fb7-55bc-93c2-abb7cd2f9a69 |  | note | – – – – – – – – – – – – – – – – –
label | 0a70df19-7b50-5c3a-bc2b-f49ca6cb8c92 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2995cdc5-0dbe-5e25-b737-460696bbcfe9 |  | note | – – – – – – – – – – – – – – – – –
label | 94eac283-2537-5eaf-a854-6abe07cd74fc |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | b33b1515-a26a-54b7-bd45-4344a1731b9e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | 4e2f0ff9-b1ce-5e55-9f1b-6943d66cc567 |  | note | REFERENCE: IFC Drawings 610.47, Table 610.472
label | c883ff68-048d-52c0-812b-a135ec89df70 |  | note | – – – – – – – – – – – – – – – – –
label | 747e6fde-2d46-54c3-926e-5c185da6b20f |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | b681ac31-4eb6-5877-9c6a-6ac69b997f8b |  | note | Attach: Survey As-builts / Survey Report
label | b64d4650-e20f-5087-8b8a-6cb8cf2f8d91 |  | note | – – – – – – – – – – – – – – – – –
label | f3fd0252-eff2-51ea-86d8-d405472a9269 |  | note | METHOD: Document Review
label | f64c9ecb-7f5b-5b30-8582-17db68b1db3f |  | note | – – – – – – – – – – – – – – – – –
label | 931c7b0e-c31e-5683-8095-1bf149132445 |  | note | FREQUENCY: Each element
label | 85093da8-0d4d-5e3f-b39e-f60841b922a8 |  | note | – – – – – – – – – – – – – – – – –
label | 63a97d44-18a5-539d-9787-58ed330be2f2 |  | note | CATEGORY: IP
label | 2ec859ff-2be8-5786-b94f-1fa92657f0ca |  | note | – – – – – – – – – – – – – – – – –
label | 171b1206-728c-58e4-a041-015a6f59724f |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 4b0b89ee-913a-5b3f-93a2-cb5d9a8efd70 |  | note | – – – – – – – – – – – – – – – – –
label | 9140098b-408f-52d8-a4dc-0d3891d4fe46 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | ff24c6db-df11-5511-87d0-e681d662d276 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | e19c800a-d3b4-557d-b2cc-894a8d981390 |  | note | REFERENCE: MRPA Quality Management Plan
label | 174c21e0-7586-50eb-a323-ed871830d154 |  | note | – – – – – – – – – – – – – – – – –
label | 75868e33-abdc-59b0-a0b7-1e2c0c8f6059 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 78a2df68-7af8-5ceb-9d00-3996c3f7fd79 |  | note | – – – – – – – – – – – – – – – – –
label | beb0dbd0-f9f7-583d-b091-59d79c186c92 |  | note | METHOD: Document Review
label | 2a85e407-ed37-518c-8c35-6b708babed31 |  | note | – – – – – – – – – – – – – – – – –
label | 0fcd3d77-72fd-5c4a-abd6-b9b0626fe647 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | bed4ba33-8ca4-5007-856f-5d3f1e63b659 |  | note | – – – – – – – – – – – – – – – – –
label | f29ae1a9-7ef2-5b4a-84c6-e8ee571aad4c |  | note | CATEGORY: HP*
label | 280bc707-eb76-51c8-8d53-20aae27e4795 |  | note | – – – – – – – – – – – – – – – – –
label | 7a988826-bdca-5213-83e5-6ac20364eac6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9385e4ce-b913-563a-910c-fca2f67d635e |  | note | – – – – – – – – – – – – – – – – –
label | 43b46741-b3e7-5379-93be-e5f6ab6cf5e6 |  | note | VERIFYING DOCUMENTS: This ITP Signed Off
date | 28c9448c-8fd1-50a0-a83f-554d050febca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 059e18aa-ec6f-5378-9fd7-8f6a5c7aeb8f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5e4d66f1-07a0-557f-bf9e-a2152fcdfc76 |  | textbox | Name:
text | 665dc205-1b45-51f2-84c9-8a27fbdd2b91 |  | textbox | Position:
date | f26b4ea8-2ba3-59c3-a122-03da4b972f5e |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-144-CIV-SSB-RSS Wall Construction | itp |  |  |  | Yes | ITP-144-CIV-SSB-RSS Wall Construction Rev 0 | fc449c12-f15e-468a-8a2e-3cb6f859bec4
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 7ad3c78b-2f0b-513d-8c6f-da6190184698 |  | note | Document Title: ITP-144-CIV-SSB-RSS Wall Construction
label | d880b081-dade-5850-b050-de4600aa1b05 |  | note | ITP Description: SSB-RSS Wall Construction
label | a9a0bcdb-a8a7-5f93-9c09-9402dfb91255 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 88e74bca-e038-590c-88f1-20e96e7fa230 |  | note | Discipline (e.g. CIV/STR/RAIL): 144-CIV
label | afc06562-808d-5465-9916-83b2c7633a51 |  | note | Revision Number: 0
label | 903f386e-73a4-51be-85bf-84af5e900434 |  | note | Revision Date: 18/3/2024
label | cbebac8e-17f4-5121-a7b1-8c6407ff04f7 |  | note | ITP created by: Victor Mira
label | cddbb23b-899b-509a-a200-df903ce7564f |  | note | ITP approved for use by: Victor Mira
label | ccd2882a-0873-5f42-b217-0b353c7e2dc9 |  | note | 1.1 Non Dependent
label | 4b46dea2-ef3e-5672-86f8-86df3d031cc9 |  | note | Reference: VicRoads Section 682 November 2018
label | 89989d33-1342-51fe-9733-7a454f9a72a4 |  | note | 1.2 Non Dependent
label | ce0b7fd0-fa2a-539a-bace-ca4c9177c8bf |  | note | Reference: VicRoads Section 204 December 2015
label | dbdd145e-0b3f-5b84-8e50-600928bf60dd |  | note | 1.3 Non Dependent
label | acce2aee-1fdc-5a25-b126-5e5bcfabb53f |  | note | Reference: IFC drawings
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete-Leveling Pad
label | 12841b11-31cb-59c2-a511-54310882c823 |  | note | REFERENCE: IFC drawings
label | 3e6f675f-680b-543a-b3e4-b30a92334305 |  | note | – – – – – – – – – – – – – – – – –
label | 0d8cd981-3262-5320-932b-7fa1e6e80bc4 |  | note | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
text | 7b9389ab-22b9-5941-86e3-f5d19b738fc3 |  | textbox | Reference: Teambinder MA number:
label | 65eb4491-4549-5708-b90c-baa40fa5886a |  | note | – – – – – – – – – – – – – – – – –
label | 69e86604-782e-5b81-8026-1359a7960350 |  | note | METHOD: Document Review
label | 8893c1d3-5a3e-5a34-92da-43fe8b713d88 |  | note | – – – – – – – – – – – – – – – – –
label | 6ef02bae-8f12-582c-afde-2adb97a07544 |  | note | FREQUENCY: Each element
label | c8884770-39be-555b-9141-89a559738aef |  | note | – – – – – – – – – – – – – – – – –
label | 4a3ba61a-7e29-5d23-8431-32acb60834ed |  | note | CATEGORY: HP*
label | 935018c7-aaa8-5851-ba95-e5f701728ef0 |  | note | – – – – – – – – – – – – – – – – –
label | 4d2335d1-4704-519e-a0d9-51700c5a360e |  | note | RESPONSIBILITY: PE/Nominated Authority
label | f75e9f06-f1f6-5fed-a681-2bdcdf8c6b2d |  | note | – – – – – – – – – – – – – – – – –
label | e0358049-d6d1-5d85-8fa2-85c7978dbf7a |  | note | VERIFYING DOCUMENTS: Material approval
date | 36abb0e3-2987-55c6-b8f3-ce6d7b37032b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Select fill
label | 5538da05-feaa-5df2-94b6-8eb7434ba3ec |  | note | REFERENCE: IFC Drawings
label | cd9c5b4b-30a3-5136-9ecd-8cb4d2c851e2 |  | note | – – – – – – – – – – – – – – – – –
label | e1f2b542-6c18-5282-86d9-f5fca95f73a7 |  | note | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer:
label | 16d9e723-6f50-52fa-81fe-07330e507a9c |  | note | ○ UNIT WEIGHT: 22 ± 2 kN/m³
label | 98c581e7-e513-528e-b93a-9436682e6bdf |  | note | ○ INTERNAL FRICTION ANGLE ≥ 34.5°
label | 4aae1d1f-b387-5314-b75c-c92ff531085f |  | note | Gradation:
label | 409235d4-dd76-5a80-901d-261e26d168d3 |  | note | ○ 150mm : 100% PASSING
label | cde48e1b-8c0e-5443-a66a-6e23407ddb4a |  | note | ○ 37.5mm : 60 TO 100% PASSING
label | 047f778c-56fc-5320-8448-cd0d0782be95 |  | note | ○ 9.5mm : 25 TO 100% PASSING
label | c3769af8-8fa0-56a6-bfdf-4c8ffe1f8740 |  | note | ○ 2.36mm : 15 TO 100% PASSING
label | 77eb1c01-c387-5ae0-906f-0ebe7c8de976 |  | note | ○ 0.6mm : 10 TO 100% PASSING
label | 26d6702a-8a8c-5fe3-b761-cab58d85c7a0 |  | note | ○ 0.075mm : 0 TO 15% PASSING
label | 1a7fce39-0557-5249-898d-edaf0c0e28fd |  | note | Electrochemical Properties:
label | fcf14360-15d9-5928-afd3-329ebfb6d946 |  | note | ○ RESISTIVITY >1000 Ω-cm
label | c3685c0f-88f1-5e4b-b87d-8a627ad7a2b8 |  | note | ○ CHLORIDES <200 mg/kg
label | 3d826144-95b9-5d14-a59b-bc5f874206fa |  | note | ○ SULPHATES <200 mg/kg
label | f931cc97-7724-5fca-8ebd-41dce801ca52 |  | note | ○ ORGANIC CONTENT 0%
label | 5332a1eb-3b36-50e1-9787-5b67abd3cd2e |  | note | Structural Properties:
label | 49fe130d-491f-53bb-a217-35467b982d8c |  | note | ○ COEFFICIENT OF UNIFORMITY ≥ 5
label | f30e1e07-cdae-5e2d-8c22-9b9b0e3e771a |  | note | ○ LIQUID LIMIT ≤ 30%
label | 05a797f5-601f-591c-bb02-660ed051439b |  | note | ○ PLASTICITY INDEX ≤ 12
label | abfe3017-4c42-523b-b463-7fd939f1777e |  | note | – The select backfill must meet the minimum requirements of Vicroads Type A filling
text | b62174d2-f934-5310-966b-95a9e5584219 |  | textbox | Reference: Material approval in Teambinder
label | a1726c78-5a9e-5a43-8610-05b1cfd71514 |  | note | – – – – – – – – – – – – – – – – –
label | 4278ada4-0aee-52f5-9d06-2864e2a4a665 |  | note | METHOD: Document Review
label | 20164af5-b0ae-57da-a26d-c1c9735ab14f |  | note | – – – – – – – – – – – – – – – – –
label | e950c5f9-1b81-5b04-b1fc-11b967a4ef66 |  | note | FREQUENCY: Each material specification
label | 2238bd13-cc08-50f8-baa1-1c38a1f7858f |  | note | – – – – – – – – – – – – – – – – –
label | 2219de46-0ad1-5a63-8905-8b6f14830894 |  | note | CATEGORY: HP
label | 5ec9cb57-0111-5d60-b1b2-3d6daa32321a |  | note | – – – – – – – – – – – – – – – – –
label | 73d6dcdf-e915-5f99-8a83-40ea9c6a4df3 |  | note | RESPONSIBILITY: Nominated Authority
label | 4f96df17-2030-5b3e-a9a4-ddb52bcae5ee |  | note | – – – – – – – – – – – – – – – – –
label | 31e39188-ef3a-5588-b378-f6d6483a8b4d |  | note | VERIFYING DOCUMENTS: Material approval
date | f5e59fd2-8dfe-5122-9c74-cbe1447e16d1 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Perforated Pipe-material
label | a9ead059-b8b3-5175-ba46-e2a4ad941b2e |  | note | REFERENCE: IFC Drawings
label | 6a910136-450a-5bd8-a1bf-c5c6c35b165a |  | note | – – – – – – – – – – – – – – – – –
label | cc06d5d2-7525-5a4a-aa05-e9adc4c8af4a |  | note | ACCEPTANCE CRITERIA: Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
text | 5a3b6409-1321-5775-8753-bdb3af193482 |  | textbox | Reference: Teambinder MA number:
label | 8001ef0e-7023-542a-aa87-bc2e87307988 |  | note | – – – – – – – – – – – – – – – – –
label | a1c29cfe-5a57-52c3-b14c-cbae3039e15c |  | note | METHOD: Document review, Measure
label | fa8b5889-3013-5b6b-942f-867c06877d97 |  | note | – – – – – – – – – – – – – – – – –
label | 123f1c54-3481-5d14-9b77-18eb62ef760f |  | note | FREQUENCY: Each wall
label | 77a2285c-f12b-5b20-a6f9-c553ec69f8c7 |  | note | – – – – – – – – – – – – – – – – –
label | d9957710-3f72-5ac3-9b61-761e76413309 |  | note | CATEGORY: HP
label | 01cf6161-989b-5d03-9df7-9e410c61c95e |  | note | – – – – – – – – – – – – – – – – –
label | ddeb2f02-2a00-594c-aa61-09ce4dff610b |  | note | RESPONSIBILITY: Nominated Authority
label | 627f4dad-b2b8-5546-afda-40a76ab5cad0 |  | note | – – – – – – – – – – – – – – – – –
label | 189f15cd-f97c-535c-9608-cb7af52418a8 |  | note | VERIFYING DOCUMENTS: Material approval
date | 3533b6bb-7a00-5e3a-bf0a-cb7255599af9 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 RSS Panels
label | 79090a72-c573-512e-acf8-ec970a324621 |  | note | REFERENCE: IFC drawings
label | c10c9a27-577a-52b4-aa26-44f650c43b22 |  | note | – – – – – – – – – – – – – – – – –
label | e7ef0130-b096-5b10-9fb6-4a4252d4aba7 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | d6c9a64f-07f6-5bcd-b288-1792e9ce54d8 |  | note | i. Certificate of Compliance / Birth Certificate
label | 19a50b73-4b6a-5835-9099-d2b59466f32b |  | note | ○ 1. Concrete strength;
label | 001a0a5e-443d-54c9-9da1-014f198c5f29 |  | note | ○ 2.Date of manufacture;
label | d5c64f41-0532-5ce6-a45b-7aad66cd3069 |  | note | ○ 3.Unique Identification number;
label | ae20fc96-8122-5e3c-9c34-1534935c609c |  | note | ○ 4.Mass;
label | 43200c0f-b98c-5c18-b138-da3972291f87 |  | note | ○ 5.Confirmation of number, type and capacity of lifting inserts;
label | 23b7c9c5-217a-52b8-98fb-77e2abb9cc65 |  | note | ○ 6.Quality assurance sign-off.
label | 717b00a8-882f-5b2d-adfa-b0d1aa737e1f |  | note | ii. Compressive strength test results
label | 053e846d-8a19-5a9e-aeab-e6a8cff9a15f |  | note | iii. Precast Lifting Design
label | b7a4adc2-5875-5bfb-833d-f4101f54d551 |  | note | iv. Pre-pour check sheet / ITP
label | e6720480-6bc6-58c2-900c-c6a4f14ba79e |  | note | v. Post-pour check sheet / ITP
label | 36cd4d9b-2573-53e5-850c-cecf22b4e59f |  | note | vi. Covermeter check record
label | b4c8b84f-46da-5ac3-8134-9b43a7b104e4 |  | note | vii. Record of dimensional measurements
label | dac40754-5737-5351-b276-9a595e320fd0 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
text | ec34e2b0-8d76-5719-a87d-e32a3b46e342 |  | textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | 3d306289-e4f8-5a62-b6ea-2647c2a61649 |  | note | – – – – – – – – – – – – – – – – –
label | c1ed81aa-9be8-5366-afdf-bfb6c21a4e5e |  | note | METHOD: Document Review
label | 4967a8f1-5b9c-5b3a-a32c-3326f2bfa482 |  | note | – – – – – – – – – – – – – – – – –
label | 32d6a93e-9882-5351-a841-fe8cb1a91b0d |  | note | FREQUENCY: Once for each type of panels
label | 02cb1273-a16e-5b6c-b66a-0074d4469ebc |  | note | – – – – – – – – – – – – – – – – –
label | d4fb2498-432c-5a7b-a46c-a1d894512acf |  | note | CATEGORY: IP
label | 176c8f73-e46a-5867-8660-ade4f9102fb5 |  | note | – – – – – – – – – – – – – – – – –
label | e7687614-7455-504f-84ae-00888180af33 |  | note | RESPONSIBILITY: PE
label | def9e81f-5601-55bd-8e8f-28c8f1eca2ac |  | note | – – – – – – – – – – – – – – – – –
label | ef6eb6bd-d2fe-5837-bbd7-a84885c46d97 |  | note | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
date | e3395073-b7dd-5a06-aa7d-85efb2e3eda8 |  | date | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Foundation
label | 1cd0bf17-fb3b-5968-9a63-3280672f256c |  | note | REFERENCE: IFC Drawings
label | fca44326-3fbd-5fc1-bb4b-768c05bc6e43 |  | note | – – – – – – – – – – – – – – – – –
label | c85e7209-11ad-50c1-ba1f-74191e8e275a |  | note | ACCEPTANCE CRITERIA: The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
label | 9710936f-c34c-5cec-a8f2-e78d7cf6d67f |  | note | ○ Effective friction angle: 28°
label | 72e8b1c7-0812-5b9c-891a-0c4909ad2669 |  | note | ○ Effective Cohession: 5 kPa
label | 03bdf0c0-2949-5f99-8c43-723d9538f9f9 |  | note | AN ARCADIS GEOTECHNICAL ENGINEER SHALL ASSESS FOUNDATION SOILS DURING CONSTRUCTION.
label | 819f6e5f-18b9-57d6-9f7a-960c616de0db |  | note | Attach: Geotechnical report/Certification
label | b984bbac-f241-572c-ad1e-d75ffd42b773 |  | note | – – – – – – – – – – – – – – – – –
label | 3cd0a9b3-9774-5bbe-a604-c94e4eb9996e |  | note | METHOD: Test, Document Review, Visual
label | 2358ce99-0e53-5494-8077-24f18d094851 |  | note | – – – – – – – – – – – – – – – – –
label | 42200a5e-ff5a-546a-87a0-f3155fcd33e7 |  | note | FREQUENCY: Each retaining Wall
label | ed0e892e-9244-5900-b16d-6ec475e1675a |  | note | – – – – – – – – – – – – – – – – –
label | 22937a1d-aa00-543e-a7ad-45c6b77cd0e1 |  | note | CATEGORY: HP*
label | 58067fed-8bdb-56e1-a45e-43cae380ebfb |  | note | – – – – – – – – – – – – – – – – –
label | fd49ae0c-3168-55de-99dc-333c4f63869c |  | note | RESPONSIBILITY: PE/Geotechnical Engineer
label | 4e5e8017-c7ba-59b0-ac5a-ba2bebb997a4 |  | note | – – – – – – – – – – – – – – – – –
label | d1551015-bd06-571c-a302-bacbd82e7ccc |  | note | VERIFYING DOCUMENTS: This ITP, Geotechnical report
date | e1e62571-f1c2-576e-a333-64f58a0c73c8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Foundation
label | cab71637-022a-5978-9f35-8bbaf7ce546a |  | note | REFERENCE: IFC Drawings
label | 02c78c07-64dc-5770-80fb-c97e8d0197b7 |  | note | – – – – – – – – – – – – – – – – –
label | 803fe055-880b-526e-a9af-3b05f6795969 |  | note | ACCEPTANCE CRITERIA: Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
label | 57bfc6c2-917f-5e66-981e-b8f2bc126b47 |  | note | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
label | d919ab1e-22e3-5558-8dc8-4fbb1edebd58 |  | note | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
label | 6e9787e1-9826-54cf-beca-25e577c14662 |  | note | – – – – – – – – – – – – – – – – –
label | 46ead4dc-2e84-5f69-838f-95d658245b3a |  | note | METHOD: Visual
label | d94a1569-52bf-5519-b86d-c077f3c83b21 |  | note | – – – – – – – – – – – – – – – – –
label | 9881fc5f-44e2-5748-89b1-ca4949885961 |  | note | FREQUENCY: Each retaining wall
label | e0b35445-1085-5b4e-a8dd-7101c67d4611 |  | note | – – – – – – – – – – – – – – – – –
label | f198d7d1-600c-50f1-b09f-3e0c14e80e83 |  | note | CATEGORY: IP
label | b1429708-190d-5bc4-a79e-3639ebd1767e |  | note | – – – – – – – – – – – – – – – – –
label | efb97b4a-c9bd-52d1-9281-2e23b4efc43f |  | note | RESPONSIBILITY: PE/Geotechnical Engineer
label | 1fc17ef4-8e95-5603-9259-2c346495fcef |  | note | – – – – – – – – – – – – – – – – –
label | cc666beb-def9-5a93-8abb-4d550378ecb6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 634c9e9c-5cdd-5bf0-896c-a723fa3a0244 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Foundation
label | cf5ca20e-362b-59de-8d5b-062c043c537a |  | note | REFERENCE: VR 204.12, VR 204.11
label | d865eeac-f3cb-5411-8af1-cefa68fa453d |  | note | – – – – – – – – – – – – – – – – –
label | df20ee42-3919-5e75-8740-c840aa5293cc |  | note | ACCEPTANCE CRITERIA: areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | b255fe5f-0b37-5e41-bd62-429c1ae782d8 |  | note | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | eed22e75-a5a0-5519-aa69-eb2a6a51ea17 |  | note | – – – – – – – – – – – – – – – – –
label | 7147e00f-ac8f-54d6-9aa6-ff5756571eef |  | note | METHOD: Visual
label | 2db224e9-f70e-5185-b77f-3921c3f5ac8c |  | note | – – – – – – – – – – – – – – – – –
label | c3d9d64e-3225-59b0-ab91-0929dae8613f |  | note | FREQUENCY: Each retaining Wall
label | 833c4cbb-f4eb-5ff5-9bcf-e8543416144d |  | note | – – – – – – – – – – – – – – – – –
label | 6a147e13-7724-5efe-985b-4b20cf500f0d |  | note | CATEGORY: HP
label | 284c9003-363f-5349-a77b-d3b011197bf2 |  | note | – – – – – – – – – – – – – – – – –
label | 51e048fb-1257-5cda-940f-ef778b4cefbb |  | note | RESPONSIBILITY: PE/Nominated Authority
label | c1bdbb93-f6e4-5a4a-943c-1b979ba418b5 |  | note | – – – – – – – – – – – – – – – – –
label | 27983d05-6f91-59d0-984d-31baa131db27 |  | note | VERIFYING DOCUMENTS: This ITP
date | ceaa93fa-4660-5a3a-bf1b-366d0c5f21f5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Levelling Pad-Survey Set out
label | b3ff7f4b-c8ce-5158-b0d3-8803af3db069 |  | note | REFERENCE: IFC Drawings VR 682.20
label | 358fffa8-d00f-558c-a407-656ee782eb79 |  | note | – – – – – – – – – – – – – – – – –
label | 1901854a-2862-553f-865e-b767b27e0f11 |  | note | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
label | 52782192-82c7-5d74-a227-3e6249b3e17c |  | note | – – – – – – – – – – – – – – – – –
label | 14c39524-58ec-56b6-ab68-a5a9e525d2a2 |  | note | METHOD: Measure, Visual
label | 22370400-034c-5874-90e6-7821ee538ba0 |  | note | – – – – – – – – – – – – – – – – –
label | 5f18d70c-b60c-5044-82f7-e70611e051c3 |  | note | FREQUENCY: Each retaining Wall
label | 38e10fa7-9618-57a4-b2f8-de49f761e9d5 |  | note | – – – – – – – – – – – – – – – – –
label | d06b5e84-2b0d-553c-b1ee-f1d3e649db51 |  | note | CATEGORY: IP
label | 364de2d2-da30-57a3-ba31-5d7a118933da |  | note | – – – – – – – – – – – – – – – – –
label | 8b7cdc3a-f0c6-5a0f-be52-a37a2cdce27d |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 7ffbc1d0-cd34-5e48-b958-9d2a77b6d830 |  | note | – – – – – – – – – – – – – – – – –
label | 57cd80be-ec5b-55ca-8b16-b3fdb417d07d |  | note | VERIFYING DOCUMENTS: This ITP
date | d98c2d0a-db24-5bf4-b899-e299e68db2af |  | date | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | Shape Arrays installation
label | 09aed333-d01b-5361-aac4-c5790d399aed |  | note | REFERENCE: IFC Drawings MRP-087-C-ACD-DRG-10-BFD-CSF-3404
label | f7f0eead-5568-5c34-a281-2f645a235c83 |  | note | – – – – – – – – – – – – – – – – –
label | 7c7d214b-c460-5519-b816-eb20931a0e99 |  | note | ACCEPTANCE CRITERIA: Shape arraye are to be installed and mainatained as specified in Design package 10 notes:
label | 02f7e053-5c23-574a-828a-20d8005268ec |  | note | ○ Shape arrays shall be installed horizontally across the full width of the embarkment prior to placement of the embankment and reinforced soil structure walls, in accordance with the manufacturer's instructions. Shape arrays shall be installed nominally 5m, 25m and 50m from both the north and south abutment face.
label | 68520ae1-249f-5060-a62a-f0e83e7c8016 |  | note | ○ Upload Shape array installation records.
label | aa392a7f-ed5b-5cd0-bf3c-6b6145fbea24 |  | note | – – – – – – – – – – – – – – – – –
label | 0789003b-b5ae-587c-8c29-04803c2933e2 |  | note | METHOD: Visual
label | 7f8c3861-03e8-5952-84cd-b4091220b75f |  | note | – – – – – – – – – – – – – – – – –
label | 3aaf4b24-6499-5f85-8d1e-3089abb04792 |  | note | FREQUENCY: Each RSS Block
label | b7ae658b-1cd6-5b11-964c-7b0d2c3ede36 |  | note | – – – – – – – – – – – – – – – – –
label | 0fd03f09-488c-539a-aea3-2ca1d802d79a |  | note | CATEGORY: IP
label | f01c55ed-9408-5d14-bb0d-adfb03f7240f |  | note | – – – – – – – – – – – – – – – – –
label | eda51fbc-2413-505d-9ba9-3d232b329616 |  | note | RESPONSIBILITY: SE
label | 2b7c9de5-0341-59a1-9f87-c8a17c47b18d |  | note | – – – – – – – – – – – – – – – – –
label | 3a3d31cf-a0fe-5b32-8334-36830af3d4ca |  | note | VERIFYING DOCUMENTS: Installation Documents
date | 258fe6d3-73b5-5c65-ba27-b20b2eb60303 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Form Levelling pad
label | e9cd0f2b-d95f-597b-bda6-c382f6961645 |  | note | REFERENCE: IFC Drawings
label | d4d4cd6a-8591-5927-ae2f-d1e9c076259b |  | note | – – – – – – – – – – – – – – – – –
label | c8cbb7a7-9ba7-5d09-a0e6-def4c8edd565 |  | note | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
label | c0d67f61-be66-5084-9e17-28fe1b68ac1a |  | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | 04bd62ee-f76f-5fd7-adb4-0558070a2bdb |  | note | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
label | 0e737d70-113a-5644-af6d-cdf5fd8d2660 |  | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | 49e167ec-89a9-55b3-8b74-5dba87e8cf4a |  | note | – – – – – – – – – – – – – – – – –
label | bc8a1bb0-d3bb-5fda-81a7-ec71d07bbe39 |  | note | METHOD: Measure, Visual
label | b960ac2f-9b1d-535e-b10a-4f8b069a637a |  | note | – – – – – – – – – – – – – – – – –
label | 6271dea0-352a-59f9-a8da-e5a4165328dd |  | note | FREQUENCY: Each Lot
label | cfec660e-660e-5585-8e54-39b6a73686f4 |  | note | – – – – – – – – – – – – – – – – –
label | ffb03464-c6bc-5918-849b-4ec4ee0d884a |  | note | CATEGORY: IP
label | e9a86b8d-e110-5be1-9855-dc267715c741 |  | note | – – – – – – – – – – – – – – – – –
label | 0bd4f8d6-30bd-5b3f-bfdb-12b487ea1574 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ad973360-9c63-520d-8b85-4e650f5d57e7 |  | note | – – – – – – – – – – – – – – – – –
label | 4bf17680-74bc-59ed-b26d-44c513c791e3 |  | note | VERIFYING DOCUMENTS: This ITP
date | 2e9570bf-fe08-57ed-964d-36ad10e6dd83 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Leveling Pad Concrete Pour
label | aa727c9a-f2b7-51a4-9d79-08e75f9bf5b5 |  | note | REFERENCE: IFC Drawings
label | dd714741-6928-5197-b711-a7bd35ae95f2 |  | note | – – – – – – – – – – – – – – – – –
label | fba66a65-9c96-5b8d-9de6-850854d6a7f5 |  | note | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
label | 68c70c17-9f5d-597d-81e9-eec0b929e9d2 |  | note | Attach: Concrete Delivery Docket
label | 0b4471ce-25ab-5e5f-90fa-cd7ad685ad97 |  | note | – – – – – – – – – – – – – – – – –
label | 37066468-de5c-5be1-85f4-e6c3a104d416 |  | note | METHOD: Visual
label | facf59e7-d364-5023-84c7-8a3766844e99 |  | note | – – – – – – – – – – – – – – – – –
label | af56a489-666d-5863-9d85-35a687aa276a |  | note | FREQUENCY: Each Lot
label | 49999b10-5a40-5fc2-b020-ca0428e8c023 |  | note | – – – – – – – – – – – – – – – – –
label | 4435172e-7306-5460-8cdf-b6a3938588c0 |  | note | CATEGORY: IP
label | fc5a2320-63a8-5d01-a460-89799dead79b |  | note | – – – – – – – – – – – – – – – – –
label | 45414a59-ed0a-586e-809e-19c4ffa926a9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f26f41b2-ca16-5778-ab13-36d7a4390847 |  | note | – – – – – – – – – – – – – – – – –
label | 8945ab04-2ae8-507b-bae0-316d235d3655 |  | note | VERIFYING DOCUMENTS: Concrete Pour record
date | 343bfad7-aa6e-502c-85ef-d8387bef0389 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Leveling Pad Concrete Testing
label | 594c6d8f-3da0-5870-bc9b-73ec4d35f907 |  | note | REFERENCE: IFC Drawings
label | c9ce1adc-e686-52a7-a7ef-9c25a0a2460f |  | note | – – – – – – – – – – – – – – – – –
label | 3e35fbbe-5663-5ddc-a984-75d390923b34 |  | note | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | 30d955b1-cbb6-5da6-a257-868069aac3b6 |  | note | Attach: Concrete test report
label | 8a7c63b0-1195-52f6-8f88-af2fdf07b4f9 |  | note | – – – – – – – – – – – – – – – – –
label | 807d0ada-8bcd-59c3-ae06-6e795d7edfd4 |  | note | METHOD: Document Review
label | 554d5f7b-da28-5009-a668-c6c9d2429cce |  | note | – – – – – – – – – – – – – – – – –
label | 7db57bbf-3b19-5a19-8719-ec8de02297cd |  | note | FREQUENCY: Each Lot
label | 1892be49-1fbe-5bc8-9812-22663bce13ea |  | note | – – – – – – – – – – – – – – – – –
label | b1d3b9bd-a708-5926-a1ac-d2cc36e3b1ec |  | note | CATEGORY: IP
label | 0fafa312-79f1-580c-925a-7a5af80c30d5 |  | note | – – – – – – – – – – – – – – – – –
label | c1dee926-404d-5a8c-a50d-08ba79627051 |  | note | RESPONSIBILITY: PE
label | abf80ebe-3b83-5157-9db5-7f64857b4a81 |  | note | – – – – – – – – – – – – – – – – –
label | 2bb5c4a3-b70b-58bc-8637-89dd2a99b2ce |  | note | VERIFYING DOCUMENTS: Attach Concrete Test Report
date | 86eec4b8-7de5-5505-942d-5651d12e50a4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
label | 490ee8f7-4a9e-54a1-89c4-472a8f5a40ae |  | note | REFERENCE: IFC Drawings
label | 52659107-caa2-5f90-b95b-f3f4a9a388b1 |  | note | – – – – – – – – – – – – – – – – –
label | 8ee36dcd-536e-5d69-949d-3c7e56de3765 |  | note | ACCEPTANCE CRITERIA: Levelling course level shall not deviate from the specified level by more than ±3mm
label | 76d56fd0-5895-57b4-aab4-b01530cebdfa |  | note | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | efa32bf9-e027-5dbb-bb4c-f9806df78e61 |  | note | – – – – – – – – – – – – – – – – –
label | 0f08dff7-9707-54ac-a86b-1c5315b0bc46 |  | note | METHOD: Measure, Visual
label | 3e05026d-9ac3-50f5-8978-c4b7b11c5a65 |  | note | – – – – – – – – – – – – – – – – –
label | 4b1c397a-2d5f-5546-b9f8-e4586befaa6b |  | note | FREQUENCY: Each retaining Wall
label | 57a66164-7580-5b5e-bbd6-c5445437490c |  | note | – – – – – – – – – – – – – – – – –
label | a64bfb34-0064-5ded-8ffd-0d66d572499f |  | note | CATEGORY: IP
label | 4b647753-29dc-5dc9-bcef-212ab2ceff34 |  | note | – – – – – – – – – – – – – – – – –
label | 835cc6d4-b903-5a6b-9487-3b5b08798e72 |  | note | RESPONSIBILITY: PE/Surveyor
label | 665823c6-afee-52ed-a751-2612175d57d4 |  | note | – – – – – – – – – – – – – – – – –
label | 52c05d7c-e0f2-5887-ba8f-cd7f0cc8cc69 |  | note | VERIFYING DOCUMENTS: Attach Survey Report
date | acb41b4b-8e58-5f90-b0ec-93b9bf1e8ee8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Wall Panels Installation
label | e365f60e-32ce-5471-9e13-345809a17a9b |  | note | REFERENCE: 682.17
label | 7f477fb4-ae85-53aa-9b1b-87aa7026eb89 |  | note | – – – – – – – – – – – – – – – – –
label | 69a26c47-d2a7-5ca1-b85e-60a5feef9c66 |  | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | 1b098574-2980-5f81-bc77-fb02ed6a8ac3 |  | note | ○ Refer to checklist for each course of panels
label | 6605377f-4861-582e-b8a8-694332c18ffa |  | note | Attach: Lot map
label | be072aba-27e1-56a8-b5b6-49145b645787 |  | note | – – – – – – – – – – – – – – – – –
label | e7ab7946-21dc-56c2-9832-a62864ec554f |  | note | METHOD: Visual Measure
label | 53634b96-50fd-5833-a4c7-4a553db5dc61 |  | note | – – – – – – – – – – – – – – – – –
label | 45459ef7-f294-5957-ae1f-248235b6b4cd |  | note | FREQUENCY: Each course of facing panel
label | 76c9e556-15bf-515c-b1c4-99d69e74b281 |  | note | – – – – – – – – – – – – – – – – –
label | e13504ea-ecb0-5f9c-85c1-1212f0b443a7 |  | note | CATEGORY: HP*
label | aaecb0dc-580d-5232-858e-893f0a065a26 |  | note | – – – – – – – – – – – – – – – – –
label | e89ec47e-f6b0-5956-8dc7-fce730b342df |  | note | RESPONSIBILITY: PE/SE
label | 8f074b5a-7d2b-55cd-aa32-a2634a33c158 |  | note | – – – – – – – – – – – – – – – – –
label | d17e41ee-68db-5a20-a0e2-b546d8a554a1 |  | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
date | 209ad745-7ca3-5b44-9001-89cca910d271 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Drainage-base of the Wall
label | da807f56-c4d4-54f0-8f70-141510e51b24 |  | note | REFERENCE: IFC Drawings VR 702 MRP-087-C-ACD-DRG-10-BFD-CSW-3520
label | d6548a8c-3f3a-54ab-8a9b-49c0d7eb4e6f |  | note | – – – – – – – – – – – – – – – – –
label | 1b415726-0c45-5599-a32b-effde5260171 |  | note | ACCEPTANCE CRITERIA: 300mm Wide Strip Drain along back of RSS Precast Panel at 2m c/c with 100mm clear distance from straps. Strop Drain to be encapsulated by Non-Woven Geotextile in accordance with DTP Section 682
label | 92b3b951-7018-5e9d-9738-ff8df186663b |  | note | ○ 100mm dia. perforated subsurface longitudinal drainage (1:100 Fall) 500mm nominal above existing surface level wrapped in geotextile and encased in free draining material.
label | 06311d75-e0cf-50c4-a6c5-b03cb64272ef |  | note | ○ Refer to Precast Panel Installation Checklist for each course of panels.
label | 2bd9f354-c94d-58fe-8719-9244a0e750b4 |  | note | Attach: Lot Maps
label | 7831e8de-5992-5b64-a518-5b72c1f51c2b |  | note | – – – – – – – – – – – – – – – – –
label | 7bb01222-27d0-5f04-948c-bd6f61cdc77a |  | note | METHOD: Visual
label | c82b7b84-9c15-5b2c-a401-bda893a1ae04 |  | note | – – – – – – – – – – – – – – – – –
label | b5e9931b-0d58-5c98-b484-f98c144264bc |  | note | FREQUENCY: Each wall
label | e80e5788-0d45-5eb9-b89f-720c0f565683 |  | note | – – – – – – – – – – – – – – – – –
label | c315c6a8-3a6e-5a5a-9552-6a7bf9ddefd4 |  | note | CATEGORY: IP
label | 881c529d-1d5e-570d-a80f-6c5e0b1c6204 |  | note | – – – – – – – – – – – – – – – – –
label | 99975a0c-ea48-535b-ad4b-d95e44fb07ef |  | note | RESPONSIBILITY: SE/PE
label | 35864f5f-3dc6-5116-925a-c7f2c843e3f5 |  | note | – – – – – – – – – – – – – – – – –
label | d94c8266-1a29-5546-a86f-fdef80de015e |  | note | VERIFYING DOCUMENTS: This Checklist
date | 094648ae-79b8-5e4c-a559-c6b28e95da70 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Fill
label | 402dfbad-a88b-5a1a-9817-117a95467f23 |  | note | REFERENCE: 682.16
label | 6dc30382-2731-5314-ad92-961005dcfbe8 |  | note | – – – – – – – – – – – – – – – – –
label | 46612f81-9bfd-5920-9266-a7bcc8485b35 |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | b11fa154-f86f-5af9-850c-968d46de8988 |  | note | ○ Refer to checklist for each fill layer
label | 4946ec95-ddc9-5922-8d70-78234f05ca7c |  | note | Attach: Lot map
label | 983975b1-ef46-5acf-9ce6-f51b3db6e05e |  | note | – – – – – – – – – – – – – – – – –
label | 861fed06-d640-56af-aca4-98fcc408fe9b |  | note | METHOD: Visual, Test, Measure
label | 85f5266e-2400-501f-9f3a-3b265aefe2e8 |  | note | – – – – – – – – – – – – – – – – –
label | d3d779dc-125e-5686-841b-114ba2103d62 |  | note | FREQUENCY: Each layer of fill
label | 97415daf-8538-5a7c-99a7-be41d33888e4 |  | note | – – – – – – – – – – – – – – – – –
label | af461c11-7523-5cd8-b742-8873c4bd3010 |  | note | CATEGORY: HP*
label | 82dcc5b4-f1e7-5600-ab4e-d65d067a08d6 |  | note | – – – – – – – – – – – – – – – – –
label | 91502871-82e5-58a9-8fa0-6560b93eb46f |  | note | RESPONSIBILITY: PE/SE
label | 22065aa6-95d1-5881-9237-ec53bfd484ee |  | note | – – – – – – – – – – – – – – – – –
label | 8bb02fe7-9911-5aeb-aaf4-556bff11c760 |  | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
date | dc894ae6-bb98-55c6-a525-9946a2ec7755 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Panel installation-Settlement monitoring
label | 13d862c2-dfda-5aa7-80a4-980411e24608 |  | note | REFERENCE: IFC Drawing MRP-087-C-ACD-DRG-10-BFD-CSF-3404
label | 3fd2a39e-4354-5699-8b39-f3a368fa6af3 |  | note | – – – – – – – – – – – – – – – – –
label | a22fde84-6cad-563f-8f3b-338c5ffd79c6 |  | note | ACCEPTANCE CRITERIA: III. DURING FILL PLACEMENT - ONCE PER FORTNIGHT (OTHER PANELS).
label | 2f633cd4-c418-559b-a840-57351a7b3cf2 |  | note | II. DURING FILL PLACEMENT - TWICE PER WEEK (SHAPE ARRAYS AND BOTTOM ROW OF PANELS ONLY).
label | e66953cd-d47c-5c58-9425-9a5048c224db |  | note | I. AT LEAST 2 WEEKLY BASELINE READINGS PRIOR TO PLACEMENT OF FILL MATERIAL.
label | c9ba1343-5ba6-5f7c-ac04-6608719d3dc3 |  | note | ○ FREQUENCY SHOWN BELOW.
label | f498f227-8b5f-5994-9f44-8fd9b77b7632 |  | note | ○ SHAPE
label | 0893058b-0448-558a-bcff-2e21f44c7c37 |  | note | – – – – – – – – – – – – – – – – –
label | 1c887cb0-2446-58b5-b0c8-3ff129ab4c00 |  | note | METHOD: Survey, Measure
label | 89a99581-1e45-59d9-a42c-7ec6fa3fbb58 |  | note | – – – – – – – – – – – – – – – – –
label | 0cd05a96-cf7a-5d3d-859b-4e647a4bb943 |  | note | FREQUENCY: When applicable as instructed in IFC
label | 871dcfcd-59b0-5004-af5d-08043e256f39 |  | note | – – – – – – – – – – – – – – – – –
label | eeedeb29-1cdd-59bc-a541-3f7c5118aa55 |  | note | CATEGORY: IP
label | 157f5d5f-da06-55d4-a5b9-f34b42ec557c |  | note | – – – – – – – – – – – – – – – – –
label | f1185485-385e-5d28-8725-d3d884185e8e |  | note | RESPONSIBILITY: SE/Surveyor
label | 5d39216d-e229-5c14-a758-b1987599d8d7 |  | note | – – – – – – – – – – – – – – – – –
label | 78618526-2741-5fb0-9058-69101d74905b |  | note | VERIFYING DOCUMENTS: Survey Report
date | 1509ed59-c235-57a9-802e-9e48ba00ba00 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | 1b7343c8-d3fe-5f83-be6a-eae86faa2f55 |  | note | REFERENCE: MRPA Quality Management Plan
label | b582cd5b-9c9c-5092-a177-11dddb08623e |  | note | – – – – – – – – – – – – – – – – –
label | a0ce6e71-c349-5e71-bb39-b3bdf8f89e88 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | fc69a99e-4509-546a-b08d-9570471095ec |  | note | Attach: Survey As-built / Survey Report
label | 723a5a1b-5c33-5846-815d-24b006465bfe |  | note | – – – – – – – – – – – – – – – – –
label | 3a39c053-15ce-59b7-9fe7-2f91f8072518 |  | note | METHOD: Document Review
label | 0d716859-9484-5944-af6d-1ac313ee3eca |  | note | – – – – – – – – – – – – – – – – –
label | d2073bf5-d809-5406-904c-b8aa258bb516 |  | note | FREQUENCY: Each element
label | 6c741aa5-4f9b-50e4-9556-02a4bb5fa29e |  | note | – – – – – – – – – – – – – – – – –
label | 1026c7bc-75f8-5650-84f3-b74945eab628 |  | note | CATEGORY: IP
label | b699f13b-e383-5643-9897-28a593aaacca |  | note | – – – – – – – – – – – – – – – – –
label | 7c3c5b9e-106d-5597-a80b-0e0d3e80c67d |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 0e424186-ce79-5026-90fc-490e90971ea6 |  | note | – – – – – – – – – – – – – – – – –
label | 2584b47e-6a00-5744-9663-94108da9c14e |  | note | VERIFYING DOCUMENTS: Survey Report
date | 68dd6227-4f82-5034-99b6-2402c3b46ed5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Wall Post construction monitoring
label | 3536d517-c783-5677-b6ac-98ea091ce583 |  | note | REFERENCE: VR 682.20, VR 682.21
label | fb2c938f-62e8-5d76-8df8-213a48ba43a0 |  | note | – – – – – – – – – – – – – – – – –
label | 27392549-5838-5640-ac79-2245f841c381 |  | note | ACCEPTANCE CRITERIA: The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | 4ad081a8-bf38-5df5-b13d-ab112b69e82e |  | note | (a) plan position shown on the drawings, at base of wall shall not exceed 15 mm;
label | 2192c37a-c71d-538a-a8f8-fac91c3d055b |  | note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | 466dc2ac-5997-5946-83a9-61106801562c |  | note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
label | 70f1e23e-c762-51e9-9139-ade2be79d1ca |  | note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
label | d6debe93-0df5-55fa-8ef7-40967553d12a |  | note | (e) the wall level shall not deviate from the specified level by more than 20 mm;
label | c92cd860-583e-5578-9f25-ead5ba3a0a96 |  | note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
label | 5e14e213-25d0-5a9b-bce2-941092ac83f7 |  | note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
label | bbd08ef9-1316-59eb-b21b-43dae8d18e1c |  | note | – – – – – – – – – – – – – – – – –
label | dfa5f473-e844-5ca6-8284-50e1ae14f268 |  | note | METHOD: Measure, Survey
label | 01eb73d4-2187-5019-b2d0-84bc484dbc7f |  | note | – – – – – – – – – – – – – – – – –
label | c526a22c-5d46-5b8f-ab94-78d51e97610d |  | note | FREQUENCY: Each wall
label | bc26f7b0-38ca-5bcd-9394-7509ac7e7520 |  | note | – – – – – – – – – – – – – – – – –
label | ec634186-5755-5093-9445-e10a250c5315 |  | note | CATEGORY: IP
date | e3621675-9968-5137-8b36-ff250a8cbb94 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | bc722485-819b-5422-b3b2-d27192eab99b |  | note | REFERENCE: MRPA Quality Management Plan
label | ce0d35f5-1c27-5dd9-9766-1d9ae5972112 |  | note | – – – – – – – – – – – – – – – – –
label | b377903d-99e6-52c7-8795-6dc1e81437f6 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 65811e7c-490d-5ed0-91f5-0d80b4ce340b |  | note | – – – – – – – – – – – – – – – – –
label | a6041e01-5dce-5251-a38a-4ac4a41e7042 |  | note | METHOD: Document Review
label | 7a943581-7cd9-5908-ad2c-c2af260faef1 |  | note | – – – – – – – – – – – – – – – – –
label | 9047362f-1b95-5fda-83e3-9cde3f59c1d0 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 8a294523-456c-5a4f-b7f0-81718f6d24c8 |  | note | – – – – – – – – – – – – – – – – –
label | 5be8992b-6fad-58ec-96a9-5af062eb95df |  | note | CATEGORY: HP*
label | 9ab04aee-bc67-5cb2-9562-142a2feb65ab |  | note | – – – – – – – – – – – – – – – – –
label | ccce0e01-3422-5e09-b0cf-3c3cf2a9d4c6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3d74cb57-dfa0-54df-a9f3-134224718247 |  | note | – – – – – – – – – – – – – – – – –
label | 79f793a3-6feb-5b31-a21a-f53c71aa35f7 |  | note | VERIFYING DOCUMENTS: This ITP
date | e6242e43-2144-5f79-82c4-f7c9608e4982 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | fee15d72-c0f6-5c20-a437-0ec69f8d879a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 741ce72d-ab13-551e-8db5-7033c74375ba |  | textbox | Name:
text | 2585d9bf-1a5b-524a-a151-381beaa64b0a |  | textbox | Position:
date | 29a8074c-d337-5d5e-a0a5-2971cf9f59e4 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP