## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation | itp |  |  |  |  | ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-171-STR-SSB-Post and Panel RW-Piling and Steel post installation
label | ITP Description: SSB-Post and Panel RW-Piling and Steel post installation
label | Discipline (e.g. CIV/STR/RAIL): 171-STR
label | Revision Number: 0
label | Revision Date: 29/05/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section VR 606 July 2017
label | 1.2 Non Dependent
label | Reference: VicRoads Section VR 610
label | 1.3 Non Dependent
label | Reference: VicRoads Section VR 611
label | 1.4 Non Dependent
label | Reference: AS2159-2009
label | 1.5 Non Dependent
label | Reference: VicRoads Section 630
label | 1.6 Non Dependent
label | Reference: AS2159-2009
section | Preliminaries - Materials
checkpoint | 2.1 Concrete Mix
label | REFERENCE: VR 610.07 Table VR 610.071
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: TeamBinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | REFERENCE: VR 611.05 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: TeamBinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once for each supplier, 14 days of award of contract
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
label | REFERENCE: VR 610.26 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: TeamBinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Steel Post
label | REFERENCE: 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | Typically this consists of but is not limited to:
label | i. Certificate of Compliance
label | ii. Completed ITP
label | iii. Weld Procedure Specifications
label | iv. Weld Procedure Qualifications
label | v. Welder Qualifications
label | vi. Material Certificates and traceability
label | vii. Quality Assurance check sheets
label | viii. Welding Consumable batch certificates
label | ix. Coating certificate(s)
label | x. Non-destructive Testing (NDT) Reports
label | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
textbox | Enter: TeamBinder MDR Lot number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: For Each Element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.2 Piling Operations Work Procedure
label | REFERENCE: VR 606.03 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
textbox | Enter: TeamBinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 Pre-qualified Pile Testing Consultant
label | REFERENCE: VR 606.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | ○ Details of the consultant to be submitted for review to the Nominated Authority.
textbox | Enter: TeamBinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, two weeks prior to testing
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on TeamBinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to starting Works and at regular intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: All
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Survey Set-out
label | REFERENCE: IFC Drawings VR 606.08 (a - c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Protection of Adjacent Piles
label | REFERENCE: VR 606.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pile construction shall not:
label | i. result in damage to adjacent newly cast piles due to ground vibration.
label | ii. commence within 2.5m clear distance from newly cast piles if that pile concrete strength <15MPa
label | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SPE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Steel Post Material Inspection
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: General inspection of structural steel elements for:
label | – Damage & distortion, twist
label | – Defect to the coating.
label | – Defects to welding between bearing plates and the profile
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each delivery
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.5 Steel Post Material - Correct post
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: For each post:
label | – Check the profile of steel post (Type and Size)
label | – Check the length
label | – Check the Bearing plates number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS:
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Boring Operations
label | REFERENCE: IFC Drawings VR 606.03 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | ○ Excavation clean and de-watered (where applicable) for inspection.
label | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Inspection of Pile Excavation
label | REFERENCE: VR 606.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | Attach: Geotechnical Field Sheet or Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Geotechnical Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 Reinforcement - Placement
label | REFERENCE: IFC Drawings
label | ○ VR 611.06
label | ○ VR 611.09
label | ○ VR 611.10
label | ○ VR 611.11
label | ○ VR 611.12
label | ○ VR 606.06 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Cast-in Items-Steel post
label | REFERENCE: IFC Drawings
label | VR 610.46 (a), Table VR 610.462
label | VR 610.47 (a), Table VR 610.472
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: For each post:
label | – Check the profile of steel post (Type and Size)
label | – Check the length
label | – Check the Bearing plates
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Cast-in Items-Steel post installation
label | REFERENCE: IFC Drawings
label | VR 610.46 (a), Table VR 610.462
label | VR 610.47 (a), Table VR 610.472
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: For each post:
label | – Check the orientation/Rotation
label | – Check the Rake/Plumbness
label | – Check the embedment and above ground height
label | – Check the level of bearing plates to accommodate for the panels to be installed horizontally
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Pre-pour Inspection
label | REFERENCE: IFC Drawings VR 610.18 (a) (ii) & (iii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ○ All foreign material has been completely removed from the excavation.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | REFERENCE: Hot and/or Cold Weather Concreting Procedure
label | VR 610.17
label | VR 610.17 (a) & (e)
label | Table VR 610.171
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | REFERENCE: Site Sampling & Testing Procedure VR 610.16 (b) Table, VR 610.1, VR 61
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 0m³ to 10m³ = 1 sample
label | 10m³ to 25m³ = 2 samples
label | 25m³ to 50m³ = 3 samples
label | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | REFERENCE: VR 610.13 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | ○ Passability = ≤10mm (aggregate height differential)
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each sample of Self-compacting Concrete
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | REFERENCE: Site Sampling & Testing Procedure VR 610.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each sample
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | REFERENCE:
label | VR 610.18 (a) & (b)
label | VR 610.18 (d) (i)
label | VR 606.06 (a & b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | ○ All concrete batches are traceable.
label | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | Record: Required information on the Concrete Pour Record.
label | Attach: Concrete Pour Record
label | Attach: Concrete Dockets
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each load
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: SP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS:
date | Date Completed:
checkpoint | Surface Finishes-top of the piles
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | ○ Provide nominal fall to top of the pile towards outward edge
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.2 Compressive Strength Test Results
label | REFERENCE: IFC Drawings Table VR 610.05.051, VR 610.16 (g)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Attach: Compressive Strength Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each cylinder
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Pile Integrity Testing
label | REFERENCE: VR 606.07 (a, d & e) AS2159 Clause 8.8
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | ○ Cross-sectional area = ≥95%
label | ○ If any test fails, all piles shall be tested.
label | Attach: Pile Integrity Test Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Piles #1 - #6.
label | ○ Reduced to 1 test per 3 piles if the first 6 tests pass
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Testing Consultant, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.6 As-built Survey
label | REFERENCE: IFC Drawings VR 606.08 (a - c), AS2159 Clause 7.2.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | i. Pile head plan location = ±75mm
label | ii. Variance from vertical or rake = 1:100
label | iii. Irregularities in straightness = 1:100
label | iv. RL = ±25mm
label | Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP