## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - SW Manholes | itp |  |  |  | Yes | ITP - SW Manholes | d3032759-f1d8-4b0c-ab38-8cec99f1c211
checkpoint-group |  |  | section | SW Manholes
checkpoint-status |  |  | checkpoint | 1 - PRE-CAST BASES AND RISERS
label | 6f821da3-8809-5a5f-901b-577ff39c38cf |  | note | Inspection / Test Point: Sign off
label | ba945d88-64df-5f01-9e0d-a14371094d78 |  | note | ACTION: H
label | 9ce76e4f-0529-5e83-88ba-38b925e7f625 |  | note | Conformance Criteria (Whats Required): Inspection of concrete product upon delivery to site. Ensure there is no damage or cracking to the precast unit.
label | c7eb7798-3cca-52f4-af35-8edaa86e9327 |  | note | Frequency: Prior to commencement
label | 84b67ffe-d301-548a-88c5-04a1761e0049 |  | note | Inspection / Test Method: Visual
label | ba94c2c3-3ca8-506b-b295-02f1b4156f18 |  | note | Verification Records: Sign This ITP
label | e95b2680-3cef-5065-89c5-b13318e27507 |  | note | Signatory: Site Foreman, Engineer's Representative
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - RCRRJ PIPE AND FITTINGS
label | 4731df2b-8ceb-5dd9-9282-ed4b378c244e |  | note | Specification / Standard: SR10.103 SR10.105
label | eb80b340-00b6-561b-b30a-e37dda498ace |  | note | Inspection / Test Point: Sign off
label | 05f67763-da85-520e-b900-803f382ca65b |  | note | ACTION: H
label | d1dde716-d1ab-5254-8a05-8bb2508a8f69 |  | note | Conformance Criteria (Whats Required): Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities
label | 021f6336-ccfd-5f59-a665-26fd46c23d2d |  | note | Frequency: Prior to installation
label | 97855d2c-c87f-51ad-ac11-d6e1821d81e0 |  | note | Inspection / Test Method: Visual
label | 089b6fd7-0c99-5dcf-983e-44d6ccb51050 |  | note | Verification Records: Sign This ITP
label | 4415deb8-dd5c-52bd-acee-5e4b7340c94e |  | note | Signatory: Site Foreman, Engineer's Representative
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | BENCHING AND OTHER MASS POURS FOR MANHOLE
label | 1487beac-254a-57ed-9f90-e8761f768661 |  | note | Specification / Standard: Contract Document
label | 0596e5e9-f326-5ce8-a6b7-59f9366c19f3 |  | note | Inspection / Test Point: Sign off
label | d2e1ab30-47c8-5efc-bfa7-89f239a0d5c1 |  | note | ACTION: H
label | a2bb13da-715b-55e8-863a-98554e7e4440 |  | note | Conformance Criteria (Whats Required): Minimum 1:4 crossfall grade towards formed channel, all surfaces finished smooth, no benching shall hold water
label | 4da56267-4bcd-57ed-b8ae-80d8c960b90e |  | note | Frequency: During Installation
label | 1be8363d-f933-5b5e-9440-e394c02371aa |  | note | Inspection / Test Method: Visual
label | 90baaf29-0a7e-5118-a273-a360548d4d05 |  | note | Verification Records: Sign This ITP
label | 5abad5a4-4046-5312-80d0-fc686662941f |  | note | Signatory: Site Foreman
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | BASE PREPARATION FOR MANHOLE
label | 776ca942-bd4e-597e-9020-8e6e9da62ad8 |  | note | Specification / Standard: Contract Document
label | aabbde68-18a1-5956-ae9e-09d8db5217c9 |  | note | Inspection / Test Point: Sign off
label | 65e408f1-821f-5000-b7a2-4eeb8f485792 |  | note | ACTION: M
label | 4108a27b-4e4b-54fd-b2fd-ccec2f4472a0 |  | note | Conformance Criteria (Whats Required): A level 150mm AP65 compacted base.
label | 26d1add9-5462-58f2-900d-b4bcecef3093 |  | note | Frequency: Prior to installation
label | 63488f11-80be-5ce6-a541-7cee1f972d5c |  | note | Inspection / Test Method: Review
label | 860a256a-7a99-570e-909a-ee805bd60956 |  | note | Verification Records: Sign This ITP
label | e39ec645-d0e9-5d4e-9587-9fc24be3112a |  | note | Signatory: Site Foreman
checkpoint-status |  |  | checkpoint | BACKFILLING AND COMPACTION ROADWAY
label | 81893c02-3fdb-5de6-a752-54a815fc4dfe |  | note | Specification / Standard: Contract Document
label | 6a8a9f1e-c972-560b-8e1a-660cec0c9f7f |  | note | Inspection / Test Point: Sign off
label | 7e099ae2-5ddd-5b1f-87ab-5657f0c72093 |  | note | ACTION: M
label | ba726267-82e3-5e94-a5b3-846f56849e69 |  | note | Conformance Criteria (Whats Required): All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally with an NDM.
label | 42a644f5-5510-58fc-b6cb-b4403647f541 |  | note | Frequency: During Installation
label | eaca6c49-b16f-51a7-906e-d60ec3308979 |  | note | Inspection / Test Method: NDM
label | f3ea933a-b954-5313-8a65-6d5f824fc71e |  | note | Verification Records: Sign This ITP
label | de7243fc-c4ca-5d45-b4a2-10d145616026 |  | note | Signatory: Site Foreman
checklist-sectioned |  |  | checklist | ITP - SW Pipe Runs 1 | itp |  |  |  | Yes | ITP - SW Pipe Runs 1 | d968e059-24a6-40a3-b630-08970084b3b1
checkpoint-group |  |  | section | SW Pipe Runs 1
checkpoint-status |  |  | checkpoint | 1 - CLASS 2 RCRRJ PIPE AND FITTINGS
label | bec159b0-bcc6-5be0-817e-43b600485bb4 |  | note | Specification / Standard: Contract Document
label | 7ca93a12-223e-5a1d-9a0c-3c96c06a73f5 |  | note | Inspection / Test Point: Sign Off
label | f683a246-a964-57c3-a402-78e3b2957fd6 |  | note | ACTION: H
label | ac8207c5-34e2-59af-9a03-937f0a53aa2d |  | note | Conformance Criteria (Whats Required): Class 2 RCRRJ pipe, pipe to be inspected upon delivery and have no damage or deformities
label | 717ec5c0-7669-5b3d-a2f6-e493773d4b4b |  | note | Frequency: Prior to commencement/upon delivery of materials
label | 4ac62f65-1c66-5070-9147-8e1a14015d71 |  | note | Inspection / Test Method: Visual
label | 0e7ef77b-6447-5c77-a0ae-f4cb27482691 |  | note | Verification Records: Sign this ITP
label | def12458-acd9-5f1a-900d-f7282e8f1229 |  | note | Signatory: Site Foreman Engineer's Representative
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - BEDDING MATERIAL
label | 9d0c9b9f-2e21-59b5-baff-7cdc4107f425 |  | note | Specification / Standard: AS/NZS 2566.2
label | cb383a83-c43f-5bd8-acc8-4d0dbd22490a |  | note | Inspection / Test Point: Aggregate Certification
label | c80260ae-a133-5082-a8df-980085bd8d33 |  | note | ACTION: M
label | 53a0212d-be09-5d2c-953e-cb32322f78a1 |  | note | Conformance Criteria (Whats Required): Clean granular non-cohesive material with a maximum particle size of 20mm
label | d0034bda-f204-5429-9efc-2e2f5e5766eb |  | note | Frequency: Continuous for pipe length
label | 13cc0ccd-a4a1-544e-b0f0-0b41aedd8445 |  | note | Inspection / Test Method: Clegg Hammer
label | 0379a546-832e-54e4-a27d-0e662a8a5063 |  | note | Verification Records: Sign this ITP
label | e7484331-a306-5fa6-83da-1d927b0affc2 |  | note | Signatory: Site Foreman
checkpoint-status |  |  | checkpoint | 3 - OPEN TRENCHING ALIGNMENT, DEPTH AND ACCURACY
label | a9f61434-e9bf-5103-acf2-e2d5b84fa5f5 |  | note | Specification / Standard: Contract Document
label | aa3fb0b5-9a93-5c64-9bb7-6c0ff207adb5 |  | note | Inspection / Test Point: Witness & Record
label | 5b937fab-2f95-5d47-88c8-debbb2f6ba0d |  | note | ACTION: M
label | cc4a465e-84ca-5d88-bee6-0d2495bc7911 |  | note | Conformance Criteria (Whats Required): Installed within +/- 10mm accuracy from design datum. Installed as per design grade and recorded on pipe laying form. Daily checks to make sure pipe is laid to design.
label | 288c22b4-80ac-5bfc-a41a-f77b9a77dc8c |  | note | Frequency: Prior to commencement and every two lengths
label | bc6469ce-9918-511b-9808-ec4f2ac3a15a |  | note | Inspection / Test Method: Review
label | 24ac7685-eb60-564d-87b6-1d2f50b48a4e |  | note | Verification Records: Sign this ITP
label | 4205f15f-2ae6-5317-b48d-14b6033ee734 |  | note | Signatory: Site Foreman
checkpoint-status |  |  | checkpoint | 4 - BACKFILLING AND COMPACTION ROADWAY
label | 1ef86efb-2641-544b-8fca-3a81f72735da |  | note | Specification / Standard: Contract Document
label | 23497acc-dd29-5bb7-8dc5-8c759eaa5934 |  | note | Inspection / Test Point: Sign off
label | 4d0079cf-2ccc-5ace-b8c2-7c23fdb62b3b |  | note | ACTION: M
label | 952d7815-a56f-520c-bcf4-fba69657b6e5 |  | note | Conformance Criteria (Whats Required): Trench backfill to be carried out with imported AP65 gravel in 250mm lifts. The subbase material shall achieve an average of 95% of the MDD. All backfilled material shall be compaction tested at a maximum of 20m intervals longitudinally and 1m vertically with an NDM. All basecourse material shall be M4AP40.
label | 773e12e0-b18a-5149-8f0b-102c73c54362 |  | note | Frequency: During Installation
label | c7784db0-de5d-5ca1-b6e2-21a450d5142d |  | note | Inspection / Test Method: NDM
label | 8091fa74-223b-52b9-a7ea-0b0b4a6d8b94 |  | note | Verification Records: Sign This ITP
label | 1493bfeb-1dbb-5adf-b8e0-6f9e87810adb |  | note | Signatory: Site Foreman
checkpoint-status |  |  | checkpoint | 5 - CCTV
label | 50bc5c08-b52b-5e27-ae01-8b5e9a147519 |  | note | Specification / Standard: Contract Document
label | 25a53815-3a8f-5b05-a4cd-832603355991 |  | note | Inspection / Test Point: CCTV Footage
label | e71c05e2-29e8-5e22-a1a7-4fe93a31dee8 |  | note | ACTION: H
label | 40c4105d-d70a-5f95-b7d4-785fb3b97f3b |  | note | Conformance Criteria (Whats Required): Clear new pipeline of any debris prior to CCTV. CCTV inspection of gravity to be as per the New Zealand Pipe Inspection manual.
label | d82e877a-5d8e-5b35-abed-7f91f18e6941 |  | note | Frequency: Once pipeline is installed
label | 2552e62e-5535-5d0a-8edb-9a2e4977c4a9 |  | note | Inspection / Test Method: CCTV
label | 08ce0b45-69de-575e-b5ed-567094e0c9ca |  | note | Verification Records: Sign this ITP
label | e9f48618-04e9-5b9f-817f-356b11245ad7 |  | note | Signatory: Site Foreman
holdpoint |  |  | signoff | HOLD POINT