## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITR 003 Stormwater Drainage In Ground |  |  |  |  | Yes | ITR 003 Stormwater Drainage In Ground | 09d970d6-1faf-4267-8a52-2731ec89de5f
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | All pits to be checked for correct invert levels & finished floor levels in accordance to specifications & requirements & IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications & requirements
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 001 Set Out Penetrations |  |  |  |  | Yes | ITR 001 Set Out Penetrations | 298f42bd-22a6-4697-a1a9-c67143bbeaed
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings. Works set out to IFC Drawing No.
checkpoint-status |  |  | checkpoint | All penetrations and fire collars to be as per specifications or alternatively approved
checkpoint-status |  |  | checkpoint | All penetrations set out using total station or surveyed grid points by the builder
checkpoint-status |  |  | checkpoint | Ensure fire collars are installed as per manufacturer’s instructions.
checkpoint-status |  |  | checkpoint | Tabs on cast in collar to be exposed.
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 014 Sanitary Fit Off |  |  |  |  | Yes | ITR 014 Sanitary Fit Off | 36905047-f656-4575-82fe-193ac1e628db
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set our as per approved Architectural Drawing No.
checkpoint-status |  |  | checkpoint | Inspect for product defects.
checkpoint-status |  |  | checkpoint | Install as per manufacturer's recommendations and requirements
checkpoint-status |  |  | checkpoint | All sanitary items to be tested in accordance to specifications and manufacturers requirements
checkpoint-status |  |  | checkpoint | Check for leaks
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-sectioned |  |  | checklist | ITR 012 Hot Water Service |  |  |  |  | Yes | ITR 012 Hot Water Service | 37139413-b6e5-491e-a7d1-c8e280df1434
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance to specifications and requirements namely 1500 kPA for 30 minutes
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-sectioned |  |  | checklist | Inspection Test Plan |  |  |  |  | Yes | Inspection Test Plan | 3dbabe74-c61d-4f86-a1a4-62ccb292ecae
checkpoint-group |  |  | section | Set Out Penetrations
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Penetrations and Fire Collars to be in accordance with specification as required for each fire compartment rating and for each fire rated element.
checkpoint-status |  |  | checkpoint | Ensure Fire Collars are installed as per manufacturer’s instructions. Tabs on cast in, collars to be exposed. Photos of collar and labelling referencing fire matrix if required
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications and drawings. All certificates completed and submitted
label | 096f87d3-3755-5163-a836-21b57aef7ccf |  | note | ITR 001
checkpoint-group |  |  | section | In Ground Sewer Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings
checkpoint-status |  |  | checkpoint | Inspection booked with VBA for in ground drainage. HP can sign off if inspector does not attend.
label | bc093778-2c9c-5748-bd03-398edc59cf40 |  | note | ITR 002
checkpoint-group |  |  | section | In Ground Storm Water Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification and AS 3500
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawings No
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted.
label | 63a993d6-b604-5a58-b546-a520f1f88d8e |  | note | ITR 003
checkpoint-group |  |  | section | In Ground Greasy Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | aa557ccf-e4e4-5d34-9928-095f87856d15 |  | note | ITR 004
checkpoint-group |  |  | section | Fire Services
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 2419 & AS 2441 or alternatively approved by CFA/MFB
checkpoint-status |  |  | checkpoint | All pipe work to be tested to 1700 kPA in accordance to specifications and requirements as per AS 2419 Hydrants & AS 2441 Hose Reels
checkpoint-status |  |  | checkpoint | Prior to handover system must be inspected & certified in accordance to drawings, code, specification, dispensation & 129 report and FER.
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted.
label | 01bd606c-19a9-5302-92a5-32ffa92f143c |  | note | ITR 005
checkpoint-group |  |  | section | Suspended Sewer Drainage
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification and acoustic engineers report
checkpoint-status |  |  | checkpoint | As per AS 3500 all traps have been tested for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | 2b22b448-fa7c-5a3f-906a-6679cce97de7 |  | note | ITR 006
checkpoint-group |  |  | section | Suspended Stormwater
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels, gradients & clearance levels/head height in accordance with specifications and requirements
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification and acoustic engineers report
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | bfeec234-ff00-5261-9c72-57bffdc1e645 |  | note | ITR 007
checkpoint-group |  |  | section | Domestic Cold Water In
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.2.2015
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 in accordance with specifications and requirements
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | eff9a08f-825f-5acc-8be8-846b7b73234c |  | note | ITR 008
checkpoint-group |  |  | section | Gas Service
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500 or alternatively approved including road sizes, clipping configurations and methods
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
checkpoint-status |  |  | checkpoint | Prior to gas being turned on ESV must be notified, inspection arrange and approval issued (if required). HP Management must be notified at the completion of works.
label | 4f6e6e54-99b3-5af0-953b-608ddd41a97e |  | note | ITR 009
checkpoint-group |  |  | section | Hot & Cold Water Rough In
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of material to be used. Ensure all materials are in accordance to specification AS 3500.1.2015 & AS 3500.4.2015 or alternatively approved.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance with specifications and requirements namely 1500 kPA for 30 minutes as per AS 3500:1 clause 18.1.3.
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted.
label | b5f4585b-3cb6-58d9-8172-e67b8bc02f6b |  | note | ITR 010
checkpoint-group |  |  | section | Hot Water Service
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples HWS.. Ensure all materials are in accordance to specification AS 3500.1.2015 & AS 3500.4.2015 or alternatively approved
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All works completed in accordance to specifications & drawings. All certificates completed and submitted
label | a0eee6a5-4c7a-5487-ae42-9ac7e0c475ce |  | note | ITR 011
checkpoint-group |  |  | section | Water Meter
checkpoint-status |  |  | checkpoint | Submit shop drawings for approval in accordance with specifications and requirements. All drawings MUST be approved prior to commencement of works
checkpoint-status |  |  | checkpoint | Submit all samples of materials. Ensure all materials are in accordance to specification AS 3500.1.2015 & AS 3500.4.2015 or alternatively approved
checkpoint-status |  |  | checkpoint | All works to be set up as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings
checkpoint-status |  |  | checkpoint | All meter work to be as per specifications and AS 3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Tested and Commissioning completed by passing an amount of known volume (bucket) and confirm the volume of water and meter reading are the same or within the required tolerances
label | f2c7ebbd-4e5a-5470-99a1-a08cc4098175 |  | note | ITR 012
checkpoint-group |  |  | section | Sanitary Fit Off
checkpoint-status |  |  | checkpoint | Submit all sanitary fixtures and tapware. Ensure all material is in accordance with specification AS 3500 and watermarked.
label | f158d0e0-ceeb-53f5-a1ec-936ac8c8054d |  | note | ITR 013
checkpoint-group |  |  | section | Backflow Test Report
checkpoint-status |  |  | checkpoint | Submit Backflow Test Report
label | 31f956cb-3b7b-566d-bcbc-a19dd5afd014 |  | note | ITR 014
checkpoint-group |  |  | section | Tempering Valve Test Report
checkpoint-status |  |  | checkpoint | Submit Tempering Valve Test Report
label | d1a379bc-b988-57a9-9a8a-4af772f8dcba |  | note | ITR 015
checkpoint-group |  |  | section | Thermostatic Mixing Valve Test Report
checkpoint-status |  |  | checkpoint | Submit Thermostatic Mixing Valve Test Report
label | 71e0b7b6-7bd7-50b8-8722-d318af80ff41 |  | note | ITR 016
checkpoint-group |  |  | section | Third Party Commissioning
checkpoint-status |  |  | checkpoint | Submit any Third Party Commissioning Reports which one are applicable:
label | bc75d24a-2e95-5ee9-a221-fb4155b0412f |  | note | Ie Pumps, Tanks, HWS, Fire Hydrants
label | 3e16f887-1392-5d75-ab14-b7b67f47cfaf |  | note | Report from Third Party
checklist-sectioned |  |  | checklist | ITR 011 Hot & Cold Rough In |  |  |  |  | Yes | ITR 011 Hot & Cold Rough In | 4260a3cd-5342-4375-bc82-893b9af7b6db
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set our as per approved IFC drawings and penetrations to be installed to - IFC Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 & in accordance with specifications and requirements . Ensure isolation from authority main, fixtures, tapware and appliances while undertaking testing
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 008 Suspended Greasy Drainage |  |  |  |  | Yes | ITR 008 Suspended Greasy Drainage | 4fb34338-8b1e-4561-bcda-8c0ee9d8b275
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 013 Water Meter |  |  |  |  | Yes | ITR 013 Water Meter | 7218665d-1de3-405b-888b-5b13431f3c3b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All meter work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Ensure that all pipework to meters has been sealed and jointed, all capping adequately installed for testing.
checkpoint-status |  |  | checkpoint | Ensure all meters are sufficient supported and installed in correct location
checkpoint-status |  |  | checkpoint | Pass an amount of water in a container of known volume (bucket) and confirm the volume of water and meter reading are the same or within the required tolerances
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-sectioned |  |  | checklist | ITR 009 Domestic Cold Water In Ground |  |  |  |  | Yes | ITR 009 Domestic Cold Water In Ground | 725277b7-907e-4e7c-b314-0a068aea376b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 & in accordance with specifications and requirements . Ensure isolation from authority main, fixtures, tapware and appliances while undertaking testing.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-sectioned |  |  | checklist | ITR 004 Greasy Drainage In Ground |  |  |  |  | Yes | ITR 004 Greasy Drainage In Ground | 7b9f7929-c794-400b-9a8b-4e32f18adb16
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 010 Gas Service |  |  |  |  | Yes | ITR 010 Gas Service | 87f37fd4-a2fc-42f3-8b38-d931d4884142
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS5601.1 or alternatively approved including rod sizes and clipping configurations and methods
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance with specifications and requirements & AS5601.1
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checkpoint-status |  |  | checkpoint | Prior to gas being turned on ESV must inspect and approved installation if required, including all builders work requirements IE signage, access panels, ventilation, riser shafts etc..
checkpoint-status |  |  | checkpoint | Must notify HP management on completion of works.
checklist-sectioned |  |  | checklist | ITR 005 Fire Service |  |  |  |  | Yes | ITR 005 Fire Service | 8a219d58-66a5-412a-8821-cac6cb1f3cb8
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & Standards or alternatively approved by CFA/MFB.
checkpoint-status |  |  | checkpoint | All pipework to be tested TO 1700 kPA in accordance to specifications &
checkpoint-status |  |  | checkpoint | requirements as per AS 2419 Hydrants & AS 2441 Hose Reels
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checkpoint-status |  |  | checkpoint | Prior to handover system must be inspected & certified in accordance to drawings, code, specification, dispensation, 129 report and FER
checklist-sectioned |  |  | checklist | Third Party Commissioning |  |  |  |  | Yes | Third Party Commissioning | 8f184a5a-72ec-4d52-9d70-4be368748879
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Submit any Third Party Commissioning Reports which one are applicable:
label | de7988af-524c-59cc-8594-4e973541f6a2 |  | note | Ie Pumps, Tanks, HWS, Fire Hydrants
label | 4e5d8169-8a2f-580f-ac84-88eedb2925fa |  | note | Report from Third Party
checklist-sectioned |  |  | checklist | Internal Audit Checklist |  |  |  |  | Yes | Internal Audit Checklist | 98d15107-4774-4326-899b-33ee4264bb24
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Drawing Register Current
checkpoint-status |  |  | checkpoint | Drawings as per Register
checkpoint-status |  |  | checkpoint | ITP Records
checkpoint-status |  |  | checkpoint | Material Specification
checkpoint-status |  |  | checkpoint | Sanitary Specification
checkpoint-status |  |  | checkpoint | Calibration records
checkpoint-status |  |  | checkpoint | Sample Register
text | 903aa14a-ce25-5420-a2fd-7bd1c29d36c5 |  | textbox | Comments
text | c0f68775-8aea-5214-94fa-da82a7f02e97 |  | textbox | Items of concern
text | 03185e92-182c-5d39-86f0-64a028a3e762 |  | textbox | Action required
text | a52c6ea5-f319-5064-b132-b548f2f814ed |  | textbox | Future recommendations
checkpoint-status |  |  | checkpoint | Signed off by Highbury Plumbing Supervisor
checklist-sectioned |  |  | checklist | ITR 002 Sewer Drainage |  |  |  |  | Yes | ITR 002 Sewer Drainage | 99a8c0d1-1a9b-41dc-b0f9-cf6a66436e17
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Notify HP Management for inspection of drainage prior to backfill.
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage. HP can sign off if inspector does not attend.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 016 Tempering Valve Test Report |  |  |  |  | Yes | ITR 016 Tempering Valve Test Report | 9c764231-9c0d-4863-b62b-d8ddea27e256
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Tempering Valve Test
text | ca651b7c-da86-5127-951e-fefb0ed8d855 |  | textbox | Licence No.
text | f4adaf61-59db-579a-8868-cff368d17eb0 |  | textbox | Test kit serial No.
text | b3d614e3-0153-52fb-a375-842c9e28cece |  | textbox | Date test kit last certified:
text | 69ace31e-5e38-587b-aa6a-fbf92bb61c57 |  | textbox | Place of certification
text | 8a3ed96e-e2e0-5ddd-9126-53ae0e534e56 |  | textbox | Make
text | 0572dab5-b66b-53bf-9e1b-018b308f7ae9 |  | textbox | Model
text | 4ed5d537-750b-5d65-a4cf-d6f767d577fd |  | textbox | Location of valve
checkpoint-status |  |  | checkpoint | Flush / Clean filters
checkpoint-status |  |  | checkpoint | One outlet in use
text | c9c68846-4954-5623-8537-60733627acc8 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Temp of warm water
text | c4de9004-3a69-55e8-bd9c-386b00ca5f5b |  | textbox | Fixture
text | 4948bdf1-997b-5c8e-a6f1-17d76b386fb4 |  | textbox | Pre Set Temp
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | 220110d2-90de-57b9-8225-113249b4e02b |  | textbox | Parts & Materials Used
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-sectioned |  |  | checklist | ITR 007 Suspended Storm Drainage |  |  |  |  | Yes | ITR 007 Suspended Storm Drainage | a978f36c-2cb3-4e31-ad0b-d92c8418800b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-sectioned |  |  | checklist | ITR 017 Thermostatic Mixing Valve Test Report |  |  |  |  | Yes | ITR 017 Thermostatic Mixing Valve Test Report | acc0b253-6b04-4ba0-add5-a61f1d6a77af
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Thermostatic Mixing Valve Test
text | 91363081-6617-5e5d-a398-3abb0819b429 |  | textbox | Licence No.
text | 174e70fa-991a-5e32-93c3-af0de0171a22 |  | textbox | Test kit serial No.
text | e5661c96-41bf-52df-bb85-2ce450eabf10 |  | textbox | Date test kit last certified:
text | ed830e65-550d-5092-9954-9a281f84560d |  | textbox | Place of certification
text | c9c16ab9-c28c-5541-87b3-9920b5364122 |  | textbox | Make
text | b87e3d2e-892c-521c-afc6-32046ea4d150 |  | textbox | Model
text | 6dc99472-18a0-5def-bcd5-b3da84758bab |  | textbox | Location of valve
checkpoint-status |  |  | checkpoint | Shut down test
checkpoint-status |  |  | checkpoint | Flush / Clean filters
checkpoint-status |  |  | checkpoint | Static Test
boolean | 06d6ed2d-d5d6-5eaf-a0f6-bebeeedfe939 |  | tickbox | One outlet in use
text | fde63c6a-db2e-57b5-9a1c-da17802ad167 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Temp of warm water
text | 7ab1d331-a9d2-548d-b97a-322dbca8e85d |  | textbox | Fixture
text | 1065156c-fa30-5e9d-b3b9-cc62eda742a6 |  | textbox | Pre Set Temp
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | c6274d09-134a-5d33-ae76-224ed4479bae |  | textbox | Parts & Materials Used
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-sectioned |  |  | checklist | ITR 015 Backflow Test Report |  |  |  |  | Yes | ITR 015 Backflow Test Report | d8d56273-391a-4d28-8a47-85f3cd3d710d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Backflow Test Report Completed
text | 1139bce2-4b38-5e18-a1f3-eeaaf34d72f4 |  | textbox | Date of test
text | e306c980-f597-5595-8552-02039b37068f |  | textbox | Location of test
text | 1dac1724-0c86-5946-a262-2b7f34a729ba |  | textbox | Licence No.
text | e0bdc3a6-ec5a-581a-b24b-049e7f4b08c3 |  | textbox | Test Kit Serial No.
text | 7815e457-19a7-561d-aec5-16cffc3a51d7 |  | textbox | Date test kit last certified
text | 897f9bc4-5e3b-5c3d-9e41-0607724b6ea2 |  | textbox | Place of certification
text | 2ba194aa-b5da-5818-a0af-c6761edffbaf |  | textbox | Make of device
text | 6b81989a-520f-5456-b859-e16e14f0e5a7 |  | textbox | Size (mm)
text | 5d62b4a2-2c43-5e4d-8a62-27411ccd4c17 |  | textbox | Model
text | da9f5607-db23-5793-b8f4-77900f0dcaeb |  | textbox | Serial No.
label | ac279227-5335-5de3-9f7a-3e6996f52407 |  | note | Initial Test Before Maintenance
checkpoint-status |  |  | checkpoint | Permission to shut of water
boolean | 77a1c110-3bae-5630-8fed-239f4e47f4df |  | tickbox | Reduced Pressure Zone Device
boolean | c5ecf65b-a67d-5cf4-8b79-68a384631e11 |  | tickbox | Double Check Valve (Columns 1 & 2)
boolean | b8255868-1a55-50c8-be06-ec4db7766556 |  | tickbox | Pressure Type
checkpoint-status |  |  | checkpoint | Check Valve No 1
boolean | f51d7471-2350-52f5-899e-46883050ae46 |  | tickbox | Closed Tight
boolean | bc4e416e-4763-55b3-97d6-bae5a9f7b3ad |  | tickbox | Leaked
text | 9282abfa-79fe-56f4-8f5d-951718178c50 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve No 2
boolean | 789edfbe-543f-5968-8013-d56d025c452f |  | tickbox | Closed Tight
boolean | f0ef0708-f0dc-55ee-9c71-766d922984a6 |  | tickbox | Leaked
text | a74fced7-7230-543f-ab33-48a865fba821 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Relief Valve
boolean | 60fda72e-a441-569c-a86d-75d899cd60c1 |  | tickbox | Opened At
boolean | c3657ee2-4079-566d-bc4c-13ee86d4ae9a |  | tickbox | Not Opened
text | 1c847878-06d2-59c2-8f40-a75e6ffec49c |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve
boolean | 4339d36d-c47a-5a6f-81e1-fdcbe5f27935 |  | tickbox | Closed Tight
boolean | 455e46d8-548f-5938-af41-f70ac98f4e2e |  | tickbox | Leaked
text | ddcee386-a528-5d24-9849-21b7601dba1b |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Air Inlet
boolean | 19e3a41d-9d93-55f6-bd1b-91cc62f765ed |  | tickbox | Opened At
boolean | b425f924-9676-509b-bd5a-84b7038cb314 |  | tickbox | Not Opened
text | 7ba55cb1-58d3-5755-ba82-626dbfdf37d1 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Downstream Isolation Valve
boolean | 53e6ffa3-b55c-50b6-8c3a-f31f447c0ea2 |  | tickbox | Closed Tight
boolean | d9bcd445-881a-5072-836d-e3adb9beeae4 |  | tickbox | Leaked
text | 8e32c362-1130-5f25-bdd7-758327f49227 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Comment / Take photos of any reasons for failure (NA if not required)
label | 614ad7cf-2020-52d0-af9a-32a692752fe7 |  | note | Re-Test After
checkpoint-status |  |  | checkpoint | Permission to shut of water
boolean | b214e04a-f76f-5673-a7bb-c0881686e044 |  | tickbox | Reduced Pressure Zone Device
boolean | c09a2dc2-014d-5697-8ff8-003eefe7cf38 |  | tickbox | Double Check Valve (Columns 1 & 2)
boolean | d9a2b9ac-93a8-5ea9-8df2-ce1b7b25ebb0 |  | tickbox | Pressure Type
checkpoint-status |  |  | checkpoint | Check Valve No 1
boolean | 64bea399-0e6a-57dd-95b2-ce8daff3cafe |  | tickbox | Closed Tight
boolean | 687036ca-b738-5a08-9ced-1091d8a8648e |  | tickbox | Leaked
text | a5e5c53c-bff2-5fb7-8687-0bbeb60c5c3a |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve No 2
boolean | a74fe07d-2b5c-506e-82f7-eb5d886ca26b |  | tickbox | Closed Tight
boolean | 1fd4f4b8-b326-5c19-a4fc-5a35668052bb |  | tickbox | Leaked
text | e86ff7ce-0964-5421-b856-459e0a8afd6c |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Relief Valve
boolean | 882de44c-e9f0-5307-84bd-8ad85e289a94 |  | tickbox | Opened At
boolean | 6c09102c-b60d-5abf-8fe2-c1967df6b45a |  | tickbox | Not Opened
text | cecc992c-1bfe-517d-8da7-4b4a37b10099 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve
boolean | d4e77760-2359-5d20-8d3e-c24b34ba58c0 |  | tickbox | Closed Tight
boolean | 5ef06bce-3772-5ae9-93fb-a0415b6a4061 |  | tickbox | Leaked
text | 2c0114aa-87f5-5462-bc52-b7fb1f272046 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Air Inlet
boolean | 55104723-469e-561f-a415-a9013e5ea094 |  | tickbox | Opened At
boolean | 0ca8761f-5c6b-5d8e-a90c-320a98186011 |  | tickbox | Not Opened
text | a73d20b6-243c-5ab5-9a53-d1b63c5eecf4 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Downstream Isolation Valve
boolean | 70831a9f-5563-5202-ac7d-a1257fb847a3 |  | tickbox | Closed Tight
boolean | a6d18abe-6baa-5819-b95f-555761fbfe37 |  | tickbox | Leaked
text | a29b1868-ac12-52a6-87b5-97792bf0a313 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | 0f68a4dc-8939-5965-95bb-c5a139109c21 |  | textbox | Parts & Materials Used
text | 5f5fae1a-4d02-5904-88aa-cd6580125679 |  | textbox | Water Meter Number
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-sectioned |  |  | checklist | ITR 006 Suspended Sewer Drainage |  |  |  |  | Yes | ITR 006 Suspended Sewer Drainage | defd6f16-b102-4ae3-a45a-22952385a1c8
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | Documentation |  |  |  |  | Yes | Documentation | f35964a5-b1bd-4b25-b0a3-990c7495fb11
checkpoint-status |  |  | checkpoint | Attach relevant documents
checklist-sectioned |  |  | checklist | Non Conformance Report |  |  |  |  | Yes | Non Conformance Report | fd5c9de0-2497-4d67-b013-6e77cd440fe5
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Report completed
text | 0781a8b5-5b0f-5515-b97e-7913547d2e09 |  | textbox | Short description
text | ad8f77c2-d606-5f0e-9314-bbc93f1061df |  | textbox | NCN NO:
text | 80acf376-27c2-5f8e-aaf0-c8395cd201ea |  | textbox | Level / Area
text | d5fb8c39-ea16-5981-9cec-65fcb90ef29d |  | textbox | Grid Coord
text | f8337274-8c43-55f6-837b-d76de8523eaf |  | textbox | Responsibility
text | e44755b2-d5dd-5fdc-9572-48f15ac58387 |  | textbox | Non Conformance Details
checkpoint-status |  |  | checkpoint | Method of disposition
text | eecde534-b77e-5443-a4e1-adf0ff623700 |  | textbox | Approval required from
checkpoint-status |  |  | checkpoint | Repair / Use as is
text | d854911a-f1ee-5a40-a448-2322cf6e2961 |  | textbox | Customer
checkpoint-status |  |  | checkpoint | Rework / Replace
text | 8934436f-1b46-5142-a92b-b1ada14e4837 |  | textbox | Project Manager
checkpoint-status |  |  | checkpoint | Signed off by Highbury Plumbing Supervisor
checkpoint-status |  |  | checkpoint | Signed off by Scentre Group