## ITP Cover Page
Subsoils Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 108 - Rev D
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 108
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status:
ITP Description: |  |  | Subsoil Drainage |  |  |  |  | Revision: | 1000 |  | D
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA F5, TNZ F/6 & TNZ F/7
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Review | 2023-03-31 |  | Callun Purchase |  | First revision for internal review |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2023-03-31 |  | Callun Purchase |  | First Revision for External Review and Approval |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Draft for Approval | 2023-04-13 |  | Callun Purchase |  | Second Revision for External Review and Approval |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
D | Draft for approval | 2023-07-19 |  | Callun Purchase |  | Added 5.01.09 & 5.01.10 from NCRs |  |  |  | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Subsoils Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JESA to the Engineer before works | Downer | Construction Pack | Submit 10 days prior to commencement of works | H | PE
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.04 | Topographic surveys for measurement | The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities. | PS 2.2.12 | As-built | Prior to works and Post Works | H | PE
3.01.05 | Permits | The contractor shall complete internal and external permits for construction requirements | ITP Register | ITP Sign Off | Prior to commencement of construction activity | R | SE
3.01.06 | Stakeholder Management | Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners | Project Stakeholder Management Plan | ITP Sign Off | Prior to Construction with continue updates throughout the works | R | SE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | SUB ACTIVITY
4.01.01 | Subsoil Pipes | Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer. | GWS 3.2.1 | Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class | Every Delievery to Site | C | SE
4.01.02 | Subsoil Drainage Aggregate | When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max) | GWS 3.2.2 & 3.4 | PSD, CR | Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required. | C | SE
4.01.03 | Filter Cloth | Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent) | GWS 3.2.3 | Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class | Every Delievery to Site | C | SE
4.01.04 | Securing Pins | Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length |  | Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,. | Every Delievery to Site | C | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | SUB ACTIVITY
5.01.01 | Filter Cloth Wrap Inspection | Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line. | GWS 3.2.2 | Every line | Photos of trench prior to backfill | HP | ENG
5.01.02 | Trench Backfill | Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied. | GWS 3.3 | Site Record | Each trench | I | SE
5.01.03 | Drainage Outlets and Inspection Points | At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete. | GWS 3.6 | Site Records | Each Subsoil Line | I | SE
5.01.04 | Subsoil Flushing | On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer. | GWS 3.6 | Site Records | On completion of earthworks | HP | ENG
5.01.05 | Survey | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
5.01.06 | Excavation | Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings | Downer | Records | Prior to laying filter cloth | I | SE
5.01.07 | Bedding | TNZ F/5 - Bedding thickness shall be no less than 100mm | TNZ F/5 | Records | Prior to laying Novacoil | I | SE
5.01.08 | Joining Pipes | TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations | TNZ F/5 | Copy of delivery dockets, photos of pipes onsite with tag showing class | Every join | I | SE
5.01.09 | Pipe Grade | Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5) | TNZ F/5 | AsBuilt | Every 10m | H | SV
5.01.10 | Pipe Cover | Drainage aggregate must be placed till -0.1m from Top of SIL and verified by surveyor | N/A | Site Record | Every 10m | H | SV
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level | Downer | Records | As-builts taken every 10m prior to backfill | H | SV
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations | Downer | Redlines | Post construction | H | PE
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE
6.01.05 | Photos | Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill. | Downer | Photo Records | Post construction | H | SE