## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 112 - Subsoil Drains Rev D | itp |  |  |  |  | ITP - 112 - Subsoil Drains Rev D
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.04 - Topographic surveys for measurement
label | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | Standard / Specification - PS 2.2.12
label | Verifying Document - As-built
label | Frequency - Prior to works and Post Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.05 - Permits
label | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
label | Standard / Specification - ITP Register
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to commencement of construction activity
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 3.01.06 - Stakeholder Management
label | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
label | ○ Agree plans for maintaining access to properties during construction with landowners
label | Standard / Specification - Project Stakeholder Management Plan
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction with continue updates throughout the works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Subsoil Pipes
label | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | Standard / Specification - GWS 3.2.1
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | Frequency - Every Delievery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Subsoil Drainage Aggregate
label | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
label | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
label | ○ Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
label | ○ Test Sieve Aperture (mm) Percentage Passing (%)
label | ○ 53 100
label | ○ 13.2 10 (max)
label | Standard / Specification - GWS 3.2.2 & 3.4
label | Verifying Document - PSD, CR
label | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Filter Cloth
label | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
label | Standard / Specification - GWS 3.2.3
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | Frequency - Every Delievery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.01.04 - Securing Pins
label | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
label | Standard / Specification -
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
label | Frequency - Every Delievery to Site
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
label | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
label | Standard / Specification - GWS 3.2.2
label | Verifying Document - Every line
label | Frequency - Photos of trench prior to backfill
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Trench Backfill
label | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
label | Standard / Specification - GWS 3.3
label | Verifying Document - Site Record
label | Frequency - Each trench
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
label | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
label | Standard / Specification - GWS 3.6
label | Verifying Document - Site Records
label | Frequency - Each Subsoil Line
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.04 - Subsoil Flushing
label | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | Standard / Specification - GWS 3.6
label | Verifying Document - Site Records
label | Frequency - On completion of earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.05 - Survey
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.01.06 - Excavation
label | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Prior to laying filter cloth
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.07 - Bedding
label | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
label | Standard / Specification - TNZ F/5
label | Verifying Document - Records
label | Frequency - Prior to laying Novacoil
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.08 - Joining Pipes
label | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
label | Standard / Specification - TNZ F/5
label | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
label | Frequency - Every join
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.09 - Pipe Grade
label | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
label | Standard / Specification - TNZ F/5
label | Verifying Document - AsBuilt
label | Frequency - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 5.01.10 - Pipe Cover
label | Acceptance / Conformance Criteria - Drainage aggregate must be placed till -0.1m from Top of SIL and verified by surveyor
label | Standard / Specification - N/A
label | Verifying Document - Site Record
label | Frequency - Every 10m
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - As-builts taken every 10m prior to backfill
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 6.01.05 - Photos
label | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | Standard / Specification - Downer
label | Verifying Document - Photo Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE