## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | MMBE-056 Pre-Sheeting ITP | itp |  |  |  |  | MMBE-056 Pre-Sheeting ITP
section | MMBE-056 Pre-Sheeting
checkpoint | Installation of Ceiling Mounted Brackets and Bracing
button | 1. Verify Approved Shop Drawing Revision (Include photo of title block with drawing number and revision). | Yes,No,N/A
button | 2. Mark up and drill ceiling as per shop drawing. | Yes,No,N/A
button | 3. Ensure the ceiling has been installed at the correct ceiling height. | Yes,No,N/A
textbox | Height:
button | 4. Ensure threaded rod, rails and ceiling brackets have been installed as per relevant shop drawing. | Yes,No,N/A
button | 5. For ressessed rails - ensure spring clips and side profiles are attached. | Yes,No,N/A
button | 6. For ressessed rails - ensure spring clips and emd profiles are attached. | Yes,No,N/A
button | 7. Ensure all brackets are tightened with correct torque. | Yes,No,N/A
checkpoint | Weight Testing
button | 1. Ensure the rail system has been tested for (SWL x 1.5) 20 minutes. | Yes,No,N/A
button | 2. Ensure rail system has been labelled with a completed installer's label. | Yes,No,N/A
label | Serial number provided in asset register.
checklist | MMBE-056 Trolley Fit Off ITP | itp |  |  |  |  | MMBE-056 Trolley Fit Off ITP
section | MMBE-056 Trolley Fit Off
checkpoint | Installation/Test of Track Trolley
button | 1. Ensure the track trolley is fully functional. | Yes,No,N/A
button | 2. Ensure a lock split has been inserted and locks the end stop in place / tightened. | Yes,No,N/A
button | 3. Check and ensure that the travelling trolley moves silently in the rail system. | Yes,No,N/A
checklist | MMBE-057 Pre-Sheeting ITP | itp |  |  |  |  | MMBE-057 Pre-Sheeting ITP
section | MMBE-057 Pre-Sheeting
checkpoint | Installation of Ceiling Mounted Brackets and Bracing
button | 1. Verify Approved Shop Drawing Revision (Include photo of title block with drawing number and revision). | Yes,No,N/A
button | 2. Mark up and drill ceiling as per shop drawing. | Yes,No,N/A
button | 3. Ensure the ceiling has been installed at the correct ceiling height. | Yes,No,N/A
textbox | Height:
button | 4. Ensure threaded rod, rails and ceiling brackets have been installed as per relevant shop drawing. | Yes,No,N/A
button | 5. For ressessed rails - ensure spring clips and side profiles are attached. | Yes,No,N/A
button | 6. For ressessed rails - ensure spring clips and emd profiles are attached. | Yes,No,N/A
button | 7. Ensure all brackets are tightened with correct torque. | Yes,No,N/A
checkpoint | Weight Testing
button | 1. Ensure the rail system has been tested for (SWL x 1.5) 20 minutes. | Yes,No,N/A
button | 2. Ensure rail system has been labelled with a completed installer's label. | Yes,No,N/A
label | Serial number provided in asset register.
checklist | MMBE-057 Hoist Fit OFF ITP | itp |  |  |  |  | MMBE-057 Hoist Fit OFF ITP
section | MMBE-057 Hoist Fit OFF
checkpoint | Installation/Test of Ceiling Hoist and Drive Motor
button | 1. Ensure the ceiling hoist has been tested and is fully functional. | Yes,No,N/A
button | 2. Ensure that the emergency cord has been cut to 1.9m from the floor | Yes,No,N/A
button | 3. Ensure a lock split has been inserted and locks the end stop in place / tightened. | Yes,No,N/A
checkpoint | Test of Charging Station, Charging Liners and Remote Control
button | Ensure that the ceiling hoist charges when the ceiling hoist is placed in the charging station. | Yes,No,N/A
button | Ensure that the ceiling hoist is charged in the charging liners. | Yes,No,N/A
button | Ensure that the remote control has been tested and is fully functional. | Yes,No,N/A
button | Check and ensure that the travelling trolley moves silently in the rail system. | Yes,No,N/A
checklist | Underhung Patient Lifter Pre-Sheeting ITP (MMBE-061 MMBE-071 MMBE-505) | itp |  |  |  |  | Underhung Patient Lifter Pre-Sheeting ITP (MMBE-061 MMBE-071 MMBE-505)
section | Underhung - Pre-sheeting
checkpoint | Installation of Ceiling Mounted Brackets and Bracing
button | 1. Verify Approved Shop Drawing Revision (Include photo of title block with drawing number and revision). | Yes,No,N/A
button | 2. Mark up and drill ceiling as per shop drawing. | Yes,No,N/A
button | 3. Ensure the ceiling has been installed at the correct ceiling height. | Yes,No,N/A
textbox | Height:
button | 4. Ensure threaded rod and ceiling brackets have been installed as per relevant shop drawing. | Yes,No,N/A
checklist | Patient Lifter ITP - Track Hoist Fit Off | itp |  |  |  |  | Patient Lifter ITP - Track Hoist Fit Off
section | Underhung - Track Hoist Fit Off
checkpoint | Installation of Rail
button | 1. Ensure all brackets are tightened with correct torque, once rail is hung. | Yes,No,N/A
checkpoint | Weight Testing
button | 1. Ensure the rail system has been tested for (SWL x 1.5) 20 minutes. | Yes,No,N/A
button | 2. Ensure rail system has been labelled with a completed installer's label. | Yes,No,N/A
label | Serial number provided in asset register.
checkpoint | Installation/Test of Ceiling Hoist and Drive Motor
button | 1. Ensure the ceiling hoist has been tested and is fully functional. | Yes,No,N/A
button | 2. Ensure that the emergency cord has been cut to 1.9m from the floor | Yes,No,N/A
button | 3. Ensure a lock split has been inserted and locks the end stop in place / tightened. | Yes,No,N/A
checkpoint | Test of Charging Station, Charging Liners and Remote Control
button | Ensure that the ceiling hoist charges when the ceiling hoist is placed in the charging station. | Yes,No,N/A
button | Ensure that the ceiling hoist is charged in the charging liners. | Yes,No,N/A
button | Ensure that the remote control has been tested and is fully functional. | Yes,No,N/A