## Window openings
Window openings
Checklist
l1
FAP
101
D101
l2
W101
W102
W103
W104
W105
W106
W107
W108
W109
W110
W111
W112
W113
W114
W115
W116
W117
W118
W119
W120
W121
W122
W123
W124
W125
W126
W127
W128
W129
W130
W131
W132
W133
W134
W135
W136
W137
W138
W139
W140
W141
W142
W143
W144
W145
W146
W147
W148
W149
W150
W151
W152
W153
W154
W155
W156
W157
W158
W159
W160
l3 | W203
W204
W205
W206
W207
W208
W209
W210
W211
W212
W213
W214
W215
W216
W217
W218
W219
W220
W221
W222
W223
W224
W225
W226
W227
W228
W229
W230
W231
W232
W233
W234
W235
W236
W237
W238
W239
W240
W241
W242
W243
W244
W245
W246
W247
W248
W249
W250
W251
W252
W253
W254
W255
W256
W257
W258
W259
W260
l3 | W301
W302
W303
W304
W305
W306
W307
W308
W309
W310
W311
W312
W313
W314
W315
W316
W317
W318
W319
W320
W321
W322
W323
W324
W325
W326
W327
W328
W329
W330
W331
W332
W333
W334
W335
W336
W337
W338
W339
W340
W341
W342
W343
W344
W345
W346
W347
W348
W349
W350
W351
W352
W353
W354
W355
W356
W357
W358
W359
W360
l4 | W401
W402
W403
W404
W405
W406
W407
W408
W409
W410
W411
W412
W413
W414
W415
W416
W417
W418
W419
W420
W421
W422
W423
W424
W425
W426
W427
W428
W429
W430
W431
W432
W433
W434
W435
W436
W437
W438
W439
W440
W441
W442
W443
W444
W445
W446
W447
W448
W449
W450
W451
W452
W453
W454
W455
W456
W457
W458
W459
W460
l5 | W501
W502
W503
W504
W505
W506
W507
W508
W509
W510
W511
W512
W513
W514
W515
W516
W517
W518
W519
W520
W521
W522
W523
W524
W525
W526
W527
W528
W529
W530
W531
W532
W533
W534
W535
W536
W537
W538
W539
W540
l6 | W601
W602
W603
W604
W605
W606
W607
W608
W609
W610
W611
W612
W613
W614
W615
W616
W617
W618
W619
W620
W621
W622
W623
W624
W625
W626
W627
W628
W629
W630
W631
W632
W633
W634
W635
W636
W637
W638
W639
W640

## Checklists
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | Boxing to footing | [5 empty] | QA - Internal Frames Checklist
section | Wall
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm cut ground hieghts
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | Site concrete in place and 80 mm thick
checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint | Concrete hieght bead in place
checkpoint | Botls to bottom place every 600 mm
checkpoint | Braces in place - every 600
checkpoint | Strong back in place if required
Checkpoint | Area stripped
checklist | Boxing Pad
section | Pad
Checkpoint | Has area been handed over by W & H
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | Site concrete in place and 80 mm thick
checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint | Concrete hieght bead in place
checkpoint | Botls to bottom place every 600 mm
checkpoint | Braces in place - every 600
checkpoint | Strong back in place if required
Checkpoint | Area stripped
checklist | Uppper floor slab
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm hieghts
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint | Concrete hieght bead in place if required
checkpoint | Botls to bottom place every 600 mm
checkpoint | Braces in place - every 600
checkpoint | Strong back in place if required
Checkpoint | Area stripped
Checkpoint | Shower rabate in place
Check point | Bathroom rabate in place
checklist | Ground floor slab
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm hieghts
checkpoint | Boxing mark off grid
checkpoint | Shutter to hieght or over size
checkpoint | rebate in place
checkpoint | rebate type correct
checklist | Precast install
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Grid marked / survey point given
checkpoint | shims in place at base
checkpoint | Gap maintained between panels
checkpoint | starters in place
checkpoint | props installed as per plan
checklist | Precast install - flat slabs
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Grid marked / survey point given
checkpoint | back propping in place and at hieght
checkpoint | layout confirmed
checkpoint | glav angle in place
checklist | Precast install - Balcony
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Grid marked / survey point given
checkpoint | back propping in place and at hieght
checkpoint | Front front level
checkpoint | Side level
checklist | Window door Opening / Framing
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm hieghts of datum
checkpoint | Is rebate correct
checkpoint | Framing bolted as requied
checkpoint | DPC installed
checkpoint | Correct framing Members
checkpoint | Is wall plumb
checkpoint | is opening square
checklist | Framing to steel beam
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Confirm location
checkpoint | Are services installed
checkpoint | All bolts installed
checkpoint | DPC installed where required
checklist | GIB Weatherline
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Framing inspected to be covered
Checkpoint | Thermax installed
checkpoint | Screw patten achieve
checkpoint | All joints taped
checkpoint | Window area taped
checkpoint | Rebates taped
Checklist | Balcony soffit framing
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Framing inspected to be covered
checkpoint | DPC in place
checkpoint | are bolts installed
checkpoint | Set out correct
Checkpoint | weatherline to face installed and screw pattern achived.
Checkpoint | Proclima and all penetrations sealed
checklist | Roof framing
section
Checkpoint | Has area been handed over by W & H
Checkpoint | Is steel complete
checkpoint | Steel beams packed
checkpoint | All bolts installed to bearers
checkpoint | DPC installed where required
checkpoint | trusses installed
checkpoint | Hip trusse nogged
checkpoint | Ridge nogged
checkpoint | hardware install
checkpoint | Lintel bolts and brackets
checkpoint | Point load fixings
checkpoint | Space braces installed
checkpoint | Diagonal strape braces installed
Checkpoint | Rafters installed as per LVL plan
Checkpoint | Ribbon boards installed and bolted
Checkpoint | Structural steel in place and packed (B9)
Checkpoint | Hardware installed
Check list | Apartment #
Section
Checkpoint | Has area been handed over by W&H
Checkpoint | All service nogs installed
Checkpoint | Tv nogs installed
Checkpoint | Timber on pod installed
Checkpoint | Door framing opening correct
Checkpoint | Door framing plumb
Checkpoint | Door installed correctly.
Check list | Common Area Doors
Section
Checkpoint | Has area been handed over by W&H
Checkpoint | Door framing opening correct
Checkpoint | Door framing plumb
Checkpoint | Door installed correctly.
Check list | Window opening
Section
Checkpoint | Window opening number
Checkpoint | Pre tape
Checkpoint | Top corners
Checkpoint | Lower corners - include danco
Checkpoint | Outside view - with weather line
Checkpoint | Inside view

## b & 6
B 5 & ^
Level | area on floor / Grid | lists required
Footings Ground | [5 empty] | Ground Floor framing
| Grid 1 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 2 | Pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | pad | footing | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 20 | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | pad | footing | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid b | Pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d |  |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | pad |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | footing |  | precast install | Ground Floor slab |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 1 Slab | [7 empty] | Ground Floor framing
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony |  |  |  |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs
|  | Balcony install |  | Precast install - Balcony |  |  |  |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 2 Slab | [6 empty] | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab | footing | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 3 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | [5 empty] | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 4 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab | footing | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
[9 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
Level 5 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  |  |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
Level 6 Slab | [8 empty] | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 1 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 2 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 3 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 4 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 5 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 6 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 7 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 8 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 9 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 10 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 11 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 12 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid 13 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 14 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 15 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 16 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid 17 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 18 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 19 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid 20 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid 21 | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
|  |  |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid A | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing
| Grid b | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid c | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid d | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
| Grid e | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline
| Grid f | Upper Floor Slab |  | precast install |  |  | Precast install - flat slabs |  | Window door Opening / Framing | Framing to steel beam | GIB Weatherline |  | Roof framing
|  | Balcony install |  | Precast install - Balcony | [7 empty] | Balcony soffit framing