## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Upper Floor Slab |  |  |  |  | Yes | Upper Floor Slab | 031cc020-ec2a-4d9e-85a3-8219960365bd
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm hieghts
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to hieght or over size
checkpoint-status |  |  | checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint-status |  |  | checkpoint | Concrete hieght bead in place if required
checkpoint-status |  |  | checkpoint | Botls to bottom place every 600 mm
checkpoint-status |  |  | checkpoint | Braces in place - every 600
checkpoint-status |  |  | checkpoint | Strong back in place if required
checkpoint-status |  |  | checkpoint | Area stripped
checkpoint-status |  |  | checkpoint | Shower rabate in place
checkpoint-status |  |  | checkpoint | Bathroom rabate in place
checklist-sectioned |  |  | checklist | GIB Weatherline |  |  |  |  | Yes | GIB Weatherline | 20b41e07-63d8-4244-98ba-38ec916d56c8
checkpoint-group |  |  | section | Details:
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Framing inspected to be covered
checkpoint-status |  |  | checkpoint | Screw pattern achieve
checkpoint-status |  |  | checkpoint | All joints taped
checkpoint-status |  |  | checkpoint | Window area taped
checkpoint-status |  |  | checkpoint | Rebates taped
checklist-flat |  |  | checklist | Precast Install |  |  |  |  | Yes | Precast Install | 27649068-6f99-49ae-9e4f-d16af55544b8
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm location
checkpoint-status |  |  | checkpoint | Grid marked / survey point given
checkpoint-status |  |  | checkpoint | Shims in place at base
checkpoint-status |  |  | checkpoint | Gap maintained between panels
checkpoint-status |  |  | checkpoint | Starters in place
checkpoint-status |  |  | checkpoint | Props installed as per plan
checklist-sectioned |  |  | checklist | Window Opening |  |  |  |  | Yes | Window Opening | 325ea6fe-086d-4b9f-aa26-45e7463f3c81
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Window opening number
checkpoint-status |  |  | checkpoint | Pre tape
checkpoint-status |  |  | checkpoint | Top corners
checkpoint-status |  |  | checkpoint | Lower corners - include danco
checkpoint-status |  |  | checkpoint | Outside view - with weather line
checkpoint-status |  |  | checkpoint | Inside view
checklist-flat |  |  | checklist | Precast Install - Flat Slabs |  |  |  |  | Yes | Precast Install - Flat Slabs | 3d84679c-7858-4cd8-9c1c-0a4f8cf9857a
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm location
checkpoint-status |  |  | checkpoint | Grid marked / survey point given
checkpoint-status |  |  | checkpoint | Back propping in place and at height
checkpoint-status |  |  | checkpoint | Layout confirmed
checkpoint-status |  |  | checkpoint | Glav angle in place
checklist-flat |  |  | checklist | Site Issues |  |  |  |  | Yes | Add Site Issue | 4437dd07-7637-4c81-abae-6656da4bbce9
checkpoint-status |  |  | checkpoint | Site Issue/s captured - add comments/photos
checklist-flat |  |  | checklist | Boxing Pad |  |  |  |  | Yes | Boxing Pad | 53e5eec6-dff5-4dc9-9f9a-d63d0adb4cdc
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to hieght or over size
checkpoint-status |  |  | checkpoint | Site concrete in place and 80 mm thick
checkpoint-status |  |  | checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint-status |  |  | checkpoint | Concrete hieght bead in place
checkpoint-status |  |  | checkpoint | Botls to bottom place every 600 mm
checkpoint-status |  |  | checkpoint | Braces in place - every 600
checkpoint-status |  |  | checkpoint | Strong back in place if required
checkpoint-status |  |  | checkpoint | Area stripped
checklist-sectioned |  |  | checklist | Balcony Soffit Framing |  |  |  |  | Yes | Balcony Soffit Framing | 5f795c6d-5df8-45d1-bee2-94417233b0b7
checkpoint-group |  |  | section | Details:
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Framing inspected to be covered
checkpoint-status |  |  | checkpoint | DPC in place
checkpoint-status |  |  | checkpoint | are bolts installed
checkpoint-status |  |  | checkpoint | Set out correct
checklist-sectioned |  |  | checklist | Roof Framing |  |  |  |  | Yes | Roof Framing | 5fcf5a78-b07d-4570-9443-4e3c8a968334
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Is steel complete
checkpoint-status |  |  | checkpoint | Steel beams packed
checkpoint-status |  |  | checkpoint | All bolts installed to bearers
checkpoint-status |  |  | checkpoint | DPC installed where required
checkpoint-status |  |  | checkpoint | Trusses installed
checkpoint-status |  |  | checkpoint | Hip trusse nogged
checkpoint-status |  |  | checkpoint | Ridge nogged
checkpoint-status |  |  | checkpoint | Hardware install
checkpoint-status |  |  | checkpoint | Lintel bolts and brackets
checklist-sectioned |  |  | checklist | Framing to Steel Beam |  |  |  |  | Yes | Framing to Steel Beam | 68f80efe-19b6-49c0-a1e1-3cfc67157ba0
checkpoint-group |  |  | section | Details:
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm location
checkpoint-status |  |  | checkpoint | Are services installed
checkpoint-status |  |  | checkpoint | All bolts installed
checkpoint-status |  |  | checkpoint | DPC installed where required
checklist-flat |  |  | checklist | Ground Floor Slab |  |  |  |  | Yes | Ground Floor Slab | 7d3ddbd2-a088-4403-826d-bcb685129ecc
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm heights
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to height or over size
checkpoint-status |  |  | checkpoint | Rebate in place
checkpoint-status |  |  | checkpoint | Rebate type correct
checklist-flat |  |  | checklist | Precast Install - Balcony |  |  |  |  | Yes | Precast Install - Balcony | 9b6edfde-de9b-40c8-b6a2-704118132816
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm location
checkpoint-status |  |  | checkpoint | Grid marked / survey point given
checkpoint-status |  |  | checkpoint | back propping in place and at hieght
checkpoint-status |  |  | checkpoint | Front front level
checkpoint-status |  |  | checkpoint | Side level
checklist-flat |  |  | checklist | Boxing to Footing |  |  |  |  | Yes | Boxing to Footing | bf4c9c91-ddd2-4850-a150-d5d3b7f29597
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm cut ground hieghts
checkpoint-status |  |  | checkpoint | Boxing mark off grid
checkpoint-status |  |  | checkpoint | Shutter to hieght or over size
checkpoint-status |  |  | checkpoint | Site concrete in place and 80 mm thick
checkpoint-status |  |  | checkpoint | Has footing been cut back 500 mm from face of shutter line
checkpoint-status |  |  | checkpoint | Concrete hieght bead in place
checkpoint-status |  |  | checkpoint | Botls to bottom place every 600 mm
checkpoint-status |  |  | checkpoint | Braces in place - every 600
checkpoint-status |  |  | checkpoint | Strong back in place if required
checkpoint-status |  |  | checkpoint | Area stripped
checklist-sectioned |  |  | checklist | Window door Opening / Framing |  |  |  |  | Yes | Window door Opening / Framing | f4dc6553-d781-4fce-9f98-0b3f42664f6a
checkpoint-group |  |  | section | Details:
checkpoint-status |  |  | checkpoint | Has area been handed over by W & H
checkpoint-status |  |  | checkpoint | Confirm heights of datum
checkpoint-status |  |  | checkpoint | Is rebate correct
checkpoint-status |  |  | checkpoint | Framing bolted as required
checkpoint-status |  |  | checkpoint | DPC installed
checkpoint-status |  |  | checkpoint | Correct framing Members
checkpoint-status |  |  | checkpoint | Is wall plumb
checkpoint-status |  |  | checkpoint | is opening square