## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-017 - Basin Construction | itp |  |  |  |  | FHC-ITP-017 - Basin Construction
section | Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
note | FREQUENCY: Prior to commencing
note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to Placement
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Excavation Permit
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
note | • Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of excavation
note | REFERENCE DOCUMENTS: Excavation permit
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Materials - Drainage layer
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Material to be clean, Fine Gravel: 2-5mm washed screenings
note | • Particle distribution size: D
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.5 Materials - Transition
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Material to consist of clean well graded sand containing 2% Fines.
note | • Particle distribution size: D
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.6 Materials - Filter
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: The filter media shall be a natural or amended natural soil meeting the following requirement:
note | ○ Hydraulic conductivity (ks):
note | – 180mm/hour as tested using astm F1815-06 method particle size distribution as follows:
note | – Clay & silt <3% (0.05mm)
note | – Very fine sand 5-30% (0.05-0.15mm)
note | – Fine sand 10-30% (0.15-0.25mm)
note | – Medium to coarse sand 40-60% (0.25-1.0mm)
note | – Coarse sand 7-10% (1.0-2.0mm)
note | – Fine gravel <3% (2.0-3.4mm)
note | ○ Properties:
note | – Total nitrogen (tn) content <800mg/kg
note | – Orthophosphate (po) content <80mg/kg
note | – Organic matter content - at least 3% (w/w)
note | – pH: 5.5-7.5
note | – EC: <1.2ds/m
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.7 Material - Rock beaching
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Larger (e.g. 400-600mm dia) placed rock
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP*
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Survey set-out
note | FREQUENCY: Prior to Commencing Excavation
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | INSPECTION/TEST METHOD: Site Inspection
note | RECORD OF CONFORMITY: Survey records & pegs on the ground
note | SCP
note | RESPONSIBILITY: Site Engineer/Surveyor
textbox | Date Completed:
checkpoint | 2.2 In situ Material
note | FREQUENCY: Initial
note | ACCEPTANCE CRITERIA: In situ material ripped and re-compacted to provide a smooth, stable working surface. Material to be free of debris, roots, sticks and sharp rocks/ boulders larger than 50mm
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.3 Bentofix GCL Installation
note | FREQUENCY: Prior to compaction of natural subgrade
note | ACCEPTANCE CRITERIA: Geotextile clay liner (GCL) shall be installed in accordancewith the manufacturer's requirements.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Installation of Peforated Pipe
note | FREQUENCY: Once GCL has been installed
note | ACCEPTANCE CRITERIA: Contractor to install 150mm DIA uPVC perforated pipe as per the manufacturers specifications.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Drainage layer
note | FREQUENCY: Once perforated pipe has been installed
note | ACCEPTANCE CRITERIA: Material to be clean, fine gravel of 2=5mm washes screenings.
note | • Install layer to 150mm thick as per the detail.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Transition layer
note | FREQUENCY: Once drainage layer has been installed
note | ACCEPTANCE CRITERIA: Material to consist of clean well graded sand containing 2% fines.
note | • Install layer to 100mm thick as per the detail.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0021
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.7 Rock Beaching
note | FREQUENCY: Once transition layer has been installed
note | ACCEPTANCE CRITERIA: Install a 300mm rock beaching and lightly compacted with a single pass of a vibrating plate as per detail.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.8 Filter layer
note | FREQUENCY: Once transition layer has been installed
note | ACCEPTANCE CRITERIA: Filter media to be a natural or amended natural soil.
note | • Install layer to 300mm thick as per the detail.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.9 Type A and Bunker Rock Bund
note | FREQUENCY: Once filter media has been installed
note | ACCEPTANCE CRITERIA: Install 100mm type-A capping for the bund base. Once compacted, install 75mm - 150mm bunker rock.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Completion
checkpoint | 3.1 Survey conformance
note | FREQUENCY: Each Layer
note | ACCEPTANCE CRITERIA: Base layer of basin and top layer of batter to achieve specified finished surface level as per detail.
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-12-TNT-CRG-0022
note | INSPECTION/TEST METHOD: Site Inspection
note | RECORD OF CONFORMITY: Survey records & pegs on the ground
note | SCP
note | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: