## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-037 - Structural Concrete Construction Rev1 | itp |  |  |  |  | FHC-ITP-037 - Structural Concrete Construction Rev1
section | 1 - Design and Submissions
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Approval of mix design
note | FREQUENCY: Prior to the first concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.07
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Reinforcement schedule
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 611.04
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction/Erection of Formwork
checkpoint | 2.1 Excavation
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Contract Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Inspect
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Construction Methodology
note | FREQUENCY: Prior to erection
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 614.04, 614.06
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
section | 3 - Pre-Pour Planning and Inspection
checkpoint | 3.1 Excavation/Foundation – Blinding, sealing or foundation concrete
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Blinding, sealing or foundation concrete shall not be placed until the bottom of the excavation has been reviewed by the Superintendent. Inspected and approved by the Superintendent. Hold Point released by the Superintendent.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 602.03
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan / VicRoads
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Formwork levels and position
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: A pre-pour survey carried out to confirm erected formwork within the tolerance. Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 614.06
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | SCP, HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.3 Location of splices
note | FREQUENCY: Schedule Review
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: In lapped splices, the bars shall be placed in contact and the specified cover shall be maintained.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 611.11
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Inspect
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.4 Cleaning formwork
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.18 (a) (iii)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.5 Correct forms, reinforcements, rag bolt assembly and embedments
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
note | • Pre-pour checklist completed and signed.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.18 (a)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan / VicRoads
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 Reinforcement assembly of piles
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by the Superintendent.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 Monitoring weather
note | FREQUENCY: Prior to concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
note | • All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.17 (b), (c), (d)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
section | 4 - Placing and Finishing Concrete
checkpoint | 4.1 Carry out sampling of concrete
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.16
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 4.2 Discharge time
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 4.3 Methodology of placement (structural)
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
note | • Concrete shall not be moved horizontally by vibrators
note | • In continuous pours the max. time lag between truckloads on site is 25 minutes
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.18
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
section | 5 - Post-Pour Details and Inspection
checkpoint | 5.1 Curing
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.23
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 5.2 Formwork removal
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.25
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Dimensions within the tolerances given in Cl 17.5 of AS3600 (-10,+40)
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: AS3600 Cl 17.5 607.06
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 5.4 Concrete Sampling and Testing
note | FREQUENCY: Prior to lot closure
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete sampled and tested for Compressive Strength, and Slump.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.16
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 5.5 As Built Drawings
note | FREQUENCY: Prior to lot closure
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: