## ITP Cover Page
Fencing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 124 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 124
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Fencing |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | Fencing and Barrier Drawing Set
Client: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, Conventional Farm Fencing
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 11.02.25 |  | Zion Nordstrom | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval |  |  | Zion Nordstrom |  | Add RITS detail |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Draft for Approval | Approved |  | Zion Nordstrom | [5 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Fencing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 124 - Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.02 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.04 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.05 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.06 | Subcontractors | Ensure that subcontract and supplier agreements have been completed. All subcontractors have been inducted. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.07 | Pre-commencement Meeting | Unless advised otherwise, pre-commencement meeting will be conducted with designer and contractor to determine final location of fencing. Contractor to co-ordinate all fencing alignment and fencing accommodation works with Engineer, HCC Representatives, and Landowners including on- site meetings. | Project Specification | InEight Correspondence | Prior to works start | HP | ENG
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Materials
4.01.01 | Timber Posts | Brand new 1.8m long H4 treated no. 1 grade full round posts. Or equivalent as per "2016 Conventional Farm Fencing Taratahi" guide. | PS 2.1.2 Fencing | Dockets | At delivery | H | SE
4.01.02 | Timber Battens | Brand new 50x50 H3 treated battens between each post. | PS 2.1.2 Fencing | Dockets | At delivery | H | SE
4.01.03 | Wire | 2.5mm galvanised steel high-tensile 7-wire. | PS 2.1.2 Fencing | Dockets Mill Certs | At delivery | H | SE
4.01.04 | Special Fences and Gates | To be confirmed with designer. | Designer | InEight Correspondence | Prior to installation | HP | ENG
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Permanent Fence - Post and Batten
5.01.01 | 7-Wire standard Boundary Fence Installation | The minimum standard of fence for a straight section on flat ground with favourable ground conditionsshall be a post and batten fence with 1.8m long H4 treated No.1 grade full round posts spaced at 4.0m centres, five 50×50 H3 treated battens between each post and seven 2.5mm high-tensile wires. extending and adjusting all lateral fence lines to tie in with the new permanent fencing. | Designer | Installation Record Photos | Each Area | H | SE
5.01.02 | Posts | Strainer and angle posts shall be included on the new fence lines at the laterals, and the laterals re-tensioned. Line posts shall be minimum 1.8m long H4 No.1 grade full round posts. 4m spacings. | Designer | Installation Record Photos | Each Area | H | SE
5.01.03 | Gates | 3.6m light gate or 4.2m light barred gates. Singles or double gate. As per designer's requirements. | Designer | Installation Record Photos Miscellaneous | Each Area | HP | ENG
5.01.04 | Corner | No.2 2.4m long strainer and at the ends of the fence line. | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
5.01.05 | Height of Fence | Standard height to be 1.150m. | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
5.01.06 | Staples | Installed at approximately 170-175 degrees and staggered to prevent splitting of the post/batten | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
5.01.07 | Wire Spacing | Distance from ground - general arrangement. Wire 1 - 125mm, 2 - 250mm, 3 - 375mm, 4 - 500mm, 5- 650mm, 6- 730mm, 7 - 930mm. | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
5.02 | Permanent Fence - Post and Three-Rail
5.02.01 | Posts | Posts Strainer/Angle Posts should be a minimum of 2.4m Long and 175-200mm Diameter or 2.4m Long x 200-225mm Diameter, Line Posts Minimum 1.8m Length x No 1 (H4 treated) Full Round 1 1 5-135mm Diameter at a maximum spacing of 4.0m or less depending on the contour of the ground. | Designer | Installation Record Photos | Each Area | H | SE
5.02.02 | Timber rails | A minimum of three timber rails shall be provided. Timber rails shall be no less than 150mm x 50mm (unless accepted by the Owner where an alternative size matches their existing fence). Rough sawn grade is acceptable. Rails shall be fixed to each post using a minimum of three 6- inch galvanised flat head nails. | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
5.02.03 | Height of Fence | The standard height for the fence is 1.150m | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
5.02.04 | Timber rail spacings | Timber rails shall be equally spaced between the top rail and the bottom rail. The top rail being positioned at the standard fence height (above), noting that tops of posts may need to be trimmed to match the top rail height. The gap beneath the bottom rail shall be no more than 150mm. | Designer | Installation Record Photos Miscellaneous | Each Area | H | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Red-line Markup | Provide red-line markups for items that have been moved, modified, etc. | Downer | Red-line Markup | Upon Completion | H | SE
6.01.02 | As-built plans | As-built plans to comply with RITS. | Downer | As-built | Upon Completion | H | SE