## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Fencing | itp |  |  |  |  | ITP - Fencing Rev C
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.02 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.03 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.05 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Subcontractors
label | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
label | ○ All subcontractors have been inducted.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.07 - Pre-commencement Meeting
label | Acceptance / Conformance Criteria - Unless advised otherwise, pre-commencement meeting will be conducted with designer and contractor to determine final location of fencing. Contractor to co-ordinate all fencing alignment and fencing accommodation works with Engineer, HCC Representatives, and Landowners including on- site meetings.
label | Standard / Specification - Project Specification
label | Verifying Document - InEight Correspondence
label | Frequency - Prior to works start
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Timber Posts
label | Acceptance / Conformance Criteria - Brand new 1.8m long H4 treated no. 1 grade full round posts.
label | ○ Or equivalent as per "2016 Conventional Farm Fencing Taratahi" guide.
label | Standard / Specification - PS 2.1.2 Fencing
label | Verifying Document - Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Timber Battens
label | Acceptance / Conformance Criteria - Brand new 50x50 H3 treated battens between each post.
label | Standard / Specification - PS 2.1.2 Fencing
label | Verifying Document - Dockets
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Wire
label | Acceptance / Conformance Criteria - 2.5mm galvanised steel high-tensile 7-wire.
label | Standard / Specification - PS 2.1.2 Fencing
label | Verifying Document - Dockets, Mill Certs
label | Frequency - At delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.04 - Special Fences and Gates
label | Acceptance / Conformance Criteria - To be confirmed with designer.
label | Standard / Specification - Designer
label | Verifying Document - InEight Correspondence
label | Frequency - Prior to installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - 7-Wire standard Boundary Fence Installation
label | Acceptance / Conformance Criteria - The minimum standard of fence for a straight section on flat ground with favourable ground conditionsshall be a post and batten fence with 1.8m long H4 treated No.1 grade full round posts spaced at 4.0m centres, five 50×50 H3 treated battens between each post and seven 2.5mm high-tensile wires. extending and adjusting all lateral fence lines to tie in with the new permanent fencing.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.02 - Posts
label | Acceptance / Conformance Criteria - Strainer and angle posts shall be included on the new fence lines at the laterals, and the laterals re-tensioned.
label | ○ Line posts shall be minimum 1.8m long H4 No.1 grade full round posts. 4m spacings.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Gates
label | Acceptance / Conformance Criteria - 3.6m light gate or 4.2m light barred gates. Singles or double gate. As per designer's requirements.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.04 - Corner
label | Acceptance / Conformance Criteria - No.2 2.4m long strainer and at the ends of the fence line.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.05 - Height of Fence
label | Acceptance / Conformance Criteria - Standard height to be 1.150m.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.06 - Staples
label | Acceptance / Conformance Criteria - Installed at approximately 170-175 degrees and staggered to prevent splitting of the post/batten
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.07 - Wire Spacing
label | Acceptance / Conformance Criteria - Distance from ground - general arrangement.
label | ○ Wire 1 - 125mm, 2 - 250mm, 3 - 375mm, 4 - 500mm, 5- 650mm, 6- 730mm, 7 - 930mm.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.02.01 - Posts
label | Acceptance / Conformance Criteria - Posts Strainer/Angle Posts should be a minimum of 2.4m Long and 175-200mm Diameter or 2.4m Long x 200-225mm Diameter, Line Posts Minimum 1.8m Length x No 1 (H4 treated) Full Round 1 1 5-135mm Diameter at a maximum spacing of 4.0m or less depending on the contour of the ground.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.02.02 - Timber rails
label | Acceptance / Conformance Criteria - A minimum of three timber rails shall be provided.
label | ○ Timber rails shall be no less than 150mm x 50mm (unless accepted by the Owner where an alternative size matches their existing fence). Rough sawn grade is acceptable. Rails shall be fixed to each post using a minimum of three 6-inch galvanised flat head nails.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.02.03 - Height of Fence
label | Acceptance / Conformance Criteria - The standard height for the fence is 1.150m
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.02.04 - Timber rail spacings
label | Acceptance / Conformance Criteria - Timber rails shall be equally spaced between the top rail and the bottom rail. The top rail being positioned at the standard fence height (above), noting that tops of posts may need to be trimmed to match the top rail height. The gap beneath the bottom rail shall be no more than 150mm.
label | Standard / Specification - Designer
label | Verifying Document - Installation Record, Photos, Miscellaneous
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Red-line Markup
label | Acceptance / Conformance Criteria - Provide red-line markups for items that have been moved, modified, etc.
label | Standard / Specification - Downer
label | Verifying Document - Red-line Markup
label | Frequency - Upon Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - As-built plans
label | Acceptance / Conformance Criteria - As-built plans to comply with RITS.
label | Standard / Specification - Downer
label | Verifying Document - As-built
label | Frequency - Upon Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature