## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
DTM-ITP-014- Water Main Relocation
| Scope |  |  | water main relocation
Rows
|  | Water Main Relocation | dynamic | water main relocation
Columns
|  | 1.1 - Obtain the TasWater Engineering Design Approval |  | 1.1 - obtain the taswater engineering design approval
|  | 1.2 - Pre job-start meeting with TasWater |  | 1.2 - pre job-start meeting with taswater
|  | 1.3 - Apply for and obtain permit to construct |  | 1.3 - apply for and obtain permit to construct
|  | 1.4 - Preparation and submission of construction management plan |  | 1.4 - preparation and submission of construction management plan
|  | 1.5 - Request and schedule booking for a witness pressure test with TasWater |  | 1.5 - request and schedule booking for a witness pressure test with taswater
|  | 1.6 - Request and schedule the isolation and cuttover to new infrastructure |  | 1.6 - request and schedule the isolation and cuttover to new infrastructure
|  | 1.7 - Check for correct documentation |  | 1.7 - check for correct documentation
|  | 1.8 - Implementation of all measures and controls |  | 1.8 - implementation of all measures and controls
|  | 2.1 - Survey Set-Out |  | 2.1 - survey set-out
|  | 2.2 - Excavation Permit |  | 2.2 - excavation permit
|  | 2.3 - Vacuum excavation of trench |  | 2.3 - vacuum excavation of trench
|  | 2.4 - Installation of pipework (including new property connection). |  | 2.4 - installation of pipework (including new property connection).
|  | 2.5 - Installation of thrust blocks (temporary and permanent) |  | 2.5 - installation of thrust blocks (temporary and permanent)
|  | 2.6 - TasWater Inspection |  | 2.6 - taswater inspection
|  | 2.7 - Back-fill of trench for purpose of pressure testing |  | 2.7 - back-fill of trench for purpose of pressure testing
|  | 2.8 - Removal of old section of water main |  | 2.8 - removal of old section of water main
|  | 3.1 - Pressure Testing of new pipework |  | 3.1 - pressure testing of new pipework
|  | 3.2 - Cut-Over |  | 3.2 - cut-over
|  | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. |  | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Print Name: | QAV - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | QAV - Position: | QAV - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Print Name: | Fulton Hogan - Print Name: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Fulton Hogan - Position: | Fulton Hogan - Position: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction
|  | Work Completed On: | Work Completed On: | the signature below verifies that this itp has been completed in accordance with the fh’s quality system procedures and verifies lot compliance with specifications. | 6 - post construction