## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7b20b81b-b080-43d1-912e-02cb09f7c6ba | checklist | External CFC |  | External 8.5mm fine Texture cladding
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8d02989b-3b9a-49d5-b486-418f239d05df | checkpoint | Check external wall frames alignment
53cfd175-09f6-4dd7-ba62-a302fb552138 | checkpoint | Install all flashing as per wall detail and project drawings
378579b9-974e-4138-a1e7-43bde94e84b1 | checkpoint | Install sarking and tophats
7b7b43e1-3e4a-4855-8d5b-1538410df5a2 | checkpoint | Horizontal & Vertical Alignment
41464048-e2ee-4d5d-a2aa-a5944194d330 | checkpoint | Install CFC
bf66b374-1cf6-4080-8aae-8e5f2d2f01f0 | checkpoint | Joints caulking & Sealing
95337c75-15f2-4ecd-9283-4e38cd47b38c | checkpoint | Defects
2190a4de-c220-4143-8cf6-ca60ddbe69e0 | checkpoint | Final Inspection (water test by builder)
25f6e81c-f7c8-44f7-a45d-3cc9bd8bc99f | checklist | External Hebel wall |  | External Hebel wall
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
567d25d5-4f80-4ed3-b064-1b7062d8da6b | checkpoint | Angle/sarkingor rab board/top hats in place
c69a1d84-7107-4443-8d73-5138c7d4fbc8 | checkpoint | Hebel panels Alignment
4df1b82a-2205-4b86-b218-ff25dbbc01b3 | checkpoint | Ensure Hebel power panel finish are as per the finishes shown on project drawings and elevations
13242eda-f2e8-469d-af2a-2c9d3a520bae | checkpoint | All sarking /rad board has been installed as per manufacturer's recommendations
a8668415-791c-47dc-84ef-be2300f2b942 | checkpoint | Sarking overlap flashing by min. 150mm.
921ddb6d-489b-4134-990a-70543b17c80e | checkpoint | Flashings are installed correctly, are continuous and free of any imperfections
afbef785-8605-4cb0-935d-a5495a216e21 | checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
88d849b1-fdad-4706-b9b2-400a9a2711dc | checkpoint | Window seal cuts to be neat & consistent
1f136805-a32b-49b0-bd63-feded9117479 | checkpoint | Hebel Panel cut treatment reinforcement
2d16ba7d-958f-479b-8517-15958bf24d0d | checkpoint | Ensure hebel panels are in full and not cracked
79c16726-8e31-4655-beed-37f04242989b | checkpoint | Ensure on site routing of panels to be perfectly straight and level
eac8f9a3-80cd-4de3-97fd-f665d627d49f | checkpoint | Enure control joints have been installed in accordance with manufacturers specifications and installation guide
87debc5c-acf4-4a9b-8e7c-8d4e6bda44c5 | checkpoint | Hebel expansion joints have been installed and are consistent including slab junctions
9a37cc4d-0ef8-4885-a313-36b473329f8d | checkpoint | Weep holes have been installed correctly and at correct heights and spacings
d1540784-0665-4897-8608-b24b77c53edc | checkpoint | All Hebel walls line up with elements above
185549c7-999f-466c-8b00-6dfe9a67a58f | checkpoint | Panels finish(patches done)
9b79fcff-951c-42a7-8827-d45f2a2bb860 | checkpoint | Fire-rated caulking and sealing(Junctions should treated with Sealant and backing rod - for both top and bottom junction)
6d750180-cfdc-43fa-9833-2dc8caf6c593 | checkpoint | Satisfaction and sign off from CSR inspection (Provide report to ALAND)
e3db7131-b980-41b8-af3a-30501c5d882e | checklist | Plastering & Internal Hebel |  | Plastering & Internal Hebel
63d35af1-8b83-4d8e-8595-5322ef7c03f5 | section | External and internal Framing
0076064a-4ad7-4a21-8acb-c7fce5874fda | checkpoint | All frames/studs set out correctly
4eca20a4-97e1-4393-b5ab-5d25c5fa25fb | checkpoint | All frames plumb and square
a53d6379-3546-42e7-a3d0-8580165f063b | checkpoint | Fix to structural members
f086f5c0-8017-40b0-ba7e-3d0842cb6637 | checkpoint | All window and sliding door openings are as per plan and line up with above elements.
c21ea66e-2da5-479b-ab68-914fd5b256f9 | checkpoint | Nogging all installed correctly
7026e9bb-156d-47b4-ae0a-b94173ec3660 | checkpoint | Plywood installed to all wet areas to adaptable units
f75577a5-bfc0-4cc1-82ce-0d59b8365ca4 | checkpoint | Door frames fixing
e3ec31fd-ca84-4d6c-ae77-8c7dd0c78d93 | checkpoint | Studco Supplier inspection (Provide report to Bathla)
e3351297-2a1f-44d6-9366-c522730aa075 | section | Internal Hebel wall
24f270b5-b941-4277-a89b-7d5a3e8db0b2 | checkpoint | Angle/sarking/top hats in place
0debaf74-48fe-46ea-a4cf-3fbabc4fadd9 | checkpoint | Hebel panels Alignment
0fa29d1b-010f-4ab9-afff-a8118ed5d25e | checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
e84bfbc4-d8a4-4a20-b1de-7e098eeaffd9 | checkpoint | Ensure hebel panels are in full and not cracked
4a0a8a0e-390d-4470-829b-e4902cf2cd8e | checkpoint | Enure control joints have been installed in accordance with manufacturers specifications and installation guide
b48c8099-d7e2-41cf-b13a-99a8eeed581e | checkpoint | Hebel expansion joints have been installed and are consistent including slab junctions
434f2fbe-41c4-4dca-906b-900edc1c94c4 | checkpoint | Insulation installed as per AS/BCA (party walls + external)
4547ea3b-6e2a-4f7e-8468-6be82367ebf2 | checkpoint | Panels finish(patches done)
42bff550-8754-4a36-b3ff-67c8f4013512 | checkpoint | Fire-rated caulking and sealing
f371c1f3-7dbd-4176-aa7c-eca8141a580d | checkpoint | Satisfaction and sign off from CSR inspection (Provide report to Bathla)
dafa8b29-969b-4870-8175-14f39758c507 | section | Plasterboard for Walls
3da179b4-23d8-4ff0-89b0-c716694bc3f4 | checkpoint | Ply nogging
ea9aca9f-72f2-42a0-a953-555e704fb2b5 | checkpoint | Rough-in sign off
35d85959-bc2c-463f-b824-28db5d061196 | checkpoint | Insulation installed as per AS/BCA
0c31882e-816c-4258-aa76-a641881d6957 | checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
1b708039-e252-4790-834d-1db1c65261f2 | checkpoint | 13mm WR to wet areas ONLY
0f606d97-c009-4431-93b8-b3d668e95ce7 | checkpoint | Plasterboard Lining to be installed as per installation guide
bacc16cf-a267-485d-b48c-fdfe453d89ae | section | Plasterboard for Ceiling
ca6f20c9-017c-47d9-9ac5-c3942fe7a728 | checkpoint | Confirm Ceiling height
f7a4f6ca-d97e-404d-8175-073b253d43aa | checkpoint | Confirm Access panel location
a95bce67-1db7-4027-95f0-7d4923562dd6 | checkpoint | Ceiling frame work
2274cae9-7fbb-4e6b-8765-5fe3b525cb26 | checkpoint | Ceiling bulkheads where required
cd9a5c00-fc40-4efe-959a-8f92cda2b9f2 | checkpoint | Pelmets
a14717bb-5e9d-4a15-b99d-a916a35478ba | checkpoint | Ceiling insulation where required as per AS/BCA
5cdf6b3a-a7d6-49df-b0f5-c2ad902779a5 | checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
5d4510f1-e356-4bcb-b2a5-fc0915769b3d | checkpoint | 13mm WR to wet areas ONLY
a1cf5af7-6fb1-4974-9bae-94a9c1bad680 | checkpoint | Ceiling plasterboard Lining
2415e6c4-fd4d-4803-b00e-5bad7f1cbd1b | section | Setting & Sanding
3428f24e-54dd-4acd-84ff-a380e4b2f017 | checkpoint | Angle /LB/P50 install
3d8d1fa4-7f57-41a7-8546-784c90222570 | checkpoint | First coat setting
bab30fc7-e81e-4548-b64c-562753c43d3d | checkpoint | Second coat setting
ac6eb326-388e-452e-bef5-13c8b238c6cd | checkpoint | Final coat setting
ace079bd-c081-4d1a-b542-5b4f47c3b14a | checkpoint | Sanding
39694627-ba73-4d69-a889-80dd03fb8f2e | checkpoint | patching
db8ac2e1-7ac4-4de8-b953-118482912677 | checkpoint | Defects
2c83e93c-16af-4ee9-aab9-ef0e4b485bab | checkpoint | Final Inspection
cfde1efa-9dcf-43bf-b7c9-fe29b40cbd6d | checklist | Rigid Insulation |  | Rigid Insulation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7d91e47a-1c0e-4fe6-a08a-ee68b311dff6 | checkpoint | Surface preparation
a9673b45-5277-4400-9f0c-f8c3ecc7b62c | checkpoint | Photos of substrate prior to installation of rigid insulation
9fca3205-f386-4dde-94ee-751cd7dee0fe | checkpoint | Install rigid insulation
08456b62-2870-4cb6-9dd5-91f7f253c828 | checkpoint | Tape all joints properly