## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
3c467505-2921-4ad5-a7a2-2a3d7af7a021 | checklist | Balcony Waterproofing QA |  | Balcony Waterproofing QA
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
bdde7e69-4987-4366-a3df-bac5aeea434c | checkpoint | Area
ebf19140-aec1-44ab-8790-011fff0ad160 | checkpoint | Substrate is smooth and clean
1e9e48c9-490b-4f09-9a04-331904c9f06c | checkpoint | Prime substrate with Bituthene solvent primer
6d67051b-8127-4c8f-ba1d-bd9d59aaf71a | checkpoint | Bitumen triangular fillets
e0564528-9d7d-4496-8a94-82c0b654877c | checkpoint | Nuraply 3PB base layer
f306674d-5ed1-4dc1-ac32-cfe383319bde | checkpoint | Nuraply 3PM cap sheet
baf3a74a-9661-48d4-bdfe-1969a6546007 | checkpoint | Termination
40f7a276-a192-4281-a5a3-e80304b95c42 | checkpoint | ILD report
2edac5dd-8c5c-4560-ae4d-0e7cb7ab7f05 | checkpoint | ILD repairs
a5914dc2-ed34-43c9-a717-1e9a7b779a09 | checklist | Bentonite QA |  | Bentonite QA
e58d40ff-c3e1-40ff-bc0f-549e3fdaeb64 | section | Details
36338ddc-8ee3-498c-a0ec-10f31e4aa71c | checkpoint | Area
f3018d1e-f302-4ad6-8a13-9f8b0afa7b8c | checkpoint | Substrate
20e650af-9ad9-4e4d-bbc9-5bbadd6441c4 | checkpoint | Bentonite with 100mm lap
1a636618-fef4-4250-a642-4b509697e54a | checkpoint | All laps pasted
82696f44-d7bb-4c26-b5c1-74e8f0c16112 | checkpoint | Sikalastic 152
1c44e555-e019-4e40-b590-26f6fd6a247a | checkpoint | Termination
2daccb36-7389-4569-bfa1-cf7f1c082210 | checklist | Documents & Photos |  | Documents & Photos
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c2957035-7dfb-4eb2-b8f9-fffc12e60497 | checkpoint | Please upload the relevant document(s) / photos and press PASS.
fab947da-0587-45c4-840a-e0d8dd7799c2 | checklist | Gripset Waterproofing QA |  | Gripset Waterproofing QA
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
2fabef4a-0c39-4bca-8b13-47fdf72151e1 | checkpoint | Prep, mask and apply Bostik prep primer M
1945ffdd-9815-412d-b3d1-66dc08f2c2da | checkpoint | Bostik ISR 70-03
2425a4a3-c56d-4d4c-82c0-216e3339dfbd | checkpoint | Gripset OP primer
2abad017-a3be-4f16-a8d9-9f74094e7a23 | checkpoint | Gripset 38FC
ae716da4-c0ab-4ce8-baf3-73fab5a26012 | checkpoint | Gripset E60
9b3217c0-bda9-40a8-a9b3-49d3991ff3be | checkpoint | Detail
8f3d63b8-b9d4-4796-8d23-77a8da44557a | checklist | Sarnafil QA |  | Sarnafil QA
f41ddb0e-93b3-46f1-b65c-64ff65b04754 | section | Details
15cb81a4-d148-43db-86eb-518d63293396 | checkpoint | Area
aad15f44-5397-4ebe-b4d3-7288f7c7f19a | checkpoint | Sarnavap
cd8960a8-c09f-46b4-8722-e3f6ba6e6eeb | checkpoint | Sarnatherm
4ea000d0-3de5-4f86-89d3-57c4618b778b | checkpoint | Sarnafil
99b25332-65d0-4473-a41c-bbf206d3dfc6 | checkpoint | Termination
53ab7cae-ec7b-45a6-b393-cc22297753d1 | checkpoint | Probe test
9c966f66-2f57-4301-800e-75dd38b5f55c | checkpoint | Drainage composite
a9bcb519-65d1-45cd-a503-c4f16c74755b | checkpoint | Geotextile cloth
e5f3cfba-2112-4a3e-8a0c-3976d721c8fe | checkpoint | Stones