## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Checklist to use
Project QA
Lift pit
Volclay QA
Ground Floor
Common areas
Lift / Lift Lobby
Communal Space
Reception
Entry/Lobby
Corridor
Stairs
Service areas
Services (Riser)
Main Equip.Room (MER)
MSB room / Services
Residential areas
4001
4002
4003
4004
4005
Level 01
Common areas
Lift / Lift Lobby
Communal Space
Reception
Entry/Lobby
Corridor
Stairs
Car Park
Service areas
Services (Riser)
MSB room / Services
Residential areas
4101
4102
4103
4104
4105
5101
5102
Level 02
Common areas
Lift / Lift Lobby
Communal Space
Reception
Entry/Lobby
Corridor
Stairs
Car Park
Service areas
Services (Riser)
MSB room / Services
Residential areas
4201
4202
4203
4204
4205
5201
5202
Level 03
Common areas
Lift / Lift Lobby
Communal Space
Reception
Entry/Lobby
Corridor
Stairs
Car Park
Service areas
Services (Riser)
MSB room / Services
Residential areas
4301
4302
4303
4304
4305
4306
4307
4308
5301
5302
5303
5304
Level 04
Common areas
Lift / Lift Lobby
Communal Space
Reception
Entry/Lobby
Corridor
Stairs
Service areas
Services (Riser)
MSB room / Services
Residential areas
4401
4402
4403
4404
4405
4406
4407
4408
5401
5402
5403
5404
Level 05
Common areas
Lift / Lift Lobby
Communal Space
Reception
Entry/Lobby
Corridor
Stairs
Service areas
Services (Riser)
MSB room / Services
Residential areas
4501
4502
4503
4504
4505
4506
4507
4508

## Project Checklist Templates
Type | Name | Values
checklist | Volclay QA
checkpoint | Voclay
checkpoint
checkpoint
checkpoint
checkpoint
checkpoint
checklist | Documents & Photos
checkpoint | Please upload the relevant document(s) / photos and press PASS.

## Generic CONQA Templates
Type | Name | Values
checklist | Add AR250 Waterbar
section | Details
checkpoint | Area/ Section installed
checkpoint | AR250 Waterbar installed and Checked against Survey Points
checkpoint | All Welds visually Checked
checkpoint | Method of Fixing
textbox
checkpoint | Signed off as completed
checklist | Add Sealant QA
section | Details
checkpoint | Date
checkpoint | Area
checkpoint | Installer
checkpoint | Sika Specification (if any)
checkpoint | Substrate
checkpoint | Sika Products used last 6 digits of batch number
checkpoint | Method of substrate preparation (eg grinding, abrading, drying etc)
checkpoint | Sika Cleaner / Primer used
checkpoint | Joint dimmensions width x depth
checkpoint | Weather Conditions
checklist | Add Sika 11FC Checklist
section | Area Prep
checkpoint | Area clean and accessible (attach photo)
textbox | Substrate type
checkpoint | Substrate acceptable, dry and free from dust and other contaminants
checkpoint | Record weather conditions
section | Application QA
checkpoint | Sika Products used last 6 digits of batch number (attach photo)
textbox | Method of substrate preparation
textbox | Sika Cleaner used (attach photo)
textbox | Appropriate Primer used (attach photo)
checkpoint | Masking tape used to protect outside face
checkpoint | Sealant firmly extruded and tooled to promote adhesion
checkpoint | Tape removed before curing starts
section | Handover
checkpoint | Attach general site comments and photos
checkpoint | Work completed as per spec and area left neat and tidy
signoff | Main Contractor Signoff
checklist | Add Sika Blackseal BE
section | Details
checkpoint | Date
checkpoint | Applicators
checkpoint | Surface and what prep was required
checkpoint | Method of preparing joints
checkpoint | Method of detailing pipe and other penetrations
checkpoint | Area of work and m2 completed
checkpoint | Sika Blackseal Elastic amount used and last 6 digits of batch number
checkpoint | Dry film thickness in microns
checkpoint | Weather conditions including temperature in Celsius
checkpoint | Surface Temp
checkpoint | Protection used
checklist | Add Sikadur Combiflex
section | Details
checkpoint | Date
checkpoint | Applicators
checkpoint | Area
checkpoint | Surface and preparation completed
checkpoint | Method of Preparing joints or cracks
checkpoint | Hypalon tape used type and length
checkpoint | Sikadur 31 number of units and last 6 digits of batch number
checkpoint | Weather conditions (degrees )
checkpoint | Surface Temperature (degrees)
checklist | Allco - Hydrotech Checklist
section | Hydrotech Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
section | Hydrotech Site & Substrate Prep
checkpoint | Wind uplift has been considered prior to installation
checkpoint | Ensure all drains and outlets are membrane compatible. Confirm with Allco rep if required
checkpoint | Concrete substrate has been allowed to fully cure with a minimum wood float finish
checkpoint | Substrate clean, dry and free of debris or release agents
checkpoint | Substrate photos taken
section | Hydrotech Horizontal & Vertical Application
checkpoint | Test conducted to ensure membrane creates a mechanical bond to the substrate
note | Attach application photo (1 photo per 20m2 or separate area)
checkpoint | First membrane layer applied at 3mm thickness
note | Attach application photos (1 photo per 20m2)
checkpoint | Top coat of Hydrotech applied at 3mm thickness
note | Attach application photos (1 photo per 20m2)
checkpoint | Photo proving total thickness of membrane system is 9mm (including protection layer)
checkpoint | Photo of complete installation
section | Hydrotech Detailing
checkpoint | All penetrations have detailed as per Allco specifications
section | Hydrotech Terminations
checkpoint | Ensure the approved sealant or tape is used for termination
checklist | Allco - Protection & Backfill Checklist
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
checkpoint | Allguard has been installed as per Allco specifications?
checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm?
textbox | Backfill date
checklist | Allco - Sweltite Checklist
section | Sweltite Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
section | Sweltite Site & Substrate Prep
checkpoint | Appropriate site conditions for installation
checkpoint | Appropriate water control in place
checkpoint | Substrate photos taken
section | Sweltite - Foundation walls
checkpoint | Appropriate detailing done as per Allco specifications
checkpoint | Ensure 100mm laps between membrane
checkpoint | All laps seam taped horizontally & vertically using Allco seam tape
checkpoint | Sweltite exceeds 150mm past F.F.L
checkpoint | Drainage coil has been placed 100mm from the floor/wall joint
section | Sweltite Penetrations
checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
section | Sweltite Termination
checkpoint | Termination bar used on vertical & horizonal edges
checkpoint | Cetcoat applied at appropriate areas
checkpoint | Termination sealed off correctly (i.e. M2000, Cetseal)
section | Sweltite Backfill & Protection
checkpoint | Allguard has been installed as per Allco specifications
checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
textbox | Backfill date
checklist | Allco - Voltex Checklist
section | Voltex Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
section | Voltex Site & Substrate Prep
checkpoint | Appropriate site conditions for installation
checkpoint | Appropriate water control in place
textbox | Concrete pour date
checkpoint | Substrate photos taken
section | Voltex Walls, Underslab and Footings
checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up
checkpoint | 100 mm overlap between each sheet, and stagger sheets end at a minimum of 300mm
checkpoint | Appropriate detailing done to external/internal corners
section | Voltex Penetrations
checkpoint | Penetrations detailed as per Allcos recommendations
section | Voltex Backfill & Protection
checkpoint | Allguard has been installed as per Allco specifications
checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
textbox | Backfill date
checklist | Allco - Waterstop-RX Checklist
section | Waterstop-RX Area of Installation
checkpoint | Checklist named with location or text box below or marked up drawing attached
textbox | Description, grid sections, etc:
section | Waterstop-RX Site & Substrate Prep
checkpoint | Substrate is acceptable
checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
textbox | Concrete pour date
checkpoint | Substrate photos taken
section | Waterstop-RX Installation
checkpoint | Waterstop-RX has been installed as per Allco specifications
checkpoint | All parties aware of Waterstop-RX requirements with exposure to climatic conditions
checklist | Ardex Butynol
section | Prestart
checkpoint | Area Accessible
checkpoint | Substrate must be dry with max 18% moisture content
checkpoint | Sheeting laid staggered joints (brick bond), the edge of sheet supported with framing.
checkpoint | Plywood fix S/S screw countersunk with a 3mm gap between all sheets, 150mm centre on edges & 200mm in the body.
checkpoint | All joints of plywood and junctions with other materials covered with 25mm release
section | Roof QA
checkpoint | Installed so that laps facing down
checkpoint | Correct adhesive used as per spec
checkpoint | Membrane fully adhered to plywood
checkpoint | Adhesive evenly spread
checkpoint | Overlaps at lease 50mm
checkpoint | Seam tape and seam primer used
checkpoint | All lap, penetrations and details fully closed and tested.
checklist | Ardex Plywood Substrates
section | Prestart
checkpoint | Edge protection/scaffold in place
signoff | Raise remedial / request review
checkpoint | Safety nets installed
signoff | Raise remedial / request review
checkpoint | Purlins/battens & all necessary timberwork complete
signoff | Raise remedial / request review
checkpoint | Other trades works damage free & protected
signoff | Raise remedial / request review
section | Roof QA
checkpoint | A minimum of 17mm complying with AS/NZS 2269. CD Structural Grade plywood with the sanded C face upwards, and H3 with Waterborne treatment
checkpoint | Substrates must be dry when an ARDEX waterproofing membrane is applied. The plywood and the timber substructure shall have a maximum moisture content of 18% when an ARDEX waterproofing membrane is adhered
checkpoint | Plywood panels shall be laid with staggered joints (brick bond), the edge of sheets shall be supported with dwangs or framing
checkpoint | Plywood shall be laid with the face grain at right angles to the supports. A 20mm triangular fillet shall be used at the base of any 90° upstand. External edges shall be chamfered with a minimum radius of 5mm
checkpoint | Plywood shall be fixed with 10 gauge x 50mm stainless steel countersunk head screws with 3mm gaps between all sheets, at 150mm centres on edges, and 200mm in the body of the sheets
checkpoint | All joints in the plywood and junctions of plywood with other materials must have a 25mm release tape applied before application of the membrane
checkpoint | Framing supports at a maximum 400mm centres (in one direction). All plywood edges must also be supported. Do not use tongue and groove plywood. If thicker plywood is to be used support spacing needs tomeet NZBC and NZS3064, or engineer specific design
checkpoint | Clarify for how long the plywood has been exposed?
checkpoint | Minimum17mmF8 CCA H3.2 treated structural plywood (not LOSP treated).
checkpoint | Minimum CD grade with the sanded C face upwards
checkpoint | Minimum required falls are met , Correct falls to outlets
checkpoint | Plywood laid with face grain at right angles to supports
checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges. Bond breaker tape to be applied to all plywood sheet joints prior to membrane application
checkpoint | All outlets and overflows fitted and rebated into the substrate
checkpoint | Plywood is screwed with 10g x 50mm SS counter sunk screws at 150mmcentres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm
checkpoint | Provide 20mmtimber fillets at the base of all upstands
checkpoint | Chamfer all external edges with aminimumradius of 5mm
checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisturecontent
checkpoint | All drains and outlets aremembrane compatible
checkpoint | Has the installer accepted the condition of the plywood?
checkpoint | Please ensure you have clearly ordered the correctmembrane, colour and thickness for your project
checklist | Chevaline Dexx Checklist
section | Details
checkpoint | Substrate clean and dry
checkpoint | Substrate grinding completed
checkpoint | Chevaline Dexx base coat applied
checkpoint | Chop strand matt installed
checkpoint | Chevaline Dexx second coat applied
checkpoint | All upstands and details completed
checkpoint | Area left clean and tidy
checklist | CONQA Roofing QA
section | Details
checkpoint | Details
dropdown | Warranty Type? | Full System, Product only
dropdown | Roofing System? | Cold Roof, Warm Roof, Recover Roof
textbox | For warm roof and recover roof systems,please list materials.
dropdown | What is the substrate? | Plywood, Concrete, Metal Tray
button | Does the substrate meet Allco’s substrate requirements? | Yes, No
dropdown | What membrane system was installed? | Casali, Hydrotech,TPO
button | What adhesive system was used? | Primer, Adhesive
button | All laps and details have been seam probed | Yes, No
button | All internal/ external corners and tee joints are detailed correctly | Yes, No
dropdown | Outlet/ Overflow type | Scupper, Clamping, Sumps
button | Outlets and overflows detailed correctly | Yes, No
checkpoint | Photos of Membrane sheet laps?
note | Please note in the comments the details of the photos, areas/gridlines/specifics
checkpoint | Photos of Internal/ External corners?
note | Please note in the comments the details of the photos, areas/gridlines/specifics
checkpoint | Photos of Outlets/ Overflows?
note | Please note in the comments the details of the photos, areas/gridlines/specifics
checkpoint | Photos of Penetrations?
note | Please note in the comments the details of the photos, areas/gridlines/specifics
checkpoint | Photos of Terminations?
note | Please note in the comments the details of the photos, areas/gridlines/specifics
checklist | Detec Checklist
section | Details
checkpoint-no-value | Details
date | Date
dropdown | Weather | Clear, Cloudy, Rain, Thunderstorms
checkpoint | Membrane Damages
checkpoint | Leaks
checkpoint | Containminations
checkpoint | Breaches detected
checkpoint | Visual check
tickbox | Photos uploaded
checkpoint | Final test completed
signoff | Request signoff from PM
checklist | Drawings attached
checkpoint | Document Attached
checklist | EcoTUFF TPO & WarmSEAL Quality Control
section | Substrate
checkpoint | WarmSEAL Polyiso substrate stagger-bond laid with each sheet offset at least 300mm and tight butted.
checkpoint | Polyiso Screws installed in straight lines and distance apart (screw pattern) as per wind loading requirements. A minimum of 9 per sqm required.
checkpoint | Correct amount of Adphalt insulation adhesive used (8-10sqm per can). Minimum of 4 runs per sheet and ends adhered.
checkpoint | Substrate clean, dry, and free from foreign matter and sharp edges.
section | Pre Install
checkpoint | No damage evident to the WarmSEAL polyiso insulation. No soft or loose areas of WarmSEAL polyiso and no dents or hollows in the top surface.
checkpoint | All external corners chamfered 5mm radius.
checkpoint | Movement joints identified and installed to approved specification / detail (attach detail drawings)
section | Install
checkpoint | Pipe penetrations and rainwater outlets detailed as per Sealco specification. Use only EcoTUFF® accessories.
checkpoint | Gutters correctly and neatly installed, particularly the internal corners - ensure laps above roof line.
checkpoint | DrainRITE roof drains installed to Sealco specification.
checkpoint | VentRITE overflows installed to Sealco specification.
checkpoint | EcoTUFF adhesive within shelf life and correctly mixed.
checkpoint | EcoTUFF installed to Sealco specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint | All laps minimum 40mm. Lap tested and watertight.
checkpoint | No air entrapment or foreign matter contamination under the EcoTUFF membrane.
checkpoint | EcoTUFF sheets laid across the roof slope, with vertical lap edges fully welded and sealed with cut edge sealer where necessary.
checklist | Equus Deboflex K180 Checklist
section | Details
checkpoint | Substrate acceptable and area ready to begin work
checkpoint | Loose lay Soprema DeboFlex 3.5 CS/F K180 Special to fit inside the formwork with granular surface facing upwards.
checkpoint | Fully heat weld all sheet joints minimum 100mm by gas torch and ensure all are well sealed.
checkpoint | End Joints: Weld end joints as side joints, and scrape away granular chip prior to welding.
checkpoint | All concrete work has been completed, formwork removed and correct curing times have been observed. All cold joints ground smooth.
checkpoint | All joins to receive a bandage of Soprema Debovix 3 T/F P180 heat welded to the outside of the Soprema DeboFlex 3.5 CS/F K180 Special membrane.
checkpoint | Ensure all fastener heads are covered and protruding nail/ staples are cut off and well sealed, using Soprema Duo kit.
checkpoint | All external/internal corners shall receive the same bandage as required.
checkpoint | The Polythene floor membrane shall be turned up the external face of the wall approx. 300mm and taped into place with 300mm strip Soprema Debotack 2.5 SD C175 self adhesive membrane to Soprema DeboFlex 3.5 CS/F K180 Special.
checkpoint | Newly installed membrane shall be protected with the use of drainage board such as Danosa Danodren H15 Plus.Care taken to prevent damage to membrane during backfill.
checkpoint | System to be inspected on completion.
checkpoint | Area left clean and tidy
checklist | Equus Deboflex K180 Checklist
section | Details
checkpoint | Substrate acceptable and area ready to begin work
checkpoint | Loose lay Soprema DeboFlex 3.5 CS/F K180 Special to fit inside the formwork with granular surface facing upwards.
checkpoint | Fully heat weld all sheet joints minimum 100mm by gas torch and ensure all are well sealed.
checkpoint | End Joints: Weld end joints as side joints, and scrape away granular chip prior to welding.
checkpoint | All concrete work has been completed, formwork removed and correct curing times have been observed. All cold joints ground smooth.
checkpoint | All joins to receive a bandage of Soprema Debovix 3 T/F P180 heat welded to the outside of the Soprema DeboFlex 3.5 CS/F K180 Special membrane.
checkpoint | Ensure all fastener heads are covered and protruding nail/ staples are cut off and well sealed, using Soprema Duo kit.
checkpoint | All external/internal corners shall receive the same bandage as required.
checkpoint | The Polythene floor membrane shall be turned up the external face of the wall approx. 300mm and taped into place with 300mm strip Soprema Debotack 2.5 SD C175 self adhesive membrane to Soprema DeboFlex 3.5 CS/F K180 Special.
checkpoint | Newly installed membrane shall be protected with the use of drainage board such as Danosa Danodren H15 Plus.Care taken to prevent damage to membrane during backfill.
checkpoint | System to be inspected on completion.
checkpoint | Area left clean and tidy
checklist | Equus Warm Roof
section | Prestart
checkpoint | All workers inducted to site
checkpoint | Pre Start safety meeting held
checkpoint | Area Accessible
checkpoint | Edge protection and safety installed
checkpoint | Purlins in place
section | Equus Soprema DuOtherm Warm Roof Metal deck substrate install
checkpoint | discuss details and execution of system
checkpoint | Metal deck installed in accordance with Manufacturer’s recommendation.
checkpoint | Outlets are sufficiently sized for anticipated run-off.
checkpoint | Metal roof edges overhanging into gutters are cut back and timber upstand installed at the height of PIR board.
checkpoint | Metal surface satisfactory for installation of Duo membrane by Equus Applicator.
checkpoint | Sufficient and correct fixings installed
checkpoint | No metal edges protruding up high
checkpoint | Flashings installed over hips/ridges and valleys
checkpoint | all swarf swept from roof
section | Vapour Barrier installation Denosa Self Dan
checkpoint | Prime upstands and details only where membrane shall be fully bonded.
checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past Equus PIR Insulation board.
checkpoint | Correct side laps and end laps
checkpoint | Vapour barrier terminated correctly to ensure vapour layer continuity at roof openings, transitions and horizontal to vertical roof openings
checkpoint | Any damage to vapour layer to be repaired to 100 % continuous
section | Insulation
checkpoint | Correct insulation delivered as per specs
checkpoint | Insulation damage free no crushed edges etc
checkpoint | Insulation has been kept dry out of weather at all times
checkpoint | Insulation to be installed in a brick bond pattern
checkpoint | Correct fixing being used including the correct insulation plate or thermal plug
checkpoint | Correct fixing pattern used as per manufacturer's specs or site specific wind uplift calculation
section | Base sheet installation
checkpoint | Mechanically fasten as per job specific Equus Soprema fixing pattern through base sheet to metal deck substrate
checkpoint | All laps torched closed
checkpoint | Maintain side laps of 80mm and 100mm for head laps
section | Cap sheet installation Equus Soprema Duo
checkpoint | Unroll DuO cap sheet, align and cut to length. Re-roll each end back to centre.
checkpoint | Torch evenly and off-set laps to not coincide with basesheet
checkpoint | All joints back sealed separately ensure correctly closed.
checkpoint | Maintain a minimum 80mm side and 100mm head laps.
checkpoint | Detailing shall occur using DuO cap sheet and/or Matacryl Thix/Dexx Topcoat on all outlets, pipe penetrations, gutter stops ends, parapet upstands, machinery plinths and anything above or below roof surface.
checkpoint | System to be inspected on completion.
section | Flashings
checkpoint | Flashings made in specified material/colour
checkpoint | Flashings installed neatly and fixed sufficiently
checkpoint | Flashings sealed with correct sealant
section | Clean up
checkpoint | All rubbish from all stages removed from site
checkpoint | Roofs cleaned down
checkpoint | Scaffold checked on every level for rubbish
checkpoint | Grounds checked for rubbish (under scaffold etc)
checkpoint | Site foreman agrees site is clean
checklist | Head Wall Bituthene 3000
section | Details
checkpoint | Substrate and all voids filled
checkpoint | Substrate primed ready to receive the Bituthene 3000
checkpoint | Bituthene 3000 placed on the prepped area
checkpoint | Laps sealed with Liquid Membrane
checkpoint | Coreflute protection placed
checklist | Inspection of Fukoswell / Sikaswell
section | Details
checkpoint | Inspection of Fukoswell / Sikaswell
textbox | Area being inspected
textbox | Types of swellable being re-inspected
textbox | Location of injection box
textbox | Length of time since the Fuko/Waterstops have been installed
textbox | Final waterproofing system check
textbox | Check for damage, physical or water
textbox | Is there any remedial work required
textbox | Inspect remedial work if required
checkpoint | Final Sign Off
checklist | Membrane Deck Checklist
section | Details
checkpoint | Area Ready and Substrate acceptable to begin work
checkpoint | 2 Coats of Nuraglaze over Nuraply 3PM
checkpoint | Installation of vapour barrier & 60mm Nuratherm board to roof area (Glued)
checkpoint | Lay Nuraply 3PB-SA & 3PM membrane over Nuratherm board
checkpoint | Area left clean and tidy
checklist | Membrane Roofing Checklist
section | Details
checkpoint | Area Ready and Substrate acceptable to begin work
checkpoint | Installation of Dimond NPM 900 0.75mm metal tray onto roof framing structure
checkpoint | Installation of 50x50 dripedge to external gutter area
checkpoint | Application of primer
checkpoint | Installation of vapour barrier & 80mm Nuratherm board to roof area (Mechanically fixed)
checkpoint | Installation of Nuraply 3PB-SA and 3PM membrane over Nuratherm board
checkpoint | 2 Coats of Nuraglaze over Nuraply 3PM
checkpoint | Area left clean and tidy
checklist | Miscellaneous Docs
section | Details
checkpoint | Document Attached
checklist | Nuralite Warm Roof
section | Details
checkpoint | Substrate readiness form completed Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
checkpoint | Under flashings installed to all corners and upstands (pay attention to parapets, gutters, junctions)
checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint | Membrane adequately adhered to substrate with no evidence of bubbles or lifting.
checkpoint | Correct quantities of primer or adhesive used as per specification.
checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination.
checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off.
checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2- 3mm).
checkpoint | Cap sheet and base sheet laps offset satisfactorily.
checkpoint | No three layer lap build-ups Overall installation free of wrinkles, creases and splits
checkpoint | All penetration details completed to specification including under/over flashing
checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint | All non-standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint | Gutters and outlets have been flood tested Any damage to cap sheet repaired to specification.
checklist | Nuraply 3PM Installation Checklist
section | Location of Work
checkpoint | Area where product is being installed
textbox | Area
textbox | Grids
textbox | Other
section | New Concrete Substrate Readiness Checksheet received from Main Contractor and Accepted
checkpoint | Underflashings installed to all corners and upstands (pay attention to parapets,gutters, junctions)
checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint | Membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer or adhesive used as per specification.
checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination.
checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm).
checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint | Nuravents installed to specification.
checkpoint | All penetration details completed to specification including under/overflashing
checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint | Gutters and outlets have been floodtested
textbox | Initial height check made
tickbox | Flooded for 24 hours
textbox | Height check assessed
tickbox | Remedials closed out
checkpoint | Any damage to cap sheet repaired to specification.
checklist | Nuraply 3PT and 3PTM Installation Checklist
section | Location of Work
checkpoint | Area where product is being installed
textbox | Area
textbox | Grids
textbox | Other
section | Nuraply 3PT and 3PTM Concrete Substrate Readiness Checklist
checkpoint | Nuraply 3PT and 3PTM Concrete Substrate Readiness Checklist received from Main Contractor
checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content
checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured.
checkpoint | Nuraswell installed to construction joints as per specification - located 50mm from rebar.
checkpoint | Concrete surface firm with any soft concrete or laitance removed.
checkpoint | All protrusions removed. Surface free from foreign matter
checkpoint | Mortar or bitumen fillets to all upstands and smooth 5mm radius to all external edges
checkpoint | If terminating into a chase, pre-form the chase and ensure its straight and 20mm deep.
checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite system.
section | 3PT and 3PTM Installed Product Checklist on Concrete Substrate
checkpoint | Concrete Substrate checklist completed before work commenced.
checkpoint | Any movement joints installed to approved specification/detail.
checkpoint | Mortar/concrete fillets fitted to all internal junctions and corners chamfered at a 45°.
checkpoint | All corners and upstands incorporate reinforcing or under flashing
checkpoint | Under-slab membrane extends beyond footing and protected until vertical membrane installed.
checkpoint | Side laps 100mm and end laps 150mm fully torched and seamed. Bleed visible on all joints.
checkpoint | All penetrations installed to specification including under/over flashings.
checkpoint | Junction of the floor and wall membranes installed to specification fully bonded and watertight.
checkpoint | All non-standard details installed as per pre-approved specification (attach approved drawings).
checkpoint | Any mechanical damage to membrane repaired to specification.
checkpoint | Membrane termination completed to approved detail.
checkpoint | Suitable drainage system installed below footing as per specification.
checkpoint | Membrane protection boards installed correctly.
checkpoint | Membrane fully adhered to substrate with no bridging, bubbling, or delaminating.
checkpoint | Overall installation free of wrinkles, bubbles, creases and splits.
checklist | Preprufe 300R beams and underfloor
section | Details
checkpoint | Area Specified Below
checkpoint | Geotextile to substrate
checkpoint | Preprufe placed all laps taped Preprufe bedded into LM 300 on top of piles
checkpoint | Adcor 500 T placed around top of pile
checkpoint | Swell seal WA placed around all pile bars
checklist | Preprufe 300R walls
section | Details
checkpoint | Area Specified Below
checkpoint | Geotextile to walls
checkpoint | Preprufe to walls
checkpoint | All laps taped
checklist | QA - Ardex Butynol
section | Prestart
checkpoint | Area Accessible
checkpoint | Substrate must be dry with max 18% moisture content
checkpoint | Sheeting laid staggered joints (brick bond), the edge of sheet supported with framing.
checkpoint | Plywood fix S/S screw countersunk with a 3mm gap between all sheets, 150mm centre on edges & 200mm in the body.
checkpoint | All joints of plywood and junctions with other materials covered with 25mm release
section | Roof QA
checkpoint | Installed so that laps facing down
checkpoint | Correct adhesive used as per spec
checkpoint | Membrane fully adhered to plywood
checkpoint | Adhesive evenly spread
checkpoint | Overlaps at lease 50mm
checkpoint | Seam tape and seam primer used
checkpoint | All lap, penetrations and details fully closed and tested.
checklist | QA - Balconies Waterproofing
checkpoint | Substrate inspected & accepted
note | Substrate must be clean and smooth, dry and free from dust or contaminants. All sharp points and loose materials to be removed.
checkpoint | Surfaces primed with approved primer
checkpoint | Application of first layer of approved membrane
checkpoint | Application of second layer of approved membrane (where applicable)
checkpoint | Check that all laps are 100 > 150 (sheet membrane systems)
checkpoint | Check that all penetrations are sealed with applicable mastic and membrane
checkpoint | Application of topcoat (where applicable)
checkpoint | Flood test (where applicable)
checkpoint | Walk over to inspect soundness
checkpoint | Builder Final Inspection (where required)
checkpoint | Subcontractor Final Inspection
note | Upload signature
checkpoint | Supplier Final Inspection (where required)
checklist | QA - Balcony
checkpoint | Existing coating removed by grinding (photos)
checkpoint | Deck prepared in accordance with specification (photos)
checkpoint | Remove Joint caulking where required (photos)
checkpoint | 1st Coat of Tremco Non-porous primer to steel perimeter@ 100mm (photo's)
checkpoint | 1st Coat of Tremco MPE Epoxy Primer Applied (photo's)
checkpoint | 2nd Coat of Tremco MPE Epoxy Primer with 30/60 broadcast Applied (photo's)
checkpoint | Caulk perimeter steel junction (photos)
checkpoint | Caulk joints as required (photos)
checkpoint | 1st Coat of Tremco Vulkem 350 R Membrane Applied (photo's)
checkpoint | 1st Coat of Tremco Vulkem 951 UV stable trafficable top coat with broadcast 18/40 for non slip Applied (photo's)
checkpoint | 2nd Coat of Tremco Vulkem 951 UV stable trafficable top coat Applied (photo's)
checkpoint | Deck area complete and handover
checkpoint | ILD test report attached
checklist | QA - Coloursteel Cladding Checklist
section | Prestart
checkpoint | Edge protection/scaffold in place
signoff | Raise remedial / request review
checkpoint | Safety nets installed
signoff | Raise remedial / request review
checkpoint | Purlins/battens & all necessary timberwork complete
signoff | Raise remedial / request review
section | Substrate Checklist : Enviroclad Plywood
checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint | Minimum CD grade with the sanded C face upwards.
checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint | Chamfer all external edges with a minimum radius of 5mm.
note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint | All drains and outlets are membrane compatible.
note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
section | Wall Cladding QA
checkpoint | Base flashing installed & taped with correct fall
checkpoint | Cladding installed correct sequence
checkpoint | Screws uniform & intact
checkpoint | Foam installed where required
checkpoint | Flashing junctions cut correctly & uniformed - as rev details
checkpoint | Cladding clean & damage free
checkpoint | Site clean, rubbish in bin or removed
checklist | QA - Coloursteel Roofing Checklist
section | Prestart
checkpoint | Edge protection/scaffold in place
signoff | Raise remedial / request review
checkpoint | Safety nets installed
signoff | Raise remedial / request review
checkpoint | Purlins/battens & all necessary timberwork complete
signoff | Raise remedial / request review
section | Substrate Checklist : Enviroclad Plywood
checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint | Minimum CD grade with the sanded C face upwards.
checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint | Chamfer all external edges with a minimum radius of 5mm.
note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint | All drains and outlets are membrane compatible.
note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
section | Roof QA
checkpoint | Fascia straight, cut in correctly
checkpoint | Spouting installed with correct falls & outlets as per plans
checkpoint | Underlay over fascia & trimmed neatly
checkpoint | Valleys straight
checkpoint | Screws installed correctly & washers intact
checkpoint | Roof clean from debris & swarf
checkpoint | Flashing junctions tidy & sealed correctly
checkpoint | Roof laid correctly & damage free
checkpoint | Site clean, rubbish in bin or removed
checklist | QA - Coloursteel with R2.6 Insulation Checklist
section | Prestart
checkpoint | Edge protection/scaffold in place
checkpoint | Safety nets installed
checkpoint | Purlins/battens & all necessary timberwork complete
checkpoint | Other trades works damage free & protected
section | Roof QA
checkpoint | Safety mesh installed correctly
checkpoint | Covertex 407 installed correctly
checkpoint | 75mm Bayonet installed correctly
checkpoint | 140mm Insulation installed correctly
checkpoint | 20mm Cavity bat installed correctly
checkpoint | Screws installed correctly.
checkpoint | Roof clean from debris & swarf
checkpoint | Flashing junctions tidy & sealed correctly
checkpoint | Roof laid correctly & damage free
checkpoint | Site clean, rubbish in bin or removed
checklist | QA - Fiberglass System Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Surface Prep
checkpoint | Concrete free of contaminants
checkpoint | Concrete flat and smooth
checkpoint | Bug holes in plinths filled and smooth
checkpoint | All 90deg corners chamfered
section | Membrane install
checkpoint | Install sealant angle fillets to all wall floor junctions
checkpoint | Prime surfaces with Epistixx
checkpoint | 1st body coat with 300gram fiberglass installed
checkpoint | 2nd body coat
checkpoint | 3rd body coat
checkpoint | Traxx 2000 wear coat.
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertherm Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Metal Deck
checkpoint | Timber to have separation
checkpoint | End openings to have closure foam installed
checkpoint | Base deck screwed down in every pan
checkpoint | VCL tape to be installed to all sheet laps
checkpoint | VCL tape to all upstands
section | Post and Rail install
checkpoint | Post installed at correct fixing centers
checkpoint | Thermal break pad under post foot
checkpoint | Rail installed to posts
checkpoint | Gutter line colsure/drip edge flashing installed
section | Insulation install
checkpoint | Specified Insulation installed
checkpoint | No Gaps
section | Top Deck install
checkpoint | Lay sheets straight
checkpoint | Hang over into gutter min 75mm
checkpoint | Top end of sheets turned up
checkpoint | Bottom end of sheets turned down
checkpoint | Fixing back to rail
checkpoint | Profile washers
checkpoint | Screwed off as per fixing plan
section | Flashing install
checkpoint | Installed correctly, accoriding to spec's & drawings
checkpoint | Fixings according to specs & details
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertite Overlay Install Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Substrate
checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
checkpoint | Cut back existing roof edge at gutter
checkpoint | Remove ridge as we go
section | VCL-Vapour Control Layer
checkpoint | Surface/Substrate is dry, clean and free from sharp edges
checkpoint | All areas covered and lapped a minimum of 50mm
checkpoint | All holes/penetrations patched and made watertight
section | Roof Pan Infills
checkpoint | Surface is dry before installing Poly
checkpoint | Infills to be a minimum 5mm above ridges on roof
checkpoint | Every pan has been infilled
section | Roofboard
checkpoint | Substrate/surface dry & clean prior to being installed
checkpoint | Installed in brick pattern
checkpoint | Correct screws with load washer
checkpoint | Installed as per wind uplift fixing plan
checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
section | Fibertite
checkpoint | Correct Glue being used for substrate
checkpoint | Fibertite fully glued to substrate
checkpoint | Broom/rolling of fibertite
checkpoint | Wipe/clean laps with acetone prior to welding
checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
checkpoint | Clamps / rings / baskets installed
checkpoint | Flooded / ILD checked
section | Fiberclad Flashings
checkpoint | Installed correctly
checkpoint | Fixed down according to specification
checkpoint | Cleaned down with acetone prior to welding
checkpoint | Fibertite fully welded to flashing and QA'd with hook
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertite to Concrete Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Concrete Substrate
checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint | Large holes filled with grout
section | Fibertite
checkpoint | Adhesive installed to substrate
checkpoint | Laying of membrane into adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean laps prior to welding
checkpoint | Test weld with the welding machines
checkpoint | Probe of seam with QA hook
checkpoint | Membrane dressed into drains/outlets
checkpoint | Claps/rings/baskets installed
checkpoint | Flood/ILD tested
section | Fiberclad Flashings
checkpoint | Installed correctly according to specifications (right way around)
checkpoint | Fixing and welding done according to specifications and details
checkpoint | Probe of weld with QA hook
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertite to Plywood Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Plywood Substrate
checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint | No Screws/nails/fixings popping up
checkpoint | Joints flush and even
section | Fibertite Membrane
checkpoint | Correct Glue used per spec
checkpoint | Fibertite fully glued to plywood
checkpoint | Broom / roll fibertite into glue
checkpoint | All laps, details, penetrations fully closed & QA'd with hook
checkpoint | Membrane dressed into drains/outlets
checkpoint | Clamps / rings / baskets installed
checkpoint | Flooded / ILD checked
section | Fiberclad Flashings
checkpoint | Installed correctly according to specifications (right way around)
checkpoint | Fixings and welding done according to details
checkpoint | Welding of Fibertite to flashings fully finished and QA'd with hook
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertite Warm Roof Over Concrete Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Concrete Substrate
checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint | Large holes filled with grout
section | Vapor Control Layer
checkpoint | Substrate clean, dry, and free of debris
checkpoint | All areas covered and sheets lapped 50mm
checkpoint | All holes/penetrations patched and water tight
section | Insulation
checkpoint | Surface is dry prior to install
checkpoint | Vapor control layer has been checked and no damage
checkpoint | Insulation boards installed
checkpoint | Joints flush (no gaps between boards)
checkpoint | Correct length of fixing with load washer if no Securock
section | Securock
checkpoint | Surface is dry prior to install
checkpoint | Installed in brick pattern
checkpoint | Correct length of fixing with load washer
section | Fibertite
checkpoint | Adhesive installed to substrate
checkpoint | Laying of membrane into adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean laps prior to welding
checkpoint | Test weld with the welding machines
checkpoint | Probe of seam with QA hook
checkpoint | Membrane dressed into drains/outlets
checkpoint | Claps/rings/baskets installed
checkpoint | Flood/ILD tested
section | Fiberclad Flashings
checkpoint | Installed correctly according to specifications (right way around)
checkpoint | Fixings and welding done according to specifications and details
checkpoint | Probe of weld with QA hook
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertite Warm Roof Over Metal Deck Checklist
section | Pre Start
checkpoint | Area Accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Metal Deck
checkpoint | Timber to have separation barrier
checkpoint | Base deck screwed down in every pan
checkpoint | Sheet edges stiched together at 300mm centres
section | Vapour Control Layer
checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint | All areas covered and sheets lapped 50mm
checkpoint | All holes/penetrations patched and water tight
section | Insulation
checkpoint | Surface is dry prior to install
checkpoint | Vapour control layer has been checked for no damage
checkpoint | Insulation board installed in a brick pattern
checkpoint | Joints flush (no gaps between boards on ends)
checkpoint | Fixings at correct spacing according to spec if no Securock in system.
section | Securock
checkpoint | Is the surface dry
checkpoint | Installed in brick pattern
checkpoint | Correct length screw with load washer
checkpoint | Installed as per wind uplift fixing plan
section | FiberTite
checkpoint | Adhesive installed to substrate
checkpoint | Laying of membrane into the adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean of laps prior to welding
checkpoint | Test weld with welding machine
checkpoint | Membrane dressed into drains/outlets
checkpoint | Clamps / rings / baskets installed
checkpoint | Flooded / ILD checked
section | Fiberclad flashings
checkpoint | Installed correctly according to specifications (Right way around)
checkpoint | Fixings and welding done according to specifications and details
checkpoint | Probe of weld with QA hook
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Fibertite Warm Roof Over Plywood Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Plywood Substrate
checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint | No Screws/nails/fixings poping up
checkpoint | Plywood joints flush and even
section | Vapor Control Layer
checkpoint | Substrate clean, dry, and free of debris
checkpoint | All areas covered and sheets lapped 50mm
checkpoint | All holes/penetrations patched and water tight
section | Insulation
checkpoint | Surface is dry prior to install
checkpoint | Vapor control layer has been checked and no damage
checkpoint | Insulation boards installed
checkpoint | Joints flush (no gaps between boards)
checkpoint | Correct length of fixing with load washer if no Securock
section | Securock
checkpoint | Surface is dry prior to install
checkpoint | Installed in brick pattern
checkpoint | Correct length of fixing with load washer
section | Fibertite
checkpoint | Adhesive installed to substrate
checkpoint | Laying of membrane into adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean laps prior to welding
checkpoint | Test weld with the welding machines
checkpoint | Probe of seam with QA hook
checkpoint | Membrane dressed into drains/outlets
checkpoint | Claps/rings/baskets installed
checkpoint | Flood/ILD tested
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Internal Waterproofing
checkpoint | Substrate preparation test - Visual inspection
checkpoint | Clean all areas of dust and debris
checkpoint | Primer to floors/walls complete
checkpoint | Sealed all walls and floor corners
checkpoint | Waterproofing to walls & Floors
checkpoint | Water tested all bathrooms & Undertook flood testing - Visual inspection
checkpoint | Ready for screed
checklist | QA - Kingspan Roofing Checklist
section | Prestart
checkpoint | Edge protection/scaffold in place
signoff | Raise remedial / request review
checkpoint | Safety nets installed
signoff | Raise remedial / request review
checkpoint | Purlins/battens & all necessary timberwork complete
signoff | Raise remedial / request review
section | Kingspan Roof QA
checkpoint | Screws tight & washers intact
checkpoint | Roof clean of roofing debris
checkpoint | Roof clean of swarf. If FAIL, mark on plan areas of concern & include photos
checkpoint | Undamaged roofing sheet profile. If FAIL, mark on plan areas of concern & include photos
checkpoint | Scratches - mark on plan areas of concern & include photos
checkpoint | Roof laid in correct sequence
checkpoint | Flashing junctions sealed & tidy
checkpoint | Lap tape installed correctly
checklist | QA - Kuniseal Checklist
section | Details
checkpoint | Substrate is clean
checkpoint | Kuniseal waterstop installed as per specification
checklist | QA - Metal Cladding Install Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Install
checkpoint | Bottom flashing installed straight/level all the way around
checkpoint | Building wrap installed
checkpoint | Flashing tape installed (check plans)
checkpoint | Soaker flashings installed
checkpoint | Cladding installed plumb and straight
checkpoint | Screw pattern according to plan/spec/best practice
checkpoint | Flashings installed as per specification
checkpoint | Closure foams installed
checkpoint | Fixings installed correctly
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Metal Flashing Install Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Metal Flashing Install
checkpoint | Installed with a minimum upstand of 150mm or according to drawings
checkpoint | Expansion joint installed if needed (i.e. with runs longer than 12m for coloursteel or 8m for Ali.)
checkpoint | Fixings according to Code as a minimum (or plans if more are required) in a straight line
checkpoint | Laid in a straight and tidy manner
checkpoint | All laps and junctions sealed properly and facing away from waterflow
checkpoint | All visible ends & junctions cut and folded straight and tidy
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Metal Gutter Install Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Install
checkpoint | Brackets installed according to plans/spec/best practice
checkpoint | Gutter lapped and sealed correctly according to best practice
checkpoint | All terminations and ends folded/sealed properly
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - MSR Cladding Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Vapour Control Layer
checkpoint | Substrate clean and ready
checkpoint | All areas covered and sheets lapped 50mm
checkpoint | All holes / penetrations patched and watertight
section | Brackets and Rails
checkpoint | Z brackets installed to fixing plan
checkpoint | Rhom rail installed to fixing plan
section | Insulation
checkpoint | VCL no damage
checkpoint | Insulation installed with no gaps
section | Cladding
checkpoint | Covertek installed with 150mm laps
checkpoint | Starter flashings installed
checkpoint | Soaker flashings installed
checkpoint | Sheets laid straight
checkpoint | Closure foam installed
checkpoint | Correct screw pattern / fixings used
section | Flashings
checkpoint | Installed correctly according to spec and drawings
checkpoint | Fixings according to spec and details
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | QA - Nu Wall
section | Prestart
checkpoint | Substrate - Inspected and Straight
checkpoint | Single Castellated Batten 600mm Centres
checkpoint | Separation Barrier Installed
checkpoint | Windows Installed and Set 18 - 20mm out from Batten
section | Cladding QA
checkpoint | Head flashing Installed Taped and Stop ended
checkpoint | Window / Door/ Base Flashing Screwed at 300mm Centres
checkpoint | Window / Door Foam Tape Installed
checkpoint | Plastic Soakers Installed Around Window / Door Jams
checkpoint | Cladding Brackets Installed evry 600mm
checkpoint | Cladding Free from Damage / Scratches
checkpoint | Site Clean - Rubbish Removed
checklist | QA - Sheet Tanking System Checklist
section | Pre Start
checkpoint | Area Accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready
section | Primer
checkpoint | Applied as per specification on dry substrate at 5m2 per litre
section | Membrane
checkpoint | Temperature must be over 4 degrees for membrane install
checkpoint | Is the substrate clean, dry and clear
checkpoint | Membrane applied with min 50mm overlap
checkpoint | Overlap is to pressure applied or rolled for seal
section | Protection
checkpoint | Works to be protected by main contractor
checklist | QA - Sikaproof A Checklist
section | Details
checkpoint | Gridlines
textbox | Area:
checkpoint | Area clean and accessible (attach photo)
checkpoint | Site concrete poured and accepted
checkpoint | Sikaproof A placed
checkpoint | All laps taped with sikaproof tape 150
checkpoint | All waterstops and injection hoses have been placed
checkpoint | Waterbars have been installed
checklist | QA - Sikaproof P Checklist
section | Details
checkpoint | Gridlines
textbox | Area:
checkpoint | Area clean and accessible (attach photo)
checkpoint | Site concrete poured and accepted
checkpoint | Wall primed and Sikaproof P placed
checkpoint | All laps taped with sikaproof tape 150 to Thermathene
checkpoint | terminated at head complete
checkpoint | pipe pentration seal completed
checklist | QA - Sikaswell A Checklist
section | Details
checkpoint | Gridlines
textbox | Area:
checkpoint | Area clean dry and accessible (attach photo)
checkpoint | All waterstops placed
checklist | QA - Viking Tanking Checklist
section | Preparation
checkpoint | Substrate details specified
textbox | Substrate
checkpoint | If substrate is Site Concrete, must be minimum of 45mm thick
checkpoint | If substrate is Sand/Gap Seven must be minimum 40mm compacted
checkpoint | There is boxing/formwork in the footings and around the perimeter
tickbox | Builder has been made aware that they must not remove the boxing/formwork until the membrane has been torched or mechanically fixed to the top of the footing
checkpoint | All pipe penetrations held firm and on a minimum 2° downward slope
checkpoint | Bitumen fillet has been installed to the footing wall junction
checkpoint | All sharp objects or splashes removed from block concrete
checkpoint | There is enough room to work behind the wall and the bank battered or shored up so it is safe to work
checkpoint | If solvent primer is used, is there enough ventilation or is a charcoal filter mask required. Alternatively, use acrylic bitumen primer.
tickbox | The area defined as confined working space
checkpoint | Wall and footing clean and dry so the primer can be applied
checkpoint | Pointing on the blockwork is flush
checkpoint | Control joints every 6m
checkpoint | The final height has been given
textbox | Final height specified:
checkpoint | The termination detail at the top of the membrane has been finalised
checkpoint | The termination bar has been sealed
checkpoint | The drain coil is in place
checkpoint | Protection is in place on the walls
section | Application
checkpoint | Product installed correctly, checked & reviewed - as per specification
checkpoint | Area left clean & tidy
checklist | QA - Viking Warmspan Checklist
section | Prestart
checkpoint | All workers inducted to site
checkpoint | Prestart safety meeting held
checkpoint | Area Accessible
checkpoint | Edge protection and safety installed
checkpoint | Purlins in place
section | Warm Roof Metal deck substrate install
checkpoint | Pre-start o discuss details and execution of system
checkpoint | Metal deck installed in accordance with Manufacturer’s recommendation.
checkpoint | Outlets are sufficiently sized for anticipated run-off.
checkpoint | Metal roof edges overhanging into gutters are cut back and timber upstand installed at the height of PIR board.
checkpoint | Metal surface satisfactory for installation of Duo membrane by Equus Applicator.
checkpoint | Sufficient and correct fixings installed
checkpoint | No metal edges protruding up high
checkpoint | Flashings installed over hips/ridges and valleys
checkpoint | all swarf swept from roof
section | Vapour Barrier installation
checkpoint | Primer applied evenly and consistent to all surfaces and penetrations to the required height up upstands and parapets etc
checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past PIR Insulation board.
checkpoint | Correct side laps and end laps
checkpoint | Vapour barrier terminated correctly to ensure vapour layer continuity at roof openings, transitions and horizontal to vertical roof openings
checkpoint | Any damage to vapour layer to be repaired to 100 % continuous
section | Insulation
checkpoint | Correct insulation delivered as per plans and specs
checkpoint | Insulation damage free no crushed edges etc
checkpoint | Insulation has been kept dry out of weather at all times
checkpoint | Ends of insulation to be protected by a hard edge with timber or flashing
checkpoint | Insulation to be installed in a brick bond pattern
checkpoint | Correct fixing being used including the correct insulation plate or thermal plug or adhesive
checkpoint | Correct fixing pattern used as per manufacturers specs or site specific wind uplift calculation
checkpoint | Evenly distributed weight if FAST adhesive used
checkpoint | No edges protruding high
section | Coverboard
checkpoint | Correct coverboard delivered as per plans and specs
checkpoint | Any damaged insulation board to be cut out and replaced with new or not used (minimum repair 300 x 300mm)
checkpoint | Correct fastening method ie glue or fixings
checkpoint | Correct fixing pattern used as per manufacturers specs or site specific wind uplift calculation
section | Viking Enviroclad installation
checkpoint | Ensure substrate is completely free from debris, dust etc
checkpoint | Taken into account ambient temperatures prior to installation beginning
checkpoint | Taken into account incoming weather prior to installation beginning
checkpoint | Adhesive applied as per specification (refer to relevant section in specification)
checkpoint | Membrane layout to the roof has been considered carefully
checkpoint | Membrane has been installed in the correct sequence, starting from the outlets up-to the highest point of the roof/deck or gutter
checkpoint | Correct laps in Enviroclad overlapping edges a minimum of 50mm to provide for a minimum 40mm hot air weld.
checkpoint | Laps are cleaned prior to welding
checkpoint | Membrane has been fully rolled to ensure a consistent bond
checkpoint | Terminations up walls, parapets etc to be completed as detailed or to minimum code requirements
checkpoint | Terminations up walls, parapets etc to be mechanically fastened by flashing, fastening bar, TPO coated steel
checkpoint | Proprietary accessories have been used for all corners and terminations
checkpoint | Proprietary accessories have been used for all penetrations ie Pourable pocket etc
checkpoint | All welds seam probed and any inconsistencies in weld rectified
checkpoint | Cut edges of membrane to be penny welded or lap seam primer installed
section | Flashings
checkpoint | Flashings made in specified material/colour
checkpoint | Flashings installed neatly and fixed sufficiently
checkpoint | Flashings sealed with correct sealant
section | Clean up
checkpoint | All rubbish from all stages removed from site
checkpoint | Roofs cleaned down
checkpoint | Scaffold checked on every level for rubbish
checkpoint | Grounds checked for rubbish (under scaffold etc)
checkpoint | Site Foreman agrees site is clean
checklist | QA - Warm Roof Checklist
section | Substrate
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Perimeter support installed if metal deck substrate
checkpoint | Substrate acceptable (clean, dry and stable)
section | ST400
checkpoint | Falls checked and correct
checkpoint | Purlins and roof structure ready for ST400 and approval given to lay
checkpoint | Fix steel to manufacturers specifications in compliance with NZBC
checkpoint | The metal profile installed upside down and the specified fastenings installed in the trough
checkpoint | Flashings installed on hips and valleys
checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint | The timber height is exact height of the insulation and the outside edge of the timber has a generous radius to ensure maximum bond of the membrane when dressed over it
checkpoint | Outlets framed and plywood routed out
checkpoint | ST400 installed as per spec and complete. Any general observations made
section | Polyiso
checkpoint | All Polyiso sheets butt jointed - np gaps created
checkpoint | Polyiso Sheets glued down with Viking FAST Adhesive (STP900B) using a proprietary dual cartridge caulking gun
checkpoint | STP900B adhesive applied in sweeping ribbons on every steel rib and then left to foam-up over the next few minutes
checkpoint | Polyiso boards laid in a brick-bond pattern.
checkpoint | Butt the polyiso sheets up to the pre-formed timber edging where applicable
checkpoint | Entire roof inspected upon completion to ensure a uniform flat surface
checkpoint | Polyiso installed as per spec and complete. Any general observations made
section | Membrane
checkpoint | Polyiso thoroughly cleaned and checked prior to priming or membrane application
checkpoint | Checked to ensure no dye-batch colour variation
checkpoint | Ensure the specified membrane thickness and colour is used on site
checkpoint | All products installed with a Viking Membrane comply with Viking Specifications e.g. the tested system - Drains and accessories supplied by Viking Roofspec
checkpoint | All welded seams and proprietary items to to be seam probed.
checkpoint | Membrane installed as per spec and complete. Any general observations made
section | Handover
checkpoint | Area 100% completed and waterproof as per specification
signoff | Request Review / Sign Off
checkpoint | Area left clean and tidy
checkpoint | Area complete and ready for FSW inspection
checkpoint | Report sent through to client
checklist | QA - Waterproofing Balconies
checkpoint | Substrate acceptance / Surface prep
checkpoint | Primer
checkpoint | Coat 1 / Vapour Barrier
checkpoint | Prep in between coats
checkpoint | Coat 2
checkpoint | Drying time / DFT / Testing
checkpoint | Any extras - corflutes, drainage cells, etc
checkpoint | Completions and signoff if necessary
checklist | Rooflogic UltraTherm MSR Roofing System
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate acceptable (clean, dry and stable)
section | Surface Preparation
checkpoint | All purlins are in place
checkpoint | Under flashings installed
checkpoint | Sheets in good condition for roof installation
section | RL Base Deck
checkpoint | Installed in accordance with specification
checkpoint | Installed in accordance with project specific and Rooflogic standard details
checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
section | Vapour Control Layer
checkpoint | Vapour Control Layer installed to top face of acoustic board
checkpoint | Correct side laps (80mm) and end laps (100mm)
checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
section | RL Acoustic Board, PIR Board and FRU 36 Underlay
checkpoint | Acoustic Board installed over Vapour Barrier and mechanically attached to the substrate
checkpoint | Correct thickness input
textbox | Thickness (mm)
checkpoint | Any damaged insulation board has been cut out and replaced with new tightly butted piece of acoustic board (minimum 300mm x 300mm piece.)
checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
checkpoint | Install Dristud FRU 36 underlay with 150mm side laps and, if required, 200mm end laps
note | NB. The underlay can be installed in line with the fall of the roof and there is no requirement to install safety netting beneath the underlay or use a self-supporting grade underlay. The underlay is fully supported by the high density rigid insulation layers and will not sag or deflect either during application or over the life of the system.
section | Top Deck
checkpoint | Visually inspect material delivered to site. Confirm all delivered materials correspond with order and specification.
checkpoint | Fix according to specified fixing pattern to achieve required wind uplift resistance
checkpoint | Correct fixings/profiled washer assembly used.
checkpoint | Allowance for thermal expansion when fixing sheets
checkpoint | Sheet set out square
checkpoint | Sheet length as required to achieve specified gutter overhang
checkpoint | Stop-ends and turn-downs to sheets
section | Final Inspection
checkpoint | System installation is complete
checkpoint | Installation of fixings in accordance with specification and appropriate wind zone
checkpoint | All flashing details in accordance with specifications, plans and details with correct type and spacing of fixings and placement of seals and sealants
checkpoint | All construction equipment and materials removed from roof/site
checkpoint | Any damage to top skin or associated flashings rectified by repair or replacement
checkpoint | Debris, sward and other contamination cleared/removed from roof
checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
checklist | Sarnafil - Decks
section | Area Prep
checkpoint | Area clean and accessible (attach photo)
checkpoint | Concrete screeded
checkpoint | Correct Falls
section | Application QA
checkpoint | Sarnabars/ termination bars installed and sealed
checkpoint | all lap welds checked for tightness
checkpoint | Ring clamps on site
checkpoint | Deck protected
section | Handover
checkpoint | Attach general site comments and photos
checkpoint | Work completed as per spec and area left neat and tidy
signoff | Main Contractor Signoff
checklist | Sarnafil - Roofs
section | Area Prep
checkpoint | Area clean and accessible (attach photo)
checkpoint | Plywood substrate completed/ dry
checkpoint | Correct Falls
section | Application QA
checkpoint | Sarnabars/ termination bars installed and sealed
checkpoint | all lap welds checked for tightness
checkpoint | Ring clamps on site
checkpoint | Deck protected
section | Handover
checkpoint | Attach general site comments and photos
checkpoint | Work completed as per spec and area left neat and tidy
signoff | Main Contractor Signoff
checklist | Sealco EcoTUFF - TPO Quality Control V1
section | Substrate
checkpoint | Plywood substrate stagger-bond laid with each sheet offset at least 300mm and edges supported.
checkpoint | Plywood substrate s/s screw fixed to E2/AS1 specification, no loose/drummy sheets or delamination.
checkpoint | Plywood sheets to be tight butted and 3mm gap to all abutments. (No T&G sheet joints)
checkpoint | Substrate clean, dry and free from foreign matter and sharp edges
section | Pre Install
checkpoint | Plywood moisture tested with moisture meter and is below 20%.
checkpoint | Any holes or indentations filled with builders bog and flushed off smooth.
checkpoint | All soft areas in concrete filled and cracks repaired with non-shrink mortar. Any curing compounds removed.
checkpoint | Maximum moisture of relative humidity 75% - verified using an approved method.
checkpoint | All external corners chamfered 5mm radius.
section | Install
checkpoint | EcoTUFF installed to Sealco specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint | All laps minimum 40mm. Lap tested and watertight
checkpoint | Membrane termination completed to Sealco approved detail.
checkpoint | EcoTUFF roof vents installed to specification (min. two vents / roof area, with one every 90m²).
checkpoint | All non-standard details installed as per pre-approved specifications (attached approved drawings).
section | Final Checks
checkpoint | Any mechanical damage to EcoTUFF repaired to Sealco specification.
checkpoint | Overall installation free of wrinkles, creases and splits, with no air or foreign matter entrapped.
checkpoint | Job sheets completed recording area installed, date of installation, membrane batch numbers etc.
checklist | Sealco EcoTuff TPO Plywood
section | Details
checkpoint | CD Structural Grade H3.2 CCA treated Kiln Dried and min. 17mm thick.
checkpoint | Use only square edged construction plywood with all edges fully supported with timber batons
checkpoint | Sheets stagger laid (fully offset brick bond pattern), tight butted, with sanded C-face upwards and face grain at right angles to supports or crossmembers.
checkpoint | Plywood installed with correct falls and no ponding. 3mm clearances from all abutments.
checkpoint | Sheet edges supported, fixed 150mm on edges and 200mm through girth. (T&G plywood not acceptable)
checkpoint | Grade 316 stainless steel counter sunk screw fixing, min. 10-gauge x 50mm or a length 3 times that of the plywood thickness.
checkpoint | 5mm radius to all external corners.
checkpoint | Using a moisture measure ensure moisture content at the time of installation is below 20%.
checkpoint | Substrate is clean, firm and suitable condition for laying.
checklist | Sealco WarmSEAL - Steel
section | Details
checkpoint | Substrate ready and acceptable for me to start work
checkpoint | Ensure steel tray has been fixed to the following specification:
checkpoint | Steel tray is clean and dry with no damage or sharp edges.
checkpoint | Ensure minimum falls are met to comply with E2/AS1 8.5.1 (when using flat polyiso).
checkpoint | Mid span is a min of 3 purlins, end span min of 2 purlins.
checkpoint | Steel tray is fixed in reverse with trough facing upwards (flat at the top).
checkpoint | Fixings are through each rib and at every purlin with 12g C4 galvanised screws.
checkpoint | 150mm maximum overhang of steel ends.
checkpoint | All sides and soffits of steel are structurally supported.
checkpoint | 5mm chamfers to all external timber edges.
checkpoint | Area clean and ready for handover
checklist | Sika Bentonite
section | Details
checkpoint | Gridlines
checkpoint | Area is clean and accessible
checkpoint | Bentonite is placed to correct detail
checkpoint | Check all laps and they are correctly pasted
checkpoint | Check penetrations are to detail
checkpoint | Check laps to DPM are efficient
checkpoint | Area is left clean and tidy
checklist | Sikaflex Joint Sealant Checklist
section | Details
checkpoint | Substrate is clean, dry and ready
tickbox | Photo taken
checkpoint | Apply expansion tape behind installation brackets
tickbox | Photo taken
checkpoint | Apply PEF rod in the vertical joints
checkpoint | Clean and apply SIKAflex sealant to horizontal joints (incl. Primer 3N)
checkpoint | Clean and apply SIKAflex sealant to vertical joints (incl. Primer 3N)
checkpoint | Joint Sealant installed correctly, checked and reviewed as per specification
tickbox | Photo taken
checkpoint | Area left clean and tidy
checklist | Sikalastic 152 perimeter
section | Details
checkpoint | Area clean and accessible (attach photo)
checkpoint | Concrete in acceptable condition, dry and free from dust and other contaminants
checkpoint | Sika Products used last 6 digits of batch number (attach photo)
textbox | 152 required
checkpoint | Attach general site comments and photos
checkpoint | Work completed as per spec and area left neat and tidy
checklist | Sikaroof MTC 22 Liquid Membrane Checklist
section | Details
checkpoint | Substrate Inspected and is clean and ready
checkpoint | Sika Concrete Primer
checkpoint | Body Coat Sikalastic 601 BC
checkpoint | Sika Reemat Reinforcing mat
checkpoint | Sikalastic 621 TC
checkpoint | Detail any penetrations
checklist | Soprema DeboTack Tanking Checklist
section | Details
checkpoint | Block or Insitu wall constructed and allowed to cure sufficiently.—in case of Insitu 28 days minimum is required.
checkpoint | Apply Equus Soprema Duo primer to external walls where Soprastick is to be applied.
checkpoint | Apply Equus Soprema DeboTack 2.5 T/F C175 self-adhesive roll membrane to walls.
checkpoint | Heat weld all sheet joints by gas torch if required and ensure all are well sealed. Including end joints. Ensure a minimum of 100mm overlap at all connections.
checkpoint | Apply bandages at floor wall joint as detailed with Equus Soprema Debovix
checkpoint | Inspection of all areas before protection board installation.
checkpoint | Install Equus Danodren H15 Plus against Equus Soprema DeboTack. Do not use mechanical fixings.
checkpoint | Final Inspection required prior to back filling.
checklist | test Results
checkpoint | Test results @14:00:00
checkpoint | Test results @15:00:00
checklist | Variation Details -
section | Details
checkpoint | Variation Details Approved
textbox | Reference/Drawing/Instruction Number
textbox | Variation Area
textbox | Materials & labour breakdown
signoff | Request Variation Acknowledgement
checkpoint | Variation Completed
signoff | Request Variation Signoff
checklist | Viking Enviroclad Checklist
section | Details
checkpoint | Substrate acceptable and ready for work to begin
checkpoint | Adhesive applied as per specification (refer to relevant section in specification)
checkpoint | Membrane has been installed in the correct sequence, starting from the outlets up-to the highest point of the roof/deck or gutter
checkpoint | Correct laps in Enviroclad overlapping edges a minimum of 50mm to provide for a minimum 40mm hot air weld.
checkpoint | Laps are cleaned prior to welding
checkpoint | Membrane has been fully rolled to ensure a consistent bond
checkpoint | Terminations to be completed as detailed and mechanically fastened by flashing, fastening bar, TPO coated steel
checkpoint | Proprietary accessories have been used for all corners, terminations and penetrations
checkpoint | All welds seam probed and any inconsistencies in weld rectified
checkpoint | Cut edges of membrane to be penny welded or lap seam primer installed
checklist | Viking Enviroclad Checklist (sectioned)
section | Substrate
checkpoint | Kingspan roof liner
checkpoint | Polyiso substrate stagger-bond laid with each sheet offset at least 300mm and tight butted.
checkpoint | Correct amount of FAST insulation adhesive used (8-10sqm per can). Minimum of 4 runs per sheet and ends adhered.
checkpoint | Substrate clean, dry, and free from foreign matter and sharp edges.
section | Pre Install
checkpoint | No damage evident to the polyiso insulation. No soft or loose areas of polyiso and no dents or hollows in the top surface.
checkpoint | Pipe penetrations and rainwater outlets detailed as per Viking specification. Use only Enviroclad accessories.
section | Install
checkpoint | Roof drains installed to Viking specification.
checkpoint | Overflows installed to Viking specification.
checkpoint | Enviroclad adhesive within shelf life and correctly mixed.
checkpoint | Enviroclad installed to Viking specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint | All laps minimum 40mm. Lap tested and watertight.
checkpoint | No air entrapment or foreign matter contamination under the Enviroclad membrane.
checkpoint | Enviroclad sheets laid across the roof slope, with vertical lap edges fully welded and sealed with cut
checklist | Viking Enviroclad Checklist Sectioned
section | Substrate
checkpoint | Kingspan roof liner
checkpoint | Polyiso substrate stagger-bond laid with each sheet offset at least 300mm and tight butted.
checkpoint | Correct amount of FAST insulation adhesive used (8-10sqm per can). Minimum of 4 runs per sheet and ends adhered.
checkpoint | Substrate clean, dry, and free from foreign matter and sharp edges.
section | Pre Install
checkpoint | No damage evident to the polyiso insulation. No soft or loose areas of polyiso and no dents or hollows in the top surface.
checkpoint | Pipe penetrations and rainwater outlets detailed as per Viking specification. Use only Enviroclad accessories.
section | Install
checkpoint | Roof drains installed to Viking specification.
checkpoint | Overflows installed to Viking specification.
checkpoint | Enviroclad adhesive within shelf life and correctly mixed.
checkpoint | Enviroclad installed to Viking specification, ensuring adhesive applied to substrate and membrane at correct rate.
checkpoint | All laps minimum 40mm. Lap tested and watertight.
checkpoint | No air entrapment or foreign matter contamination under the Enviroclad membrane.
checkpoint | Enviroclad sheets laid across the roof slope, with vertical lap edges fully welded and sealed with cut
checklist | Water Test QA Inspection
section | Area Description
checkpoint | Area Description:
textbox
section | Installation Information
checkpoint | Installation Information:
textbox | Dates:
textbox | Material:
textbox | Batch No:
section | Water Test Preparation
checkpoint | The drainage outlets should have temporarily blocked
checkpoint | Roof/Deck or Tanking to be flooded to check the integrity of the torch-on
checkpoint | On large roofs, sand bagging may be required to prevent the spread of water
checkpoint | Allow 50mm depth to be achieved across the area being tested
checkpoint | Flood test for a duration of not less than 24 hours
section | Final Sign Off
checkpoint | Final Sign Off:
textbox | Inspected By:
textbox | Date:
checklist | Waterproofing - Sika Blackseal Elastic
section | Details
checkpoint | Area clean and accessible (attach photo)
checkpoint | Control joints installed, backing rod with Blackseal-1
checkpoint | Footing / wall junction fillet applied
checkpoint | Sharp external corners rounded off
checkpoint | Sika MonoTop Fairing coat applied, if necessary
checkpoint | Penetrations through wall sealed with Blackseal-1
checkpoint | Walls & footings primed with 50/50 mix of Blackseal & water
checkpoint | Apply minimum 2 coats per manufacturers instructions
checkpoint | Penetrations - Apply membrane per manufacturers instuctions
checkpoint | Floor/wall Junction - Apply membrane per manufacturers instuctions
checkpoint | Allowed to cure 48 hours before fixing protection sheet
checkpoint | Ensure protection sheets fixed with dimpled side to waterproofing membrane