## Project Structure
Folder Structure | [7 empty] | Checklists
30577
ESR - Frank Street
ITP Setout
Site QA
| Main Heading Name | Sub Heading Name | Section | Main Equipment Name | Equipment Name | Drawing Number | ITP Name
Offices
Warehouse 1A
Rough-In
Fan Coil Units
[5 empty] | ACU-1A.1 Office 1A Centre |  | Ducted Unit ITP RI
[5 empty] | ACU-1A.2 Office 1A East |  | Ducted Unit ITP RI
[5 empty] | ACU-1A.3 Office 1A Boardroom |  | Ducted Unit ITP RI
[5 empty] | ACU-1A.4 Office 1A Office |  | Ducted Unit ITP RI
[5 empty] | ACU-1A.5 Office 1A GF Store |  | Ducted Unit ITP RI
Condenser Units
[5 empty] | CU-1A.1 |  | Condenser ITP RI
[5 empty] | CU-1A.2 |  | Condenser ITP RI
[5 empty] | CU-1A.3 |  | Condenser ITP RI
[5 empty] | CU-1A.4 |  | Condenser ITP RI
[5 empty] | CU-1A.5 |  | Condenser ITP RI
Toilet Exhaust Fans
[5 empty] | TEF-1A WHSE 1A Roof |  | Vent Fan ITP RI
Outside Air Fans
[5 empty] | OAF-1A WHSE 1A GF Store |  | Vent Fan ITP RI
Roof Cowls
[5 empty] | RC-1A.1 WHSE 1A Office Roof |  | Roof Cowl ITP RI
[5 empty] | RC-1A.2 WHSE1A Office Roof |  | Roof Cowl ITP RI
[5 empty] | RC-1A.3 WHSE 1A Office Roof |  | Roof Cowl ITP RI
Fitoff
Fan Coil Units
[5 empty] | ACU-1A.1 Office 1A Centre |  | Ducted Unit ITP FO
[5 empty] | ACU-1A.2 Office 1A East |  | Ducted Unit ITP FO
[5 empty] | ACU-1A.3 Office 1A Boardroom |  | Ducted Unit ITP FO
[5 empty] | ACU-1A.4 Office 1A Office |  | Ducted Unit ITP FO
[5 empty] | ACU-1A.5 Office 1A GF Store |  | Ducted Unit ITP FO
Condenser Units
[5 empty] | CU-1A.1 |  | Condenser ITP FO
[5 empty] | CU-1A.2 |  | Condenser ITP FO
[5 empty] | CU-1A.3 |  | Condenser ITP FO
[5 empty] | CU-1A.4 |  | Condenser ITP FO
[5 empty] | CU-1A.5 |  | Condenser ITP FO
Toilet Exhaust Fans
[5 empty] | TEF-1A WHSE 1A Roof |  | Vent Fan ITP FO
Outside Air Fans
[5 empty] | OAF-1A WHSE 1A GF Store |  | Vent Fan ITP FO
Roof Cowls
[5 empty] | RC-1A.1 WHSE 1A Office Roof |  | Roof Cowl ITP FO
[5 empty] | RC-1A.2 WHSE1A Office Roof |  | Roof Cowl ITP FO
[5 empty] | RC-1A.3 WHSE 1A Office Roof |  | Roof Cowl ITP FO
Commissioning
Fan Coil Units
[5 empty] | ACU-1A.1 Office 1A Centre |  | Ducted Unit ITP Comm
[5 empty] | ACU-1A.2 Office 1A East |  | Ducted Unit ITP Comm
[5 empty] | ACU-1A.3 Office 1A Boardroom |  | Ducted Unit ITP Comm
[5 empty] | ACU-1A.4 Office 1A Office |  | Ducted Unit ITP Comm
[5 empty] | ACU-1A.5 Office 1A GF Store |  | Ducted Unit ITP Comm
Condenser Units
[5 empty] | CU-1A.1 |  | Condenser ITP Comm
[5 empty] | CU-1A.2 |  | Condenser ITP Comm
[5 empty] | CU-1A.3 |  | Condenser ITP Comm
[5 empty] | CU-1A.4 |  | Condenser ITP Comm
[5 empty] | CU-1A.5 |  | Condenser ITP Comm
Toilet Exhaust Fans
[5 empty] | TEF-1A WHSE 1A Roof |  | Vent Fan ITP Comm
Outside Air Fans
[5 empty] | OAF-1A WHSE 1A GF Store |  | Vent Fan ITP Comm
Roof Cowls
[5 empty] | RC-1A.1 WHSE 1A Office Roof |  | Roof Cowl ITP COMM
[5 empty] | RC-1A.2 WHSE1A Office Roof |  | Roof Cowl ITP COMM
[5 empty] | RC-1A.3 WHSE 1A Office Roof |  | Roof Cowl ITP COMM
Warehouse 1B
Rough-In
Fan Coil Units
[5 empty] | ACU-1B.1 Office 1B South |  | Ducted Unit ITP RI
[5 empty] | ACU-1B.2 Office 1B West |  | Ducted Unit ITP RI
[5 empty] | ACU-1B.3 Office 1B Centre |  | Ducted Unit ITP RI
Condenser Units
[5 empty] | CU-1B.1 |  | Condenser ITP RI
[5 empty] | CU-1B.2 |  | Condenser ITP RI
[5 empty] | CU-1B.3 |  | Condenser ITP RI
Toilet Exhaust Fan
[5 empty] | TEF-1B WHSE 1B Roof |  | Vent Fan ITP RI
Roof Cowls
[5 empty] | RC-1B WHSE 1B Office Roof |  | Roof Cowl ITP RI
Fitoff
Fan Coil Units
[5 empty] | ACU-1B.1 Office 1B South |  | Ducted Unit ITP FO
[5 empty] | ACU-1B.2 Office 1B West |  | Ducted Unit ITP FO
[5 empty] | ACU-1B.3 Office 1B Centre |  | Ducted Unit ITP FO
[5 empty] | TEF-1B WHSE 1B Roof |  | Vent Fan ITP RI
Condenser
[5 empty] | CU-1B.1 |  | Condenser ITP FO
[5 empty] | CU-1B.2 |  | Condenser ITP FO
[5 empty] | CU-1B.3 |  | Condenser ITP FO
Toilet Exhaust Fan
[5 empty] | TEF-1B WHSE 1B Roof |  | Vent Fan ITP FO
Roof Cowl
[5 empty] | RC-1B WHSE 1B Office Roof |  | Roof Cowl ITP FO
Commissioning
Fan Coil Units
[5 empty] | ACU-1B.1 Office 1B South |  | Ducted Unit ITP Comm
[5 empty] | ACU-1B.2 Office 1B West |  | Ducted Unit ITP Comm
[5 empty] | ACU-1B.3 Office 1B Centre |  | Ducted Unit ITP Comm
Condenser Units
[5 empty] | CU-1B.1 |  | Condenser ITP Comm
[5 empty] | CU-1B.2 |  | Condenser ITP Comm
[5 empty] | CU-1B.3 |  | Condenser ITP Comm
Toilet Exhaust Fan
[5 empty] | TEF-1B WHSE 1B Roof |  | Vent Fan ITP Comm
Roof Cowl
[5 empty] | RC-1B WHSE 1B Office Roof |  | Roof Cowl ITP COMM
Warehouse 2A
Rough-In
Fan Coil Units
[5 empty] | ACU-2A.1 Office 2A South |  | Ducted Unit ITP RI
[5 empty] | ACU-2A.2 Office 2A Centre-1 |  | Ducted Unit ITP RI
[5 empty] | ACU-2A.3 Office 2A Centre-2 |  | Ducted Unit ITP RI
Condenser Units
[5 empty] | CU-2A.1 |  | Condenser ITP RI
[5 empty] | CU-2A.2 |  | Condenser ITP RI
[5 empty] | CU-2A.3 |  | Condenser ITP RI
Toilet Exhaust Fan
[5 empty] | TEF-2A WHSE 2A Roof |  | Vent Fan ITP RI
Outside Air Fan
[5 empty] | OAF-2 WHSE 2 Shared Lobby |  | Vent Fan ITP RI
Fitoff
Fan Coil Units
[5 empty] | ACU-2A.1 Office 2A South |  | Ducted Unit ITP FO
[5 empty] | ACU-2A.2 Office 2A Centre-1 |  | Ducted Unit ITP FO
[5 empty] | ACU-2A.3 Office 2A Centre-2 |  | Ducted Unit ITP FO
Condenser Units
[5 empty] | CU-2A.1 |  | Condenser ITP FO
[5 empty] | CU-2A.2 |  | Condenser ITP FO
[5 empty] | CU-2A.3 |  | Condenser ITP FO
Toilet Exhaust Fan
[5 empty] | TEF-2A WHSE 2A Roof |  | Vent Fan ITP FO
|  |  |  | Outside Air Fan | OAF-2 WHSE 2 Shared Lobby |  | Vent Fan ITP FO
Commissioning
Fan Coil Units
[5 empty] | ACU-2A.1 Office 2A South |  | Ducted Unit ITP Comm
[5 empty] | ACU-2A.2 Office 2A Centre-1 |  | Ducted Unit ITP Comm
[5 empty] | ACU-2A.3 Office 2A Centre-2 |  | Ducted Unit ITP Comm
Condenser Units
[5 empty] | CU-2A.1 |  | Condenser ITP Comm
[5 empty] | CU-2A.2 |  | Condenser ITP Comm
[5 empty] | CU-2A.3 |  | Condenser ITP Comm
Toilet Exhaust Fan
[5 empty] | TEF-2A WHSE 2A Roof |  | Vent Fan ITP Comm
Outside Air Fan
[5 empty] | OAF-2 WHSE 2 Shared Lobby |  | Vent Fan ITP Comm
Warehouse 2B
Rough-In
Fan Coil Units
[5 empty] | ACU-2B.1 Office 2B South |  | Ducted Unit ITP RI
[5 empty] | ACU-2B.2 Office 2B Centre-1 |  | Ducted Unit ITP RI
[5 empty] | ACU-2B.3 Office 2B Centre-2 |  | Ducted Unit ITP RI
Condenser Units
[5 empty] | CU-2B.1 |  | Condenser ITP RI
[5 empty] | CU-2B.2 |  | Condenser ITP RI
[5 empty] | CU-2B.3 |  | Condenser ITP RI
Toilet Exhaust Fan
[5 empty] | TEF-2B WHSE 2B Roof |  | Vent Fan ITP RI
Fitoff
Fan Coil Units
[5 empty] | ACU-2B.1 Office 2B South |  | Ducted Unit ITP FO
[5 empty] | ACU-2B.2 Office 2B Centre-1 |  | Ducted Unit ITP FO
[5 empty] | ACU-2B.3 Office 2B Centre-2 |  | Ducted Unit ITP FO
Condenser Units
[5 empty] | CU-2B.1 |  | Condenser ITP FO
[5 empty] | CU-2B.2 |  | Condenser ITP FO
[5 empty] | CU-2B.3 |  | Condenser ITP FO
Toilet Exhaust Fan
[5 empty] | TEF-2B WHSE 2B Roof |  | Vent Fan ITP FO
Commissioning
Fan Coil Units
[5 empty] | ACU-2B.1 Office 2B South |  | Ducted Unit ITP Comm
[5 empty] | ACU-2B.2 Office 2B Centre-1 |  | Ducted Unit ITP Comm
[5 empty] | ACU-2B.3 Office 2B Centre-2 |  | Ducted Unit ITP Comm
Condenser Units
[5 empty] | CU-2B.1 |  | Condenser ITP Comm
[5 empty] | CU-2B.2 |  | Condenser ITP Comm
[5 empty] | CU-2B.3 |  | Condenser ITP Comm
Toilet Exhaust Fan
[5 empty] | TEF-2B WHSE 2B Roof |  | Vent Fan ITP Comm
Warehouse 3A
Rough-In
Fan Coil Units
[5 empty] | ACU-3A.1 Office 3A North |  | Ducted Unit ITP RI
[5 empty] | ACU-3A.2 Office 3A Centre-1 |  | Ducted Unit ITP RI
[5 empty] | ACU-3A.3 Office 3A Centre-2 |  | Ducted Unit ITP RI
Condenser Units
[5 empty] | CU-3A.1 |  | Condenser ITP RI
[5 empty] | CU-3A.2 |  | Condenser ITP RI
[5 empty] | CU-3A.3 |  | Condenser ITP RI
Toilet Exhaust Fan
[5 empty] | TEF-3A WHSE 3A Office Roof |  | Vent Fan ITP RI
Outside Air Fan
[5 empty] | OAF-3 WHSE 3 Shared Lobby |  | Vent Fan ITP RI
Fitoff
Fan Coil Units
[5 empty] | ACU-3A.1 Office 3A North |  | Ducted Unit ITP FO
[5 empty] | ACU-3A.2 Office 3A Centre-1 |  | Ducted Unit ITP FO
[5 empty] | ACU-3A.3 Office 3A Centre-2 |  | Ducted Unit ITP FO
Condenser Units
[5 empty] | CU-3A.1 |  | Condenser ITP FO
[5 empty] | CU-3A.2 |  | Condenser ITP FO
[5 empty] | CU-3A.3 |  | Condenser ITP FO
Toilet Exhaust Fan
[5 empty] | TEF-3A WHSE 3A Office Roof |  | Vent Fan ITP FO
Outside Aire Fan
[5 empty] | OAF-3 WHSE 3 Shared Lobby |  | Vent Fan ITP FO
Commissioning
Fan Coil Units
[5 empty] | ACU-3A.1 Office 3A North |  | Ducted Unit ITP Comm
[5 empty] | ACU-3A.2 Office 3A Centre-1 |  | Ducted Unit ITP Comm
[5 empty] | ACU-3A.3 Office 3A Centre-2 |  | Ducted Unit ITP Comm
Condenser Units
[5 empty] | CU-3A.1 |  | Condenser ITP Comm
[5 empty] | CU-3A.2 |  | Condenser ITP Comm
[5 empty] | CU-3A.3 |  | Condenser ITP Comm
Toilet Exhaust Fan
[5 empty] | TEF-3A WHSE 3A Office Roof |  | Vent Fan ITP Comm
Outside Air Fan
[5 empty] | OAF-3 WHSE 3 Shared Lobby |  | Vent Fan ITP Comm
Warehouse 3B
Rough-In
Fan Coil Units
[5 empty] | ACU-3B.1 Office 3B North |  | Ducted Unit ITP RI
[5 empty] | ACU-3B.2 Office 3B Centre-1 |  | Ducted Unit ITP RI
[5 empty] | ACU-3B.3 Office 3B Centre-2 |  | Ducted Unit ITP RI
Condenser Units
[5 empty] | CU-3B.1 |  | Condenser ITP RI
[5 empty] | CU-3B.2 |  | Condenser ITP RI
[5 empty] | CU-3B.3 |  | Condenser ITP RI
Toilet Exhaust Fan
[5 empty] | TEF-3B WHSE 3B Office Roof |  | Vent Fan ITP RI
Fitoff
Fan Coil Units
[5 empty] | ACU-3B.1 Office 3B North |  | Ducted Unit ITP FO
[5 empty] | ACU-3B.2 Office 3B Centre-1 |  | Ducted Unit ITP FO
[5 empty] | ACU-3B.3 Office 3B Centre-2 |  | Ducted Unit ITP FO
Condenser Units
[5 empty] | CU-3B.1 |  | Condenser ITP FO
[5 empty] | CU-3B.2 |  | Condenser ITP FO
[5 empty] | CU-3B.3 |  | Condenser ITP FO
Toilet Exhaust Fan
[5 empty] | TEF-3B WHSE 3B Office Roof |  | Vent Fan ITP FO
Commissioning
Fan Coil Units
[5 empty] | ACU-3B.1 Office 3B North |  | Ducted Unit ITP Comm
[5 empty] | ACU-3B.2 Office 3B Centre-1 |  | Ducted Unit ITP Comm
[5 empty] | ACU-3B.3 Office 3B Centre-2 |  | Ducted Unit ITP Comm
Condenser Units
[5 empty] | CU-3B.1 |  | Condenser ITP Comm
[5 empty] | CU-3B.2 |  | Condenser ITP Comm
[5 empty] | CU-3B.3 |  | Condenser ITP Comm
Toilet Exhaust Fan
[5 empty] | TEF-3B WHSE 3B Office Roof |  | Vent Fan ITP Comm
Warehouse Fans
Rough-In
Smoke Exhaust Fans
[5 empty] | SEF-2A.1 WHSE 2A Roof |  | Vent Fan ITP RI
[5 empty] | SEF-2A.2 WHSE 2A Roof |  | Vent Fan ITP RI
[5 empty] | SEF-2B.1 WHSE 2B Roof |  | Vent Fan ITP RI
[5 empty] | SEF-2B.2 WHSE 2B Roof |  | Vent Fan ITP RI
[5 empty] | SEF-3A.1 WHSE 3A Roof |  | Vent Fan ITP RI
[5 empty] | SEF-3A.2 WHSE 3A Roof |  | Vent Fan ITP RI
[5 empty] | SEF-3B.1 WHSE 3B Roof |  | Vent Fan ITP RI
[5 empty] | SEF-3B.2 WHSE 3B Roof |  | Vent Fan ITP RI
Fitoff
Smoke Exhaust Fans
[5 empty] | SEF-2A.1 WHSE 2A Roof |  | Vent Fan ITP FO
[5 empty] | SEF-2A.2 WHSE 2A Roof |  | Vent Fan ITP FO
[5 empty] | SEF-2B.1 WHSE 2B Roof |  | Vent Fan ITP FO
[5 empty] | SEF-2B.2 WHSE 2B Roof |  | Vent Fan ITP FO
[5 empty] | SEF-3A.1 WHSE 3A Roof |  | Vent Fan ITP FO
[5 empty] | SEF-3A.2 WHSE 3A Roof |  | Vent Fan ITP FO
[5 empty] | SEF-3B.1 WHSE 3B Roof |  | Vent Fan ITP FO
[5 empty] | SEF-3B.2 WHSE 3B Roof |  | Vent Fan ITP FO
Commissioning
Smoke Exhaust Fans
[5 empty] | SEF-2A.1 WHSE 2A Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-2A.2 WHSE 2A Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-2B.1 WHSE 2B Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-2B.2 WHSE 2B Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-3A.1 WHSE 3A Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-3A.2 WHSE 3A Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-3B.1 WHSE 3B Roof |  | Vent Fan ITP Comm
[5 empty] | SEF-3B.2 WHSE 3B Roof |  | Vent Fan ITP Comm
Electrical Boards
Rough-In
[5 empty] | MSSB-1A.1 Office 1A |  | Electrical Board ITP RI
[5 empty] | MSSB-1B.1 Office 1B |  | Electrical Board ITP RI
[5 empty] | MSSB-2A.1 Office 2A |  | Electrical Board ITP RI
[5 empty] | MSSB-2A.2 Office 2A |  | Electrical Board ITP RI
[5 empty] | MSSB-2B.1 Office 2B |  | Electrical Board ITP RI
[5 empty] | MSSB-2B.2 Office 2B |  | Electrical Board ITP RI
[5 empty] | MSSB-3A.1 Office 3A |  | Electrical Board ITP RI
[5 empty] | MSSB-3A.2 Office 3A |  | Electrical Board ITP RI
[5 empty] | MSSB-3B.1 Office 3B |  | Electrical Board ITP RI
[5 empty] | MSSB-3B.2 Office 3B |  | Electrical Board ITP RI
Fitoff
[5 empty] | MSSB-1A.1 Office 1A |  | Electrical Board ITP FO
[5 empty] | MSSB-1B.1 Office 1B |  | Electrical Board ITP FO
[5 empty] | MSSB-2A.1 Office 2A |  | Electrical Board ITP FO
[5 empty] | MSSB-2A.2 Office 2A |  | Electrical Board ITP FO
[5 empty] | MSSB-2B.1 Office 2B |  | Electrical Board ITP FO
[5 empty] | MSSB-2B.2 Office 2B |  | Electrical Board ITP FO
[5 empty] | MSSB-3A.1 Office 3A |  | Electrical Board ITP FO
[5 empty] | MSSB-3A.2 Office 3A |  | Electrical Board ITP FO
[5 empty] | MSSB-3B.1 Office 3B |  | Electrical Board ITP FO
[5 empty] | MSSB-3B.2 Office 3B |  | Electrical Board ITP FO
Commissioning
[5 empty] | MSSB-1A.1 Office 1A |  | Electrical Board ITP Comm
[5 empty] | MSSB-1B.1 Office 1B |  | Electrical Board ITP Comm
[5 empty] | MSSB-2A.1 Office 2A |  | Electrical Board ITP Comm
[5 empty] | MSSB-2A.2 Office 2A |  | Electrical Board ITP Comm
[5 empty] | MSSB-2B.1 Office 2B |  | Electrical Board ITP Comm
[5 empty] | MSSB-2B.2 Office 2B |  | Electrical Board ITP Comm
[5 empty] | MSSB-3A.1 Office 3A |  | Electrical Board ITP Comm
[5 empty] | MSSB-3A.2 Office 3A |  | Electrical Board ITP Comm
[5 empty] | MSSB-3B.1 Office 3B |  | Electrical Board ITP Comm
[5 empty] | MSSB-3B.2 Office 3B |  | Electrical Board ITP Comm
Fire Dampers
Rough-In
Fire Damper ITP RI
Fire Damper ITP RI
Fitoff
Fire Damper ITP FO
Fire Damper ITP FO
Commissioning
Fire Damper ITP Comm
Fire Damper ITP Comm
Fire Stopping | Ability to Add |  |  |  |  | Ability to Add
Site Diary | Ability to Add |  |  |  |  | Ability to Add

## Checklists
Rough-In ITPs
type | name | values
checklist | Ducted Unit ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Greenstar Duct
checkpoint | Location Correct As per Plan/Drawing
section | Rough-in
checkpoint | Unit has clearance from other services
checkpoint | Correct Fan Coil Installed - take photo of data plate
checkpoint | FCU installed with anti vibration mounts
checkpoint | SA and RA Boxes fitted with anti vibration mounts
checkpoint | RA Box has filters
checkpoint | FCU Installed in accordance with Seismic Design Drawing
checkpoint | Refrigeration Pipe work installed securely with insulation
checkpoint | Tundish Available
checkpoint | Drain Pipe work installed and insulated to tundish
checkpoint | Electrical supply cabling installed with isolation point
checkpoint | Interconnect and Control Cabling installed and secured
checkpoint | Check Access to Filters and Electrical Box
checkpoint | Ductwork installed with clearance from other services
checkpoint | Ductwork Joints Sealed
checkpoint | Ductwork adequately supported
checkpoint | All spigots protected from dust ingress
checkpoint | Flex Installed and Supported with Gutter Guard or equivalent
checkpoint | Provisions for future access are adequate
checkpoint | Ready for Ceiling and Wall Sheeting
checklist | Condenser ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Unit has clearance from other services
checkpoint | Correct Condenser Installed - take photo of data plate
checkpoint | Condenser Feet installed with anti vibration mounts
checkpoint | Condenser Installed in accordance with Seismic Design Drawing
checkpoint | Tundish Available
checkpoint | Electrical supply cabling installed with isolation point
checkpoint | Interconnect and Control Cabling installed and secured
checklist | Roof Cowl ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Penetration has been marked for Roofing Contractor to Cut
checkpoint | Take photo of mark out for penetration
checkpoint | Soaker Sheet provided by Roofer
checkpoint | Upstand is correct size
checkpoint | Ready for Fitoff
checklist | Vent Fan ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
checkpoint | GreenStar - Duct Delivery
section | Roughin
checkpoint | Unit has clearance from other services
checkpoint | Correct Fan Installed - take photo of data plate
checkpoint | Fan installed with anti vibration mounts
checkpoint | Fan and Duct Installed in accordance with Seismic Design Drawing
checkpoint | Electrical supply cabling installed with isolation point
checkpoint | Control Cabling installed and secured
checkpoint | Check Access to Fan - Mark Access Panel if required
checkpoint | Ductwork installed with clearance from other services
checkpoint | Ductwork Joints Sealed
checkpoint | Ductwork adequately supported
checkpoint | All spigots open 100% and protected from dust ingress
checkpoint | Flex Installed and Supported with Gutter Guard or equivalent
checkpoint | Provisions for future access are adequate
checkpoint | Ready for Ceiling and Wall Sheeting
checklist | Fire Damper ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Penetration is correct size
checkpoint | Penetration is correct substrate
checkpoint | Core is filled to correct depth if required
checklist | Electrical Board ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Electrical Board has the correct Clearance from other Services
checkpoint | Electrical Board Installed in accordance with Seismic Design Drawing
checkpoint | Cable Tray Installed where Required
checkpoint | Provisions for future access are adequate
checkpoint | Ready for Ceiling and Wall Sheeting
Fitoff ITPs
type | name | values
checklist | Ducted Unit ITP FO
section | Fit off
checkpoint | Grilles and Cushion Boxes Installed
checkpoint | Adequate Access Achieved
checkpoint | Condensate drains from drain tray
checkpoint | Drain Terminated to Tundish
checkpoint | Wall Controller Installed and labelled
checklist | Condenser ITP FO
section | Fit off
checkpoint | Electrical and Control Terminations Complete
checkpoint | Refrigeration Pipe work installed securely with insulation
checkpoint | Correct Master Unit Installed - Data Plate photo
checkpoint | Drain Terminated to Tundish
checklist | Roof Cowl ITP FO
section | Fit off
checkpoint | Dropper installed and Sealed
checkpoint | Roof Cowl installed with a minimum of 4 screws
checkpoint | Cowl sealed against water ingress
checklist | Vent Fan ITP FO
section | Fit off
checkpoint | Grilles and Cushion Boxes Installed
checkpoint | Adequate Access Achieved
checkpoint | Wall Controller Switch is Installed if Required
checklist | Fire Damper ITP FO
section | Roughin
checkpoint | Take photo of Smoke/Seal product to be applied
checkpoint | Take photo with fixing angles off - pre application
checkpoint | Take photo with fixing angles off - post application
checkpoint | Take photo with fixing angles on
checklist | Electrical Board ITP FO
section | Fit off
checkpoint | Cable Containment has been completed
checkpoint | Mains Supply provided by House Electrical Contractor
checkpoint | All Terminations Complete
Commissioning ITPs
type | name | values
checklist | Ducted Unit ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete
checkpoint | Refrigeration Commissioning Complete
checkpoint | Clear Access is Achieved
checkpoint | Electrical Isolation Point labelled
checkpoint | Air Off Coil Heating
checkpoint | Air Off Coil Cooling
checkpoint | Air Balance Complete
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Condenser ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete
checkpoint | 24 Hour Pressure Test - Before
checkpoint | 24 Hour Pressure Test - After
checkpoint | Electrical Isolation Point Labelled
checkpoint | Evacuate System - Microns
checkpoint | Gas Charge
checkpoint | Units Test Run on Heating and Cooling - Air Off Temps
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Roof Cowl ITP Comm
section | Commissioning
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Vent Fan ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete
checkpoint | Unit Test Run - Works as Designed
checkpoint | Clear Access is Achieved
checkpoint | Electrical Isolation Labelled
checkpoint | Air Balance Complete
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Fire Damper ITP Comm
section | Roughin
checkpoint | Fire Damper Label is fixed and clearly visible
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Electrical Board ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete by Licensed Electrical Contractor
checkpoint | All systems tested and working as designed
checkpoint | Handover - Work completed as per specification, checked and accepted
values
checklist | Site Diary
section | General
checkpoint | Areas of work accessible for the day | Text
checkpoint | Number of workers on site | Number
checkpoint | HSR on site today - enter name | Text
checkpoint | First Aider on site today - enter name | Text
checkpoint | Injury on site today - enter name | Text
checkpoint | Work Areas - Take a photo and add comments | Text