## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Rough-In
| Scope |  |  | Rough-In
Rows
|  | Offices - Warehouse 1A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 1A | Rough-In | Fan Coil Units
|  | Offices - Warehouse 1A - Condenser Units | dynamic | Site QA | Offices | Warehouse 1A | Rough-In | Condenser Units
|  | Offices - Warehouse 1A - Toilet Exhaust Fans | dynamic | Site QA | Offices | Warehouse 1A | Rough-In | Toilet Exhaust Fans
|  | Offices - Warehouse 1A - Outside Air Fans | dynamic | Site QA | Offices | Warehouse 1A | Rough-In | Outside Air Fans
|  | Offices - Warehouse 1A - Roof Cowls | dynamic | Site QA | Offices | Warehouse 1A | Rough-In | Roof Cowls
|  | Offices - Warehouse 1B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 1B | Rough-In | Fan Coil Units
|  | Offices - Warehouse 1B - Condenser Units | dynamic | Site QA | Offices | Warehouse 1B | Rough-In | Condenser Units
|  | Offices - Warehouse 1B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 1B | Rough-In | Toilet Exhaust Fan
|  | Offices - Warehouse 1B - Roof Cowls | dynamic | Site QA | Offices | Warehouse 1B | Rough-In | Roof Cowls
|  | Offices - Warehouse 2A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 2A | Rough-In | Fan Coil Units
|  | Offices - Warehouse 2A - Condenser Units | dynamic | Site QA | Offices | Warehouse 2A | Rough-In | Condenser Units
|  | Offices - Warehouse 2A - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 2A | Rough-In | Toilet Exhaust Fan
|  | Offices - Warehouse 2A - Outside Air Fan | dynamic | Site QA | Offices | Warehouse 2A | Rough-In | Outside Air Fan
|  | Offices - Warehouse 2B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 2B | Rough-In | Fan Coil Units
|  | Offices - Warehouse 2B - Condenser Units | dynamic | Site QA | Offices | Warehouse 2B | Rough-In | Condenser Units
|  | Offices - Warehouse 2B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 2B | Rough-In | Toilet Exhaust Fan
|  | Offices - Warehouse 3A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 3A | Rough-In | Fan Coil Units
|  | Offices - Warehouse 3A - Condenser Units | dynamic | Site QA | Offices | Warehouse 3A | Rough-In | Condenser Units
|  | Offices - Warehouse 3A - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 3A | Rough-In | Toilet Exhaust Fan
|  | Offices - Warehouse 3A - Outside Air Fan | dynamic | Site QA | Offices | Warehouse 3A | Rough-In | Outside Air Fan
|  | Offices - Warehouse 3B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 3B | Rough-In | Fan Coil Units
|  | Offices - Warehouse 3B - Condenser Units | dynamic | Site QA | Offices | Warehouse 3B | Rough-In | Condenser Units
|  | Offices - Warehouse 3B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 3B | Rough-In | Toilet Exhaust Fan
|  | Warehouse Fans - Rough-In - Smoke Exhaust Fans | dynamic | Site QA | Warehouse Fans | Rough-In | Smoke Exhaust Fans
|  | Electrical Boards | dynamic | Site QA | Electrical Boards | Rough-In
|  | Fire Dampers | grouping | Fire Dampers
|  | Fire Dampers |  | Site QA | Fire Dampers | Rough-In
Columns
|  | All spigots open 100% & protected from dust ingress |  | All spigots open 100% and protected from dust ingress
|  | All spigots protected from dust ingress |  | All spigots protected from dust ingress
|  | Area ready & accessible for work |  | Area ready and accessible for work - take picture if required
|  | Cable Tray Installed where Required |  | Cable Tray Installed where Required
|  | Check Access to Fan - Mark Access Panel |  | Check Access to Fan - Mark Access Panel if required
|  | Check Access to Filters & Electrical Box |  | Check Access to Filters and Electrical Box
|  | Condenser Feet installed with anti vibration mounts |  | Condenser Feet installed with anti vibration mounts
|  | Condenser Installed in accordance with Seismic Design Drawing |  | Condenser Installed in accordance with Seismic Design Drawing
|  | Control Cabling installed & secured |  | Control Cabling installed and secured
|  | Core is filled to correct depth |  | Core is filled to correct depth if required
|  | Correct Condenser Installed |  | Correct Condenser Installed - take photo of data plate
|  | Correct Fan Coil Installed |  | Correct Fan Coil Installed - take photo of data plate
|  | Correct Fan Installed |  | Correct Fan Installed - take photo of data plate
|  | Drain Pipe work installed & insulated to tundish |  | Drain Pipe work installed and insulated to tundish
|  | Ductwork adequately supported |  | Ductwork adequately supported
|  | Ductwork installed with clearance from other services |  | Ductwork installed with clearance from other services
|  | Ductwork Joints Sealed |  | Ductwork Joints Sealed
|  | Electrical Board has the correct Clearance from other Services |  | Electrical Board has the correct Clearance from other Services
|  | Electrical Board Installed in accordance with Seismic Design Drawing |  | Electrical Board Installed in accordance with Seismic Design Drawing
|  | Electrical supply cabling installed with isolation point |  | Electrical supply cabling installed with isolation point
|  | Fan & Duct Installed in accordance with Seismic Design Drawing |  | Fan and Duct Installed in accordance with Seismic Design Drawing
|  | Fan installed with anti vibration mounts |  | Fan installed with anti vibration mounts
|  | FCU Installed in accordance with Seismic Design Drawing |  | FCU Installed in accordance with Seismic Design Drawing
|  | FCU installed with anti vibration mounts |  | FCU installed with anti vibration mounts
|  | Flex Installed & Supported with Gutter Guard or equivalent |  | Flex Installed and Supported with Gutter Guard or equivalent
|  | GreenStar - Duct Delivery |  | GreenStar - Duct Delivery
|  | Greenstar Duct |  | Greenstar Duct
|  | Inspect - Materials free from Damage |  | Inspect - Materials free from Damage
|  | Interconnect & Control Cabling installed & secured |  | Interconnect and Control Cabling installed and secured
|  | Location Correct As per Plan/Drawing |  | Location Correct As per Plan/Drawing
|  | Penetration has been marked for Roofing Contractor to Cut |  | Penetration has been marked for Roofing Contractor to Cut
|  | Penetration is correct size |  | Penetration is correct size
|  | Penetration is correct substrate |  | Penetration is correct substrate
|  | Provisions for future access are adequate |  | Provisions for future access are adequate
|  | RA Box has filters |  | RA Box has filters
|  | Ready for Ceiling & Wall Sheeting |  | Ready for Ceiling and Wall Sheeting
|  | Ready for Fitoff |  | Ready for Fitoff
|  | Refrigeration Pipe work installed securely with insulation |  | Refrigeration Pipe work installed securely with insulation
|  | SA & RA Boxes fitted with anti vibration mounts |  | SA and RA Boxes fitted with anti vibration mounts
|  | Soaker Sheet provided by Roofer |  | Soaker Sheet provided by Roofer
|  | Take photo of mark out for penetration |  | Take photo of mark out for penetration
|  | Tundish Available |  | Tundish Available
|  | Unit has clearance from other services |  | Unit has clearance from other services
|  | Upstand is correct size |  | Upstand is correct size
Fitoff
| Scope |  |  | Fitoff
Rows
|  | Offices - Warehouse 1A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 1A | Fitoff | Fan Coil Units
|  | Offices - Warehouse 1A - Condenser Units | dynamic | Site QA | Offices | Warehouse 1A | Fitoff | Condenser Units
|  | Offices - Warehouse 1A - Toilet Exhaust Fans | dynamic | Site QA | Offices | Warehouse 1A | Fitoff | Toilet Exhaust Fans
|  | Offices - Warehouse 1A - Outside Air Fans | dynamic | Site QA | Offices | Warehouse 1A | Fitoff | Outside Air Fans
|  | Offices - Warehouse 1A - Roof Cowls | dynamic | Site QA | Offices | Warehouse 1A | Fitoff | Roof Cowls
|  | Offices - Warehouse 1B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 1B | Fitoff | Fan Coil Units
|  | Offices - Warehouse 1B - Condenser Units | dynamic | Site QA | Offices | Warehouse 1B | Fitoff | Condenser Units
|  | Offices - Warehouse 1B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 1B | Fitoff | Toilet Exhaust Fan
|  | Offices - Warehouse 1B - Roof Cowls | dynamic | Site QA | Offices | Warehouse 1B | Fitoff | Roof Cowls
|  | Offices - Warehouse 2A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 2A | Fitoff | Fan Coil Units
|  | Offices - Warehouse 2A - Condenser Units | dynamic | Site QA | Offices | Warehouse 2A | Fitoff | Condenser Units
|  | Offices - Warehouse 2A - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 2A | Fitoff | Toilet Exhaust Fan
|  | Offices - Warehouse 2A - Outside Air Fan | dynamic | Site QA | Offices | Warehouse 2A | Fitoff | Outside Air Fan
|  | Offices - Warehouse 2B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 2B | Fitoff | Fan Coil Units
|  | Offices - Warehouse 2B - Condenser Units | dynamic | Site QA | Offices | Warehouse 2B | Fitoff | Condenser Units
|  | Offices - Warehouse 2B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 2B | Fitoff | Toilet Exhaust Fan
|  | Offices - Warehouse 3A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 3A | Fitoff | Fan Coil Units
|  | Offices - Warehouse 3A - Condenser Units | dynamic | Site QA | Offices | Warehouse 3A | Fitoff | Condenser Units
|  | Offices - Warehouse 3A - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 3A | Fitoff | Toilet Exhaust Fan
|  | Offices - Warehouse 3A - Outside Air Fan | dynamic | Site QA | Offices | Warehouse 3A | Fitoff | Outside Air Fan
|  | Offices - Warehouse 3B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 3B | Fitoff | Fan Coil Units
|  | Offices - Warehouse 3B - Condenser Units | dynamic | Site QA | Offices | Warehouse 3B | Fitoff | Condenser Units
|  | Offices - Warehouse 3B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 3B | Fitoff | Toilet Exhaust Fan
|  | Warehouse Fans - Fitoff - Smoke Exhaust Fans | dynamic | Site QA | Warehouse Fans | Fitoff | Smoke Exhaust Fans
|  | Electrical Boards | dynamic | Site QA | Electrical Boards | Fitoff
|  | Fire Dampers | grouping | Fire Dampers
|  | Fire Dampers |  | Site QA | Fire Dampers | Fitoff
Columns
|  | Adequate Access Achieved |  | Adequate Access Achieved
|  | All Terminations Complete |  | All Terminations Complete
|  | Cable Containment has been completed |  | Cable Containment has been completed
|  | Condensate drains from drain tray |  | Condensate drains from drain tray
|  | Correct Master Unit Installed - Data Plate photo |  | Correct Master Unit Installed - Data Plate photo
|  | Cowl sealed against water ingress |  | Cowl sealed against water ingress
|  | Drain Terminated to Tundish |  | Drain Terminated to Tundish
|  | Dropper installed & Sealed |  | Dropper installed and Sealed
|  | Electrical & Control Terminations Complete |  | Electrical and Control Terminations Complete
|  | Grilles & Cushion Boxes Installed |  | Grilles and Cushion Boxes Installed
|  | Mains Supply provided by House Electrical Contractor |  | Mains Supply provided by House Electrical Contractor
|  | Refrigeration Pipe work installed securely with insulation |  | Refrigeration Pipe work installed securely with insulation
|  | Roof Cowl installed with a minimum of 4 screws |  | Roof Cowl installed with a minimum of 4 screws
|  | Take photo of Smoke/Seal product to be applied |  | Take photo of Smoke/Seal product to be applied
|  | Take photo with fixing angles off - post application |  | Take photo with fixing angles off - post application
|  | Take photo with fixing angles off - pre application |  | Take photo with fixing angles off - pre application
|  | Take photo with fixing angles on |  | Take photo with fixing angles on
|  | Wall Controller Installed & labelled |  | Wall Controller Installed and labelled
|  | Wall Controller Switch is Installed |  | Wall Controller Switch is Installed if Required
Commissioning
| Scope |  |  | Commissioning
Rows
|  | Offices - Warehouse 1A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 1A | Commissioning | Fan Coil Units
|  | Offices - Warehouse 1A - Condenser Units | dynamic | Site QA | Offices | Warehouse 1A | Commissioning | Condenser Units
|  | Offices - Warehouse 1A - Toilet Exhaust Fans | dynamic | Site QA | Offices | Warehouse 1A | Commissioning | Toilet Exhaust Fans
|  | Offices - Warehouse 1A - Outside Air Fans | dynamic | Site QA | Offices | Warehouse 1A | Commissioning | Outside Air Fans
|  | Offices - Warehouse 1A - Roof Cowls | dynamic | Site QA | Offices | Warehouse 1A | Commissioning | Roof Cowls
|  | Offices - Warehouse 1B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 1B | Commissioning | Fan Coil Units
|  | Offices - Warehouse 1B - Condenser Units | dynamic | Site QA | Offices | Warehouse 1B | Commissioning | Condenser Units
|  | Offices - Warehouse 1B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 1B | Commissioning | Toilet Exhaust Fan
|  | Offices - Warehouse 1B - Roof Cowls | dynamic | Site QA | Offices | Warehouse 1B | Commissioning | Roof Cowls
|  | Offices - Warehouse 2A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 2A | Commissioning | Fan Coil Units
|  | Offices - Warehouse 2A - Condenser Units | dynamic | Site QA | Offices | Warehouse 2A | Commissioning | Condenser Units
|  | Offices - Warehouse 2A - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 2A | Commissioning | Toilet Exhaust Fan
|  | Offices - Warehouse 2A - Outside Air Fan | dynamic | Site QA | Offices | Warehouse 2A | Commissioning | Outside Air Fan
|  | Offices - Warehouse 2B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 2B | Commissioning | Fan Coil Units
|  | Offices - Warehouse 2B - Condenser Units | dynamic | Site QA | Offices | Warehouse 2B | Commissioning | Condenser Units
|  | Offices - Warehouse 2B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 2B | Commissioning | Toilet Exhaust Fan
|  | Offices - Warehouse 3A - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 3A | Commissioning | Fan Coil Units
|  | Offices - Warehouse 3A - Condenser Units | dynamic | Site QA | Offices | Warehouse 3A | Commissioning | Condenser Units
|  | Offices - Warehouse 3A - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 3A | Commissioning | Toilet Exhaust Fan
|  | Offices - Warehouse 3A - Outside Air Fan | dynamic | Site QA | Offices | Warehouse 3A | Commissioning | Outside Air Fan
|  | Offices - Warehouse 3B - Fan Coil Units | dynamic | Site QA | Offices | Warehouse 3B | Commissioning | Fan Coil Units
|  | Offices - Warehouse 3B - Condenser Units | dynamic | Site QA | Offices | Warehouse 3B | Commissioning | Condenser Units
|  | Offices - Warehouse 3B - Toilet Exhaust Fan | dynamic | Site QA | Offices | Warehouse 3B | Commissioning | Toilet Exhaust Fan
|  | Warehouse Fans - Commissioning - Smoke Exhaust Fans | dynamic | Site QA | Warehouse Fans | Commissioning | Smoke Exhaust Fans
|  | Electrical Boards | dynamic | Site QA | Electrical Boards | Commissioning
|  | Fire Dampers | grouping | Fire Dampers
|  | Fire Dampers |  | Site QA | Fire Dampers | Commissioning
Columns
|  | 24 Hour Pressure Test - After |  | 24 Hour Pressure Test - After
|  | 24 Hour Pressure Test - Before |  | 24 Hour Pressure Test - Before
|  | Air Balance Complete |  | Air Balance Complete
|  | Air Off Coil Cooling |  | Air Off Coil Cooling
|  | Air Off Coil Heating |  | Air Off Coil Heating
|  | All systems tested & working as designed |  | All systems tested and working as designed
|  | Clear Access is Achieved |  | Clear Access is Achieved
|  | Electrical Commissioning Complete |  | Electrical Commissioning Complete
|  | Electrical Commissioning Complete by Licensed Electrical Contractor |  | Electrical Commissioning Complete by Licensed Electrical Contractor
|  | Electrical Isolation Labelled |  | Electrical Isolation Labelled
|  | Electrical Isolation Point Labelled |  | Electrical Isolation Point Labelled
|  | Evacuate System - Microns |  | Evacuate System - Microns
|  | Fire Damper Label is fixed & clearly visible |  | Fire Damper Label is fixed and clearly visible
|  | Gas Charge |  | Gas Charge
|  | Handover - Work completed as per specification, checked & accepted |  | Handover - Work completed as per specification, checked and accepted
|  | Refrigeration Commissioning Complete |  | Refrigeration Commissioning Complete
|  | Unit Test Run - Works as Designed |  | Unit Test Run - Works as Designed
|  | Units Test Run on Heating & Cooling - Air Off Temps |  | Units Test Run on Heating and Cooling - Air Off Temps