## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Ducted Unit ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Greenstar Duct
checkpoint | Location Correct As per Plan/Drawing
section | Rough-in
checkpoint | Unit has clearance from other services
checkpoint | Correct Fan Coil Installed - take photo of data plate
checkpoint | FCU installed with anti vibration mounts
checkpoint | SA and RA Boxes fitted with anti vibration mounts
checkpoint | RA Box has filters
checkpoint | FCU Installed in accordance with Seismic Design Drawing
checkpoint | Refrigeration Pipe work installed securely with insulation
checkpoint | Tundish Available
checkpoint | Drain Pipe work installed and insulated to tundish
checkpoint | Electrical supply cabling installed with isolation point
checkpoint | Interconnect and Control Cabling installed and secured
checkpoint | Check Access to Filters and Electrical Box
checkpoint | Ductwork installed with clearance from other services
checkpoint | Ductwork Joints Sealed
checkpoint | Ductwork adequately supported
checkpoint | All spigots protected from dust ingress
checkpoint | Flex Installed and Supported with Gutter Guard or equivalent
checkpoint | Provisions for future access are adequate
checkpoint | Ready for Ceiling and Wall Sheeting
checklist | Condenser ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Unit has clearance from other services
checkpoint | Correct Condenser Installed - take photo of data plate
checkpoint | Condenser Feet installed with anti vibration mounts
checkpoint | Condenser Installed in accordance with Seismic Design Drawing
checkpoint | Tundish Available
checkpoint | Electrical supply cabling installed with isolation point
checkpoint | Interconnect and Control Cabling installed and secured
checklist | Roof Cowl ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Penetration has been marked for Roofing Contractor to Cut
checkpoint | Take photo of mark out for penetration
checkpoint | Soaker Sheet provided by Roofer
checkpoint | Upstand is correct size
checkpoint | Ready for Fitoff
checklist | Vent Fan ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
checkpoint | GreenStar - Duct Delivery
section | Roughin
checkpoint | Unit has clearance from other services
checkpoint | Correct Fan Installed - take photo of data plate
checkpoint | Fan installed with anti vibration mounts
checkpoint | Fan and Duct Installed in accordance with Seismic Design Drawing
checkpoint | Electrical supply cabling installed with isolation point
checkpoint | Control Cabling installed and secured
checkpoint | Check Access to Fan - Mark Access Panel if required
checkpoint | Ductwork installed with clearance from other services
checkpoint | Ductwork Joints Sealed
checkpoint | Ductwork adequately supported
checkpoint | All spigots open 100% and protected from dust ingress
checkpoint | Flex Installed and Supported with Gutter Guard or equivalent
checkpoint | Provisions for future access are adequate
checkpoint | Ready for Ceiling and Wall Sheeting
checklist | Fire Damper ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Penetration is correct size
checkpoint | Penetration is correct substrate
checkpoint | Core is filled to correct depth if required
checklist | Electrical Board ITP RI
section | General
checkpoint | Area ready and accessible for work - take picture if required
checkpoint | Inspect - Materials free from Damage
checkpoint | Location Correct As per Plan/Drawing
section | Roughin
checkpoint | Electrical Board has the correct Clearance from other Services
checkpoint | Electrical Board Installed in accordance with Seismic Design Drawing
checkpoint | Cable Tray Installed where Required
checkpoint | Provisions for future access are adequate
checkpoint | Ready for Ceiling and Wall Sheeting
checklist | Ducted Unit ITP FO
section | Fit off
checkpoint | Grilles and Cushion Boxes Installed
checkpoint | Adequate Access Achieved
checkpoint | Condensate drains from drain tray
checkpoint | Drain Terminated to Tundish
checkpoint | Wall Controller Installed and labelled
checklist | Condenser ITP FO
section | Fit off
checkpoint | Electrical and Control Terminations Complete
checkpoint | Refrigeration Pipe work installed securely with insulation
checkpoint | Correct Master Unit Installed - Data Plate photo
checkpoint | Drain Terminated to Tundish
checklist | Roof Cowl ITP FO
section | Fit off
checkpoint | Dropper installed and Sealed
checkpoint | Roof Cowl installed with a minimum of 4 screws
checkpoint | Cowl sealed against water ingress
checklist | Vent Fan ITP FO
section | Fit off
checkpoint | Grilles and Cushion Boxes Installed
checkpoint | Adequate Access Achieved
checkpoint | Wall Controller Switch is Installed if Required
checklist | Fire Damper ITP FO
section | Roughin
checkpoint | Take photo of Smoke/Seal product to be applied
checkpoint | Take photo with fixing angles off - pre application
checkpoint | Take photo with fixing angles off - post application
checkpoint | Take photo with fixing angles on
checklist | Electrical Board ITP FO
section | Fit off
checkpoint | Cable Containment has been completed
checkpoint | Mains Supply provided by House Electrical Contractor
checkpoint | All Terminations Complete
checklist | Ducted Unit ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete
checkpoint | Refrigeration Commissioning Complete
checkpoint | Clear Access is Achieved
checkpoint | Electrical Isolation Point labelled
checkpoint | Air Off Coil Heating
checkpoint | Air Off Coil Cooling
checkpoint | Air Balance Complete
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Condenser ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete
checkpoint | 24 Hour Pressure Test - Before
checkpoint | 24 Hour Pressure Test - After
checkpoint | Electrical Isolation Point Labelled
checkpoint | Evacuate System - Microns
checkpoint | Gas Charge
checkpoint | Units Test Run on Heating and Cooling - Air Off Temps
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Roof Cowl ITP Comm
section | Commissioning
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Vent Fan ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete
checkpoint | Unit Test Run - Works as Designed
checkpoint | Clear Access is Achieved
checkpoint | Electrical Isolation Labelled
checkpoint | Air Balance Complete
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Fire Damper ITP Comm
section | Roughin
checkpoint | Fire Damper Label is fixed and clearly visible
checkpoint | Handover - Work completed as per specification, checked and accepted
checklist | Electrical Board ITP Comm
section | Commissioning
checkpoint | Electrical Commissioning Complete by Licensed Electrical Contractor
checkpoint | All systems tested and working as designed
checkpoint | Handover - Work completed as per specification, checked and accepted