## ITP Cover Page
Traffic Services Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: 1208 - 809 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH1/29 Intersection Upgrade |  |  |  |  | ITP Number: |  |  | 809
Project Number: |  |  | 1208 |  |  |  |  | ITP Status: |  |  | For Construction
ITP Description: |  |  | Traffic Services Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | 7991 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | Z8
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2023-12-18 |  | Stuart McCarron |  | Combined Remaining Items Inspection and Test Plan |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2024-08-02 |  | Michael Randall |  | Have made ammendments based on Stantec review |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
1 | For Construction | 2024-12-10 |  | Hennie van der Walt |  | Comments from Stantec incorporated |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Traffic Services
Traffic Services Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: 1208 - 809 - Rev 1
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.34 | Traffic Service Materials
4.34.01 | Safe Lane Delineator and Guard Rail Concrete | Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days. | PS 23.7 PS 23.6 M23 | Delivery Dockets/Test Cube Results from Supplier | Prior to use |  | R | SE
4.34.02 | Proposed Guard Rails (including Wire Rope Barriers) | The Contractor shall submit details of proposed proprietary materials and systems. Submission to include checklists, post spacing, footing type and barrier deflection for both wire rope and w beam barrier in accordance with M23 | PS 23.6 M23 | Datasheets | Prior to material order (4 weeks prior to installation) |  | HP | ENG
4.34.03 | Guard Rail Maintenance Instructions | The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed. | PS 23.6 M23 | Maintenance Instructions | Upon completion of the Guardrail Construction |  | HP | ENG
4.34.04 | Coloured Surfacing | The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33. | PS 23.4 | Datasheets | Prior to use |  | R | SE
4.35 | Sign Materials
4.35.01 | Retro-reflective sheeting | All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting. | PS 23.2.6 | Datasheet | Prior to use |  | R | PE
4.35.02 | Anti-Graffiti Coating | Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign. | PS 23.2.14 | Datasheet | Prior to use |  | R | PE
4.35.03 | Dew Effect Coating | All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’. Conractor shall submit special handling and washing methodology for installation of dew effect coated signs | PS 23.2.15 | Datasheet | Prior to use |  | R | PE
4.35.04 | Stickers | Installation of manufacturer and installer stcikers accroding to P24 specification | NZTA P24: 2020 | Site Record | Installation |  | S | PE
4.35.05 | Sign Shop Drawings | The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, reflective sheeting classes used, footing and post designs for larger signs and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign. | PS 23.2.6 | Shop Drawings | At least ten working days prior to manufacture of the sign. |  | R | PE
4.35.06 | Post Embedment | All post foundation shall comply with the requirements of NZTA P24 specification of permanent traffic signs. All posts shall be encased in a concrete foundation 300mm minimum diameter and have a 100mm cover to the base of the post, unless specified otherwise. | PS 23.2.18 | Site Record | Every foundation |  | I | PE
4.35.07 | Timber Posts | Timber posts shall not exceed 100mm x 100mm section size. They shall be Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level. | PS 23.2.19 | Datasheet | Prior to use |  | R | PE
4.35.08 | Steel Posts | Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps. | PS 23.2.20 | Datasheet | Prior to use |  | R | PE
4.35.09 | Aluminium Poles | Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps. | PS 23.2.21 | Datasheet | Prior to use |  | R | PE
4.35.10 | Sign Fixings | All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign. | PS 23.2.23 | Datasheet | Prior to use |  | R | PE
4.36 | Long-life Road Markings Materials
4.36.01 | Applicator Approval | The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12. Also provide T/8 cert for temporary markings | PS 23.5.2 | Engineers Approval | Prior to Installation |  | HP | ENG
4.36.02 | Approval of Road Marking Materials | Only products approved that meet M07 specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works. The Contractor shall nominate the brand, type (white, yellow, and structured if different) and proposed application methods for materials to be used. | M07 2022 | Data Sheet | Prior to Installation |  | HP | ENG
4.36.03 | Installation Limitations | The contractor must provide the engineer with the supplier's specifications or installation instructions for the proposed long-life road marking system including temporary paint and permanent CAP | PS 23.5.4 | Data Sheet | Prior to Installation |  | HP | ENG
4.36.04 | Glass beads | Provide evidence beads meet M07 cl. 6.8. Report As/NZS 2009 appendix N Heavy metals. Provide evidence beads meet proprietry CAP product requirements. | PS 23.5.5 PS 23.3.1 | Data Sheet | Prior to Installation |  | HP | ENG
4.36.05 | Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. Specifically, Contractor shall provide evidence prior to application that raised markers meet M/12 type approval | PS 23.5.6 PS 23.3.1 | Datasheets | Prior to Installation |  | H | PE
4.36.06 | Raised Pavement Markers (adhesive) | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. Specifically, Contractor shall provide evidence prior to application that the adhesive to be used is an approved type | PS 23.5.6 PS 23.3.1 | Datasheets | Prior to Installation |  | H | PE
4.36.07 | Application Crew | The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed. | PS 23.5.7 | Engineers Approval | Prior to Installation |  | HP | ENG
4.37 | Pavement Marking Materials
| High performance markings | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application. | PS 23.3.1 | Datasheets | Prior to Installation |  | HP | ENG
| Glass beads | All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17). | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
| Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
| Edge Marker Posts: | Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval. | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
SECTION 16 – CONSTRUCTION ACTIVITY – TRAFFIC SERVICES
16.01 | Signs
| Redundant Signs | All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use. All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner. | PS 23.2.2 | Site Records | Where Required |  | R | SE
16.01.01 | Relocated Signs | Relocated signs must be inspected by the Engineer for suitability, installed vertically, and securely attached to posts with appropriate brackets. | PS 23.2.3 | Site Records | Each Sign |  | H | PE
| Posts and poles | The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification. The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures. | PS 23.2.17 PS 23.2.18 PS 23.2.24 | Checksheet | Each Sign |  | I | SE
| Ground Mounted Signs | All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1. | PS 23.2.27 | Site Records | Each Ground Mounted Sign |  | V | SE
16.02 | Pavement Markings
16.02.01 | Surplus Chip Removal | Accumulations of surplus chip and other coarse material shall be removed prior to road marking. | PS 23.3.2 | Site Records | Prior to Marking |  | V | SE
16.02.02 | High Performance Marking | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. | PS 23.3.1 | Site Records | Each Marking |  | V | SE
16.02.03 | Roadmarking Removal | All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide. The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains. | PS 23.3.2 | Site Records | Each Removed marking |  | V | SE
16.02.04 | Raised Pavement Markers | These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers. | PS 23.3.2 | Site Records | Each Marking |  | V | SE
16.02.05 | Edge Marker Posts: | Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings. | PS 23.3.2 | Site Records | Each Marking |  | V | SE
16.02.06 | Coloured Surfacing | Coloured surfacing must meet NZTA P33 requirements and come with a minimum five-year warranty. The contractor must provide proof to the Engineer that the material complies with NZTA P33 before preparing and marking the surfacing. | PS 23.3.2 PS 23.4 | Site Records | Each Application |  | HP | ENG
16.03 | Long-life Road Markings
16.03.01 | Mark out the Contract Works with Engineer | The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site. | PS 23.5.9 | Notice | 5 Working Day notice prior to mark out |  | HP | ENG
16.03.02 | Initial Paint Setout Inspection | Verify the setout of the initial paint following the completion of the Asphalt Concrete (AC) construction. | PS 23.5.19 | Markout Records | Upon completion of AC laying. |  | HP | ENG
16.03.03 | ATP Setout Inspection | Verify the setout of the Audio Tactile Profiled (ATP) | PS 23.5.8 | Markout Records | Prior to Installation |  | HP | ENG
16.03.04 | Applicator, Marking System, Marking Format and Applicator Crew Trial | The contractor shall demonstrate the application of each marking system format in the presence of the Engineer.The contractor must provide the Engineer with a minimum of 5 working days' notice prior to the trial date.Installation of the marking systems shall only commence if the Engineer is satisfied with the trial. | PS 23.5.11 | Engineers Approval | Prior to Installation |  | HP | ENG
16.03.05 | Inspection Post Installation | Formal visual drive over inspections. The visual inspection shall include an initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor.The visual inspection shall include the following - Colour, Night and Day Time Visibility, Alignment, Coverage (structured only) and Damage.First Inspection following installation of all contract works. | PS 23.5.16 | Report | Three inspections are required: first, 2-4 weeks post-installation; second, six months later; third, before issuing the Final Completion Certificate. The Engineer may waive monitoring if satisfied with the first results. |  | V | PE
16.03.06 | Monitoring Post Installation | Three monitoring sets are required: First monitoring following installation of all contract works. The Contractor shall report on the performance of long-life road markings based on the following criteria: Colour: Inspected using AS 2700 standards. Discolouration should not exceed 4/5 per ISO 105-A03 and refers only to the material’s natural colour, not external build-up. The Engineer will investigate if necessary. Road markings should retain their daytime colour at night. Retroreflectivity: Dry (R): Minimum of 150 mcd/m²/lux for the warranted period. Wet (RW): Minimum of 80 mcd/m²/lux for the warranted period. Measured per IS EN 1436 or ASTM E1710. Mobile device measurements must use 30-metre geometry. Concerns identified by mobile retroreflectometer should be validated with a hand-held device per BS EN 1436 or ASTM E1710. | PS 23.5.17 | Report | First, 2-4 weeks post-installation; second, six months later; third, before issuing the Final Completion Certificate. The Engineer may waive monitoring if satisfied with the first results |  | HP | ENG
16.04 | Safety Barriers
Wire Rope?
16.04.01 | Ground profile w-beam | The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10. | PS 23.6 M23 | Site Records | Prior to post installation |  | V | SE
16.04.02 | Installation Notice | The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction. | PS 23.6 M23 | Notice | Prior to Guardrail Construction |  | HP | ENG
16.04.03 | Guardrail Alignment Visual Inspection | The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable. | PS 23.6 M23 | Site Records | When erected but before posts are permanently fixed |  | V | SE
16.04.04 | Safety Barrier Installation Checksheets | The Contractor shall submit a completed and signed installation check sheet to the Engineer for acceptance | PS 23.6 M23 | Ingal Mashflex and Ezy-Guard 4 checklists and w-beam terminal checklist | Upon completion of the Guardrail Construction |  | HP | ENG
16.05 | Wire Rope Specific Requirements
16.05.01 | Pull Test | Per the manufacturer static pull test requirements | NZTA M23 | Test record | A sample of not less than 3% (or one post in every 100 m, whichever percentage is greater) of each installed length of WRSB shall be tested in accordance with the System Owner’s |  | HP | ENG
16.05.02 | Foundation inspection for depth and width | Per the manufacturer’s requirements (table 1 assuming mashflex) | NZTA M23 | foundation logs/site records | Each post |  | S | SE
16.05.03 | End terminal Anchorage | Per the manufacturer's requirements (Assuming Mashflex) RECTANGULAR (TYPE 1) ANCHOR BLOCK RECTANGULAR (TYPE 3) ANCHOR BLOCK | NZTA M23 | Subgrade test record and As-built of anchor | Each anchor |  | HP | ENG
16.05.04 | Concrete for anchor | Must be 30 MPA |  | Concrete mix design and 28-day cores | Prior to pouring each anchor |  | HP | ENG
16.06 | W-Beam Barriers
16.06.01 | Terminal | Terminals should be installed in accordance with the proprietor’s drawings and specifications. | NZTA M23 and manufacturers manual | Site records | Each post |  | S | SE
16.06.02 | Posts on Base Plates | Constructed as per Ingal Civil Products drawings for the installation of posts on base plates |  | Site records | Each post |  | S | SE