## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Traffic Services - 809 - Rev 1 | itp |  |  |  |  | ITP - Traffic Services - 809 - Rev 1
section | 3.01 - General
checkpoint | 3.01.01 - Precondition Surveys
label | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
label | Standard / Specification - PS 2.13
label | Verifying Document - Precondition Survey
label | Frequency - Prior to the Contractor taking possession of the Site.
label | Verification Activity: Activity - H
label | Verification Activity: By - PM
section | 4.34 - Traffic Service Materials
checkpoint | 4.34.01 - Safe Lane Delineator and Guard Rail Concrete
label | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
label | Standard / Specification - PS 23.7, PS 23.6, M23
label | Verifying Document - Delivery Dockets/Test Cube Results from Supplier
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 4.34.02 - Proposed Guard Rails (including Wire Rope Barriers)
label | Acceptance / Conformance Criteria - The Contractor shall submit details of proposed proprietary materials and systems. Submission to include checklists, post spacing, footing type and barrier deflection for both wire rope and w beam barrier in accordance with M23
label | Standard / Specification - PS 23.6, M23
label | Verifying Document - Datasheets
label | Frequency - Prior to material order (4 weeks prior to installation)
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.03 - Guard Rail Maintenance Instructions
label | Acceptance / Conformance Criteria - The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed.
label | Standard / Specification - PS 23.6, M23
label | Verifying Document - Maintenance Instructions
label | Frequency - Upon completion of the Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.34.04 - Coloured Surfacing
label | Acceptance / Conformance Criteria - The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33.
label | Standard / Specification - PS 23.4
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.35 - Sign Materials
checkpoint | 4.35.01 - Retro-reflective sheeting
label | Acceptance / Conformance Criteria - All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting.
label | Standard / Specification - PS 23.2.6
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.02 - Anti-Graffiti Coating
label | Acceptance / Conformance Criteria - Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign.
label | Standard / Specification - PS 23.2.14
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.03 - Dew Effect Coating
label | Acceptance / Conformance Criteria - All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’. Conractor shall submit special handling and washing methodology for installation of dew effect coated signs
label | Standard / Specification - PS 23.2.15
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.04 - Stickers
label | Acceptance / Conformance Criteria - Installation of manufacturer and installer stcikers accroding to P24 specification
label | Standard / Specification - NZTA P24: 2020
label | Verifying Document - Site Record
label | Frequency - Installation
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 4.35.05 - Sign Shop Drawings
label | Acceptance / Conformance Criteria - The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, reflective sheeting classes used, footing and post designs for larger signs and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign.
label | Standard / Specification - PS 23.2.6
label | Verifying Document - Shop Drawings
label | Frequency - At least ten working days prior to manufacture of the sign.
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.06 - Post Embedment
label | Acceptance / Conformance Criteria - All post foundation shall comply with the requirements of NZTA P24 specification of permanent traffic signs. All posts shall be encased in a concrete foundation 300mm minimum diameter and have a 100mm cover to the base of the post, unless specified otherwise.
label | Standard / Specification - PS 23.2.18
label | Verifying Document - Site Record
label | Frequency - Every foundation
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 4.35.07 - Timber Posts
label | Acceptance / Conformance Criteria - Timber posts shall not exceed 100mm x 100mm section size. They shall be Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level.
label | Standard / Specification - PS 23.2.19
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.08 - Steel Posts
label | Acceptance / Conformance Criteria - Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.20
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.09 - Aluminium Poles
label | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.21
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 4.35.10 - Sign Fixings
label | Acceptance / Conformance Criteria - All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign.
label | Standard / Specification - PS 23.2.23
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 4.36 - Long-life Road Markings Materials
checkpoint | 4.36.01 - Applicator Approval
label | Acceptance / Conformance Criteria - The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12. Also provide T/8 cert for temporary markings
label | Standard / Specification - PS 23.5.2
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.36.02 - Approval of Road Marking Materials
label | Acceptance / Conformance Criteria - Only products approved that meet M07 specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works.
label | ○ The Contractor shall nominate the brand, type (white, yellow, and structured if different) and proposed application methods for materials to be used.
label | Standard / Specification - M07 2022
label | Verifying Document - Data Sheet
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.36.03 - Installation Limitations
label | Acceptance / Conformance Criteria - The contractor must provide the engineer with the supplier's specifications or installation instructions for the proposed long-life road marking system including temporary paint and permanent CAP
label | Standard / Specification - PS 23.5.4
label | Verifying Document - Data Sheet
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.36.04 - Glass beads
label | Acceptance / Conformance Criteria - Provide evidence beads meet M07 cl. 6.8. Report As/NZS 2009 appendix N Heavy metals. Provide evidence beads meet proprietry CAP product requirements.
label | Standard / Specification - PS 23.5.5, PS 23.3.1
label | Verifying Document - Data Sheet
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.36.05 - Raised Pavement Markers
label | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. Specifically, Contractor shall provide evidence prior to application that raised markers meet M/12 type approval
label | Standard / Specification - PS 23.5.6, PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.36.06 - Raised Pavement Markers (adhesive)
label | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. Specifically, Contractor shall provide evidence prior to application that the adhesive to be used is an approved type
label | Standard / Specification - PS 23.5.6, PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.36.07 - Application Crew
label | Acceptance / Conformance Criteria - The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed.
label | Standard / Specification - PS 23.5.7
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Edge Marker Posts:
label | Acceptance / Conformance Criteria - Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 16.01 - Signs
checkpoint | 16.01.01 - Relocated Signs
label | Acceptance / Conformance Criteria - Relocated signs must be inspected by the Engineer for suitability, installed vertically, and securely attached to posts with appropriate brackets.
label | Standard / Specification - PS 23.2.3
label | Verifying Document - Site Records
label | Frequency - Each Sign
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | 16.02 - Pavement Markings
checkpoint | 16.02.01 - Surplus Chip Removal
label | Acceptance / Conformance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Prior to Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 16.02.04 - Raised Pavement Markers
label | Acceptance / Conformance Criteria - These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 16.02.05 - Edge Marker Posts:
label | Acceptance / Conformance Criteria - Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 16.02.06 - Coloured Surfacing
label | Acceptance / Conformance Criteria - Coloured surfacing must meet NZTA P33 requirements and come with a minimum five-year warranty. The contractor must provide proof to the Engineer that the material complies with NZTA P33 before preparing and marking the surfacing.
label | Standard / Specification - PS 23.3.2, PS 23.4
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.03 - Long-life Road Markings
checkpoint | 16.03.01 - Mark out the Contract Works with Engineer
label | Acceptance / Conformance Criteria - The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site.
label | Standard / Specification - PS 23.5.9
label | Verifying Document - Notice
label | Frequency - 5 Working Day notice prior to mark out
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.03.02 - Initial Paint Setout Inspection
label | Acceptance / Conformance Criteria - Verify the setout of the initial paint following the completion of the Asphalt Concrete (AC) construction.
label | Standard / Specification - PS 23.5.19
label | Verifying Document - Markout Records
label | Frequency - Upon completion of AC laying.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.03.03 - ATP Setout Inspection
label | Acceptance / Conformance Criteria - Verify the setout of the Audio Tactile Profiled (ATP)
label | Standard / Specification - PS 23.5.8
label | Verifying Document - Markout Records
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.03.04 - Applicator, Marking System, Marking Format and Applicator Crew Trial
label | Acceptance / Conformance Criteria - The contractor shall demonstrate the application of each marking system format in the presence of the Engineer.The contractor must provide the Engineer with a minimum of 5 working days' notice prior to the trial date.Installation of the marking systems shall only commence if the Engineer is satisfied with the trial.
label | Standard / Specification - PS 23.5.11
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.03.05 - Inspection Post Installation
label | Acceptance / Conformance Criteria - Formal visual drive over inspections. The visual inspection shall include an initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor.The visual inspection shall include the following - Colour, Night and Day Time Visibility, Alignment, Coverage (structured only) and Damage.First Inspection following installation of all contract works.
label | Standard / Specification - PS 23.5.16
label | Verifying Document - Report
label | Frequency - Three inspections are required: first, 2-4 weeks post-installation; second, six months later; third, before issuing the Final Completion Certificate. The Engineer may waive monitoring if satisfied with the first results.
label | Verification Activity: Activity - V
label | Verification Activity: By - PE
checkpoint | 16.03.06 - Monitoring Post Installation
label | Acceptance / Conformance Criteria - Three monitoring sets are required: First monitoring following installation of all contract works.
label | The Contractor shall report on the performance of long-life road markings based on the following criteria:
label | ○ Colour: Inspected using AS 2700 standards. Discolouration should not exceed 4/5 per ISO 105-A03 and refers only to the material’s natural colour, not external build-up. The Engineer will investigate if necessary. Road markings should retain their daytime colour at night.
label | Retroreflectivity:
label | ○ Dry (R): Minimum of 150 mcd/m²/lux for the warranted period.
label | ○ Wet (RW): Minimum of 80 mcd/m²/lux for the warranted period.
label | ○ Measured per IS EN 1436 or ASTM E1710. Mobile device measurements must use 30-metre geometry. Concerns identified by mobile retroreflectometer should be validated with a hand-held device per BS EN 1436 or ASTM E1710.
label | Standard / Specification - PS 23.5.17
label | Verifying Document - Report
label | Frequency - First, 2-4 weeks post-installation; second, six months later; third, before issuing the Final Completion Certificate. The Engineer may waive monitoring if satisfied with the first results
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.04 - Safety Barriers
checkpoint | 16.04.01 - Ground profile w-beam
label | Acceptance / Conformance Criteria - The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10.
label | Standard / Specification - PS 23.6, M23
label | Verifying Document - Site Records
label | Frequency - Prior to post installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 16.04.02 - Installation Notice
label | Acceptance / Conformance Criteria - The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction.
label | Standard / Specification - PS 23.6, M23
label | Verifying Document - Notice
label | Frequency - Prior to Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.04.03 - Guardrail Alignment Visual Inspection
label | Acceptance / Conformance Criteria - The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable.
label | Standard / Specification - PS 23.6, M23
label | Verifying Document - Site Records
label | Frequency - When erected but before posts are permanently fixed
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 16.04.04 - Safety Barrier Installation Checksheets
label | Acceptance / Conformance Criteria - The Contractor shall submit a completed and signed installation check sheet to the Engineer for acceptance
label | Standard / Specification - PS 23.6, M23
label | Verifying Document - Ingal Mashflex and Ezy-Guard 4 checklists and w-beam terminal checklist
label | Frequency - Upon completion of the Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.05 - Wire Rope Specific Requirements
checkpoint | 16.05.01 - Pull Test
label | Acceptance / Conformance Criteria - Per the manufacturer static pull test requirements
label | Standard / Specification - NZTA M23
label | Verifying Document - Test record
label | Frequency - A sample of not less than 3% (or one post in every 100 m, whichever percentage is greater) of each installed length of WRSB shall be tested in accordance with the System Owner’s
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.05.02 - Foundation inspection for depth and width
label | Acceptance / Conformance Criteria - Per the manufacturer’s requirements (table 1 assuming mashflex)
label | Standard / Specification - NZTA M23
label | Verifying Document - foundation logs/site records
label | Frequency - Each post
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 16.05.03 - End terminal Anchorage
label | Acceptance / Conformance Criteria - Per the manufacturer's requirements
label | (Assuming Mashflex)
label | ○ RECTANGULAR (TYPE 1) ANCHOR BLOCK
label | ○ RECTANGULAR (TYPE 3) ANCHOR BLOCK
label | Standard / Specification - NZTA M23
label | Verifying Document - Subgrade test record and As-built of anchor
label | Frequency - Each anchor
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.05.04 - Concrete for anchor
label | Acceptance / Conformance Criteria - Must be 30 MPA
label | Verifying Document - Concrete mix design and 28-day cores
label | Frequency - Prior to pouring each anchor
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.06 - W-Beam Barriers
checkpoint | 16.06.01 - Terminal
label | Acceptance / Conformance Criteria - Terminals should be installed in accordance with the proprietor’s drawings and specifications.
label | Standard / Specification - NZTA M23 and manufacturers manual
label | Verifying Document - Site records
label | Frequency - Each post
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 16.06.02 - Posts on Base Plates
label | Acceptance / Conformance Criteria - Constructed as per Ingal Civil Products drawings for the installation of posts on base plates
label | Verifying Document - Site records
label | Frequency - Each post
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature