## QA lots subfolders and ITPs
Tier1 (Discipline) | Tier2 - (Design Package) - Hopkins Road | Tier 3 (Location) | Tier 4 (Name of the activity) | Tier 5 (ITP) |  | ITP Status | Lot No/WBS No
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0001 - Bored Piles - South Abutment - P1-1 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-1 | Approved | 102-0001
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0002 - Bored Piles - South Abutment - P1-2 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-2 | Approved | 102-0002
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0003 - Bored Piles - South Abutment - P1-3 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-3 | Approved | 102-0003
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0004 - Bored Piles - South Abutment - P1-4 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-4 | Approved | 102-0004
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0005 - Bored Piles - South Abutment - P1-5 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-5 | Approved | 102-0005
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0006 - Bored Piles - South Abutment - P1-6 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-6 | Approved | 102-0006
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0007 - Bored Piles - South Abutment - P1-7 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-7 | Approved | 102-0007
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0008 - Bored Piles - South Abutment - P1-8 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-8 | Approved | 102-0008
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0009 - Bored Piles - South Abutment - P1-9 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-9 | Approved | 102-0009
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0010 - Bored Piles - South Abutment - P1-10 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-10 | Approved | 102-0010
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0011 - Bored Piles - South Abutment - P1-11 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-11 | Approved | 102-0011
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0012 - Bored Piles - South Abutment - P1-12 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - South Abutment - P1-12 | Approved | 102-0012
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0013 - Bored Piles - Pier 1 - P2-1 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-1 | Approved | 102-0013
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0014 - Bored Piles - Pier 1 - P2-2 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-2 | Approved | 102-0014
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0015 - Bored Piles - Pier 1 - P2-3 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-3 | Approved | 102-0015
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0016 - Bored Piles - Pier 1 - P2-4 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-4 | Approved | 102-0016
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0017 - Bored Piles - Pier 1 - P2-5 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-5 | Approved | 102-0017
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0018 - Bored Piles - Pier 1 - P2-6 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-6 | Approved | 102-0018
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0019 - Bored Piles - Pier 1 - P2-7 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-7 | Approved | 102-0019
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0020 - Bored Piles - Pier 1 - P2-8 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-8 | Approved | 102-0020
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0021 - Bored Piles - Pier 1 - P2-9 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-9 | Approved | 102-0021
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0022 - Bored Piles - Pier 1 - P2-10 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-10 | Approved | 102-0022
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0023 - Bored Piles - Pier 1 - P2-11 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-11 | Approved | 102-0023
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0024 - Bored Piles - Pier 1 - P2-12 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 1 - P2-12 | Approved | 102-0024
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0025 - Bored Piles - North Abutment - P1-13 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-13 | Approved | 102-0025
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0026 - Bored Piles - North Abutment - P1-14 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-14 | Approved | 102-0026
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0027 - Bored Piles - North Abutment - P1-15 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-15 | Approved | 102-0027
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0028 - Bored Piles - North Abutment - P1-16 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-16 | Approved | 102-0028
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0029 - Bored Piles - North Abutment - P1-17 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-17 | Approved | 102-0029
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0030 - Bored Piles - North Abutment - P1-18 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-18 | Approved | 102-0030
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0031 - Bored Piles - North Abutment - P1-19 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-19 | Approved | 102-0031
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0032 - Bored Piles - North Abutment - P1-20 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-20 | Approved | 102-0032
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0033 - Bored Piles - North Abutment - P1-21 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-21 | Approved | 102-0033
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0034 - Bored Piles - North Abutment - P1-22 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-22 | Approved | 102-0034
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0035 - Bored Piles - North Abutment - P1-23 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-23 | Approved | 102-0035
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0036 - Bored Piles - North Abutment - P1-24 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - North Abutment - P1-24 | Approved | 102-0036
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0037 - Bored Piles - Pier 2 - P2-13 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-13 | Approved | 102-0037
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0038 - Bored Piles - Pier 2 - P2-14 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-14 | Approved | 102-0038
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0039 - Bored Piles - Pier 2 - P2-15 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-15 | Approved | 102-0039
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0040 - Bored Piles - Pier 2 - P2-16 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-16 | Approved | 102-0040
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0041 - Bored Piles - Pier 2 - P2-17 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-17 | Approved | 102-0041
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0042 - Bored Piles - Pier 2 - P2-18 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-18 | Approved | 102-0042
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0043 - Bored Piles - Pier 2 - P2-19 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-19 | Approved | 102-0043
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0044 - Bored Piles - Pier 2 - P2-20 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-20 | Approved | 102-0044
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0045 - Bored Piles - Pier 2 - P2-21 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-21 | Approved | 102-0045
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0046 - Bored Piles - Pier 2 - P2-22 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-22 | Approved | 102-0046
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0047 - Bored Piles - Pier 2 - P2-23 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-23 | Approved | 102-0047
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0001 - Bored Piles - Pier 2 - P2-24 | ITP-220-STR-HOP-Bored Piling Rev 0 | Bored Piles - Pier 2 - P2-24 | Approved | 102-0001
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0050 - Abutment wall - South Abutment |  | Abutment wall - South Abutment |  | 102-0050
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0051 - Abutment crosshead - South Abutment |  | Abutment crosshead - South Abutment |  | 102-0051
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0052 - Pile Cap - South Abutment |  | Pile Cap - South Abutment |  | 102-0052
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0053 - Wing wall - South Abutment |  | Wing wall - South Abutment |  | 102-0053
| MRP-102-C-AUR-DRG-30-CSP-CBR | South Abutment | 102-0054 - Fender wall - South Abutment |  | Fender wall - South Abutment |  | 102-0054
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0055 - Blade wall - Pier 1 |  | Blade wall - Pier 1 |  | 102-0055
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0056 - Pier crosshead - Pier 1 |  | Pier crosshead - Pier 1 |  | 102-0056
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 1 | 102-0057 - Pile cap - Pier 1 |  | Pile cap - Pier 1 |  | 102-0057
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0058 - Abutment wall - North Abutment |  | Abutment wall - North Abutment |  | 102-0058
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0059 - Abutment crosshead - North Abutment |  | Abutment crosshead - North Abutment |  | 102-0059
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0060 - Pile cap - North Abutment |  | Pile cap - North Abutment |  | 102-0060
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0061 - Wing wall - North Abutment |  | Wing wall - North Abutment |  | 102-0061
| MRP-102-C-AUR-DRG-30-CSP-CBR | North Abutment | 102-0062 - Fender wall - North Abutment |  | Fender wall - North Abutment |  | 102-0062
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0063 - Blade wall - Pier 2 |  | Blade wall - Pier 2 |  | 102-0063
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0064 - Pier crosshead - Pier 2 |  | Pier crosshead - Pier 2 |  | 102-0064
| MRP-102-C-AUR-DRG-30-CSP-CBR | Pier 2 | 102-0065 - Pile cap - Pier 2 |  | Pile cap - Pier 2 |  | 102-0065
| MRP-102-C-AUR-DRG-30-CSP-CBR | Restraint Block | 102-0066 - Lateral Restraint Block - South Abutment -01 |  | Lateral Restraint Block - South Abutment -01 |  | 102-0066
| MRP-102-C-AUR-DRG-30-CSP-CBR | Restraint Block | 102-0067 - Lateral Restraint Block - Pier 1 - 02 |  | Lateral Restraint Block - Pier 1 - 02 |  | 102-0067
| MRP-102-C-AUR-DRG-30-CSP-CBR | Restraint Block | 102-0068 - Lateral Restraint Block - North Abutment -01 |  | Lateral Restraint Block - North Abutment -01 |  | 102-0068
| MRP-102-C-AUR-DRG-30-CSP-CBR | Restraint Block | 102-0069 - Lateral Restraint Block - Pier 2 - 02 |  | Lateral Restraint Block - Pier 2 - 02 |  | 102-0069
| MRP-102-C-AUR-DRG-30-CSP-CBR | Bearing Pedestals | 102-0070 - Bearing Pedestals - South Abutment - AB1B1S1-1 to AB1B1S1-9 |  | Bearing Pedestals - South Abutment - AB1B1S1-1 to AB1B1S1-9 |  | 102-0070
| MRP-102-C-AUR-DRG-30-CSP-CBR | Bearing Pedestals | 102-0071 - Bearing Pedestals - Pier 1 - P1B1S1-1 - P1B1S1-9 |  | Bearing Pedestals - Pier 1 - P1B1S1-1 - P1B1S1-9 |  | 102-0071
| MRP-102-C-AUR-DRG-30-CSP-CBR | Bearing Pedestals | 102-0072 - Bearing Pedestals - Pier 1 - P1B1S2-1 - P1B1S2-9 |  | Bearing Pedestals - Pier 1 - P1B1S2-1 - P1B1S2-9 |  | 102-0072
| MRP-102-C-AUR-DRG-30-CSP-CBR | Bearing Pedestals | 102-0073 - Bearing Pedestals - North Abutment - AB2B1S3-1 to AB2B1S3-9 |  | Bearing Pedestals - North Abutment - AB2B1S3-1 to AB2B1S3-9 |  | 102-0073
| MRP-102-C-AUR-DRG-30-CSP-CBR | Bearing Pedestals | 102-0074 - Bearing Pedestals - Pier 2 - P2B1S2-1 - P2B1S2-9 |  | Bearing Pedestals - Pier 2 - P2B1S2-1 - P2B1S2-9 |  | 102-0074
| MRP-102-C-AUR-DRG-30-CSP-CBR | Bearing Pedestals | 102-0075 - Bearing Pedestals - Pier 2 - P2B1S3-1 - P2B1S3-9 |  | Bearing Pedestals - Pier 2 - P2B1S3-1 - P2B1S3-9 |  | 102-0075
| MRP-102-C-AUR-DRG-30-CSP-CBR | Deflection wall | 102-0372 - Deflection wall - Pier 1 |  | Deflection wall - Pier 1 |  | 102-0372
| MRP-102-C-AUR-DRG-30-CSP-CBR | Deflection wall | 102-0373 - Deflection wall - Pier 2 |  | Deflection wall - Pier 2 |  | 102-0373
| MRP-102-C-AUR-DRG-30-CSP-CBR | Deflection wall | 102-0374 - Pile Cap - deflection wall - Pier 1 |  | Pile Cap - deflection wall - Pier 1 |  | 102-0374
| MRP-102-C-AUR-DRG-30-CSP-CBR | Deflection wall | 102-0375 - Pile Cap - deflection wall - Pier 2 |  | Pile Cap - deflection wall - Pier 2 |  | 102-0375
| MRP-102-C-AUR-DRG-35-CSP-CBR | Retaining wall | 102-0376 - Reatining wall 1 - North West |  | Reatining wall 1 - North West |  | 102-0376
| MRP-102-C-AUR-DRG-35-CSP-CBR | Retaining wall | 102-0377 - Reatining wall 2 - North East |  | Reatining wall 2 - North East |  | 102-0377
| MRP-102-C-AUR-DRG-35-CSP-CBR | Retaining wall | 102-0378 - Reatining wall 3 - South West |  | Reatining wall 3 - South West |  | 102-0378
| MRP-102-C-AUR-DRG-35-CSP-CBR | Retaining wall | 102-0379 - Reatining wall 4 - South East |  | Reatining wall 4 - South East |  | 102-0379
| MRP-102-C-AUR-DRG-31-CSP-CBR | North Abutment | 102-0076 - Approach Slab - North Abutment |  | Approach Slab - North Abutment |  | 102-0076
| MRP-102-C-AUR-DRG-31-CSP-CBR | North Abutment | 102-0077 - Expansion Joint - North Abutment |  | Expansion Joint - North Abutment |  | 102-0077 | 77
| MRP-102-C-AUR-DRG-31-CSP-CBR | Pier 1 | 102-0078 - Deck slab - Pier 1 |  | Deck slab - Pier 1 |  | 102-0078
| MRP-102-C-AUR-DRG-31-CSP-CBR | Pier 2 | 102-0079 - Deck slab - Pier 2 |  | Deck slab - Pier 2 |  | 102-0079
| MRP-102-C-AUR-DRG-31-CSP-CBR | Span 1 | 102-0080 - Deck pour - S1 |  | Deck pour - S1 |  | 102-0080
| MRP-102-C-AUR-DRG-31-CSP-CBR | Span 2 | 102-0081 - Deck pour - S2 |  | Deck pour - S2 |  | 102-0081
| MRP-102-C-AUR-DRG-31-CSP-CBR | Span 3 | 102-0082 - Deck pour - S3 |  | Deck pour - S3 |  | 102-0082
| MRP-102-C-AUR-DRG-31-CSP-CBR | South Abutment | 102-0083 - Approach Slab - South Abutment |  | Approach Slab - South Abutment |  | 102-0083
| MRP-102-C-AUR-DRG-31-CSP-CBR | South Abutment | 102-0084 - Expansion Joint - South Abutment |  | Expansion Joint - South Abutment |  | 102-0084
| MRP-102-C-AUR-DRG-31-CSP-CBR | Girder | 102-0085 - Precast Super-T Girder - B1S1 to B9S1 |  | Precast Super-T Girder - B1S1 to B9S1 |  | 102-0085
| MRP-102-C-AUR-DRG-31-CSP-CBR | Girder | 102-0086 - Precast Super-T Girder - B1S2 to B9S2 |  | Precast Super-T Girder - B1S2 to B9S2 |  | 102-0086
| MRP-102-C-AUR-DRG-31-CSP-CBR | Girder | 102-0087 - Precast Super-T Girder - B1S3 to B9S3 |  | Precast Super-T Girder - B1S3 to B9S3 |  | 102-0087
| MRP-102-C-AUR-DRG-31-CSP-CBR | West Edge Parapets | 102-0088 - On Structure Parapet - PPB01-SB01 to PPB01-SB04 - West Edge |  | On Structure Parapet - PPB01-SB01 to PPB01-SB04 - West Edge |  | 102-0088
| MRP-102-C-AUR-DRG-31-CSP-CBR | East Edge Barriers | 102-0089 - On Structure Barrier - MPB02-SB01 to MPB02-SB08 - East Edge |  | On Structure Barrier - MPB02-SB01 to MPB02-SB08 - East Edge |  | 102-0089
| MRP-102-C-AUR-DRG-31-CSP-CBR | Median Barriers | 102-0090 - On Structure Barrier - MPB01-SB01 to MPB01-SB04 - Centre Median |  | On Structure Barrier - MPB01-SB01 to MPB01-SB04 - Centre Median |  | 102-0090
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0380 - Off Structure -Barrier Footing - Type 1 - East Edge - South |  | Off Structure -Barrier Footing - Type 1 - East Edge - South |  | 102-0380
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0381 - Off Structure -Barrier Footing - Type 1 - East Edge - North |  | Off Structure -Barrier Footing - Type 1 - East Edge - North |  | 102-0381
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0382 - Off Structure -Barrier Footing - Type 2 - East Edge - North |  | Off Structure -Barrier Footing - Type 2 - East Edge - North |  | 102-0382
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0383 - Off Structure -Barrier Footing - Type 2 - East Edge - South |  | Off Structure -Barrier Footing - Type 2 - East Edge - South |  | 102-0383
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0384 - Off Structure -Barrier Footing - Type 3 - East Edge - North |  | Off Structure -Barrier Footing - Type 3 - East Edge - North |  | 102-0384
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0385 - Off Structure -Barrier Footing - Type 3 - East Edge - South |  | Off Structure -Barrier Footing - Type 3 - East Edge - South |  | 102-0385
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0386 - Off Structure -Barrier Footing - Type 4 - West Edge - North |  | Off Structure -Barrier Footing - Type 4 - West Edge - North |  | 102-0386
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0387 - Off Structure -Barrier Footing - Type 4 - West Edge - South |  | Off Structure -Barrier Footing - Type 4 - West Edge - South |  | 102-0387
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0388 - Off Structure -Barrier Footing - Type 5 - West Edge - South |  | Off Structure -Barrier Footing - Type 5 - West Edge - South |  | 102-0388
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0389 - Off Structure -Barrier Footing - Type 5 - West Edge - North |  | Off Structure -Barrier Footing - Type 5 - West Edge - North |  | 102-0389
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0390 - Off Structure -Barrier Footing - Type 6 - West Edge - North |  | Off Structure -Barrier Footing - Type 6 - West Edge - North |  | 102-0390
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0391 - Off Structure -Barrier Footing - Type 5B - West Edge - South |  | Off Structure -Barrier Footing - Type 5B - West Edge - South |  | 102-0391
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0392 - Off Structure -Barrier Footing - Type 2A - West Edge - North |  | Off Structure -Barrier Footing - Type 2A - West Edge - North |  | 102-0392
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0393 - Off Structure -Barrier Footing - Type 2A - West Edge - South |  | Off Structure -Barrier Footing - Type 2A - West Edge - South |  | 102-0393
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0394 - Off Structure -Barrier Footing - Type 2B - West Edge - South |  | Off Structure -Barrier Footing - Type 2B - West Edge - South |  | 102-0394
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0395 - Off Structure -Barrier Footing - Type 2B - West Edge - North |  | Off Structure -Barrier Footing - Type 2B - West Edge - North |  | 102-0395
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0396 - Off Structure -Barrier Footing - Type 3A - West Edge - North |  | Off Structure -Barrier Footing - Type 3A - West Edge - North |  | 102-0396
| MRP-102-C-AUR-DRG-32-CSP-CBR | Off Structure | 102-0397 - Off Structure -Barrier Footing - Type 3A - West Edge - South |  | Off Structure -Barrier Footing - Type 3A - West Edge - South |  | 102-0397
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0398 - Off-Structure - Anti-Throw/Balustrade Type 1 - West Edge - North |  | Off-Structure - Anti-Throw/Balustrade Type 1 - West Edge - North |  | 102-0398
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0399 - Off-Structure - Anti-Throw/Balustrade Type 1A - West Edge - North |  | Off-Structure - Anti-Throw/Balustrade Type 1A - West Edge - North |  | 102-0399
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0400 - On-Structure - Anti-Throw/Balustrade Type 2 - West Edge |  | On-Structure - Anti-Throw/Balustrade Type 2 - West Edge |  | 102-0400
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0401 - Off-Structure - Anti-Throw/Balustrade Type 2 - West Edge - North |  | Off-Structure - Anti-Throw/Balustrade Type 2 - West Edge - North |  | 102-0401
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0402 - Off-Structure - Anti-Throw/Balustrade Type 2 - West Edge - South |  | Off-Structure - Anti-Throw/Balustrade Type 2 - West Edge - South |  | 102-0402
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0403 - On-Structure - Anti-Throw/Balustrade Type 3 - West Edge |  | On-Structure - Anti-Throw/Balustrade Type 3 - West Edge |  | 102-0403
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0404 - On-Structure - Anti-Throw/Balustrade Type 4 - East Edge |  | On-Structure - Anti-Throw/Balustrade Type 4 - East Edge |  | 102-0404
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0405 - On-Structure - Anti-Throw/Balustrade Type 5 - East Edge |  | On-Structure - Anti-Throw/Balustrade Type 5 - East Edge |  | 102-0405
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0406 - Off-Structure - Anti-Throw/Balustrade Type 5 - West Edge - North |  | Off-Structure - Anti-Throw/Balustrade Type 5 - West Edge - North |  | 102-0406
| MRP-102-C-AUR-DRG-32-CSP-CBR | Balustrade and Anti-Throw Screens | 102-0407 - Off-Structure - Anti-Throw/Balustrade Type 5 - West Edge - South |  | Off-Structure - Anti-Throw/Balustrade Type 5 - West Edge - South |  | 102-0407
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0408 - SUP - Platform pour 1 |  | SUP - Platform pour 1 |  | 102-0408
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0409 - SUP - Platform pour 2 |  | SUP - Platform pour 2 |  | 102-0409
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0410 - SUP - Platform pour 3 |  | SUP - Platform pour 3 |  | 102-0410
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0411 - SUP - Platform pour 4 |  | SUP - Platform pour 4 |  | 102-0411
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0412 - SUP - Platform pour 5 |  | SUP - Platform pour 5 |  | 102-0412
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0413 - SUP - Platform pour 6 |  | SUP - Platform pour 6 |  | 102-0413
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0414 - SUP - Platform pour 7 |  | SUP - Platform pour 7 |  | 102-0414
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0415 - SUP - Platform pour 8 |  | SUP - Platform pour 8 |  | 102-0415
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0416 - SUP - Platform pour 9 |  | SUP - Platform pour 9 |  | 102-0416
| MRP-102-C-AUR-DRG-32-CSP-CBR | SUP | 102-0417 - SUP - Platform pour 10 |  | SUP - Platform pour 10 |  | 102-0417
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0418 - Material inspection precast parapets 1 |  | Material inspection precast parapets 1 |  | 102-0418
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0419 - Material inspection precast parapets 2 |  | Material inspection precast parapets 2 |  | 102-0419
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0420 - Material inspection precast parapets 3 |  | Material inspection precast parapets 3 |  | 102-0420
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0421 - Material inspection precast parapets 4 |  | Material inspection precast parapets 4 |  | 102-0421
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0422 - Material inspection precast parapets 5 |  | Material inspection precast parapets 5 |  | 102-0422
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0423 - Material inspection precast Barriers 1 |  | Material inspection precast Barriers 1 |  | 102-0423
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0424 - Material inspection precast Barriers 2 |  | Material inspection precast Barriers 2 |  | 102-0424
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0425 - Material inspection precast Barriers 3 |  | Material inspection precast Barriers 3 |  | 102-0425
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0426 - Material inspection precast Barriers 4 |  | Material inspection precast Barriers 4 |  | 102-0426
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0427 - Material inspection precast Barriers 5 |  | Material inspection precast Barriers 5 |  | 102-0427
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0428 - Material inspection precast Barriers 6 |  | Material inspection precast Barriers 6 |  | 102-0428
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0429 - Material inspection T Beams 1 |  | Material inspection T Beams 1 |  | 102-0429
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0430 - Material inspection T Beams 2 |  | Material inspection T Beams 2 |  | 102-0430
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0431 - Material inspection T Beams 3 |  | Material inspection T Beams 3 |  | 102-0431
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0432 - Material inspection T Beams 4 |  | Material inspection T Beams 4 |  | 102-0432
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0433 - Material inspection T Beams 5 |  | Material inspection T Beams 5 |  | 102-0433
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0434 - Material inspection L Walls 1 |  | Material inspection L Walls 1 |  | 102-0434
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0435 - Material inspection L Walls 2 |  | Material inspection L Walls 2 |  | 102-0435
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0436 - Material inspection L Walls 3 |  | Material inspection L Walls 3 |  | 102-0436
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0437 - Material inspection L Walls 4 |  | Material inspection L Walls 4 |  | 102-0437
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0438 - Material inspection L Walls 5 |  | Material inspection L Walls 5 |  | 102-0438
| MRP-102-C-AUR-DRG-31-CSP-CBR | Material Inspection | 102-0439 - Material inspection L Walls 6 |  | Material inspection L Walls 6 |  | 102-0439