## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
a4138663-421c-45f1-bbf9-a563732e8f12 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 001 - NW BESS pad - Cut & Fill | Layer 1 | RR-SEPD-BESS-FIC-004-01 - Proof roll
f6296851-66d5-41ae-aba9-bcb330c256c3 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 001 - NW BESS pad - Cut & Fill | Layer 2 | RR-SEPD-BESS-FIC-004-01 - Proof roll
ba358fc9-9d9f-42f3-906c-4a7e52e85508 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 001 - NW BESS pad - Cut & Fill | Layer 3 | RR-SEPD-BESS-FIC-004-01 - Proof roll
0f82abc0-ad29-4816-88ad-75c7faeb78b4 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 002 - SE Contaminated material access gate 2 | RR-SEPD-BESS-FIC-004-01 - Proof roll
d3234b63-67a7-49cb-9d17-49d7cf2cff27 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 003 - East BESS pad - Cut & Fill | RR-SEPD-BESS-FIC-004-01 - Proof roll
3c709b47-bcbc-48f8-b5ac-6eb84007d0bf |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 004 - WRW Permeable Sand Backfill T1 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 2 - RL 48.850
90d570bd-8c65-4273-88b9-c683ec9d8084 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 004 - WRW Permeable Sand Backfill T1 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 3 - RL 49.150
2bc17ef7-00bd-43a4-bec6-332fbe52e4f9 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 004 - WRW Permeable Sand Backfill T1 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 4 - RL 49.350
b017314d-5ab0-4f5c-803d-2988919d1744 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 004 - WRW Permeable Sand Backfill T1 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 5 - RL 49.650
1a3a8ce9-96ad-4013-b0fc-32b6f441e938 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 005 - WRW Clayey Backfill T1 | ROBAR FIC ¦ Clay ¦ Proof roll Layer 1 - RL 48.550
067da14e-29b7-4e0c-b82c-7d5a3c473d90 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 2 - RL 49.950
fd1aa9e9-3816-4835-b2e3-05166749829a |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 3 - RL 50.250
b568bb64-e5f8-4b33-92bb-bef3f244433c |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 4 - RL 50.550
305b71a3-5ece-48be-b3e2-ea3ad1cc2812 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 5 - RL 50.850
78948018-63ad-4fb5-b89b-3b4a32cc9a91 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 6 - RL 51.150
b9316923-e47f-4d5a-ba2d-00823006965e |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 7 - RL 51.450
1daea11d-d768-4def-a85c-12df64a03b57 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 8 - RL 51.750
4778be2f-549b-4657-9420-ef8403e3b408 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 9 - RL 52.050
39c21d6b-94f6-4185-8f18-55192b84af61 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 10 - RL 52.350
5c6bdf32-c4e1-4182-886b-d34add2d0764 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 11 - RL 52.650
bb146d2c-8077-45d7-84a0-55bd01ed2705 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 12 - RL 52.950
5d71fb5e-baac-4e75-8bc3-912734885551 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Sand ¦ Proof roll Layer 13 - RL 53.250
d20d1a74-93c0-4c3d-9714-160ad1b9e0f6 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 1 - RL 49.650
1255937a-e4e6-4767-a50c-6eb125c6121f |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 2 - RL 49.950
3c3d3fc2-5ccc-4f8a-87f6-3f5c67b97c18 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 3 - RL 50.250
b65e9f43-ee7c-403b-b7b5-42350f60dcfa |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 4 - RL 50.550
77552da5-5c00-4c5a-87f4-e22b925972c0 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 5 - RL 50.850
a4fc4053-378d-4029-9471-455725205dbe |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 6 - RL 51.150
5860dcea-ea4e-4ac3-91f0-5754081238b0 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 7 - RL 51.450
4a79afd5-1f3e-4be8-8822-6dd50c1932b1 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 8 - RL 51.750
548bc193-6898-4e8b-80cb-147ec7562491 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 9 - RL 52.050
64b894dd-1d24-4e1f-b9db-0bd6a7a056aa |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 10 - RL 52.350
e555c30f-d180-4cd4-bbe2-808d4eafb7f2 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 11 - RL 52.650
0f499a31-4c7c-4f1f-b170-f2d9b3cc5e8c |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 12 - RL 52.950
08a109da-7917-4312-9f4c-70e6492f6d0f |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof roll Layer 13 - RL 53.250
d0bca7ea-b7f9-479e-83b5-96fd6d402ace |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Subgrade
be591e53-2559-4ceb-a72a-19c997501395 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 1 - RL 51.450
2bbafe1c-65ba-463e-ba6e-b2aebaf299d6 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 2 - RL 51.750
d5ae6c3d-3d91-44f7-b736-0b802f9cd711 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 3 - RL 52.050
62ad9573-d822-42b2-8af7-7052f083ad1f |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 4 - RL 52.350
e936e614-0123-4bb4-9159-e77842e9002d |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 5 - RL 52.650
550af0b5-4722-4dad-9439-36f5f6422577 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 6 - RL 52.950
177c26ee-d0f5-496c-a95d-0a439c91d6ee |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 7 - RL 53.250
d2931765-762e-4851-acfd-57de74928b00 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 8 - RL 53.550
c67ecb2a-7bcd-4a24-921b-1bdc86719286 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 9 - RL 53.850
b94971cf-7fb9-43c8-9c4e-f2c645ab8bbf |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 10 - RL 54.150
72788be4-2957-4d9d-8fcc-667f037dd23b |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 10 - Subgrade
b78b6f2f-b136-4e3d-9969-fd7864ba082e |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 11 - RL 54.450
74251ba4-1d7b-438e-a44a-f37d9bdba5ba |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 12 - RL 54.750
17284397-9af3-468b-8109-ef2b4abe0967 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 13 - RL 55.050
dec3f490-af71-45ff-858e-b3fbc17efb0c |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 13 - RL 55.050 Switchroom Subgrade
49bb78a5-845f-4f67-8c72-fea4f9d43ccc |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 14 - RL 55.350
b2a1b43a-22f3-4ec0-aa94-c556c882a432 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 15 - RL 55.650
0b0a03f9-5a8e-4397-aa8c-626dde529f56 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 16 - RL 55.835
3720678c-0ad2-45a8-878f-fad0ed2360ee |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 009 - Bay 8 to Bay 10 backfill | Proof Rolls | ROBAR FIC ¦ Proof Roll Subgrade
a3b828f3-1459-47da-b26a-23b24f2975d7 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 009 - Bay 8 to Bay 10 backfill | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 1 - RL
44a926e6-726e-4afb-a719-4f41f2a135c4 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 009 - Bay 8 to Bay 10 backfill | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 2 - RL
ef9d20bd-f3e2-4707-acb2-b9784638ba9f |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 009 - Bay 8 to Bay 10 backfill | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 3 - RL
0c81977e-8b8b-4eed-927b-81386060f27d |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 009 - Bay 8 to Bay 10 backfill | Proof Rolls | ROBAR FIC ¦ Clay ¦ Proof Roll Layer 4 - RL
eb52aaab-3e91-4f31-9b7e-2ab8efd381dd |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 13 | RR-SEPD-BESS-FIC-004-01 - Proof roll
7957ed38-069a-4ae7-959a-96727bbcce55 |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 14 | RR-SEPD-BESS-FIC-004-01 - Proof roll
4a30dd91-0add-41a8-b29b-f3c25e2452ba |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 15 | RR-SEPD-BESS-FIC-004-01 - Proof roll
3796fe4e-a847-4074-8bc9-9a995fc04cef |  | pass | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 16 | RR-SEPD-BESS-FIC-004-01 - Proof roll
9b769919-98fc-4a2a-8413-77b1c2aca471 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 4 | RR-SEPD-BESS-FIC-004-01 - Proof roll
a9c9a9c9-dae5-4868-9669-31865ff0b649 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 10 | RR-SEPD-BESS-FIC-004-01 - Proof roll
7baab7b6-fcc6-495c-b281-357ed74c0228 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 11 | RR-SEPD-BESS-FIC-004-01 - Proof roll
cb3007ec-e5e4-4f5f-8d0a-ba94401e0bb9 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Switchroom | RR-SEPD-BESS-FIC-004-01 - Proof roll - Subgrade
fd1ef57c-fae0-4230-8c0b-9f6a82f5cd9d |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A0 to A1)
9f9ba635-39fe-489b-a782-577a67eafb82 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A1 to A2)
abe68bbb-f2e2-41a4-928c-548d9bb2fc36 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A2 to A3)
04f8029e-4bf5-4261-b7e5-10bc11b8ce6a |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A3 to A4)
ffc0b74d-427f-4846-823d-013734e76c62 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A4 to A5)
e7633d96-a7f4-44d5-97b8-78dd28dd94b0 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A5 to A6)
88983ada-5698-41c9-a108-766998f48c69 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A6 to A7)
2dad31c2-c34e-4d2e-b173-e86ff6e6bf7b |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A7 to A8)
1cf5cbce-cf92-4590-ba90-2a0a56d9d30a |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A8 to A9)
57ecda81-8cc2-4ae4-a059-ea4bac8b02ca |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A9 to A10)
204cc1ce-851e-4636-ad4b-9fccc59ec387 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A10 to A11)
f4a3b8a3-e16b-4969-8b7f-1c2d5449f098 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A11 to A12)
dd7d14f8-323d-434a-ab1f-31528f1dacba |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A12 to A13)
5c7975c3-1afd-45d5-9b37-bb028831add3 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A13 to A14)
7921418b-64c9-4196-b115-43c8a55f0cad |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 001 - "A" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (A14 to Existing-1)
ec8a2b8c-d7b3-48e9-b585-31a8c8c8ced0 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 002 - "B" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (B0 to B1)
9b788cf9-7fce-4238-8732-f46db31a673e |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 002 - "B" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (B1 to B2)
fe9b5618-6e8f-44a3-9053-8ad1b77a33cd |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 002 - "B" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (B2 to B3)
df168fe7-7d31-4d72-9bc4-16f1b9762875 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 002 - "B" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (B3 to A9)
c278b955-e73a-4b78-a649-b3ee1ac2a9d2 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 003 - "C" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (C0 to C1)
facb43da-4c92-4222-bf2a-829c8bda4373 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 003 - "C" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (C1 to C2)
f35aa223-a14d-43a9-89de-c0733e7ec872 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 003 - "C" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (C2 to C3)
60a30783-5af8-407d-883f-c13148076c46 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 003 - "C" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (C3 to C4)
db48d3ee-cc12-4438-a455-b8780819b235 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 003 - "C" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (C4 to A14)
6e2b21e4-cb27-46bb-beaa-8ad8bf796b19 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 004 - "D" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (D1 to D2)
ecaa03fd-e142-4e0c-8dc3-67306c428da0 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 004 - "D" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (D2 to A5)
76cbb359-3831-44fb-b2d8-e1aea5d25a5c |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 005 - "E" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (E0 to E1)
09653489-671b-47ae-944e-0d70d7c22267 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 005 - "E" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (E1 to E2)
75453405-45ac-49ac-9b2f-156b11fa53b4 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 005 - "E" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (E2 to A6)
7982dc04-b2c6-49d9-a24e-cc8773ac6460 |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 006 - "F" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (F1 to F2)
74a87f4b-c023-46d0-85de-29cd78c9be7f |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 006 - "F" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (F2 to A7)
716070f4-8ea7-4b5e-a379-46de76c6c5da |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 007 - "G" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (G0 to G1)
d7ae88b8-b4d2-4aef-8d38-118c3c9650be |  | work-in-progress | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 007 - "G" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (G1 to G2)
9cb0d42d-c9d9-4917-be00-430ce66175a0 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 007 - "G" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (G2 to A8)
c0d6064d-ae7c-4e9a-8ec8-803f4f6af51a |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 008 - "H" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (H1 to H2)
929c8c7e-c76f-440e-ac3f-22d57d7ce8d5 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 008 - "H" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (H2 to A10)
f013dded-357c-4756-a2ee-f47a9d6b5d16 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 009 - "I" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (I1 to I2)
23c8e939-46fc-4971-be16-9210153af183 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 009 - "I" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (I2 to A11)
a0bdebfb-95db-45e0-a959-aaae4a6079de |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 010 - "J" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (J1 to J2)
d52f88eb-2af9-4ef7-ae8c-021fd916d6ea |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 010 - "J" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (J2 to A12)
4bee2f9f-e916-4239-9cd3-b5baef3cee87 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 011 - "K" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (K1 to K2)
889475a9-7e88-4f3f-b2c7-1a0228339c19 |  | not-started | RR-SEPD-BESS-FIC-004-01 - Proof roll | checklist | FALSE | FALSE | Drainage | Lot 011 - "K" Drainage line | Subgrade & Proof Rolls | ROBAR FIC ¦ Subgrade ¦ Proof roll (K2 to A13)