## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
a2598102-a6c1-4c50-8cbd-b03844619b65 |  | work-in-progress | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 001 - NW BESS pad - Cut & Fill | RR-SEPD-BESS-ITP-001-01 - Earthworks
91d1112c-6ee1-4183-9421-b452b22e2731 |  | work-in-progress | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 002 - SE Contaminated material access gate 2 | RR-SEPD-BESS-ITP-001-01 - Earthworks
8664bca8-14a1-4897-86f6-f902aa0e0300 |  | work-in-progress | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 003 - East BESS pad - Cut & Fill | RR-SEPD-BESS-ITP-001-01 - Earthworks
4af9d7c8-fd08-4833-9a0f-236ba69e65e4 |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 004 - WRW Permeable Sand Backfill T1 | RR-SEPD-BESS-ITP-001-01 - Earthworks
ceae291b-b03b-41dc-9837-8bd13c3c5f02 |  | pass | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 005 - WRW Clayey Backfill T1 | RR-SEPD-BESS-ITP-001-01 - Earthworks
f5b83c5a-d2b7-477d-86a4-a7a6bb18d02f |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 006 - WRW Permeable Sand Backfill T1+T2 | RR-SEPD-BESS-ITP-001-01 - Earthworks
c13770ed-d1c6-496f-8c85-7fe5219a0695 |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 007 - WRW Clayey Fill Backfill T1+T2 | RR-SEPD-BESS-ITP-001-01 - Earthworks
7c03cba3-5018-4bde-8fc6-b962e76b7345 |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Bulk Earthworks | Lot 008 - SRW Clayey Backfill (SB-11 to SB-14) | RR-SEPD-BESS-ITP-001-01 - Earthworks
3807e3db-c36e-4e33-8971-dbe5583bf735 |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 4 | RR-SEPD-BESS-ITP-001-01 - Earthworks
c1739d95-35f6-42a1-a217-f01c91d621fa |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 10 | RR-SEPD-BESS-ITP-001-01 - Earthworks
efd72d16-fa26-480d-8893-5f7a317900a7 |  | not-started | RR-SEPD-BESS-ITP-001-01 - Earthworks | checklist | FALSE | FALSE | Earthworks | Electrical Trenching | Bay 11 | RR-SEPD-BESS-ITP-001-01 - Earthworks