## ITP-01
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [8 empty] | Document # FHC-8B4000-ITP-050
[12 empty] | Revision : 01 | Date : 07/12/2022
Client: |  | Yarra Trams - ZALEP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  |  | Approved by :
Project: |  | New Preston Depot - Maintenance Shed |  | Structural Steel Installation |  | Name: | Aaron Hatch | Name: | Charles Bate |  |  | Name: | Damon Bromwich
Contract No: |  |  |  | Specifications: AS/NZS5131, Contract Drawing Specifications
Project No: |  | 8B4000 |  | Structure / Component: |  | Signed : |  | Signed : |  |  |  | Signed :
|  |  |  | Location (Include Map): |  | Date : | 2022-12-07 | Date : | 2022-12-07 |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Building Surveyor | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer JSME | N/A | N/A
1.3 | Base Plate Grout or Mortar |  | Once, for each product, prior to placement of product | Product to be selected based on the following criteria: i. either a single component, self consolidating and dual shrinkage compensating cementitious grout ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum iii. have a flowable consistency iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also) v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings | IFC Drawings | Document Review | This ITP Signed | IP | Fulton Hogan Engineer |  | N/A
2 | Installation Activities
2.1 | Material Inspection |  | Each Component | General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used. Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. | IFC Drawings AS4860 Clause 7 AS2312 Clause 9.6.4 (i) AS4506 Clause 2.3 | Measure Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.2 | Structural Steel Handling |  | Each component | The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings. | Contract Drawings AS4100 Clause 15.2.2 & 3 AS5131 Clause 11.5.6 | Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.3 | Structural Steel Erection |  | Each component | Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia | AS4100 Clause 15.2.3 AS5131 Clause 11.5.7 | Measure Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.4 | Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S) |  | Where applicable, each bolted connection | Place bolts, washers and nuts as detailed on the IFC Drawings. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | AS4100 Clause 14.3.5.2 AS5131 Clause 6.7.4 AS4100 Clause 15.2.5.2 (a) AS5131 Clause 8.3 | Measure Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.5 | Survey Conformance |  | Each element | Grouting of base plates shall not commence until verification that the Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, -5mm | IFC Drawings AS4100 Clause 15.3.1 - 7 AS5131 Appendix F, Table F3 | Measure Visual | This ITP signed | HP* | Fulton Hogan Engineer |  | N/A
2.6 | Base Plate Formwork Construction & Placement |  | Each Column Location | Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks. | IFC Drawings | Measure Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.7 | Pre-soaking Concrete Surface |  | Each Column Location | Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS. Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower. | Product TDS | Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.8 | Mixing Product |  | Each batch | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record. | Product TDS | Measure Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.9 | Placement & Compaction |  | Each Column Location | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Required information on the Grout Pour Record | Product TDS | Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
2.1 | Surface Finishes & Protection of Works |  | Where applicable | If shaping of the unformed surface is required, shape prior to the product fully hardening. All freshly finished surfaces shall be protected where required from the sun, wind or rain. If applicable, implement curing measures as per product TDS | IFC Drawings Product TDS | Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
3 | Post-Installation Activities
3.1 | Inspection of Coating |  | Each component | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure. | IFC Drawings AS4680 Clause 8.3 & 8.4 AS4506 Appendix E | Visual | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A
3.2 | As-built Survey |  | Each component | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Attach: Survey As-builts / Survey Report | IFC Drawings AS5131 Appendix F, Table F3 | Visual | As-Built Drawing | IP | Fulton Hogan Engineer | N/A | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent