## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing | [5 empty] | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing
section | 1.0 Pre-start activities
checkpoint | 1.1 - Define Lot
note | Ref docs - 1200.15 (b) (i) (B)
note | Acceptance criteria - Clearly mark out lot and extents.
note | • All No-Go Zones must be protected by temporary fencing and signage visible.
note | • All fencing of No-Go Zones must be:
note | a. erected a minimum of 1 metre beyond the boundary of the habitat to be protected, at the Tree Protection Zone or as directed by the Superintendent;
note | b. at minimum, constructed of star picket and paraweb with two wire supports. The star pickets must be 1.3m in height, installed to a height of 1m above ground level and the paraweb must be installed to ensure a minimum 30cm gap is available between the bottom of the fence and existing ground to allow for fauna movement;
note | c. communicated by signage installed on the temporary fencing at intervals no less than 10 metres apart stating ‘Environmental No-Go Zone – no unauthorised access’;
note | d. installed prior to commencement of works in the immediate area, in accordance with the relevant approved SEP; and
note | e. retained in place for the duration of construction activities.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Prior to start of works
note | Key - R
note | Resp - SE
checkpoint | 1.2 - Works required inside a No-Go Zone
note | Ref docs - 1200.15 (b) (i) (B)
note | Acceptance criteria - No works are to occur inside any No-Go Zones, except for where the following process is followed:
note | • Before commencement, where works have potential to impact flora and fauna protected by a No Go Zone, the Superintendent has been provided a report to the requirements of 1200.15 (b) (i) (B) for approval 5 days before the proposed Delivery Activities and it has been approved by the Superintendent.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Prior to start of works
note | Key - H
note | Resp - SE
checkpoint | 1.3 - MRPV Vegetation Removal Permit
note | Ref docs - Vegetation Removal Permit / PS3020.07 (a) (ii)
note | Acceptance criteria - Sign off by the Project and MRPV Environmental Representatives. This is to be reviewed by the Superintendent prior to removal and provided to Environmental team
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Prior to start of works
note | Key - H
note | Resp - SE
note | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Design Documents Required
note | Ref docs - 1170.11
note | Acceptance criteria - For site clearing and grubbing, the documents needed are:
note | (1) marked up drawings that relate to the design Documents and clearly define the scope of the Enabling Works;
note | (2) any relevant Construction Specification for the Enabling Works.
note | (3) a drawing showing environmental approval boundaries, activity areas and no-go zones.
note | (4) evidence that any required design related Approvals have been obtained; and
note | (5) a list of all required Approvals.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Prior to start of works
note | Key - R
note | Resp - SE
checkpoint | 1.5 - Site Environmental Protection Plan
note | Acceptance criteria - Site Environmental Protection Plans and Site Erosion Control Plans have been reviewed and approved for works.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Prior to start of works
note | Key - R
note | Resp - ENV REP
section | 2.0 Pre-Clearing activities
checkpoint | 2.1 - Pre-Clearing Identification
note | Ref docs - 1200.15 (b)(i)(C)
note | Acceptance criteria - No less than 7 days prior clearing, an ecologist has certified that all habitat trees are clearly identified and marked with flagging tape or survey, consistent with the Design Documents and permits and approvals.
note | • Any salvageable timber suitable for reuse to be identified and marked for stockpiling, for it to be reused after clearing.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - 7 days prior to proposed clearing
note | Key - H
note | Resp - SE
checkpoint | 2.2 - On-site inspection
note | Ref docs - 1200.15 (b)(i)(C) (4)
note | Acceptance criteria - Prior to removal of vegetation, site inspection to be arranged with the Superintendent and other authorities to confirm the requirements of Sections 1200.15(b)(i)(C)(1) and 1200.15(b)(i)(C)(2) have been achieved.
note | • All Approvals are in place and the ecologist is always on site, ready to perform further inspections in accordance with Sections 1200.15(b)(i)(C)(3) and 200.15(b)(i)(C)(5).
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Prior to clearing
note | Key - H
note | Resp - SE
note | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Onsite Clearing and Grubbing
checkpoint | 3.1 - Clearing
note | Ref docs - VR201.04 1200.15 (b)(i)(C) (5)
note | Acceptance criteria - Only non-habitat trees can be removed during the first stage of clearing. Habitat trees can then be removed after approvals have been received and a minimum of 24 hours after the removal of non-habitat trees.
note | • Prior to commencing of clearing each day, the ecologist appointed should inspect the area for signs of wildlife.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each lot
note | Key - H
note | Resp - SE
checkpoint | 3.2 - Grubbing
note | Ref docs - VR201.05
note | Acceptance criteria - In areas where excavation will be undertaken, all vegetation shall be grubbed as per the requirements of VR 201.05 and early works – subgrade improvement design package
note | • Holes resulting from grubbing shall be backfilled with similar material and compacted to same degree as surrounding material.
note | Freq - Each Lot
note | Key - R
note | Resp - SE
checkpoint | 3.3 - Clearing at Culvert Sites
note | Ref docs - VR201.06
note | Acceptance criteria - Any trees or stumps with 10m of any portion of a proposed culvert having a waterway area greater than 6m^2 shall be cleared and grubbed in accordance with the requirements of VR201.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each lot
note | Key - R
note | Resp - SE
checkpoint | 3.4 - Flora and fauna handling and removal
note | Ref docs - 1200.15 (b)(i)(F)
note | Acceptance criteria - The Superintendent must be notified if any significant flora and fauna is found, and an ecologist must identify and provide advice on what to do with the found flora or fauna.
note | • The Superintendent must notify Environmental representative of any flora and fauna found.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each lot
note | Key - I
note | Resp - SE
checkpoint | 3.5 - Identified habitat
note | Ref docs - VR201.10 1200.15
note | Acceptance criteria - Trees with hollows can only be removed during initial clearing, if hollow is occupied, the section is to be left and cut after clearance from the ecologist and a minimum of 24 hours after removal of non-habitat trees in the area.
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each lot
note | Key - I
note | Resp - SE
checkpoint | 3.6 - Reuse of Material
note | Ref docs - 1200.15 (b)(i)(G)
note | Acceptance criteria - Seek and adopt where practical reuse opportunities for vegetation felled during the vegetation clearing operations. Reuse may include:
note | a. retention of sections of a branch/trunk with hollows;
note | b. habitat logs on the ground in revegetation sites;
note | c. placement as in-stream habitat with the appropriate approval of the relevant Catchment Management Authority; or
note | d. timber for furniture construction
note | e. Mulch provided to Council, local schools, or to landscaping facilities
note | Update tree removal/retention register
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each lot
note | Key - R
note | Resp - SE
checkpoint | 3.7 - Disposal of Material
note | Ref docs - VR201.07 VR177.I2 PS3020.07 (a)
note | Acceptance criteria - No removal of noxious weeds from the site. Identify and undertake treatment of declared noxious weeds prior to the commencement of any ground disturbing activities.
note | • The disposal of these materials shall be in accordance with the CEMP and its sub plans
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each lot
note | Key - R
note | Resp - SE
checkpoint | 3.8 - Salvage of Vegetation
note | Ref docs - VR201.11
note | Acceptance criteria - Salvaging any plants as well as collecting cuttings and available seed from areas of native vegetation on site to be completed where applicable
button | Has all of the above been completed? | Yes, No, N/A
note | Freq - Each Lot
note | Key - R
note | Resp - SE
section | 4.0 Work Lot Close Out
checkpoint | 4.1 - Product Non-Conformance
note | Ref docs - CQMP
note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
note | Freq - Each lot
note | Key - R
note | Resp - SE
textbox | NCR No:
bool | NCR reports
checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
note | Ref docs - CQMP Lot Records
note | Acceptance criteria - All above criteria met, and records identified attached.
note | Freq - Each lot
note | Key - R
note | Resp - SE
bool | Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint | Works complete
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checkpoint | Lot conforms
textbox | Name:
textbox | Position:
textbox | Date lot closed:
textbox | NCR/s no. raised:
textbox | Date NCR closed for this lot:
signoff | Sign ITP