## Bulk Earthworks
Inspection and Test Plan
BULK EARTHWORKS
Project: | [7 empty] | Revision: | 1
Job number: | [7 empty] | Date:
Client:
H - Hold point: | Contractor must not proceed past this point until verification documentation has been reviewed and approved. |  |  | W - Witness point: | Witnessing party is requested to witness activity on site. If the signatory is not available work may proceed with documentation reviewed at a later date.
S - Surveillance: | No notification required but activity is still subject to monitoring. |  |  | R - Review: | Work may proceed while documents are reviewed.
Item # | Activity Descrption | Inspection / Test Method | Acceptance Criteria | Frequency | Verifying Documents | Inspection Point |  |  | Comments
[6 empty] | Sub Contractor | Head Contractor | Engineer / Client
1 | PRELIMINARY / GENERAL
1.1 | Construction management plan / dust control and erosion sedimant control plans | Document review | Compliant with conditions of resource consent | Prior to construction |  | H | H
1.2 | Environmental controls | Site inspection | Compliant with approved construction management plan | Prior to bulk activities | As builts / photos / Engineer site inspection | H | H
1.3 | Traffic management plan | Document review | Approved by RCA | Prior to construction | Approved plan | H | H
2 | MATERIALS
2.1.1 | Bulk fill - granular | NZ 4407 Test 3.15 |  | Test prior to placement. | IANZ accedited laboratory | H | W | R
2.1.2 | Bulk fill - lime | Specific approval |  | Test prior to placement. |  | H | W | R
3 | BULK EARTHWORKS - SUBGRADE & EXCAVATION PREPARATION
3.1 | Topsoil stripping | Geotechnical inspection | Prior to any fill, all organic topsoil mterials are removed. | Prior to fill. | Geotechnical approval | H | H
3.2 | Subgrade - fill to sub base | Proof roll / NDM testing / DCP testing | Maximum layer thickness = 200mm. 95% SMDD mean, 92% minimum | 5 tests per 1,000m2 | NDM test results | H | H
4 | CLOSEOUT
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of bulk earethworks | Producer statements | H | H | H
4.2 | Collate and supply as builts | Documete review / as builts | Collate and supply as-builts. | Upon completion of bulk earethworks | As-builts |  | H | S

## Roading
Inspection and Test Plan
ROADING
Project: | [7 empty] | Revision: | 1
Job number: | [7 empty] | Date:
Client:
H - Hold point: | Contractor must not proceed past this point until verification documentation has been reviewed and approved. |  |  | W - Witness point: | Witnessing party is requested to witness activity on site. If the signatory is not available work may proceed with documentation reviewed at a later date.
S - Surveillance: | No notification required but activity is still subject to monitoring. |  |  | R - Review: | Work may proceed while documents are reviewed
Item # | Activity Descrption | Inspection / Test Method | Acceptance Criteria | Frequency | Verifying Documents | Inspection Point |  |  | Comments
[6 empty] | Sub Contractor | Head Contractor | Engineer / Client
1 | PRELIMINARY / GENERAL
1.1 | Subgrade testing | Beam testing / proof rolling or scala | Consistent with design assuptions. | Prior to construction | Test results | H | H |  | Required to confirm assumed CBR.
2 | MATERIALS
2.1 | Sub Base | Production testing to NZS 4407 | Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN. | 1 test prior to placement | IANZ Lab report | H
2.2 | Base Course | TNZ M/4 | Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run". | 1 test per 500m3 prior to placement | IANZ Lab report | H
2.3 | Ashphaltic concrete surfaceing | TNZ M/10 | Job mix formula | Prior to placement | Mix design | H | H
2.4 | Concrete | NZS 3109 | 25MPa concrete at 28 days. |  |  | H | H
2.5 | Vehicle crossings | NZS 3109 | 30MPa concrete at 28 days |  |  |  |  | R
2.6 | Kerb and channel, nibs and dish channels | NZS 3109 | 20MPa concrete at 28 days |  |  |  |  | R
2.7 | Traffic signs and name plates | "Standard for the manuafacture and maintenace of traffic signs, post and fittings" - NZTA | Compliance with the standard. |  |  |  |  | R
2.8 | Road marking paint | TNZ M/7 | Compliance with the standard. |  |  |  |  | R
3 | SUB BASE CONSTRUCTION
3.1 | Topsoil stripping | Geotechnical inspection | Prior to any fill, all organic topsoil mterials are removed. | Prior to fill. | Geotechnical approval. | H | H
3.2 | Surface finish and levels. | Survey / string lines at 20m centres. | Surface finish in accordance with TNZ F/1, section 11 | Prior to fill. | Engineer approval. | H | H
3.3 | Density testing | Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes. | 95% SMDD mean, 92% minimum | Prior to basecourse placement. | IANZ Lab report | H | H
3.4 | Sub base surface finish | TNZ B/2 | Visual inspection - tight mosaic finish. | Prior to placement of bascourse | Engineer approval. | H | H
3.5 | Road marking paint | Mark out on site | Mark out dimensionally in conformance with the design. | Prior to application of paint | Engineer approval. | H | H
4 | BASECOURSE CONSTRUCTION
4.1 | Basecourse finished level setout | Survey / string lines at 20m centres | +15mm / -5mm vertical from sub base design surface. | Prior to basecourse placement. | Engineer approval. | H | H
4.2 | Density testing | Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes. | 98% SMDD mean, 95% minimum | Prior to surfacing. | IANZ Lab report | H | H | R
4.3 | Beam testing | TNZ T/1 | Average: 1.5mm, Maximum 1.8mm | Prior to surfacing. | Test results. | H | H | R
4.4 | Surface finish | TNZ M/4 | Visual inspection | Prior to surfacing. | Engineer approval. | H | H
5 | ASHPHALT SURFACING
5.1 | Ashphaltic concrete finished level setout | Survey / string lines | 10m centres, 3m straight edge. | Prior to surfacing | +10mm / -0mm from finished design. | H | H
6 | FOOTPATH AND VEHICLE CROSSINGS
6.1 | Setout | Survey / string lines | +15mm / -5mm vertical from sub base design surface. | Prior to pour. | Engineer approval. | H | H
6.2 | Basecourse compaction | Clegg | Mimimum 25. | Prior to pour. | Engineer approval. | H | H
7 | KERB AND CHANNEL, NIB, DISH CHANEL
7.1 | Setout | Survey / string lines | +15mm / -5mm vertical from sub base design surface. | Prior to pour. | Engineer approval. | H | H
7.2 | Basecourse compaction | Clegg | Mimimum 25. | Prior to pour. | Engineer approval. | H | H
4 | CLOSEOUT
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of bulk roadworks | Producer statements | H | H | H
4.2 | Collate and supply as builts | Documate review / as builts | Collate and supply as-builts. | Upon completion of roadworks | As-builts |  | H | S

## Stormwater
Inspection and Test Plan
STORMWATER
Project: | [7 empty] | Revision: | 1
Job number: | [7 empty] | Date:
Client:
H - Hold point: | Contractor must not proceed past this point until verification documentation has been reviewed and approved. |  |  | W - Witness point: | Witnessing party is requested to witness activity on site. If the signatory is not available work may proceed with documentation reviewed at a later date.
S - Surveillance: | No notification required but activity is still subject to monitoring. |  |  | R - Review: | Work may proceed while documents are reviewed
Item # | Activity Descrption | Inspection / Test Method | Acceptance Criteria | Frequency | Verifying Documents | Inspection Point |  |  | Comments
[6 empty] | Sub Contractor | Head Contractor | Engineer / Client
1 | PRELIMINARY / GENERAL
1.1 | Consents and trench opening notices | Document review | Authority approvals. | Prior to excavation | Approval from relevant authorities. |  |  | R
1.2 | Drainlayer registration | Document review | Certification | Prior to drain laying works. | Scanned copy |  |  | R
2 | MATERIALS
2.1 | Concrete pipes | Document review | New and in good condition and compliant with AS/NZS4058 reinforced cast rubber ring jointed, class 2 uless otherwise noted. | Prior to order | Technical documents. |  |  | R
2.2 | PVC pipes | Document review | New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise) | Prior to order | Technical documents. |  |  | R
2.3 | Precast chambers | Document review | Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads. | Prior to order | Technical documents. |  |  | R
2.4 | Access covers and frames | Document review | Removable with a clear opening >600mm (except for non-access MHs). Designed to minimum AS 3996 Class D or better. | Prior to order | Technical documents. |  |  | R
2.5 | Sump grates | Document review | Complaince with HDC ECoP. | Prior to order | Technical documents. |  |  | R
2.6 | Concrete Wing wall | Document review | Compliance with NZS 3109 with surface finishes to | Prior to order | Technical documents. |  |  | R
2.7 | Backfill material
2.7.1 | Bedding haunching and overlay. | Inspection | 5-14mm clean washed granualr mix. | Prior to placement. | Engineer approval. | H | H
2.7.2 | Fill to subbase | Inspection | AP65 of other approved imported material. | Prior to placement. | Engineer approval. | H | H
2.8 | Stormwater pump station
2.8.1 | Chamber, pumps, controller | Document review | New and in accordance with the specifications | Prior to order | Technical documents. |  |  | R
3 | CONSTRUCTION
3.1 | Set out | Document review. | Survey setout information in accordance with the design. | Prior to excavation. | Survey file. |  |  | R
3.2 | Trenching | Site inspection. | Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width, pipe dia DN150 - DN300 = 450 - 600mm width, pipe dia DN300 - DN400mm = 700 - 850mm width. | Prior to pipe laying | Engineer approval. | H | H
3.3 | Pipe laying | Survey | Record level of main upstream and downstream of each chamber. Maximum discrepancy +-10% of design gradient, and maximum +-15mm from design level. | Prior to backfill. | Survey as builts |  |  | R
3.4 | Chambers / sumps / wingwalls | Survey / site inspection. | Benching in accordance with specifcations and drawings. Position in accordance with the design | Prior to backfill. | Engineer approval. | H | H
3.5 | Pipe bedding / haunching /overlay | Document review site inspection. | In accordance with AS/NZS 2566 for PVC pipelines and AS/NZS 3725 for concrete pipelines. Bedding minimum 100mm up to 450 diamter pipe and 150mm pipes > 450mm. For PVC overlay >100mm over pipe and for concrete 1/3 diamter of pipe. | Prior to backfill. | Photos or site inspection. | H | H
3.6 | Backfill | Clegg every 10m alignment for each layer of backfill (not exceeding 200mm) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. | H | H
3.7 | Stormwater pump station
3.7.1 | Excavation | Site inspection. | Base level in accordance with the design | Prior to backfill. | Engineer approval. | H | H
3.7.2 | Backfill | Clegg for each layer of backfill (not exceeding 200mm depth) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. | H | H
4 | CLOSEOUT
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of stormwater works. | Producer statements | H | H | H
4.2 | Collate and supply Council inspection reports. | Document review. | Collate and supply Council inspection reports. | Upon completion of stormwater works. | Inspection records. | H | H | S
4.3 | Collate and supply compaction records. | Document review. | Collate and supply compaction records. | Upon completion of stormwater works. | Inspection records. | H | H | S
4.4 | Collate and supply as builts / CCTV inspections / water tests | Document review / as builts | Collate and supply as-builts and inspection records. | Upon completion of stormwater works. | As-builts | H | H | S

## Wastewater
Inspection and Test Plan
WASTEWATER
Project: | [7 empty] | Revision: | 1
Job number: | [7 empty] | Date:
Client:
H - Hold point: | Contractor must not proceed past this point until verification documentation has been reviewed and approved. |  |  | W - Witness point: | Witnessing party is requested to witness activity on site. If the signatory is not available work may proceed with documentation reviewed at a later date.
S - Surveillance: | No notification required but activity is still subject to monitoring. |  |  | R - Review: | Work may proceed while documents are reviewed
Item # | Activity Descrption | Inspection / Test Method | Acceptance Criteria | Frequency | Verifying Documents | Inspection Point |  |  | Comments
[6 empty] | Sub Contractor | Head Contractor | Engineer / Client
1 | PRELIMINARY / GENERAL
1.1 | Consents and trench opening notices | Document review | Authority approvals. | Prior to excavation | Approval from relevant authorities. |  |  | R
1.2 | Drainlayer registration | Document review | Certification | Prior to drain laying works. | Scanned copy |  |  | R
2 | MATERIALS
2.1 | PVC pipes | Document review | New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise) | Prior to order | Technical documents. |  |  | R
2.2 | Precast chambers | Document review | Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads. | Prior to order | Technical documents. |  |  | R
2.3 | Access covers and frames | Document review | Removable with a clear opening >600mm (except for non-access MHs). Designed to minimum AS 3996 Class D or better. | Prior to order | Technical documents. |  |  | R
2.7 | Backfill material
2.7.1 | Bedding haunching and overlay. | Inspection | 5-14mm clean washed granualr mix. | Prior to placement. |  | H | H
2.7.2 | Fill to subbase | Inspection | AP65 of other approved imported material. | Prior top placement. |  | H | H
2.8 | Wastewater pump station
2.8.1 | Chamber, storage, pumps, controller | Document review | New and in accordance with the specifications | Prior to order | Technical documents. |  |  | R
3 | CONSTRUCTION
3.1 | Set out | Document review. | Survey setout information in accordance with the design. | Prior to excavation. | Survey file. |  |  | R
3.2 | Trenching | Site inspection. | Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. | Prior to pipe laying | Engineer approval. | H | H
3.3 | Pipe laying | Survey | Record level of main upstream and downstream of each chamber. Maximum discrepancy +-10% of design gradient, and maximum +-15mm from design level. | Prior to backfill. | Survey as builts |  |  | R
3.5 | Pipe bedding / haunching /overlay | Document review site inspection. | In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe. | Prior to backfill. | Photos or site inspection. | H | H
3.6 | Hydrostatic testing | Document review | In accordance with AS/NZS 3500.2 section 15.2 | Prior to backfill. | Test records and Council inspection records. | H | H
3.6 | Backfill | Clegg every 10m alignment for each layer of backfill (not exceeding 200mm) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. | H | H
3.7 | Wastewater pump station
3.7.1 | Excavation | Site inspection. | Excavation levels in accordance with the design | Prior to backfill. | Engineer approval. | H | H
3.7.2 | Backfill | Clegg for each layer of backfill (not exceeding 200mm depth) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. | H | H
4 | CLOSEOUT
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of wastewater works. | Producer statements | H | H | H
4.2 | Collate and supply Council inspection reports. | Document review. | Collate and supply Council inspection reports. | Upon completion of wastewater works. | Inspection records. | H | H | S
4.3 | Collate and supply compaction records. | Document review. | Collate and supply compaction records. | Upon completion of wastewater works. | Inspection records. | H | H | S
4.4 | Collate and supply as builts / CCTV inspections / water tests | Document review / as builts | Collate and supply as-builts and inspection records. | Upon completion of wastewater works. | As-builts / test records. | H | H | S

## Water Supply
Inspection and Test Plan
WATER SUPPLY
Project: | [7 empty] | Revision: | 1
Job number: | [7 empty] | Date:
Client:
H - Hold point: | Contractor must not proceed past this point until verification documentation has been reviewed and approved. |  |  | W - Witness point: | Witnessing party is requested to witness activity on site. If the signatory is not available work may proceed with documentation reviewed at a later date.
S - Surveillance: | No notification required but activity is still subject to monitoring. |  |  | R - Review: | Work may proceed while documents are reviewed
Item # | Activity Descrption | Inspection / Test Method | Acceptance Criteria | Frequency | Verifying Documents | Inspection Point |  |  | Comments
[6 empty] | Sub Contractor | Head Contractor | Engineer / Client
1 | PRELIMINARY / GENERAL
1.1 | Consents and trench opening notices | Document review | Authority approvals. | Prior to excavation | Approval from relevant authorities. |  |  | R
1.2 | Installer registration | Document review | Certification | Prior to drain laying works. | Scanned copy |  |  | R
2 | MATERIALS
2.1 | PVC pipes | Document review | New and in good condition and compliant with AS/NZS1477 (min PN9) | Prior to order | Technical documents. |  |  | R
2.1 | PE pipes | Document review | New and in good condition and compliant with AS/NZS1430 (min PN12.5) | Prior to order | Technical documents. |  |  | R
2.2 | Precast chambers | Document review | Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads. | Prior to order | Technical documents. |  |  | R
2.3 | Access covers and frames | Document review | Removable with a clear opening >600mm (except for non-access MHs). Designed to minimum AS 3996 Class D or better. | Prior to order | Technical documents. |  |  | R
2.7 | Backfill material
2.7.1 | Bedding haunching and overlay. | Inspection | 5-14mm clean washed granualr mix. | Prior to placement. |  | H | H
2.7.2 | Fill to subbase | Inspection | AP65 of other approved imported material. | Prior top placement. |  | H | H
3 | CONSTRUCTION
3.1 | Set out | Document review. | Survey setout information in accordance with the design. | Prior to excavation. | Survey file. |  |  | R
3.2 | Trenching | Site inspection. | Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. | Prior to pipe laying | Engineer approval. |  |  | S
3.3 | Pipe laying | Survey | Alignment +-50mm from design, surface cover in accordance with HDC ECoP. | Prior to backfill. | Survey as builts |  |  | R
3.5 | Pipe bedding / haunching /overlay | Document review site inspection. | In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe. | Prior to backfill. | Photos or site inspection. |  |  | S
3.6 | Pressure test | Inspection. | In accordance with section C3 of NZS4404 and AS/NZS 2556. To a pressure no less than 800kPa and no greater than 25% above the rated pressure of the pipeline. | Prior to backfill over joints and fittings wherever possible. | Test records. | H | H | W
3.8 | Backfill | Clegg every 10m alignment for each layer of backfill (not exceeding 200mm) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. |  |  | S
3.7 | Disinfection | Inspection. | Carried out in accordance with HDC ECoP (amended appendix D of NZS4404:2010. | Prior to connectioun to mains supply | Test records. | H | H | W
4 | CLOSEOUT
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of Water supply works. | Producer statements | H | H | H
4.2 | Collate and supply Council inspection reports. | Document review. | Collate and supply Council inspection reports. | Upon completion of water supply works. | Inspection records. | H | H | S
4.3 | Collate and supply compaction records. | Document review. | Collate and supply compaction records. | Upon completion of water supply works. | Inspection records. | H | H | S
4.4 | Collate and supply as builts / CCTV inspections / water tests | Document review / as builts | Collate and supply as-builts and inspection records. | Upon completion of water supply works. | As-builts / test records. | H | H | S

## Service Trenching and Ducting
Inspection and Test Plan
SERVICE TRENCHING AND DUCTING
Project: | [7 empty] | Revision: | 1
Job number: | [7 empty] | Date:
Client:
H - Hold point: | Contractor must not proceed past this point until verification documentation has been reviewed and approved. |  |  | W - Witness point: | Witnessing party is requested to witness activity on site. If the signatory is not available work may proceed with documentation reviewed at a later date.
S - Surveillance: | No notification required but activity is still subject to monitoring. |  |  | R - Review: | Work may proceed while documents are reviewed
Item # | Activity Descrption | Inspection / Test Method | Acceptance Criteria | Frequency | Verifying Documents | Inspection Point |  |  | Comments
[6 empty] | Sub Contractor | Head Contractor | Engineer / Client
1 | PRELIMINARY / GENERAL
1.1 | Consents and trench opening notices | Document review | Authority approvals. | Prior to excavation | Approval from relevant authorities. |  |  | R
2 | MATERIALS
2.1 | PVC ducts | Document review | New and in good condition and compliant. | Prior to order | Technical documents. |  |  | R
2.2 | Chambers / pits | Document review | ACO type pits with class D covers in accordance with the specifications. | Prior to order | Technical documents. |  |  | R
2.7 | Backfill material
2.7.1 | Bedding haunching and overlay. | Inspection | 5-14mm clean washed granualr mix. | Prior to placement. |  | H | H
2.7.2 | Fill to subbase | Inspection | AP65 of other approved imported material. | Prior top placement. |  | H | H
3 | CONSTRUCTION
3.1 | Set out | Document review. | Survey setout of chambers / pits in accordance with the design - marked on site | Prior to excavation. | Survey file / site inspection. |  |  | W
3.2 | Trenching | Site inspection. | Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications. | Prior to pipe laying | Engineer approval. |  |  | S
3.5 | Pipe bedding / haunching /overlay | Document review site inspection. | In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe. | Prior to backfill. | Photos or site inspection. |  |  | S
3.8 | Backfill | Clegg every 10m alignment for each layer of backfill (not exceeding 200mm) | Minimum 20 Clegg reading | Prior to placement of each layer of backfill. | Test records. |  |  | S
4 | CLOSEOUT
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of Water supply works. | Producer statements | H | H | H
4.2 | Collate and supply Council inspection reports. | Document review. | Collate and supply Council inspection reports. | Upon completion of water supply works. | Inspection records. | H | H | S
4.3 | Collate and supply compaction records. | Document review. | Collate and supply compaction records. | Upon completion of water supply works. | Inspection records. | H | H | S
4.4 | Collate and supply as builts / CCTV inspections / water tests | Document review / as builts | Collate and supply as-builts and inspection records. | Upon completion of water supply works. | As-builts / test records. | H | H | S