## Sheet1
1.1 | Subgrade testing | Beam testing / proof rolling or scala | Consistent with design assuptions. | Prior to construction | Test results | H | H |  | 1.1 - Subgrade testing | Inspection / Test Method - Beam testing / proof rolling or scala | Acceptance Criteria - Consistent with design assuptions. | Frequency - Prior to construction | Verifying Documents - Test results | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | 1.1 - Subgrade testing
2.1 | Sub Base | Production testing to NZS 4407 | Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN. | 1 test prior to placement | IANZ Lab report | H |  |  | 2.1 - Sub Base | Inspection / Test Method - Production testing to NZS 4407 | Acceptance Criteria - Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN. | Frequency - 1 test prior to placement | Verifying Documents - IANZ Lab report | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - | Inspection Point: Engineer / Client - | Inspection / Test Method - Beam testing / proof rolling or scala
2.2 | Base Course | TNZ M/4 | Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run". | 1 test per 500m3 prior to placement | IANZ Lab report | H |  |  | 2.2 - Base Course | Inspection / Test Method - TNZ M/4 | Acceptance Criteria - Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run". | Frequency - 1 test per 500m3 prior to placement | Verifying Documents - IANZ Lab report | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - | Inspection Point: Engineer / Client - | Acceptance Criteria - Consistent with design assuptions.
2.3 | Ashphaltic concrete surfaceing | TNZ M/10 | Job mix formula | Prior to placement | Mix design | H | H |  | 2.3 - Ashphaltic concrete surfaceing | Inspection / Test Method - TNZ M/10 | Acceptance Criteria - Job mix formula | Frequency - Prior to placement | Verifying Documents - Mix design | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Frequency - Prior to construction
2.4 | Concrete | NZS 3109 | 25MPa concrete at 28 days. |  |  | H | H |  | 2.4 - Concrete | Inspection / Test Method - NZS 3109 | Acceptance Criteria - 25MPa concrete at 28 days. | Frequency - | Verifying Documents - | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Verifying Documents - Test results
2.5 | Vehicle crossings | NZS 3109 | 30MPa concrete at 28 days |  |  |  |  | R | 2.5 - Vehicle crossings | Inspection / Test Method - NZS 3109 | Acceptance Criteria - 30MPa concrete at 28 days | Frequency - | Verifying Documents - | Inspection Point: Sub Contractor - | Inspection Point: Head Contractor - | Inspection Point: Engineer / Client - R | Inspection Point: Sub Contractor - H
2.6 | Kerb and channel, nibs and dish channels | NZS 3109 | 20MPa concrete at 28 days |  |  |  |  | R | 2.6 - Kerb and channel, nibs and dish channels | Inspection / Test Method - NZS 3109 | Acceptance Criteria - 20MPa concrete at 28 days | Frequency - | Verifying Documents - | Inspection Point: Sub Contractor - | Inspection Point: Head Contractor - | Inspection Point: Engineer / Client - R | Inspection Point: Head Contractor - H
2.7 | Traffic signs and name plates | Standard for the manuafacture and maintenace of traffic signs, post and fittings - NZTA | Compliance with the standard. |  |  |  |  | R | 2.7 - Traffic signs and name plates | Inspection / Test Method - Standard for the manuafacture and maintenace of traffic signs, post and fittings - NZTA | Acceptance Criteria - Compliance with the standard. | Frequency - | Verifying Documents - | Inspection Point: Sub Contractor - | Inspection Point: Head Contractor - | Inspection Point: Engineer / Client - R | Inspection Point: Engineer / Client -
2.8 | Road marking paint | TNZ M/7 | Compliance with the standard. |  |  |  |  | R | 2.8 - Road marking paint | Inspection / Test Method - TNZ M/7 | Acceptance Criteria - Compliance with the standard. | Frequency - | Verifying Documents - | Inspection Point: Sub Contractor - | Inspection Point: Head Contractor - | Inspection Point: Engineer / Client - R | 2.1 - Sub Base
3.1 | Topsoil stripping | Geotechnical inspection | Prior to any fill, all organic topsoil mterials are removed. | Prior to fill. | Geotechnical approval. | H | H |  | 3.1 - Topsoil stripping | Inspection / Test Method - Geotechnical inspection | Acceptance Criteria - Prior to any fill, all organic topsoil mterials are removed. | Frequency - Prior to fill. | Verifying Documents - Geotechnical approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Inspection / Test Method - Production testing to NZS 4407
3.2 | Surface finish and levels. | Survey / string lines at 20m centres. | Surface finish in accordance with TNZ F/1, section 11 | Prior to fill. | Engineer approval. | H | H |  | 3.2 - Surface finish and levels. | Inspection / Test Method - Survey / string lines at 20m centres. | Acceptance Criteria - Surface finish in accordance with TNZ F/1, section 11 | Frequency - Prior to fill. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Acceptance Criteria - Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN.
3.3 | Density testing | Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes. | 95% SMDD mean, 92% minimum | Prior to basecourse placement. | IANZ Lab report | H | H |  | 3.3 - Density testing | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes. | Acceptance Criteria - 95% SMDD mean, 92% minimum | Frequency - Prior to basecourse placement. | Verifying Documents - IANZ Lab report | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Frequency - 1 test prior to placement
3.4 | Sub base surface finish | TNZ B/2 | Visual inspection - tight mosaic finish. | Prior to placement of bascourse | Engineer approval. | H | H |  | 3.4 - Sub base surface finish | Inspection / Test Method - TNZ B/2 | Acceptance Criteria - Visual inspection - tight mosaic finish. | Frequency - Prior to placement of bascourse | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Verifying Documents - IANZ Lab report
3.5 | Road marking paint | Mark out on site | Mark out dimensionally in conformance with the design. | Prior to application of paint | Engineer approval. | H | H |  | 3.5 - Road marking paint | Inspection / Test Method - Mark out on site | Acceptance Criteria - Mark out dimensionally in conformance with the design. | Frequency - Prior to application of paint | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Inspection Point: Sub Contractor - H
4.1 | Basecourse finished level setout | Survey / string lines at 20m centres | +15mm / -5mm vertical from sub base design surface. | Prior to basecourse placement. | Engineer approval. | H | H |  | 4.1 - Basecourse finished level setout | Inspection / Test Method - Survey / string lines at 20m centres | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface. | Frequency - Prior to basecourse placement. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Inspection Point: Head Contractor -
4.2 | Density testing | Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes. | 98% SMDD mean, 95% minimum | Prior to surfacing. | IANZ Lab report | H | H | R | 4.2 - Density testing | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes. | Acceptance Criteria - 98% SMDD mean, 95% minimum | Frequency - Prior to surfacing. | Verifying Documents - IANZ Lab report | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - R | Inspection Point: Engineer / Client -
4.3 | Beam testing | TNZ T/1 | Average: 1.5mm, Maximum 1.8mm | Prior to surfacing. | Test results. | H | H | R | 4.3 - Beam testing | Inspection / Test Method - TNZ T/1 | Acceptance Criteria - Average: 1.5mm, Maximum 1.8mm | Frequency - Prior to surfacing. | Verifying Documents - Test results. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - R | 2.2 - Base Course
4.4 | Surface finish | TNZ M/4 | Visual inspection | Prior to surfacing. | Engineer approval. | H | H |  | 4.4 - Surface finish | Inspection / Test Method - TNZ M/4 | Acceptance Criteria - Visual inspection | Frequency - Prior to surfacing. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Inspection / Test Method - TNZ M/4
5.1 | Ashphaltic concrete finished level setout | Survey / string lines | 10m centres, 3m straight edge. | Prior to surfacing | +10mm / -0mm from finished design. | H | H |  | 5.1 - Ashphaltic concrete finished level setout | Inspection / Test Method - Survey / string lines | Acceptance Criteria - 10m centres, 3m straight edge. | Frequency - Prior to surfacing | Verifying Documents - +10mm / -0mm from finished design. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Acceptance Criteria - Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run".
6.1 | Setout | Survey / string lines | +15mm / -5mm vertical from sub base design surface. | Prior to pour. | Engineer approval. | H | H |  | 6.1 - Setout | Inspection / Test Method - Survey / string lines | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface. | Frequency - Prior to pour. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Frequency - 1 test per 500m3 prior to placement
6.2 | Basecourse compaction | Clegg | Mimimum 25. | Prior to pour. | Engineer approval. | H | H |  | 6.2 - Basecourse compaction | Inspection / Test Method - Clegg | Acceptance Criteria - Mimimum 25. | Frequency - Prior to pour. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Verifying Documents - IANZ Lab report
7.1 | Setout | Survey / string lines | +15mm / -5mm vertical from sub base design surface. | Prior to pour. | Engineer approval. | H | H |  | 7.1 - Setout | Inspection / Test Method - Survey / string lines | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface. | Frequency - Prior to pour. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Inspection Point: Sub Contractor - H
7.2 | Basecourse compaction | Clegg | Mimimum 25. | Prior to pour. | Engineer approval. | H | H |  | 7.2 - Basecourse compaction | Inspection / Test Method - Clegg | Acceptance Criteria - Mimimum 25. | Frequency - Prior to pour. | Verifying Documents - Engineer approval. | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - | Inspection Point: Head Contractor -
4.1 | Collate and supply Producer Statements / Waranty Schedules | Document review | Collate and supply producer statements | Upon completion of bulk roadworks | Producer statements | H | H | H | 4.1 - Collate and supply Producer Statements / Waranty Schedules | Inspection / Test Method - Document review | Acceptance Criteria - Collate and supply producer statements | Frequency - Upon completion of bulk roadworks | Verifying Documents - Producer statements | Inspection Point: Sub Contractor - H | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - H | Inspection Point: Engineer / Client -
4.2 | Collate and supply as builts | Documate review / as builts | Collate and supply as-builts. | Upon completion of roadworks | As-builts |  | H | S | 4.2 - Collate and supply as builts | Inspection / Test Method - Documate review / as builts | Acceptance Criteria - Collate and supply as-builts. | Frequency - Upon completion of roadworks | Verifying Documents - As-builts | Inspection Point: Sub Contractor - | Inspection Point: Head Contractor - H | Inspection Point: Engineer / Client - S | 2.3 - Ashphaltic concrete surfaceing
Inspection / Test Method - TNZ M/10
Acceptance Criteria - Job mix formula
Frequency - Prior to placement
Verifying Documents - Mix design
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
2.4 - Concrete
Inspection / Test Method - NZS 3109
Acceptance Criteria - 25MPa concrete at 28 days.
Frequency -
Verifying Documents -
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
2.5 - Vehicle crossings
Inspection / Test Method - NZS 3109
Acceptance Criteria - 30MPa concrete at 28 days
Frequency -
Verifying Documents -
Inspection Point: Sub Contractor -
Inspection Point: Head Contractor -
Inspection Point: Engineer / Client - R
2.6 - Kerb and channel, nibs and dish channels
Inspection / Test Method - NZS 3109
Acceptance Criteria - 20MPa concrete at 28 days
Frequency -
Verifying Documents -
Inspection Point: Sub Contractor -
Inspection Point: Head Contractor -
Inspection Point: Engineer / Client - R
2.7 - Traffic signs and name plates
Inspection / Test Method - Standard for the manuafacture and maintenace of traffic signs, post and fittings - NZTA
Acceptance Criteria - Compliance with the standard.
Frequency -
Verifying Documents -
Inspection Point: Sub Contractor -
Inspection Point: Head Contractor -
Inspection Point: Engineer / Client - R
2.8 - Road marking paint
Inspection / Test Method - TNZ M/7
Acceptance Criteria - Compliance with the standard.
Frequency -
Verifying Documents -
Inspection Point: Sub Contractor -
Inspection Point: Head Contractor -
Inspection Point: Engineer / Client - R
3.1 - Topsoil stripping
Inspection / Test Method - Geotechnical inspection
Acceptance Criteria - Prior to any fill, all organic topsoil mterials are removed.
Frequency - Prior to fill.
Verifying Documents - Geotechnical approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
3.2 - Surface finish and levels.
Inspection / Test Method - Survey / string lines at 20m centres.
Acceptance Criteria - Surface finish in accordance with TNZ F/1, section 11
Frequency - Prior to fill.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
3.3 - Density testing
Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes.
Acceptance Criteria - 95% SMDD mean, 92% minimum
Frequency - Prior to basecourse placement.
Verifying Documents - IANZ Lab report
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
3.4 - Sub base surface finish
Inspection / Test Method - TNZ B/2
Acceptance Criteria - Visual inspection - tight mosaic finish.
Frequency - Prior to placement of bascourse
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
3.5 - Road marking paint
Inspection / Test Method - Mark out on site
Acceptance Criteria - Mark out dimensionally in conformance with the design.
Frequency - Prior to application of paint
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
4.1 - Basecourse finished level setout
Inspection / Test Method - Survey / string lines at 20m centres
Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
Frequency - Prior to basecourse placement.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
4.2 - Density testing
Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes.
Acceptance Criteria - 98% SMDD mean, 95% minimum
Frequency - Prior to surfacing.
Verifying Documents - IANZ Lab report
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client - R
4.3 - Beam testing
Inspection / Test Method - TNZ T/1
Acceptance Criteria - Average: 1.5mm, Maximum 1.8mm
Frequency - Prior to surfacing.
Verifying Documents - Test results.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client - R
4.4 - Surface finish
Inspection / Test Method - TNZ M/4
Acceptance Criteria - Visual inspection
Frequency - Prior to surfacing.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
5.1 - Ashphaltic concrete finished level setout
Inspection / Test Method - Survey / string lines
Acceptance Criteria - 10m centres, 3m straight edge.
Frequency - Prior to surfacing
Verifying Documents - +10mm / -0mm from finished design.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
6.1 - Setout
Inspection / Test Method - Survey / string lines
Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
Frequency - Prior to pour.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
6.2 - Basecourse compaction
Inspection / Test Method - Clegg
Acceptance Criteria - Mimimum 25.
Frequency - Prior to pour.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
7.1 - Setout
Inspection / Test Method - Survey / string lines
Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
Frequency - Prior to pour.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
7.2 - Basecourse compaction
Inspection / Test Method - Clegg
Acceptance Criteria - Mimimum 25.
Frequency - Prior to pour.
Verifying Documents - Engineer approval.
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client -
4.1 - Collate and supply Producer Statements / Waranty Schedules
Inspection / Test Method - Document review
Acceptance Criteria - Collate and supply producer statements
Frequency - Upon completion of bulk roadworks
Verifying Documents - Producer statements
Inspection Point: Sub Contractor - H
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client - H
4.2 - Collate and supply as builts
Inspection / Test Method - Documate review / as builts
Acceptance Criteria - Collate and supply as-builts.
Frequency - Upon completion of roadworks
Verifying Documents - As-builts
Inspection Point: Sub Contractor -
Inspection Point: Head Contractor - H
Inspection Point: Engineer / Client - S