## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Bulk Earthworks | itp |  |  |  |  | ITP - Bulk Earthworks Rev 1
section | 1 - PRELIMINARY / GENERAL
checkpoint | 1.1 - Construction management plan / dust control and erosion sedimant control plans
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Compliant with conditions of resource consent
label | Frequency - Prior to construction
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 1.2 - Environmental controls
label | Inspection / Test Method - Site inspection
label | Acceptance Criteria - Compliant with approved construction management plan
label | Frequency - Prior to bulk activities
label | Verifying Documents - As builts / photos / Engineer site inspection
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 1.3 - Traffic management plan
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Approved by RCA
label | Frequency - Prior to construction
label | Verifying Documents - Approved plan
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 2 - MATERIALS
checkpoint | 2.1.1 - Bulk fill - granular
label | Inspection / Test Method - NZ 4407 Test 3.15
label | Frequency - Test prior to placement.
label | Verifying Documents - IANZ accedited laboratory
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - W
label | Inspection Point: Engineer / Client - R
holdpoint | HOLD POINT
checkpoint | 2.1.2 - Bulk fill - lime
label | Inspection / Test Method - Specific approval
label | Frequency - Test prior to placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - W
label | Inspection Point: Engineer / Client - R
holdpoint | HOLD POINT
section | 3 - BULK EARTHWORKS - SUBGRADE & EXCAVATION PREPARATION
checkpoint | 3.1 - Topsoil stripping
label | Inspection / Test Method - Geotechnical inspection
label | Acceptance Criteria - Prior to any fill, all organic topsoil mterials are removed.
label | Frequency - Prior to fill.
label | Verifying Documents - Geotechnical approval
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.2 - Subgrade - fill to sub base
label | Inspection / Test Method - Proof roll / NDM testing / DCP testing
label | Acceptance Criteria - Maximum layer thickness = 200mm. 95% SMDD mean, 92% minimum
label | Frequency - 5 tests per 1,000m2
label | Verifying Documents - NDM test results
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 4 - CLOSEOUT
checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Collate and supply producer statements
label | Frequency - Upon completion of bulk earethworks
label | Verifying Documents - Producer statements
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | 4.2 - Collate and supply as builts
label | Inspection / Test Method - Documete review / as builts
label | Acceptance Criteria - Collate and supply as-builts.
label | Frequency - Upon completion of bulk earethworks
label | Verifying Documents - As-builts
label | Inspection Point: Sub Contractor -
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checklist | ITP - Roading | itp |  |  |  |  | ITP - Roading Rev 1
section | 1 - PRELIMINARY / GENERAL
checkpoint | 1.1 - Subgrade testing
label | Inspection / Test Method - Beam testing / proof rolling or scala
label | Acceptance Criteria - Consistent with design assuptions.
label | Frequency - Prior to construction
label | Verifying Documents - Test results
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Comments - Required to confirm assumed CBR.
holdpoint | HOLD POINT
section | 2 - MATERIALS
checkpoint | 2.1 - Sub Base
label | Inspection / Test Method - Production testing to NZS 4407
label | Acceptance Criteria - Max particle size lesser of 65mm or 40% of layer depth. and no more than 8% by mass of material shall pass the 150 micron sieve. The CBR value should not be less than 60 - and minimum crushing resistance of 100kN.
label | Frequency - 1 test prior to placement
label | Verifying Documents - IANZ Lab report
label | Inspection Point: Sub Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.2 - Base Course
label | Inspection / Test Method - TNZ M/4
label | Acceptance Criteria - Compliance with TNZ M/4. Refer to Table 5 in the M/2 specification for detailsfor "Napier River Run".
label | Frequency - 1 test per 500m3 prior to placement
label | Verifying Documents - IANZ Lab report
label | Inspection Point: Sub Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.3 - Ashphaltic concrete surfaceing
label | Inspection / Test Method - TNZ M/10
label | Acceptance Criteria - Job mix formula
label | Frequency - Prior to placement
label | Verifying Documents - Mix design
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.4 - Concrete
label | Inspection / Test Method - NZS 3109
label | Acceptance Criteria - 25MPa concrete at 28 days.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.5 - Vehicle crossings
label | Inspection / Test Method - NZS 3109
label | Acceptance Criteria - 30MPa concrete at 28 days
label | Inspection Point: Engineer / Client - R
checkpoint | 2.6 - Kerb and channel, nibs and dish channels
label | Inspection / Test Method - NZS 3109
label | Acceptance Criteria - 20MPa concrete at 28 days
label | Inspection Point: Engineer / Client - R
checkpoint | 2.7 - Traffic signs and name plates
label | Inspection / Test Method - Standard for the manuafacture and maintenace of traffic signs, post and fittings - NZTA
label | Acceptance Criteria - Compliance with the standard.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.8 - Road marking paint
label | Inspection / Test Method - TNZ M/7
label | Acceptance Criteria - Compliance with the standard.
label | Inspection Point: Engineer / Client - R
section | 3 - SUB BASE CONSTRUCTION
checkpoint | 3.1 - Topsoil stripping
label | Inspection / Test Method - Geotechnical inspection
label | Acceptance Criteria - Prior to any fill, all organic topsoil mterials are removed.
label | Frequency - Prior to fill.
label | Verifying Documents - Geotechnical approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.2 - Surface finish and levels.
label | Inspection / Test Method - Survey / string lines at 20m centres.
label | Acceptance Criteria - Surface finish in accordance with TNZ F/1, section 11
label | Frequency - Prior to fill.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.3 - Density testing
label | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes.
label | Acceptance Criteria - 95% SMDD mean, 92% minimum
label | Frequency - Prior to basecourse placement.
label | Verifying Documents - IANZ Lab report
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.4 - Sub base surface finish
label | Inspection / Test Method - TNZ B/2
label | Acceptance Criteria - Visual inspection - tight mosaic finish.
label | Frequency - Prior to placement of bascourse
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.5 - Road marking paint
label | Inspection / Test Method - Mark out on site
label | Acceptance Criteria - Mark out dimensionally in conformance with the design.
label | Frequency - Prior to application of paint
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 4 - BASECOURSE CONSTRUCTION
checkpoint | 4.1 - Basecourse finished level setout
label | Inspection / Test Method - Survey / string lines at 20m centres
label | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
label | Frequency - Prior to basecourse placement.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 4.2 - Density testing
label | Inspection / Test Method - Nuclear densometer to NZS 4407 Test 3.7 - 50m intervals staggered between lanes.
label | Acceptance Criteria - 98% SMDD mean, 95% minimum
label | Frequency - Prior to surfacing.
label | Verifying Documents - IANZ Lab report
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - R
holdpoint | HOLD POINT
checkpoint | 4.3 - Beam testing
label | Inspection / Test Method - TNZ T/1
label | Acceptance Criteria - Average: 1.5mm, Maximum 1.8mm
label | Frequency - Prior to surfacing.
label | Verifying Documents - Test results.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - R
holdpoint | HOLD POINT
checkpoint | 4.4 - Surface finish
label | Inspection / Test Method - TNZ M/4
label | Acceptance Criteria - Visual inspection
label | Frequency - Prior to surfacing.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 5 - ASHPHALT SURFACING
checkpoint | 5.1 - Ashphaltic concrete finished level setout
label | Inspection / Test Method - Survey / string lines
label | Acceptance Criteria - 10m centres, 3m straight edge.
label | Frequency - Prior to surfacing
label | Verifying Documents - +10mm / -0mm from finished design.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 6 - FOOTPATH AND VEHICLE CROSSINGS
checkpoint | 6.1 - Setout
label | Inspection / Test Method - Survey / string lines
label | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
label | Frequency - Prior to pour.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 6.2 - Basecourse compaction
label | Inspection / Test Method - Clegg
label | Acceptance Criteria - Mimimum 25.
label | Frequency - Prior to pour.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 7 - KERB AND CHANNEL, NIB, DISH CHANEL
checkpoint | 7.1 - Setout
label | Inspection / Test Method - Survey / string lines
label | Acceptance Criteria - +15mm / -5mm vertical from sub base design surface.
label | Frequency - Prior to pour.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 7.2 - Basecourse compaction
label | Inspection / Test Method - Clegg
label | Acceptance Criteria - Mimimum 25.
label | Frequency - Prior to pour.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 8 - CLOSEOUT
checkpoint | 8.1 - Collate and supply Producer Statements / Waranty Schedules
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Collate and supply producer statements
label | Frequency - Upon completion of bulk roadworks
label | Verifying Documents - Producer statements
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | 8.2 - Collate and supply as builts
label | Inspection / Test Method - Documate review / as builts
label | Acceptance Criteria - Collate and supply as-builts.
label | Frequency - Upon completion of roadworks
label | Verifying Documents - As-builts
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checklist | ITP - Stormwater | itp |  |  |  |  | ITP - Stormwater Rev 1
section | 1 - PRELIMINARY / GENERAL
checkpoint | 1.1 - Consents and trench opening notices
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Authority approvals.
label | Frequency - Prior to excavation
label | Verifying Documents - Approval from relevant authorities.
label | Inspection Point: Engineer / Client - R
checkpoint | 1.2 - Drainlayer registration
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Certification
label | Frequency - Prior to drain laying works.
label | Verifying Documents - Scanned copy
label | Inspection Point: Engineer / Client - R
section | 2 - MATERIALS
checkpoint | 2.1 - Concrete pipes
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in good condition and compliant with AS/NZS4058 reinforced cast rubber ring jointed, class 2 uless otherwise noted.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.2 - PVC pipes
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise)
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.3 - Precast chambers
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.4 - Access covers and frames
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs). Designed to minimum AS 3996 Class D or better.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.5 - Sump grates
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Complaince with HDC ECoP.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.6 - Concrete Wing wall
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Compliance with NZS 3109 with surface finishes to
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
section | 2.7 - Backfill material
checkpoint | 2.7.1 - Bedding haunching and overlay.
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - 5-14mm clean washed granualr mix.
label | Frequency - Prior to placement.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.7.2 - Fill to subbase
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - AP65 of other approved imported material.
label | Frequency - Prior to placement.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 2.8 - Stormwater pump station
checkpoint | 2.8.1 - Chamber, pumps, controller
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in accordance with the specifications
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
section | 3 - CONSTRUCTION
checkpoint | 3.1 - Set out
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Survey setout information in accordance with the design.
label | Frequency - Prior to excavation.
label | Verifying Documents - Survey file.
label | Inspection Point: Engineer / Client - R
checkpoint | 3.2 - Trenching
label | Inspection / Test Method - Site inspection.
label | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width, pipe dia DN150 - DN300 = 450 - 600mm width, pipe dia DN300 - DN400mm = 700 - 850mm width.
label | Frequency - Prior to pipe laying
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.3 - Pipe laying
label | Inspection / Test Method - Survey
label | Acceptance Criteria - Record level of main upstream and downstream of each chamber. Maximum discrepancy +-10% of design gradient, and maximum +-15mm from design level.
label | Frequency - Prior to backfill.
label | Verifying Documents - Survey as builts
label | Inspection Point: Engineer / Client - R
checkpoint | 3.4 - Chambers / sumps / wingwalls
label | Inspection / Test Method - Survey / site inspection.
label | Acceptance Criteria - Benching in accordance with specifcations and drawings. Position in accordance with the design
label | Frequency - Prior to backfill.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.5 - Pipe bedding / haunching /overlay
label | Inspection / Test Method - Document review site inspection.
label | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines and AS/NZS 3725 for concrete pipelines. Bedding minimum 100mm up to 450 diamter pipe and 150mm pipes > 450mm. For PVC overlay >100mm over pipe and for concrete 1/3 diamter of pipe.
label | Frequency - Prior to backfill.
label | Verifying Documents - Photos or site inspection.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.6 - Backfill
label | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
label | Acceptance Criteria - Minimum 20 Clegg reading
label | Frequency - Prior to placement of each layer of backfill.
label | Verifying Documents - Test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 3.7 - Stormwater pump station
checkpoint | 3.7.1 - Excavation
label | Inspection / Test Method - Site inspection.
label | Acceptance Criteria - Base level in accordance with the design
label | Frequency - Prior to backfill.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.7.2 - Backfill
label | Inspection / Test Method - Clegg for each layer of backfill (not exceeding 200mm depth)
label | Acceptance Criteria - Minimum 20 Clegg reading
label | Frequency - Prior to placement of each layer of backfill.
label | Verifying Documents - Test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 4 - CLOSEOUT
checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Collate and supply producer statements
label | Frequency - Upon completion of stormwater works.
label | Verifying Documents - Producer statements
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | 4.2 - Collate and supply Council inspection reports.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply Council inspection reports.
label | Frequency - Upon completion of stormwater works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.3 - Collate and supply compaction records.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply compaction records.
label | Frequency - Upon completion of stormwater works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
label | Inspection / Test Method - Document review / as builts
label | Acceptance Criteria - Collate and supply as-builts and inspection records.
label | Frequency - Upon completion of stormwater works.
label | Verifying Documents - As-builts
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checklist | ITP - Wastewater | itp |  |  |  |  | ITP - Wastewater Rev 1
section | 1 - PRELIMINARY / GENERAL
checkpoint | 1.1 - Consents and trench opening notices
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Authority approvals.
label | Frequency - Prior to excavation
label | Verifying Documents - Approval from relevant authorities.
label | Inspection Point: Engineer / Client - R
checkpoint | 1.2 - Drainlayer registration
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Certification
label | Frequency - Prior to drain laying works.
label | Verifying Documents - Scanned copy
label | Inspection Point: Engineer / Client - R
section | 2 - MATERIALS
checkpoint | 2.1 - PVC pipes
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in good condition and compliant with AS/NZS1254 or AS/NZS1260 rubber ring jointed, minimum SN8, (unless noted otherwise)
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.2 - Precast chambers
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.3 - Access covers and frames
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs). Designed to minimum AS 3996 Class D or better.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
section | 2.7 - Backfill material
checkpoint | 2.7.1 - Bedding haunching and overlay.
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - 5-14mm clean washed granualr mix.
label | Frequency - Prior to placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.7.2 - Fill to subbase
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - AP65 of other approved imported material.
label | Frequency - Prior top placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 2.8 - Wastewater pump station
checkpoint | 2.8.1 - Chamber, storage, pumps, controller
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in accordance with the specifications
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
section | 3 - CONSTRUCTION
checkpoint | 3.1 - Set out
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Survey setout information in accordance with the design.
label | Frequency - Prior to excavation.
label | Verifying Documents - Survey file.
label | Inspection Point: Engineer / Client - R
checkpoint | 3.2 - Trenching
label | Inspection / Test Method - Site inspection.
label | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width.
label | Frequency - Prior to pipe laying
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.3 - Pipe laying
label | Inspection / Test Method - Survey
label | Acceptance Criteria - Record level of main upstream and downstream of each chamber. Maximum discrepancy +-10% of design gradient, and maximum +-15mm from design level.
label | Frequency - Prior to backfill.
label | Verifying Documents - Survey as builts
label | Inspection Point: Engineer / Client - R
checkpoint | 3.5 - Pipe bedding / haunching /overlay
label | Inspection / Test Method - Document review site inspection.
label | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
label | Frequency - Prior to backfill.
label | Verifying Documents - Photos or site inspection.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.6 - Hydrostatic testing
label | Inspection / Test Method - Document review
label | Acceptance Criteria - In accordance with AS/NZS 3500.2 section 15.2
label | Frequency - Prior to backfill.
label | Verifying Documents - Test records and Council inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.6 - Backfill
label | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
label | Acceptance Criteria - Minimum 20 Clegg reading
label | Frequency - Prior to placement of each layer of backfill.
label | Verifying Documents - Test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 3.7 - Wastewater pump station
checkpoint | 3.7.1 - Excavation
label | Inspection / Test Method - Site inspection.
label | Acceptance Criteria - Excavation levels in accordance with the design
label | Frequency - Prior to backfill.
label | Verifying Documents - Engineer approval.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 3.7.2 - Backfill
label | Inspection / Test Method - Clegg for each layer of backfill (not exceeding 200mm depth)
label | Acceptance Criteria - Minimum 20 Clegg reading
label | Frequency - Prior to placement of each layer of backfill.
label | Verifying Documents - Test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 4 - CLOSEOUT
checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Collate and supply producer statements
label | Frequency - Upon completion of wastewater works.
label | Verifying Documents - Producer statements
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | 4.2 - Collate and supply Council inspection reports.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply Council inspection reports.
label | Frequency - Upon completion of wastewater works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.3 - Collate and supply compaction records.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply compaction records.
label | Frequency - Upon completion of wastewater works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
label | Inspection / Test Method - Document review / as builts
label | Acceptance Criteria - Collate and supply as-builts and inspection records.
label | Frequency - Upon completion of wastewater works.
label | Verifying Documents - As-builts / test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checklist | ITP - Water Supply | itp |  |  |  |  | ITP - Water Supply Rev 1
section | 1 - PRELIMINARY / GENERAL
checkpoint | 1.1 - Consents and trench opening notices
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Authority approvals.
label | Frequency - Prior to excavation
label | Verifying Documents - Approval from relevant authorities.
label | Inspection Point: Engineer / Client - R
checkpoint | 1.2 - Installer registration
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Certification
label | Frequency - Prior to drain laying works.
label | Verifying Documents - Scanned copy
label | Inspection Point: Engineer / Client - R
section | 2 - MATERIALS
checkpoint | 2.1 - PVC pipes
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in good condition and compliant with AS/NZS1477 (min PN9)
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.1 - PE pipes
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in good condition and compliant with AS/NZS1430 (min PN12.5)
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.2 - Precast chambers
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Compliant to AS/NZS4058, with concrete lids designed to HN-HO-72 traffic loadings in roads.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.3 - Access covers and frames
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Removable with a clear opening >600mm (except for non-access MHs). Designed to minimum AS 3996 Class D or better.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
section | 2.7 - Backfill material
checkpoint | 2.7.1 - Bedding haunching and overlay.
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - 5-14mm clean washed granualr mix.
label | Frequency - Prior to placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.7.2 - Fill to subbase
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - AP65 of other approved imported material.
label | Frequency - Prior top placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 3 - CONSTRUCTION
checkpoint | 3.1 - Set out
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Survey setout information in accordance with the design.
label | Frequency - Prior to excavation.
label | Verifying Documents - Survey file.
label | Inspection Point: Engineer / Client - R
checkpoint | 3.2 - Trenching
label | Inspection / Test Method - Site inspection.
label | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width.
label | Frequency - Prior to pipe laying
label | Verifying Documents - Engineer approval.
label | Inspection Point: Engineer / Client - S
checkpoint | 3.3 - Pipe laying
label | Inspection / Test Method - Survey
label | Acceptance Criteria - Alignment +-50mm from design, surface cover in accordance with HDC ECoP.
label | Frequency - Prior to backfill.
label | Verifying Documents - Survey as builts
label | Inspection Point: Engineer / Client - R
checkpoint | 3.5 - Pipe bedding / haunching /overlay
label | Inspection / Test Method - Document review site inspection.
label | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
label | Frequency - Prior to backfill.
label | Verifying Documents - Photos or site inspection.
label | Inspection Point: Engineer / Client - S
checkpoint | 3.6 - Pressure test
label | Inspection / Test Method - Inspection.
label | Acceptance Criteria - In accordance with section C3 of NZS4404 and AS/NZS 2556. To a pressure no less than 800kPa and no greater than 25% above the rated pressure of the pipeline.
label | Frequency - Prior to backfill over joints and fittings wherever possible.
label | Verifying Documents - Test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - W
holdpoint | HOLD POINT
checkpoint | 3.8 - Backfill
label | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
label | Acceptance Criteria - Minimum 20 Clegg reading
label | Frequency - Prior to placement of each layer of backfill.
label | Verifying Documents - Test records.
label | Inspection Point: Engineer / Client - S
checkpoint | 3.7 - Disinfection
label | Inspection / Test Method - Inspection.
label | Acceptance Criteria - Carried out in accordance with HDC ECoP (amended appendix D of NZS4404:2010.
label | Frequency - Prior to connectioun to mains supply
label | Verifying Documents - Test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - W
holdpoint | HOLD POINT
section | 4 - CLOSEOUT
checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Collate and supply producer statements
label | Frequency - Upon completion of Water supply works.
label | Verifying Documents - Producer statements
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | 4.2 - Collate and supply Council inspection reports.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply Council inspection reports.
label | Frequency - Upon completion of water supply works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.3 - Collate and supply compaction records.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply compaction records.
label | Frequency - Upon completion of water supply works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
label | Inspection / Test Method - Document review / as builts
label | Acceptance Criteria - Collate and supply as-builts and inspection records.
label | Frequency - Upon completion of water supply works.
label | Verifying Documents - As-builts / test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checklist | ITP - Service Trenching and Ducting | itp |  |  |  |  | ITP - Service Trenching and Ducting Rev 1
section | 1 - PRELIMINARY / GENERAL
checkpoint | 1.1 - Consents and trench opening notices
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Authority approvals.
label | Frequency - Prior to excavation
label | Verifying Documents - Approval from relevant authorities.
label | Inspection Point: Engineer / Client - R
section | 2 - MATERIALS
checkpoint | 2.1 - PVC ducts
label | Inspection / Test Method - Document review
label | Acceptance Criteria - New and in good condition and compliant.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
checkpoint | 2.2 - Chambers / pits
label | Inspection / Test Method - Document review
label | Acceptance Criteria - ACO type pits with class D covers in accordance with the specifications.
label | Frequency - Prior to order
label | Verifying Documents - Technical documents.
label | Inspection Point: Engineer / Client - R
section | 2.7 - Backfill material
checkpoint | 2.7.1 - Bedding haunching and overlay.
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - 5-14mm clean washed granualr mix.
label | Frequency - Prior to placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
checkpoint | 2.7.2 - Fill to subbase
label | Inspection / Test Method - Inspection
label | Acceptance Criteria - AP65 of other approved imported material.
label | Frequency - Prior top placement.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
holdpoint | HOLD POINT
section | 3 - CONSTRUCTION
checkpoint | 3.1 - Set out
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Survey setout of chambers / pits in accordance with the design - marked on site
label | Frequency - Prior to excavation.
label | Verifying Documents - Survey file / site inspection.
label | Inspection Point: Engineer / Client - W
checkpoint | 3.2 - Trenching
label | Inspection / Test Method - Site inspection.
label | Acceptance Criteria - Trench widths ok and no unsuitable materials present. Min widths: pipe dia DN75 - DN150 = 350mm width. Min covers in accordance with the specifications.
label | Frequency - Prior to pipe laying
label | Verifying Documents - Engineer approval.
label | Inspection Point: Engineer / Client - S
checkpoint | 3.5 - Pipe bedding / haunching /overlay
label | Inspection / Test Method - Document review site inspection.
label | Acceptance Criteria - In accordance with AS/NZS 2566 for PVC pipelines. For PVC overlay >100mm over pipe.
label | Frequency - Prior to backfill.
label | Verifying Documents - Photos or site inspection.
label | Inspection Point: Engineer / Client - S
checkpoint | 3.8 - Backfill
label | Inspection / Test Method - Clegg every 10m alignment for each layer of backfill (not exceeding 200mm)
label | Acceptance Criteria - Minimum 20 Clegg reading
label | Frequency - Prior to placement of each layer of backfill.
label | Verifying Documents - Test records.
label | Inspection Point: Engineer / Client - S
section | 4 - CLOSEOUT
checkpoint | 4.1 - Collate and supply Producer Statements / Waranty Schedules
label | Inspection / Test Method - Document review
label | Acceptance Criteria - Collate and supply producer statements
label | Frequency - Upon completion of Water supply works.
label | Verifying Documents - Producer statements
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - H
holdpoint | HOLD POINT
checkpoint | 4.2 - Collate and supply Council inspection reports.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply Council inspection reports.
label | Frequency - Upon completion of water supply works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.3 - Collate and supply compaction records.
label | Inspection / Test Method - Document review.
label | Acceptance Criteria - Collate and supply compaction records.
label | Frequency - Upon completion of water supply works.
label | Verifying Documents - Inspection records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT
checkpoint | 4.4 - Collate and supply as builts / CCTV inspections / water tests
label | Inspection / Test Method - Document review / as builts
label | Acceptance Criteria - Collate and supply as-builts and inspection records.
label | Frequency - Upon completion of water supply works.
label | Verifying Documents - As-builts / test records.
label | Inspection Point: Sub Contractor - H
label | Inspection Point: Head Contractor - H
label | Inspection Point: Engineer / Client - S
holdpoint | HOLD POINT