## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP-085-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0085 - SUP INSTALLATION (HCC)
checkpoint-group | Lot Information
checkpoint-status | 1.0 Lot Information
text | Lot Created On
text | Lot Opened On
text | Work Commenced On
select | Lot Type | CIL - Civil Lot
text | From and To Chainage
select | Construction Element | PAVI - Paving
select | Activity | SHUP – Shared User Path
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
checkpoint-group | 1 - Preliminary Works
checkpoint-status | 1.1 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | - - - - - - - - -
label | Reference Documents: Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Latest Revision Drawings
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint-status | 1.2 - Bedding Material / Base Layer
label | Frequency: Once, for each mix design, prior to placement of material
label | - - - - - - - - -
label | Acceptance Criteria: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
label | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 703.21 812.04
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Teambinder reference number
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer Superintendent
checkpoint-status | 1.3 - Concrete Mix
label | Frequency: Once, for each mix design, prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | • Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads.
label | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
label | • Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
text | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents: IFC Drawings 703.05 (a) 703.07
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Teambinder reference number
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.4 - Evaporative Retardant
label | Frequency: Once, for each product, prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents: 703.09
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Teambinder reference number
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.5 - Curing Compound
label | Frequency: Once, for each product, prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | Enter: Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents: 703.10 (a)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Teambinder reference number
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-group | 2 - Construction Works
checkpoint-status | 2.2 - Temporary Drainage Provisions (if required)
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Before obstructing any waterway, channel or culvert, the Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority.
label | • The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, VicRoads Spec Cl.703.18
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Written approval from relevant waterway authority, ITP Signed
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.3 - Pavement Thickness Increases for Crossings
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
label | i. Pram crossings
label | ii. Vehicle crossings (residential and/or commercial)
label | iii. Established / existing mature trees
label | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings
label | • VicRoads Spec 703.16 703.24 EDCM 401
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Superintendent/ Supervisor / Site Engineer
checkpoint-status | 2.4 - Subgrade Preparation
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: Subgrade to be test rolled to ensure the substrate is adequate for bedding and concrete placement
label | - - - - - - - - -
label | Reference Documents: WP 011
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.5 - Bedding Preparation
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: All bedding material shall be as specified on design drawings.
label | • Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface. Bedding to be compacted to 98% standard.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec Cl.703.21 812, 820
label | • IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.6 - Formwork
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec Cl.703.12
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.7 - Steel Reinforcement
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671. If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
label | • The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
label | • Reinforcement shall be supported using either concrete or plastic chairs.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec Cl.703.13 & Cl.703.13 AS/NZS 4671
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.8 - Pre-pour inspection
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b)(c)(d), AS 1379
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Project Engineer, Superintendent/Council & Surveyor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 2.9 - Concrete Testing
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria:
label | ○ Concrete Testing Frequency:
label | • 0m³ to 50m³ = 1 sample
label | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | • Compressive strength cylinders = 2 no. 28 day strength.
label | ○ Slump Testing Tolerances:
label | • <60mm = ±10mm
label | • ≥60mm to ≤80mm = ±15mm
label | • >80mm to ≤110mm = ±20mm
label | • >110mm to ≤150mm = ±30mm
label | • >150mm = ±40mm
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec 703.11
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Concrete Pour Record, ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.10 - Curing
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete
label | • Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec Cl. 703.10
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.11 - Tolerances
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm.
label | • Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
label | • Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl 703.15
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.12 - Joints
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: Expansion Joints: shall be placed at intervals as specified by the drawings.
label | • Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
label | • Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec Cl. 703.26 (b)
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.13 - Stripping Formwork
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | i. 2 days for vertical formwork on external surfaces; and
label | ii. 1 day for vertical forms on permanently hidden surfaces
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec 703.12, AS3610 Table C2
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 2.14 - Protection of Newly Poured Concrete
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec 703.27
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-group | 3 - Post-Construction
checkpoint-status | 3.1 - Survey data captured for as-built purposes
label | Frequency: Completion of each lot
label | - - - - - - - - -
label | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements.
label | • Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
label | • As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings / survey records
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: As-built survey records
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Project Engineer
checkpoint-status | 3.2 - Cracking of Concrete
label | Frequency: Each Lot
label | - - - - - - - - -
label | Acceptance Criteria: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl. 703.30 687
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 3.2 - Compressive Strength Test Results
label | Frequency: Completion of each lot
label | - - - - - - - - -
label | Acceptance Criteria: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, Relevant Council Drawings 703.11, Table 703.111
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Attach: Compressive Strength Test Results
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-status | 3.3 - Backfilling
label | Frequency: Completion of each lot
label | - - - - - - - - -
label | Acceptance Criteria: Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing, topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl 703.29
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Supervisor / Site Engineer
checkpoint-group | 4 - Completion
checkpoint-status | 4.1 - As-built Survey
label | Frequency: Completion of each lot
label | - - - - - - - - -
label | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | • Departure from RL = ±10mm
label | • Departure from alignment = ±10mm
label | • Rate of change of deviation from RL or alignment = 10mm in 10m
label | • Irregularities in alignment = 5mm in 3m
label | • Section dimensions = ±5mm
label | • Section dimensions (less than 25mm) = ±3mm
label | • Width of pavement = -5mm, +15mm
label | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | Attach: Survey As-builts / Survey Report
label | - - - - - - - - -
label | Reference Documents: IFC Drawings, VicRoads Spec 703.15
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 4.2 - Red-Line Markup
label | Frequency: Completion of each lot
label | - - - - - - - - -
label | Acceptance Criteria: Capture any changes in design or RFI's as per approved red-line markup procedure
label | - - - - - - - - -
label | Reference Documents: Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 4.3 - Non-conformance Report (NCR) Closure
label | Frequency: Completion of each lot
label | - - - - - - - - -
label | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | - - - - - - - - -
label | Reference Documents: Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date:
text | Work Completed On
holdpoint | Add Signature
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd (Quality Manager),Abid Hameed (Area 1 Manager),Nicola Lodo (Area 2 Manager),Nicholas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
text | Lot Closed On
text | comments
checklist-sectioned | ITP-016-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0016 - Bored Pile Construction
checkpoint-group | Lot Information
checkpoint-status | 1.0 Lot Information
text | Lot Created On
text | Lot Opened On
text | Work Commenced On
select | Lot Type | CIL - Civil Lot, DRL - Drainage Lot, EAL - Earthworks Lot, ELL - Electrical Lot, UTL - Utility Lot, STL - Structural Lot
text | From and To Chainage
select | Construction Element | FOUN - Foundation
select | Activity | BORP - Bored Pile
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
checkpoint-group | 1 - Preliminary Works / Design and Submissions
checkpoint-status | 1.1 - Induction
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been inducted to the CRG site
label | - - - - - - - - -
label | Reference Documents: Site Induction Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Site induction signed.
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint-status | 1.2 - Work pack briefing
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been briefed on the relevant work park relating to scope of works.
label | - - - - - - - - -
label | Reference Documents: WP
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Work pack signed.
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint-status | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | Frequency: Prior to commencing
label | - - - - - - - - -
label | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | - - - - - - - - -
label | Reference Documents: Health and Safety Co-Ordination Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: SWMS(s) signed
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.4 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | - - - - - - - - -
label | Reference Documents: Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: This ITP Signed
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint-status | 1.5 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environmental controls are in place
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP.
label | - - - - - - - - -
label | Reference Documents: CEMP
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: This ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.6 - Excavation Permit issued
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
label | - - - - - - - - -
label | Reference Documents: Excavation Permit
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Excavation Permit #
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.7 - Traffic Management (When required)
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Approved WTMP and MOA
label | - - - - - - - - -
label | Reference Documents: WTMP
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Superintendents Correspondence
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.8 - Mix design
label | Frequency: No less than 4 weeks prior to commencement of activity
label | - - - - - - - - -
label | Acceptance Criteria: The concrete mix design details shall be submitted for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.610.07(b)
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Approved Mix Design
label | Allocated registration number on the Register of VicRoads approved concrete mixes.
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Project Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 1.9 - Steel Reinforcement
label | Frequency: Prior to commencing works and no more than 14 days after contract award
label | - - - - - - - - -
label | Acceptance Criteria: Steel reinforcement shall comply with the requirements of Section 611. Unless otherwise shown on drawings, bars shall be grade 500N. Allowances should be made when preparing the steel reinforcement schedule to achieve the specified tolerances on member dimensions, concrete cover and location of steel reinforcement
label | Manufacturer of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance with this clause shall be submitted to the superintendent within 14 days of award of the contract.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.611.03(a)
label | Cl.611.04
label | Cl611.05(a)
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Submitted Product Details
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Project Engineer
checkpoint-status | 1.10 - Quality Procedure for pile construction
label | Frequency: No less than 4 weeks prior to commencement of activity
label | - - - - - - - - -
label | Acceptance Criteria: A quality procedure for the construction of the piles shall be submitted to the Superintendent not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
label | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent.
label | The Contractor shall submit the procedure for placing concrete in bored piles, under water and in dry bores, for review by the Superintendent at least four weeks prior to concreting.
label | Concrete shall not be placed in bored piles, under water or in a dry bore until the proposed method of placement of concrete has been approved by the Superintendent.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.606.03(a)
label | Cl.606.06(a)
label | Cl.610.18(c)
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Approval of Quality Procedure for piles construction
label | Procedure for placing concrete reviewed
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Project Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 2 - Boring
checkpoint-status | 2.1 - Survey set-out
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | - - - - - - - - -
label | Reference Documents: Project Spec. Cl.1190.06
label | Latest IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: This ITP Signed, Survey Records
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Surveyor
checkpoint-status | 2.2 - Protection of Adjacent Piles
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: No pile shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15MPa
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.606.04
label | - - - - - - - - -
label | Inspection / Test Method: Visual Inspection
label | - - - - - - - - -
label | Record of conformity: This ITP Signed, Bored Pile Checklist
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 2.3 - Excavation levels
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Check the toe levels conform to the drawing.
label | - - - - - - - - -
label | Reference Documents: Latest IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 2.4 - Inspection of Pile Excavation
label | Frequency: Each Pile, a minimum of 48 hrs notice given to the Superintendent for arrangement of the inspection of the pile excavation
label | - - - - - - - - -
label | Acceptance Criteria: The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.606.05
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Pile walls and base inspected by Superintendent, This ITP signed off
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 2.5 - Check reinforcement cages
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Steel Reinforcement shall be securely held during placing and compacting of concrete. Steel reinforcements shall be made of concrete blocks of a strength similar to the structure, strong enough to withstand the imposed loads without movement of the steel reinforcement. No other materials to be used as supports.
label | Spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
label | Reinforcement as per drawings and specification.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.606.06(a)
label | Cl.611.03(a)
label | Cl.611.04
label | Cl.611.10
label | Project Specification
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Bored Pile Checklist CRU-FH-CL-0006
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 2.6 - Pre – pour checklist
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Bored Pile Checklist completed and signed.
label | - - - - - - - - -
label | Reference Documents: Work Pack
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-group | 3 - Placing and Finishing Concrete
checkpoint-status | 3.1 - Carry out sampling of concrete
label | Frequency: As per table 610.161
label | - - - - - - - - -
label | Acceptance Criteria: Slump flow: 550-800mm spread
label | T500 time: Achieve a spread of 500 mm within 1 to 5 seconds
label | Passing ability ≤ 10 mm.
label | Observations as per Table 610.131 of VicRoads Spec.
label | – Three cylinders taken from the same sample used to test. 1 cylinder crushed at 7 days. 2 cylinders crushed at 28 days
label | – Number of samples taken shall be as per Table 610.161
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.610.13(b)
label | Cl.610.16(b)
label | Cl.610.16(n)
label | Table 610.131
label | Table 610.161
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection, Site Sampling
label | - - - - - - - - -
label | Record of conformity: Concrete Pour Record CRG-FH-CL-0003 and Bored Pile Checklist CRG-FH-CL-0006 completed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 3.2 - Place Concrete
label | Frequency: Each Concrete pour
label | - - - - - - - - -
label | Acceptance Criteria: Piles shall be concreted within 24 hours of completion of the pile excavation.
label | Discharge time between truckloads for the same cast to be <45 mins.
label | All concrete to be placed within 60 minutes from batch or as specified in the approved VR mix.
label | Each batch (truckload) of concrete delivered to site shall be visually inspected to ensure consistency of concrete supply, and the estimated slump shall be recorded on the identification certificate for the batch.
label | Piles places in the dry shall be constructed to a minimum of 300mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec.
label | Cl.610.16(b)
label | Cl.610.16(c)
label | Cl.610.13(f)
label | CL.606.06(a)
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Concrete Pour Record, Bored Pile Checklist, Concrete dockets
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-group | 4 - Testing Requirements
checkpoint-status | 4.1 - Pile Testing
label | Frequency: Representative Sample determined in consultation with the Superintendent.
label | - - - - - - - - -
label | Acceptance Criteria: Unless dispensation is granted, a representative sample of piles shall be tested by a consultant prequalified to VicRoads as per the requirements of Section 606.07 including:
label | (A) Integrity Testing - First 6 piles constructed, then 1 in 3 remaining.
label | (B) Static Load Testing
label | (C) Dynamic Load Testing - 1 in 10 Piles with a pile depth within 2m.
label | Results including raw data are to be provided to the superintendent per the timeframes requested but no less than 48 hours after collection of results.
label | - - - - - - - - -
label | Reference Documents: Project Spec. Cl.3050.07
label | VicRoads Spec. Cl.606.07
label | - - - - - - - - -
label | Inspection / Test Method: Test report
label | - - - - - - - - -
label | Record of conformity: Test reports provided to Superintendent, This ITP signed off
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Superintendent
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 4.2 - Concrete Test Results
label | Frequency: Each sample
label | - - - - - - - - -
label | Acceptance Criteria: Minimum 7 day strength (26MPa) achieved as per table 610.051
label | Minimum 28 strength (40MPa) achieved
label | Strength average of tested cylinders
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.610.05
label | Table 610.051
label | - - - - - - - - -
label | Inspection / Test Method: Test report
label | - - - - - - - - -
label | Record of conformity: Compressive Strength (MPa) Test report, This ITP signed off
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 4.3 - Tolerance Check & As Built survey
label | Frequency: Each pile
label | - - - - - - - - -
label | Acceptance Criteria: Check Tolerances & Survey Pile positions:
label | (a) pile head shall finish within 75 mm of the specified plan position;
label | (b) variation from the vertical or the specified batter/rake shall not be more than 1 in 100;
label | (c) where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line shall not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths.
label | Mark all details correctly on as-builts
label | Pile head position & verticality
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.606.08
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection/ Document review
label | - - - - - - - - -
label | Record of conformity: Survey report
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Surveyor
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
text | Work Completed On
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
text | Lot Closed On
text | comments
checklist-sectioned | ITP-009-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0009 - Unbound Pavements
checkpoint-group | Lot Information
checkpoint-status | 1.0 Lot Information
text | Lot Created On
text | Lot Opened On
text | Work Commenced On
select | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | From and To Chainage
select | Construction Element | PAVI - Paving
select | Activity | SUC4 - Subbase - Class 4
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
checkpoint-group | 1 - Preliminary Works
checkpoint-status | 1.1 - Induction
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All personnel on site have been inducted to the CRU site
label | - - - - - - - - -
label | Reference Documents: PMP Inductions Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Site induction signed.
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint-status | 1.2 - Check that current revision drawings are being used
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
label | - - - - - - - - -
label | Reference Documents: Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of conformity: Latest Revision Drawings
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Site Engineer / Site Foreman
checkpoint-status | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | - - - - - - - - -
label | Reference Documents: EMP, Site induction, Project Specification Cl. 1200.03
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
label | Frequency: Prior to commencing
label | - - - - - - - - -
label | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
label | - - - - - - - - -
label | Reference Documents: Project General Specsefication Cl.1125.07 Health and Safety Coordination Plan
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: SWMS(s) signed
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.5 - Crushed Rock Mix design
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl.812.04
label | - - - - - - - - -
label | Inspection / Test Method: Document Review
label | - - - - - - - - -
label | Record of conformity: Mix Design VicRoads Approval
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Superintendent
holdpoint | HOLD POINT AUTHORITY
checkpoint-status | 1.6 - Excavation Permit issued
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
label | - - - - - - - - -
label | Reference Documents: Excavation Permit
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Excavation Permit #
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 1.7 - Traffic Management (When required)
label | Frequency: Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria: Approved TMP and MOA
label | - - - - - - - - -
label | Reference Documents: TMP
label | - - - - - - - - -
label | Inspection / Test Method: Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity: Approved TMP & MOA
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-group | 2 - Placing Fill
checkpoint-status | 2.1 - Transverse Joints
label | Frequency: Check prior to placing material
label | - - - - - - - - -
label | Acceptance Criteria: * Material should be spread to minimize number of joints. * Transverse joints shall be offset from one layer to next by not less than 2 metres * Transverse joints shall be offset from one layer to the next by not less than 2 m.
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl.304.07 (a, b & c)
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 2.2 - Longitudinal Joints
label | Frequency: Check prior to placing material
label | - - - - - - - - -
label | Acceptance Criteria: * Material should be spread to minimize number of joints. * longitudinal joints shall be offset from one layer to the next by not less than 150 mm. * longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl.304.07 (a, d & e)
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 2.3 - Lot Size
label | Frequency: Check prior to placing material
label | - - - - - - - - -
label | Acceptance Criteria: A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser. For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173.
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl.304.08 (b)(ii & iv) Table 304.111
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 2.4 - Proof Roll
label | Frequency: After placing material
label | - - - - - - - - -
label | Acceptance Criteria: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl.304.08(b)(iv) Cl. 173
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Signed ITP
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Responsibility: Site Engineer & Superintendent
holdpoint | HOLD POINT AUTHORITY
checkpoint-group | 3 - Testing and Inspection
checkpoint-status | 3.1 - Determine Testing Scale & Initial testing frequency
label | Frequency: Prior to Testing
label | - - - - - - - - -
label | Acceptance Criteria: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Table 204.161 VicRoads Specification Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
label | - - - - - - - - -
label | Inspection / Test Method: Document Review/ Site Inspection
label | - - - - - - - - -
label | Record of conformity: Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 3.2 - Modified Compactive Effort
label | Frequency: As per 3.1
label | - - - - - - - - -
label | Acceptance Criteria: Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B. For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six.
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Test Records
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 3.3 - Permeability Testing
label | Frequency: As per 3.1
label | - - - - - - - - -
label | Acceptance Criteria: Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051
label | - - - - - - - - -
label | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.051
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Test Records from Supplier
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 3.4 - Post-compaction Plasticity Index
label | Frequency: After compaction
label | - - - - - - - - -
label | Acceptance Criteria: Post-compaction Plasticity Index must comply with the requirement of table 3040.053. Class 3: 0 < PI < 10.
label | - - - - - - - - -
label | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.053
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Test Records from Supplier
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 3.5 - Post- compaction Grading
label | Frequency: After compaction
label | - - - - - - - - -
label | Acceptance Criteria: The post compaction grading shall comply with the requirements of table 304.101
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Cl. 304.10 Table 304.101
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Test Records from Supplier
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | 3.6 - Test Requisition
text | Test Requested on
text | Location
select | Material Type | Type A,Type B,See comments
select | Material Source | Holcim,Boral,See comments
boolean | Compaction Test (Standard)
boolean | Compaction Test (Modified)
boolean | Maximum Particle Test
boolean | CBR/Swell Test
boolean | PI Test
boolean | Permeability Test
boolean | Grading
boolean | Moisture
boolean | See comments
text | Test Level/ Layer
holdpoint | Test Requisition
checkpoint-status | 3.7 - Survey Level
label | Frequency: At completion
label | - - - - - - - - -
label | Acceptance Criteria: Scale A: Minimum number of measurements per lot: 80 for Upper — Upper Subbase: Mean + 4mm to -8mm wit a maximum Standard Deviation of 8mm — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm — Base: Mean +- 5 with a maximum Standard Deviation of 8mm
label | - - - - - - - - -
label | Reference Documents: VicRoads Specification Table 304.061 Table 304.062
label | - - - - - - - - -
label | Inspection / Test Method: Site Inspection
label | - - - - - - - - -
label | Record of conformity: Test Records
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Responsibility: Site Engineer
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Name:
text | Position:
text | Date:
text | Work Completed On
holdpoint | Add Signature
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
text | Lot Closed On
text | comments
checklist-sectioned | ITP-013-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0013 - Structural Concrete
checkpoint-group | Lot Information
checkpoint-status | 1.0 Lot Information
text | Lot Created On
text | Lot Opened On
text | Work Commenced On
select | Lot Type | STL - Structural
text | From and To Chainage
select | Construction Element | STOR - Stormwater,SUBS - Substructure,SUPE - Superstructure,SUPE - Superstructure
select | Activity | DRAP - Drainage Pit,PIEH - Pier Head,OFSB - Off-structure Barrier,ONSB - On-structure Barrier
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
checkpoint-group | 1 - Referenced Documentation
checkpoint-status | Referenced Documentation
label | Document Title: ITP-013-AX-LOT-XXX - Description
label | ITP Description: Structural Concrete
label | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0013
label | Revision Number: 00
label | Revision Date: 26/05/2022
label | ITP created by: Omar El-Khub
label | ITP approved for use by: Babak Rudd
label | 1.1 VicRoads Section 204 Dec 2015
label | 1.2 VicRoads Section 602 Oct 2007
label | 1.3 VicRoads Section 610 Feb 2020
label | 1.4 VicRoads Section 611 Nov 2018
label | 1.5 VicRoads Section 613 Jun 2017
label | 1.6 VicRoads Section 614 Jun 2017
label | 1.7 AS5100
label | 1.8 AS3810
checkpoint-group | 2 - Preliminaries - Materials
checkpoint-status | 2.1 - Concrete mix design
label | Frequency - Each Mix, not less than 4 weeks prior to the placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Ensure all mix designs have been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | Concrete Mix is Registered with VicRoads.
label | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.07(b)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved Mix design
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 2.2 - Reinforcement Certification
label | Frequency - Once for each supplier, 14 days of award of contract
label | - - - - - - - - -
label | Acceptance Criteria - Ensure the manufacturer and supplier of the steel reinforcement is in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance submitted to superintendent within 14 days of contract award.
label | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.611.04
label | Cl.611.05(a)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - ACRS Certificate of Approval.
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 2.3 - Bar Chairs/Aspros Certification
label | Frequency - Once for each supplier, 14 days of award of contract
label | - - - - - - - - -
label | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.26 (a)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved bar chairs and aspros
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 2.4 - Evaporative Retardant
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.17 (f)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved evaporative retardant
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 2.5 - Curing Compound
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | Teambinder Material Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.23 (b)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved curing compound
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 3 - Preliminary Works
checkpoint-status | 3.1 - Concrete Placement and Compaction Work Method Statements
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to MRPV
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.18 (a) (i)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved WMS
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.2 - Concrete Sampling and Testing Procedure
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to MRPV
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.18 (a) (v)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved procedure
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | Minutes of this meeting to be submitted to MRPV
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.18 (a) (iv)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved quality requirements
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | Frequency - Once, 2 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to MRPV.
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.17
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved procedure
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.5 - Curing Methodology (for Concrete and Grout)
label | Frequency - Once, 4 weeks prior to placement of concrete
label | - - - - - - - - -
label | Acceptance Criteria - Curing methodology/procedure to be submitted for review to MRPV.
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.23 (a)
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved methodology
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.6 - Concrete Drilling Procedure
label | Frequency - Where applicable, once, 2 days prior to drilling
label | - - - - - - - - -
label | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | The planned locations and drilling procedure shall be submitted for review to MRPV.
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.46
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Approved drilling location and procedure
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 4 - Pre-construction activities
checkpoint-status | 4.1 - Check that IFC drawings are being used
label | Frequency - Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria - Issued For Construction (IFC) and latest available revision on TeamBinder is used
label | - - - - - - - - -
label | Reference Documents - Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Latest Revision Drawings
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer / Site Foreman
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 4.2 - Survey set out works
label | Frequency - Prior to Work Commencement
label | - - - - - - - - -
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used
label | - - - - - - - - -
label | Reference Documents - Project Spec.
label | Cl.1190.06
label | - - - - - - - - -
label | Inspection / Test Method - Site inspection
label | - - - - - - - - -
label | Record of conformity - Survey records & pegs on the ground This ITP Signed off
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Site Engineer, Foreman & Surveyor
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 4.3 - Excavation Permit issued
label | Frequency - Prior to Commencing Work
label | - - - - - - - - -
label | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
label | - - - - - - - - -
label | Reference Documents - Excavation Permit
label | - - - - - - - - -
label | Inspection / Test Method - Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity - Excavation Permit #
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 4.4 - Excavation Inspection
label | Frequency - Where applicable, prior to placing blinding concrete
label | - - - - - - - - -
label | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.602.03
label | - - - - - - - - -
label | Inspection / Test Method - Site inspection
label | - - - - - - - - -
label | Record of conformity - Superintendent approval
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Site Engineer/ Project Engineer
label | - - - - - - - - -
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 5 - Construction Activities - Formwork
checkpoint-status | 5.1 - Formwork Design and Construction
label | Frequency - Each Pour/ Type of element
label | - - - - - - - - -
label | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.614.04
label | CI.614.05
label | Cl.614.06
label | Table 614.041
label | - - - - - - - - -
label | Inspection / Test Method - Document review & Site inspection
label | - - - - - - - - -
label | Record of conformity - Proof Engineering Certificate approved This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | Frequency - Each element (where greater than 2m)
label | - - - - - - - - -
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres
label | All other concrete members
label | Any member for which self-compacting concrete is proposed.
label | Attach: Attachment A
label | Attach: Attachment B
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.614.08
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | Visual
label | Measure
label | - - - - - - - - -
label | Record of conformity - ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Temporary Works Designer
label | Proof Engineer
label | SE/PE/SPE
label | - - - - - - - - -
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | Frequency - Each element (where 2m or less)
label | - - - - - - - - -
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
label | Attach: Attachment C
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.614.08
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | Visual
label | Measure
label | - - - - - - - - -
label | Record of conformity - ConQA Hold Point Release
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | PE/SPE
label | - - - - - - - - -
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 5.4 - Reinforcement Placement
label | Frequency - Each Structure
label | - - - - - - - - -
label | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | Projecting reinforcement is the correct length and location.
label | Splice lengths achieve the minimum length and are in contact for this length.
label | The reinforcement surface condition is free from dirt, debris and damage.
label | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec 611.06
label | 611.09
label | 611.1
label | 611.11
label | 611.12
label | - - - - - - - - -
label | Inspection / Test Method - Measure
label | Visual
label | - - - - - - - - -
label | Record of conformity - This ITP Signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Foreman
label | SE/PE/SPE
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 5.5 - Pre-pour Inspection
label | Frequency - Prior to concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | Erected formwork within the tolerance as Cl.610.36.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.47
label | Table.610.471
label | Table.610.472
label | Table.610.473
label | Table.610.474
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed/
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Site Engineer/ Surveyor/Foreman
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 6 - Construction Activities - Concrete Pour
checkpoint-status | 6.1 - Construction Joint Preparation
label | Frequency - Each concrete pour, prior placing concrete (As required)
label | - - - - - - - - -
label | Acceptance Criteria - Construction joint preparation in accordance with CL.610.20
label | Existing concrete to be roughened by removing all laitance and sufficient mortar to expose the coarse aggregate to a depth of 3mm.
label | All surfaces should be cleaned, moistened with water with any excess removed immediately prior to placing concrete.
label | Joints shall be at the locations specified on the drawings
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.20
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.2 - Cast-in Items
label | Frequency - Where applicable, each element
label | - - - - - - - - -
label | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | - - - - - - - - -
label | Reference Documents - VicRoads spec.
label | Cl.610.47 (a)
label | AS3180.1 Table 3.3.6.2
label | - - - - - - - - -
label | Inspection / Test Method - Site inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer/ Foreman
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.3 - Weather Conditions & Evaporation Limits
label | Frequency - Prior to concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Unless otherwise approved by the superintendent, the following conditions must be satisfied when placing concrete:
label | a) The temperature of concrete, measured immediately prior to placing, shall not be less than 10⁰ C or greater than 32⁰ C
label | b) Concrete shall not be placed if the air temperature is greater than 35⁰ C or less than 5⁰ C.
label | c) Concrete shall not be placed during rain or when rain appears imminent. Freshly placed concrete shall be protected from the rain
label | d) Rate of evaporation < 0.50 kg/m2/hr. If not, additional controls initiated as per 610.17. Refer to concrete pour record
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. CI.610.17
label | - - - - - - - - -
label | Inspection / Test Method - Visual Inspection
label | Concrete Pour Record
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | Concrete Pour Record
label | Concrete Dockets
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer/ Foreman
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.4 - Concrete Testing - Sampling Frequency
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 0m³ to 10m³ = 1 sample
label | 10m³ to 25m³ = 2 samples
label | 25m³ to 50m³ = 3 samples
label | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | For each additional 50m³ and additional sample shall be taken.
label | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.16 (b)
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | Concrete Pour Record
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.5 - Concrete Testing - Slump
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Slump testing tolerances =
label | <60mm = ±10mm
label | ≥60mm to ≤80mm = ±15mm
label | >80mm to ≤110mm = ±20mm
label | >110mm to ≤150mm = ±30mm
label | >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.16 (c)
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.6 - Concrete Testing - Spread, Passability & Viscosity
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Spread range = 550mm to 750mm
label | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | Passability = ≤10mm (aggregate height differential)
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.13 (b)
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.7 - Concrete Testing - Compressive Strength Cylinders
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - Site Sampling and Testing Procedure
label | - - - - - - - - -
label | Inspection / Test Method - Testing
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.8 - Supply & Discharge Rates
label | Frequency - Prior to concrete pour (each load)
label | - - - - - - - - -
label | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | No water is to be added once discharge commences.
label | Maximum time between batching trucks is 25 minutes.
label | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | Concrete is not dropped freely from a height exceeding 2m.
label | Concrete is not moved horizontally by use of vibrators.
label | Record: Required information on the Concrete Pour Record.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.13 (a) & (e )
label | - - - - - - - - -
label | Inspection / Test Method - Visual Inspection
label | - - - - - - - - -
label | Record of conformity - Concrete Pour Record
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer/ Foreman
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 6.9 - Surface Finishes
label | Frequency - Each element
label | - - - - - - - - -
label | Acceptance Criteria - Surface finish as per IFC drawings.
label | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.31
label | Cl.610.20
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 7 - Post-pour Details and Inspection
checkpoint-status | 7.1 - Thermal Differential Monitoring
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | Only applicable if the element has:
label | i. the smallest sectional dimension exceeding 500mm
label | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | Attach: Thermal Monitoring Report
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.22
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Temperature data acquired and proposed control measures to reduce differential temperature submitted to Superintendent for review (if applicable)
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | Subcontractor
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 7.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | Frequency - Each concrete pour
label | - - - - - - - - -
label | Acceptance Criteria - Where IFC drawings do not nominate minimum strength development for removal of formwork, refer to Table 610.251.
label | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.25 (b)
label | Table 610.251
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 7.3 - Surface Inspection - Cracks
label | Frequency - Each element
label | - - - - - - - - -
label | Acceptance Criteria - Repair procedure submitted to the Superintendent. Repair undertaken in accordance with VicRoads Section 687.
label | Cracks investigated and if greater than specified in the table 610.241, an NCR raised. Notwithstanding the requirements of this clause the acceptable crack width at the concrete surface of precast pre-stressed concrete elements shall not exceed 0.1 mm.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.24 (a)
label | Table 610.241
label | Section 687
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Superintendent approval (if applicable)
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 7.4 - Early Age Compressive Strength Test Results - Removal of Formwork
label | Frequency - Each Pour
label | - - - - - - - - -
label | Acceptance Criteria - No fill is to be placed against concrete within 14 days of casting in accordance with the requirements of Clause 204.11 of Section 204. Proposed placement prior to 14 days from casting shall comply with the early application of loading requirements of Clause 610.16(l) or maturity testing requirements of Clause 610.16(m).
label | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | CI.610.35 Cl.204.11(b)
label | Table 204.111
label | Cl.610.16(m)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Holdpoint released
label | This ITP signed
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Site Engineer/ Superintendent
label | - - - - - - - - -
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 7.5 - Compressive Strength Result
label | Frequency - Each Specimen
label | - - - - - - - - -
label | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Attach: Compressive Strength Test Results
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | CI.610.16 (g)
label | Table 610.051
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | - - - - - - - - -
label | Record of conformity - Concrete Test Result
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 7.6 - Post Pour Concrete Cover
label | Frequency - Every 25m2 or part thereof.
label | - - - - - - - - -
label | Acceptance Criteria - Concrete cover meter check one 3m² test area for every 25m² exterior surface area.
label | Minimum 10 no. measurements recorded in each area.
label | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | Attach: cover meter Check Record
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec.
label | Cl.610.34
label | IFC drawings
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 7.7 - Prepare As Built Drawings
label | Frequency - Prior to lot closure
label | - - - - - - - - -
label | Acceptance Criteria - As-built survey completed and drawings (IFC Mark up Drawings) prepared for the lot and copy of the drawings kept in the files
label | The tolerances listed in Tables 610.471, 610.472, 610.473 and 610.474 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
label | - - - - - - - - -
label | Reference Documents - IFC Project Drawings
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - As-built survey and drawings
label | This ITP signed
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
text | Work Completed On
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
text | Work Completed On
select | Is the relevant RFI attached to the Lot? | YES,NO,N/A
select | Is the relevant NCR attached to the Lot? | YES,NO,N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES,NO,N/A
select | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | YES,NO,N/A
select | Survey conformance records attached to the Lot? | YES,NO,N/A
select | Subcontractor/ Supplier records attached to the Lot? | YES,NO,N/A
select | Conforming Test Results attached to the Lot? | YES,NO,N/A
select | As built records attached to the Lot? | YES,NO,N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
text | Lot Closed On
text | comments
checklist-sectioned | ITP-006-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep
checkpoint-group | Lot Information
checkpoint-status | 1.0 Lot Information
text | Lot Created On
text | Lot Opened On
text | Work Commenced On
select | Lot Type | EAL - Earthworks Lot
text | From and To chainage
select | Construction Element | EART - Earthwork
select | Activity | TYPB - Type B
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
checkpoint-group | 1 - Preliminaries
checkpoint-status | 1.1 - Check that current revision drawings are being used
label | Frequency - Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
label | - - - - - - - - -
label | Reference Documents - Project Drawings / Drawing Register
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Latest Revision Drawings
label | - - - - - - - - -
label | AP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer / Site Foreman
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 1.2 - Excavation Permit issued
label | Frequency - Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
label | - - - - - - - - -
label | Reference Documents - Excavation Permit
label | - - - - - - - - -
label | Inspection / Test Method - Document review
label | - - - - - - - - -
label | Record of conformity - Excavation Permit #
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 1.3 - Re-Use of insitu material
label | Frequency - Prior to Placing fill
label | - - - - - - - - -
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04.
label | Type B Material shall meet the following requirements:
label | CBR ≥ 1.5%
label | Swell < 2.5%.
label | Attach: Test Certificates
label | - - - - - - - - -
label | Reference Documents - VicRoads Specification
label | Cl. 204.04
label | Cl. 204.06
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - TestResults
label | - - - - - - - - -
label | Material Category agreed with Superintendent
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 1.4 - Type B Material Approval
label | Frequency - Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria - Prior to the import of Type B material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type B material complies with section 204 of the VicRoads Spec.
label | Type B Material shall meet the following requirements:
label | CBR ≥ 1.5%
label | Swell < 2.5%.
label | If parameters are not met, remove 400mm of material mm below Cut Floor Level and replace with conforming Type B material.
label | If removal and replacement of material below the Cut Floor Level is not required, surface shall be loosened to a depth of 150mm and re-compacted to meet the specified requirements.
label | Attach: Test Certificates, Sample Delivery Dockets
text | Teambinder Approval number
label | - - - - - - - - -
label | Reference Documents - VicRoads Specification
label | Cl. 204.04(c)
label | Cl. 204.06(e)
label | Project Specification PS3020.05
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection/ Document Review
label | - - - - - - - - -
label | Record of conformity - Geotechnical Report
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 2 - Cut Activities - 400mm below
checkpoint-status | 2.1 - Survey set-out
label | Frequency - Prior to Placing fill
label | - - - - - - - - -
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
label | The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
label | - - - - - - - - -
label | Reference Documents - Project General Specification Cl.1190.06
label | Latest IFC Drawings
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Survey records & pegs on the ground
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 2.2 - Ground water
label | Frequency - Prior to Commencing (if required)
label | - - - - - - - - -
label | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
label | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | - - - - - - - - -
label | Reference Documents - VicRoads Specification
label | Cl. 204.06(h)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection/ Document Review
label | - - - - - - - - -
label | Record of conformity - Area reviewed by Superintendent
label | Signed ITP
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
holdpoint | Authority Holdpoint
checkpoint-status | 2.3 - Acceptance of Rock Subgrade (when applicable)
label | Frequency - Prior to construction of the regulating layer
label | - - - - - - - - -
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. Cl. 204.06(f)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection/ Document Review
label | - - - - - - - - -
label | Record of conformity - Superintendent acceptance
label | Signed ITP
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
holdpoint | Authority Holdpoint
checkpoint-status | 2.4 - Proof Roll - Cut Floor
label | Frequency - Prior to Placing fill
label | - - - - - - - - -
label | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. Cl. 204.12 Cl.173.03
label | Cl. 204.10(b)
label | Cl. 204.07(d)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Area visually reviewed by Superintendent
label | Signed ITP
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
holdpoint | Authority Holdpoint
checkpoint-status | 2.5 - Compaction Testing
label | Frequency - Each Lot
label | - - - - - - - - -
label | Acceptance Criteria - Frequency = 6 tests per lot
label | Min Frequency (subject to approval) = every second lot
label | Lot = One day's production or 4,000m2, whichever is the lesser
label | Characteristic Density Ratio =
label | 97% minimum when more than 400mm below top of Type B Fill
label | 99% minimum when within 400mm of top of Type B Fill
label | Attach: NATA Compaction Test Report
label | - - - - - - - - -
label | Reference Documents - Table 204.131
label | Section 204.13, 204.14
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | - - - - - - - - -
label | Record of conformity - Sign ITP
label | NATA Compaction Test Report
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 2.6 - Survey Pickup
label | Frequency - Prior to Placing fill
label | - - - - - - - - -
label | Acceptance Criteria - Ensure the Cut Floor Level is recorded by survey
label | - - - - - - - - -
label | Reference Documents - VicRoads Specification
label | Cl. 204.03(f)
label | Cl. 204.03(g)
label | Table 204.031
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | - - - - - - - - -
label | Record of conformity - Survey As-Built
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 3 - Fill Activities
checkpoint-status | 3.1 - Placement of Fill
label | Frequency - Each Lot
label | - - - - - - - - -
label | Acceptance Criteria - Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
label | Each layer shall be keyed in to the layer above by means of a textured surface
label | Any rocky material present must be uniform throughout the layer.
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. Cl. 204.10(d)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.2 - Preparation of final surface - Subgrade
label | Frequency - Prior to construction of subgrade layer
label | - - - - - - - - -
label | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water)
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. Cl. 204.15 Cl. 204.03
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Signed ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.3 - Trimming and level conformity
label | Frequency - Each Lot (one day's production) prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria - Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping does not differ by the mean values of more than 5 mm above or 15 mm below the specified level.
label | The level at any point of the subgrade shall not lie more than 20mm below a 3m straightedge in any direction accepting crowns.
label | - - - - - - - - -
label | Reference Documents - VicRoads Specification
label | Cl. 204.03(f)
label | Cl. 204.03(g)
label | Table 204.031
label | - - - - - - - - -
label | Inspection / Test Method - Survey Report
label | - - - - - - - - -
label | Record of conformity - Survey Record
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.4 - Proof Roll - Top of fill layer
label | Frequency - Prior to Placing fill
label | - - - - - - - - -
label | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
label | Superintendent to be present during all test rolling.
label | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
label | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
label | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. Cl. 204.12 Cl.173.03
label | Cl. 204.10(b)
label | Cl. 204.07(d)
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Area visually reviewed by Superintendent
label | - - - - - - - - -
label | Signed ITP
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
label | - - - - - - - - -
text | Date Completed:
label | - - - - - - - - -
holdpoint | Authority Holdpoint
checkpoint-status | 3.5 - Post-compaction Testing
label | Frequency - Each Lot
label | - - - - - - - - -
label | Acceptance Criteria - Post compaction testing shall meet the following requirements:
label | CBR ≥ 1.5%
label | Swell ≤ 2.5%
label | Characteristic Density Ratio ≥ 99%
label | Moisture Ratio ≥ 70%
label | Subject to approval min frequency testing as follows:
label | Compaction & Moisture: 1 test per 2 lots
label | CBR & Swell: 1 test per 8 lots
label | Attach: NATA Compaction Test Report
label | - - - - - - - - -
label | Reference Documents - VicRoads Spec. Table 204.142
label | - - - - - - - - -
label | Inspection / Test Method - Site Inspection
label | - - - - - - - - -
label | Record of conformity - Signed ITP
label | - - - - - - - - -
label | TP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 3.6 - Survey Pickup - Top of subgrade
label | Frequency - Prior to Placing fill
label | - - - - - - - - -
label | Acceptance Criteria - Ensure the Top of subgrade is recorded by survey
label | - - - - - - - - -
label | Reference Documents - VicRoads Specification
label | Cl. 204.03(f)
label | Cl. 204.03(g)
label | Table 204.031
label | - - - - - - - - -
label | Inspection / Test Method - Document Review
label | - - - - - - - - -
label | Record of conformity - Survey As-Built
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | - - - - - - - - -
text | Date Completed:
checkpoint-group | 4 - LOT Closeout
checkpoint-status | 4.1 - Survey As-Built
label | Frequency - Each lot
label | - - - - - - - - -
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Scale A:
label | Min. No. of Measurements Per Lot: 80
label | Range x (mean) = +5, -15mm
label | Max S (Standard Deviation) = 12 mm
label | Attach: Survey As-builts / Survey Report
label | - - - - - - - - -
label | Reference Documents - Section 204.03 (h), 204.16
label | - - - - - - - - -
label | Inspection / Test Method - Review Document
label | - - - - - - - - -
label | Record of conformity - Attach As-Built Report
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 4.2 - Non-conformance Closure
label | Frequency - Each Lot
label | - - - - - - - - -
label | Acceptance Criteria - Ensure All related Non-conformances are recorded and closed out.
text | CAMS Case Number(s)
label | Attach: Closed NCR Report
label | - - - - - - - - -
label | Reference Documents - Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method - Review Document
label | - - - - - - - - -
label | Record of conformity - This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 4.3 - Red Line Markups
label | Frequency - Each Lot
label | - - - - - - - - -
label | Acceptance Criteria - Ensure any changes from design are captured in red-line markup drawings
text | RFI References
label | - - - - - - - - -
label | Reference Documents - Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method - Review Document
label | - - - - - - - - -
label | Record of conformity - This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | 4.4 - Final Inspection
label | Frequency - Each Lot
label | - - - - - - - - -
label | Acceptance Criteria - It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
label | - - - - - - - - -
label | Reference Documents - Quality Management Plan
label | - - - - - - - - -
label | Inspection / Test Method - Review Document
label | - - - - - - - - -
label | Record of conformity - This ITP
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
label | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Quality Manager
label | - - - - - - - - -
text | Date Completed:
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date:
text | Work Completed On
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
text | Work Commenced On
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot Plan or “Highlighted” IFC drawings (mud maps) attached to the Lot? | YES, NO, N/A
select | Survey conformance records attached to the Lot? | YES, NO, N/A
select | Subcontractor/ Supplier records attached to the Lot? | YES, NO, N/A
select | Conforming Test Results attached to the Lot? | YES, NO, N/A
select | As built records attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
text | Lot Closed On
text | comments