## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITR 005 Fire Service |  |  |  |  | Yes | ITR 005 Fire Service | 0fb0a3e7-cf26-42b4-af41-13bc9e266de1
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & Standards or alternatively approved by CFA/MFB.
checkpoint-status |  |  | checkpoint | All pipework to be tested TO 1700 kPA in accordance to specifications &
checkpoint-status |  |  | checkpoint | requirements as per AS 2419 Hydrants & AS 2441 Hose Reels
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checkpoint-status |  |  | checkpoint | Prior to handover system must be inspected & certified in accordance to drawings, code, specification, dispensation, 129 report and FER
checklist-flat |  |  | checklist | ITR 001 Set Out Penetrations |  |  |  |  | Yes | ITR 001 Set Out Penetrations | 2432305e-a94b-4b6a-b036-cf4853c86d32
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to IFC Drawing No.
checkpoint-status |  |  | checkpoint | All penetrations and fire collars to be as per specifications or alternatively approved
checkpoint-status |  |  | checkpoint | Ensure fire collars are installed as per manufacturer’s instructions.
checkpoint-status |  |  | checkpoint | Tabs on cast in collar to be exposed.
checkpoint-status |  |  | checkpoint | Photos of collar end labelling referencing fire matrix if required
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 018 Safety Shower & Eye Wash |  |  |  |  | Yes | ITR 018 Safety Shower & Eye Wash | 3800bfbf-b912-4fb7-b540-a848db7e9253
checklist-flat |  |  | checklist | ITR 004 Greasy Drainage In Ground |  |  |  |  | Yes | ITR 004 Greasy Drainage In Ground | 57c5f223-4d63-4743-89d2-06e24ed621de
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 008 Suspended Greasy Drainage |  |  |  |  | Yes | ITR 008 Suspended Greasy Drainage | 665a40fd-ee1c-444f-96a1-c7d585f73a11
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 014 Sanitary Fit Off |  |  |  |  | Yes | ITR 014 Sanitary Fit Off | 685970c6-3ec4-4180-8f1c-268acc86c2a1
checkpoint-status |  |  | checkpoint | All works to be set out as per approved Architectural Drawing No.
checkpoint-status |  |  | checkpoint | Inspect for product defects.
checkpoint-status |  |  | checkpoint | Install as per manufacturer's recommendations and requirements
checkpoint-status |  |  | checkpoint | All sanitary items to be tested in accordance to specifications and manufacturers requirements
checkpoint-status |  |  | checkpoint | Check for leaks
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | ITR 006 Suspended Sewer Drainage |  |  |  |  | Yes | ITR 006 Suspended Sewer Drainage | 70cfc640-6873-4610-9b29-d1ffe43ed4b3
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | Documentation |  |  |  |  | Yes | Documentation | 7d84a9ee-cae0-4916-b39e-912a504e57d5
checkpoint-status |  |  | checkpoint | Attach relevant documents
checklist-flat |  |  | checklist | ITR 002 Sewer Drainage |  |  |  |  | Yes | ITR 002 Sewer Drainage | 81691a94-624a-49f5-a598-fb02bf855b15
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Notify HP Management for inspection of drainage prior to backfill.
checkpoint-status |  |  | checkpoint | Book inspection with VBA for in-ground drainage. HP can sign off if inspector does not attend.
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 010 Gas Service |  |  |  |  | Yes | ITR 010 Gas Service | 8218d63c-2405-45e7-883a-2aa81d225ebd
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS5601.1 or alternatively approved including rod sizes and clipping configurations and methods
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance with specifications and requirements & AS5601.1
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checkpoint-status |  |  | checkpoint | Prior to gas being turned on ESV must inspect and approved installation if required, including all builders work requirements IE signage, access panels, ventilation, riser shafts etc..
checkpoint-status |  |  | checkpoint | Must notify HP management on completion of works.
checklist-flat |  |  | checklist | ITR 011 Hot & Cold Rough In |  |  |  |  | Yes | ITR 011 Hot & Cold Rough In | 9030beea-e445-4665-9c16-ea8242970838
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings and penetrations to be installed to - IFC Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 & in accordance with specifications and requirements . Ensure isolation from authority main, fixtures, tapware and appliances while undertaking testing
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 012 Hot Water Service |  |  |  |  | Yes | ITR 012 Hot Water Service | b4f3891f-d80d-4956-b91b-2cf698b19682
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework to be tested in accordance to specifications and requirements namely 1500 kPA for 30 minutes
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | ITR 009 Domestic Cold Water In Ground |  |  |  |  | Yes | ITR 009 Domestic Cold Water In Ground | b9acf49b-420c-4de7-a12c-27c450b93084
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawings No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be tested to 1500 kPA for 30 minutes as per AS 3500:1 clause 18.3.1 & in accordance with specifications and requirements . Ensure isolation from authority main, fixtures, tapware and appliances while undertaking testing.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | ITR 003 Stormwater Drainage In Ground |  |  |  |  | Yes | ITR 003 Stormwater Drainage In Ground | bb033d82-ebca-4872-9f3a-cc9caeb8a598
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | All pits to be checked for correct invert levels & finished floor levels in accordance to specifications & requirements & IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure correct locations of pits.
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications & requirements
checkpoint-status |  |  | checkpoint | Ensure all backfill is in accordance to specifications & compaction requirements.
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.
checklist-flat |  |  | checklist | ITR 015 Backflow Test Report |  |  |  |  | Yes | ITR 015 Backflow Test Report | c08e3d4b-9e1c-4d8f-bbb5-88119967cec5
checkpoint-status |  |  | checkpoint | Backflow Test Report Completed
text | 695ff291-b601-597f-bc52-7ee09ada0e59 |  | textbox | Date of test
text | af2a1677-eac0-588d-a271-21d8ebad5247 |  | textbox | Location of test
text | c4fb2241-ba56-556f-a66c-26ff7ad3e4f0 |  | textbox | Licence No.
text | 07ed246d-9426-57b2-ae37-9269fa2083da |  | textbox | Test Kit Serial No.
text | d4e7a0d2-4631-5ce6-b2ee-35888ed2a669 |  | textbox | Date test kit last certified
text | 31efcba8-d818-5ca0-84e5-727fd32f5e2b |  | textbox | Place of certification
text | fd9b4eac-83e8-509f-a87c-ab9920b4b137 |  | textbox | Make of device
text | d73d01df-9618-5139-a674-b0c0f8afcd76 |  | textbox | Size (mm)
text | 04e15e4e-1e2f-56cb-bbfc-a4a3a1b1d08a |  | textbox | Model
text | 9dd4c522-5d60-5fa1-9294-ede00f75e136 |  | textbox | Serial No.
label | f32563bb-4db3-569a-b44f-939b29291c08 |  | note | Initial Test Before Maintenance
checkpoint-status |  |  | checkpoint | Permission to shut of water
boolean | 3c896cdb-5f71-5bc8-8ab0-647d8de44d70 |  | tickbox | Reduced Pressure Zone Device
boolean | e1f1bce2-ee8d-5e43-b370-b12776c0b6cf |  | tickbox | Double Check Valve (Columns 1 & 2)
boolean | 39705aaf-7a53-5117-b2ec-9f67287c2009 |  | tickbox | Pressure Type
checkpoint-status |  |  | checkpoint | Check Valve No 1
boolean | 25d57e34-e894-5c54-a6a2-b3a1501265bf |  | tickbox | Closed Tight
boolean | 5d6770dd-2a09-57a5-8989-4d296dca0ec6 |  | tickbox | Leaked
text | bbbfab47-9b8f-581d-bea7-1821f57382e6 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve No 2
boolean | ef325ca9-af5c-52c6-8d0e-9b6925b1b14a |  | tickbox | Closed Tight
boolean | f24f0931-f8e9-5abb-bfc0-4cfc261e9dac |  | tickbox | Leaked
text | e71ef84d-0fd9-5ad6-a278-f9a2d46230c6 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Relief Valve
boolean | f7c60004-e3af-50ca-b7fe-8aa7c657e9fb |  | tickbox | Opened At
boolean | a911cfc5-ecd8-570c-82a3-004a13b7831b |  | tickbox | Not Opened
text | 66d9bc5b-8720-550f-8895-e88ac0ba8d4c |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve
boolean | bc056cc0-2626-5535-9f80-340969e0736b |  | tickbox | Closed Tight
boolean | 729e41b1-372e-536d-ae42-da2c1e6d6215 |  | tickbox | Leaked
text | 6c5ae7d6-8f12-5281-af8d-8ab34a117206 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Air Inlet
boolean | a23dbeb8-b861-5322-aa57-378270e6fa35 |  | tickbox | Opened At
boolean | 2b2c9727-a387-5308-972e-38fa2d086506 |  | tickbox | Not Opened
text | a07e13d4-631c-5928-9a8d-2e1122f99bc3 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Downstream Isolation Valve
boolean | 0af68873-6f5e-553e-a65d-73249ee1ad10 |  | tickbox | Closed Tight
boolean | 034dbdca-71ef-5084-a103-5eb2a8dab483 |  | tickbox | Leaked
text | d0967168-0627-55c5-859c-a7a13f3fd886 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Comment / Take photos of any reasons for failure (NA if not required)
label | fbdb1ec6-e50a-5c1f-872a-12150a70696e |  | note | Re-Test After
checkpoint-status |  |  | checkpoint | Permission to shut of water
boolean | f3582070-db46-5210-9f43-00171f7a7579 |  | tickbox | Reduced Pressure Zone Device
boolean | ecc57a46-52ca-5934-82f2-dd6cebd1b582 |  | tickbox | Double Check Valve (Columns 1 & 2)
boolean | 7491c523-c734-5c0c-a2b8-6ac722b27618 |  | tickbox | Pressure Type
checkpoint-status |  |  | checkpoint | Check Valve No 1
boolean | 0781799e-dead-5031-b58f-4c7b35a27d8f |  | tickbox | Closed Tight
boolean | 4da827b6-a54f-5c2d-8159-85f2ad8c2070 |  | tickbox | Leaked
text | 05882470-f095-5ff4-9054-005d52bae887 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve No 2
boolean | 0c8eb19f-73aa-5c03-9111-4feae05718b8 |  | tickbox | Closed Tight
boolean | 21432a36-b069-5167-b3d9-a2e30836162f |  | tickbox | Leaked
text | 6ba9c30d-1ded-5096-b75c-f04a5e373543 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Relief Valve
boolean | dcff324f-70e1-5bc8-9acd-9218860638ce |  | tickbox | Opened At
boolean | e1f263e4-3f77-5cdc-bdb5-480ebc061ba6 |  | tickbox | Not Opened
text | 29a2ff95-3840-5d25-a9f0-68478c6edc2a |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Check Valve
boolean | 7cc2a6e4-0f1c-5ca3-a4c3-59ca96293428 |  | tickbox | Closed Tight
boolean | 2b387281-b04f-53bc-91ea-fa8fa7b8e4b4 |  | tickbox | Leaked
text | 706de936-d5ad-5b3d-9fa7-85708077ee6f |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Air Inlet
boolean | bb27b9a3-dd8f-5e0a-ad60-7b504fb0c074 |  | tickbox | Opened At
boolean | ba237c11-7265-5a82-bc85-fb8b763cde3e |  | tickbox | Not Opened
text | 7fbad4b3-e3a9-5ea5-ab48-8f9df7ded456 |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Downstream Isolation Valve
boolean | 4700eb1a-c32f-528c-bf63-d0fb1ebeb491 |  | tickbox | Closed Tight
boolean | 23e1846d-cd2a-598d-973e-0b02ec81fc3d |  | tickbox | Leaked
text | 3b286780-a080-56fc-9a6f-8d59d0bef16d |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | 26e833f9-4508-59c5-9ee8-99d78ae3d9c6 |  | textbox | Parts & Materials Used
text | d17b7b43-b885-5bdd-9665-3e5ef6ae44e5 |  | textbox | Water Meter Number
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-flat |  |  | checklist | Internal Audit Checklist |  |  |  |  | Yes | Internal Audit Checklist | c1054b3e-47d7-43f0-b3ba-f5cce531925c
checkpoint-status |  |  | checkpoint | Drawing Register Current
checkpoint-status |  |  | checkpoint | Drawings as per Register
checkpoint-status |  |  | checkpoint | ITP Records
checkpoint-status |  |  | checkpoint | Material Specification
checkpoint-status |  |  | checkpoint | Sanitary Specification
checkpoint-status |  |  | checkpoint | Calibration records
checkpoint-status |  |  | checkpoint | Sample Register
text | 050312ab-57b6-5fc1-8535-de294e0596a3 |  | textbox | Comments
text | ffc81bb5-5942-5500-a415-988817449ea6 |  | textbox | Items of concern
text | 878cb8a3-2045-51b9-9b40-1b8029f7d81f |  | textbox | Action required
text | ebaeaf18-a183-5c57-828a-0418a0f74152 |  | textbox | Future recommendations
checkpoint-status |  |  | checkpoint | Signed off by Highbury Plumbing Supervisor
checklist-flat |  |  | checklist | Non Conformance Report |  |  |  |  | Yes | Non Conformance Report | c9ca2b74-73bd-42fb-9d37-43583056dc89
checkpoint-status |  |  | checkpoint | Report completed
text | 06ad03b0-5b42-53b9-a722-118cce66f5c4 |  | textbox | Short description
text | 092a57c2-0870-5b1a-b0f7-9d3167071f02 |  | textbox | NCN NO:
text | 867f69b8-0438-5f84-998f-cf28820e238f |  | textbox | Level / Area
text | cf4bf5ba-e184-5caf-80d7-ed08be5435a5 |  | textbox | Grid Coord
text | 373dbdb9-a461-5b43-b1b3-b62342c5c9fe |  | textbox | Responsibility
text | 1fe2734e-8005-5ebf-be1b-e609aa044519 |  | textbox | Non Conformance Details
checkpoint-status |  |  | checkpoint | Method of disposition
text | a7e95483-7319-5371-bc98-c72835cd0eb5 |  | textbox | Approval required from
checkpoint-status |  |  | checkpoint | Repair / Use as is
text | fe9c72e5-4a17-5ce7-b5c8-f90ff57a85e9 |  | textbox | Customer
checkpoint-status |  |  | checkpoint | Rework / Replace
text | a6b5c7d8-2788-5339-9c95-3bd8f525aa2f |  | textbox | Project Manager
checkpoint-status |  |  | checkpoint | Signed off by Highbury Plumbing Supervisor
checkpoint-status |  |  | checkpoint | Signed off by Scentre Group
checklist-flat |  |  | checklist | ITR 017 Thermostatic Mixing Valve Test Report |  |  |  |  | Yes | ITR 017 Thermostatic Mixing Valve Test Report | d195e3e4-1cb7-458a-97fa-4abfc1e2adaf
checkpoint-status |  |  | checkpoint | Thermostatic Mixing Valve Test
text | 37f8ca52-1a87-51be-9d22-2be83453ea07 |  | textbox | Licence No.
text | 6581733a-5c94-5db3-9957-c195f6d1f1b9 |  | textbox | Test kit serial No.
text | fb5137a4-b7b7-5436-b016-83b70489cc55 |  | textbox | Date test kit last certified:
text | 7de9d6d0-7e80-58c8-9559-f76855194f89 |  | textbox | Place of certification
text | 43ee067b-ef4b-57dd-a3c6-d17b1d358e3e |  | textbox | Make
text | 9be29302-d8c8-594f-abc0-f0d2d2ee700e |  | textbox | Model
text | 387daa10-660c-56f5-a9c7-46ed1bf61461 |  | textbox | Location of valve
checkpoint-status |  |  | checkpoint | Shut down test
checkpoint-status |  |  | checkpoint | Flush / Clean filters
checkpoint-status |  |  | checkpoint | Static Test
boolean | c302871d-2fa6-5ba0-8916-1398fc5f4975 |  | tickbox | One outlet in use
text | 5ea9c1c8-b06d-537d-be32-bc2c957701ec |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Temp of warm water
text | 0e4550c9-8a12-5770-8591-c5ed0b3ba825 |  | textbox | Fixture
text | a89bf4e1-745a-5aee-996e-c3530d6a428d |  | textbox | Pre Set Temp
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | b4347b7b-683c-5aec-8d15-005d56bfd116 |  | textbox | Parts & Materials Used
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-flat |  |  | checklist | ITR 016 Tempering Valve Test Report |  |  |  |  | Yes | ITR 016 Tempering Valve Test Report | d3cb58fb-8cb6-4690-ae49-5076709d1501
checkpoint-status |  |  | checkpoint | Tempering Valve Test
text | a5c11333-bf09-51bd-b6d5-1e38a3d65039 |  | textbox | Licence No.
text | 1506f981-a78c-5422-97b4-f3c39e3f8ded |  | textbox | Test kit serial No.
text | f6c13a8a-39c1-55bb-8224-45d9a6847b68 |  | textbox | Date test kit last certified:
text | c21459d6-a14e-5f4f-a383-d706b53f746b |  | textbox | Place of certification
text | a946de63-c96d-5cad-8480-33376177cee0 |  | textbox | Make
text | d69a04e8-fc44-5d11-ba92-f929dc731421 |  | textbox | Model
text | 56f84787-c96a-5266-8416-07d39836084c |  | textbox | Location of valve
checkpoint-status |  |  | checkpoint | Flush / Clean filters
checkpoint-status |  |  | checkpoint | One outlet in use
text | 9df0764d-71a4-5a76-9a92-853e37f2d03a |  | textbox | kPa
checkpoint-status |  |  | checkpoint | Temp of warm water
text | 1cd6072f-7f11-594a-bd9e-0b6a7941d9fa |  | textbox | Fixture
text | efc24675-913c-5fb4-b764-3d27fe07efed |  | textbox | Pre Set Temp
checkpoint-status |  |  | checkpoint | Described Maintenance - Add comments / photos
text | 30084551-bb23-5c14-a1f7-177586b38c41 |  | textbox | Parts & Materials Used
checkpoint-status |  |  | checkpoint | Testing signed off
checklist-flat |  |  | checklist | ITR 013 Water Meter |  |  |  |  | Yes | ITR 013 Water Meter | f454e1a4-a7c7-4ae8-b1a7-861b44e4fc14
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All meter work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | Ensure that all pipework to meters has been sealed and jointed, all capping adequately installed for testing.
checkpoint-status |  |  | checkpoint | Ensure all meters are sufficient supported and installed in correct location
checkpoint-status |  |  | checkpoint | Pass an amount of water in a container of known volume (bucket) and confirm the volume of water and meter reading are the same or within the required tolerances
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy
checklist-flat |  |  | checklist | ITR 007 Suspended Storm Drainage |  |  |  |  | Yes | ITR 007 Suspended Storm Drainage | f5b11ae2-c69e-461c-93ee-b9afadef1fa7
checkpoint-status |  |  | checkpoint | All works to be set out as per approved IFC drawings. Works set out to Drawing No.
checkpoint-status |  |  | checkpoint | All pipe work to be as per specifications & AS3500.2.2015 or alternatively approved and appropriately sized
checkpoint-status |  |  | checkpoint | All pipework, material and fittings to be installed as per approved IFC Drawing No:
checkpoint-status |  |  | checkpoint | All pipework to be checked for correct invert levels & gradients in accordance to specifications, requirements & approved IFC drawings.
checkpoint-status |  |  | checkpoint | Ensure acoustic lagging is installed if required to specification & acoustic engineers report.
checkpoint-status |  |  | checkpoint | As per AS 3500 test traps for leaks by discharging water into drains
checkpoint-status |  |  | checkpoint | Ensure all excess material is removed from work area & leave clean & tidy.